## Slide 1: Information Technology Project Management – Third Edition
By Jack T. Marchewka
Northern Illinois University
Copyright 2009 John Wiley & Sons, Inc. all rights reserved. Reproduction or translation of this work beyond that permitted in Section 117 of the 1976 United States Copyright Act without the express permission of the copyright owner is unlawful. Request for further information should be addressed to the Permissions Department, John Wiley & Sons, Inc. The purchaser may make back-up copies for his/her own use only and not for distribution or resale. The Publisher assumes no responsibility for errors, omissions, or damages caused by the use of these programs or from the use of the information contained herein.

## Slide 2: Defining and Managing Project Scope
Chapter 5

## Slide 3
Project Planning Framework

## Slide 4: Scope Management Processes
Scope is the work boundaries and deliverables of the project
  The boundary and deliverables that the project team will provide to the project sponsor
  The scope boundary acts as a fence to ensure that what needs to get done, gets done – and only what needs to get done, gets done
    What is part of the project and what is NOT
  Performing work that does not help the project achieve its MOV needlessly consumes valuable time and resources

## Slide 5: Scope Management Processes
Scope Planning
  The development of a scope management plan that defines the project’s scope and how it will be verified and controlled throughout the project
  Lays out the processes, tools and techniques to be used by the project team to define and manage the project’s scope
Scope Definition
  A detailed scope statement that defines what work will and will not be part of the project and will serve as a basis for all future project decisions
Create Work Breakdown Structure
  The decomposition or dividing of the major project deliverables (i.e., scope) into smaller and more manageable components
Scope Verification
  Confirmation and formal acceptance that the project’s scope is accurate, complete, and supports the project’s MOV
Scope Control
  Ensuring that controls are in place to manage proposed scope changes once the project’s scope is set. Must be communicated to all project stakeholders.

## Slide 6: Scope Management Plan
The processes and techniques for defining and managing scope make up the scope management plan
  The procedures for defining and managing the scope must be communicated and understood by all of the stakeholders to minimize the likelihood of misunderstandings
  The scope must align and support the project’s MOV
  The next slide summarizes the components and processes of a scope management plan

## Slide 7
Scope
Planning
Scope
Definition
Create
WBS
Scope
Verification
Scope
Control
Documents how the team will define and develop the project’s scope and WBS, as well as processes for verifying and controlling the project and product deliverables.
Builds upon the preliminary project scope statement to define all the project and product deliverables, including the processes and criteria for acceptance.
A project planning tool that that decomposes or subdivides and organizes the project’s scope into a deliverable-orientated hierarchy.
A formalized acceptance from the appropriate stakeholders that the defined project scope is complete
A defined process for managing changes to project and product scope and the impact of those changes to the project’s schedule and budget.
Scope
Management
Plan
Detailed
Project
Scope
Work
Breakdown
Structure
Scope
Verification
Checklist
Scope
Change Control
Process
Scope Management Plan

## Slide 8: Scope Planning
Initiating process to begin defining and documenting the project work (i.e., deliverables) needed to achieve the project’s MOV
  Extra work that will not help the project achieve it’s MOV will only needlessly increase the project’s schedule and budget
This process begins at a high level and will become more detailed as the project progresses and more information becomes available
Attempts to answer the question: What is and what is not to be delivered by this project?
  Need to know what work is to be done in order to estimate time and cost
  Makes the project sponsor’s needs and expectations explicit
Tools:
  Scope Boundary
  Scope Statement

## Slide 9: Scope Boundary

## Slide 10: Scope Statement
To define the scope boundary, create a more detailed scope statement to document the project sponsor’s needs and expectations
Scope statement from an outside consultant who has been hired to develop an e-commerce application for a bank
  Develop a proactive electronic commerce strategy that identifies the processes, products and services to be delivered through the World Wide Web.
  Develop an application system that supports all of the processes, products, and services identified in the electronic commerce strategy.
  The application system must integrate with the bank’s existing enterprise resource planning system.

## Slide 11: Out of Scope
Technology and organizational assessment of the current environment
  Bank’s IT dept will conduct assessment not consultants
Customer resource management and data mining components
  Will delay implementation of the project which is vital to the company’s competitive strategy

## Slide 12: Project Scope Definition
The scope boundary and scope statement provide a useful first step
The project’s scope must now be defined in more detail in terms of specific deliverables that provide a basis for developing the project’s work breakdown structure (WBS)
Tools:
  Deliverable Definition Table
  Deliverable Structure Chart
  Context Level Data Flow Diagram
  Use Case Diagram

## Slide 13: Scope
Project-Oriented Deliverables
  Support the project management and IT development processes defined in the Information Technology Project Methodology (ITPM)
  Tools
    Deliverable Definition Table (DDT)
      All the projects deliverables must have a clear and concise definition
    Deliverable Structure Chart (DSC)
      Once the deliverables have been defined, the DSC serves as an interim step to define detailed work packages that will be used to estimate the project schedule and budget
        This will, in turn , be used to create the work breakdown structure (WBS)

## Slide 14
Deliverable Definition Table (DDT)

## Slide 15
Deliverable
Structure
Chart

## Slide 16: Scope
Product-Oriented Deliverables
  What exactly is going to be delivered to the client? What does the system do?
  Identifying the specific features and functionality of the application system to be delivered to the client are critical to time and budget estimation
  Tools
    Context Dataflow Diagram (DFD)
      High-level representation of the system that has one process(circle) and depicts all the inflows and outflows of data and information between the system and external entities (squares).
      Lower level DFDs will model the processes and flows in greater detail
    Use Case Diagram (UCD)
      Identifies main functions and features of the system and the different users and external systems that interact with it
      Further refined and detailed during requirements analysis

## Slide 17
Context Data
Flow Diagram

## Slide 18: Scope
    Use Case Diagram (UCD)
      Identifies main functions and features of the system and the different users and external systems that interact with it
        May be developed iteratively during joint application development (JAD) sessions
      Further refined and detailed during requirements analysis
        Actors – people (users, customers, managers, etc.) or external systems that interact or use the system
        Use Case – depicts the major functions the system must perform for an actor or actors
      The use case diagram shows a customer actor using the system to transfer payments.
        In the requirements analysis, a set of scenarios would be developed to depict what happens when a transfer is successful, another when there are insufficient funds, etc.

## Slide 19
Use Case
Diagram

## Slide 20: Project Scope Verification
Provides a mechanism for ensuring that the project deliverables are completed according to the DDT.
MOV
  Has the project’s MOV been clearly defined and agreed upon? If not, scope changes may result later in the project.
Deliverables
  Are the deliverables tangible and verifiable?
  Do they support the project’s MOV?
Quality Standards
  Will the work be completed to meet specific standards?
Milestones
  Significant events that mark the acceptance of a deliverable
  Tell that a deliverable was not only completed but reviewed and accepted
Review and Acceptance
  Formal signoff by project stakeholders, plan sponsor and project team.

## Slide 21: Scope Change Control
Concerned with managing changes to the project’s scope and to ensure that these changes are beneficial when they occur
Mitigates:
  Scope Grope – project team’s inability to define the project scope. Use MOV as guidelines and follow scope processes and tools
  Scope Creep – increasing featurism
  Scope Leap – fundamental change in the project scope. New MOV may require killing of existing project and start of new one.
Tools/Procedures:
  Scope Change Request Form
  Scope Change Request Log

## Slide 22
Scope Change Request Form
Requestor Name: _______________ Request Date: __________
Request Title: __________________ Request Number: _______
Request Description:
Justification:
Possible Alternatives:
Impacts
Alternative 1
Alternative 2
Alternative 3
Scope
Schedule
Resources Required
Cost
Recommendation:
Authorized By:
Date:

## Slide 23
Scope Change Request Log

## Slide 24: Benefits of Scope Control
Keeps the project manager in control of the project.
  Authorized changes to the project’s scope are reflected in changes to the project’s schedule and budget.
Allows the project team to stay focused and on track
  They do not have to perform unnecessary work.