## Action Items Table TEMPLATE
Hazard | Action Item | Timeline | Plan Goals Addressed
|  |  | Life Safety | Protect Facilities | Enhance Emergency Planning | Enhance Awareness and Education
Multi-Hazard Mitigation Action Items | [6 empty] | Edit the Action Totems as appropriate for your district. These tables can be pasted into Word as pictures or as editable Excel Worksheet Objects.
Long-Term #1 | Integrate the findings and action items in the mitigation plan into ongoing programs and practices for the district. | Ongoing | X | X | X | X
Long-Term #2 | Review emergency and evacuation planning to incorporate hazard and risk information from the mitigation plan. | Ongoing | X | X | X | X
Long-Term #3 | Consider natural hazards whenever siting new facilities and locate new facilities outside of high hazard areas. | Ongoing | X | X | X | X
Long-Term #4 | Ensure that new facilities are adequately designed to minimize risk from natural hazards. | Ongoing | X | X | X | X | Make Action Items as District-specific as possible. If an Action Item applies to a specific campus(es) or building(s) list these by name.
Long-Term #5 | Maintain, update and enhance facility data and natural hazards data in the ICOS database. | Ongoing | X | X | X | X
Long-Term #6 | Develop and distribute educational materials regarding natural hazards, vulnerability and risk for K-12 facilities. | Ongoing | X |  | X | X
Long-Term #7 | Seek FEMA funding for repairs if district facilities suffer damage in a FEMA declared disaster. | Ongoing | X | X |  | X
Long-Term #8 | Pursue pre- and post-disaster mitigation grants from FEMA and other sources. | Ongoing | X | X |  | X
Long-Term #9 | Post the district's mitigation plan on the website and encourage comments stakeholders for the ongoing review and periodic update of the mitigation plan. | Ongoing | X |  |  | X
Hazard | Action Item | Timeline | Plan Goals Addressed
|  |  | Life Safety | Protect Facilities | Enhance Emergency Planning | Enhance Awareness and Education
Earthquake Mitigation Action Items
Short-Term #1 | Identify district buildings that don't meet the ASCE 31-03 criteria for being post-benchmark year and thus don't meet the screening criteria for life safety. | 1 Year | X | X |  | X
Short-Term #2 | Complete ASCE 41-13 Tier 1 evaluations for the above buildings. If funding is limited, prioritize based on discussions with a structural engineer, building structural types, year built and a quick inspection of each building. | 1-5 Years | X | X |  | X | Edited to replace 31-03
Short-Term #3 | Assess the ASCE 41-13 results and select buildings that have the greatest vulnerability for more detailed evaluations. | 1-5 Years | X | X |  | X | Edited to replace 31-03
Long-Term #1 | Complete the seismic retrofit of the classroom wing for the Washington Elementary School | 2-3 Years | X | X |  | X
Long-Term #2 | Prioritize and implement seismic retrofits or replacements based on the results of the detailed evaluations, as funding becomes available. | Ongoing | X | X |  | X
Long-Term #3 | Maintain and update building data for seismic risk assessments in the OSPI ICOS PDM database. | Ongoing | X |  | X | X
Long-Term #4 | Enhance emergency planning for earthquakes including duck and cover and evacuation drills. | Ongoing | X |  | X | X
Long-Term #4 |  | Ongoing
Long-Term #5 |  | Ongoing
Hazard | Action Item | Timeline | Plan Goals Addressed
|  |  | Life Safety | Protect Facilities | Enhance Emergency Planning | Enhance Awareness and Education
Tsunami Mitigation Action Items
Short-Term #1 | Review and update evacuation plans for tsunami, including identifying the shortest routes to safe havens that don't have major impediments to rapid travel on foot and conduct frequent practice drills. | Ongoing | X |  | X | X | Edited
Short-Term #2 | Continue and expand public education and outreach efforts to increase awareness of tsunamis and the urgency of immediate evacuation to safe areas. | Ongoing | X |  | X | X | Added
Short-Term #3 | Evaluate vertical evacuation alternatives for campuses where the evacuation travel time on foot is comparable or shorter than the anticipated warning time before tsunami arrival. | 1-2 Years | X |  | X | X
Short-Term #4 | Evaluate measures to remove impediments to rapid evacuation such as adding a pedestrian bridge across a river to shorten evacuation time. | 1-2 Years | X |  | X | X
Long-Term #1 | Implement vertical evacuation and/or measures to remove impediments to rapid evacuation, as funding becomes available. | 2-5 Years | X |  | X | X
Long-Term #2 | Locate new campuses outside of tsunami hazard areas whenever possible or in immediate proximity to natural high ground suitable for evacuation. | Ongoing | X | X | X | X
Hazard | Action Item | Timeline | Plan Goals Addressed
|  |  | Life Safety | Protect Facilities | Enhance Emergency Planning | Enhance Awareness and Education
Volcanic Hazards Mitigation Action Items
Short-Term #1 | Develop and practice an emergency evacuation plan, with designated evacuation methods and routes to the nearest safe haven location. | 1 Year | X |  | X | X | Added
Short-Term #2 | Develop emergency evacuation protocols for pre-emptive evacuation when USGS volcano warning levels reach a pre-determined level. | 1 Year | X |  | X | X | Edited
Short-Term #4 | Update public education, emergency notification procedures and emergency planning for volcanic events, including ash fall events. | 1 Year | X |  | X | X
Long-Term #1 | Construct a pedestrian bridge across the Washington River to substantially shorten the evacuation time to a safe area. | 2-5 Years | X |  | X | X | Added
Long-Term #2 | Locate new campuses outside of volcanic hazard areas whenever possible or in immediate proximity to natural high ground suitable for evacuation. | Ongoing | X | X | X | X
Hazard | Action Item | Timeline | Plan Goals Addressed
|  |  | Life Safety | Protect Facilities | Enhance Emergency Planning | Enhance Awareness and Education
Flood Mitigation Action Items
Short-Term #1 | Complete building-level flood risk assessments for campuses for which this is recommended by the OSPI ICOS PDM database campus-level flood report. | 1-2 Years | X | X | X | X
Short-Term #2 | Enhance emergency planning, including flood response measures, for all campuses that have or may have significant flood risk. | 1-2 Years | X | X | X | X
Short-Term #3 | Complete at least a preliminary flood risk study for campuses not within FEMA-mapped floodplain that meet any of the "opt-in" criteria for completing the flood data inputs in the OSPI ICOS PDM database. | 3 Years | X | X | X | X
Long-Term #1 | Evaluate and implement flood mitigation measures for campuses or buildings that have been determined to have high flood risk based on the campus-level flood report and/or local flood studies that have been completed, as funding becomes available. | Ongoing | X | X | X | X
Long-Term #2 | Locate new campuses outside of FEMA-mapped floodplains or other flood-prone areas whenever possible or construct new buildings in flood-prone areas at elevations as high as possible to minimize flood risk. | Ongoing | X | X | X | X
Hazard | Action Item | Timeline | Plan Goals Addressed
|  |  | Life Safety | Protect Facilities | Enhance Emergency Planning | Enhance Awareness and Education
Wildland/Urban Interface Fire Mitigation Action Items
Short-Term #1 | Consult with local fire agency or other fire expert regarding level of fire risk for campuses for which this is recommended by the OSPI ICOS PDM database campus-level wildland/urban interface fire report. | 1-2 Years | X | X | X | X
Short-Term #2 | Enhance emergency evacuation planning for all campuses for which wildland/urban fires are possible. | 1 year | X |  | X | X
Long-Term #1 | Evaluate and implement mitigation measures to reduce fire risk, including enhancing defensible space around buildings, fuel reduction measures adjacent or near a campus, upgrading building elements with materials designed to be fire-resistant. | Ongoing | X | X | X | X
Hazard | Action Item | Timeline | Plan Goals Addressed
|  |  | Life Safety | Protect Facilities | Enhance Emergency Planning | Enhance Awareness and Education
Landslide Mitigation Action Items
Short-Term #1 | Consult with a geologist or geotechnical engineer regarding landslide risk for campuses for which this is recommended by the OSPI ICOS PDM database campus-level landslide report. | 1-2 Years | X | X | X | X
Long-Term #1 | Evaluate and implement landslide mitigation measures if recommended by the geologist or geotechnical engineer. | Ongoing | X | X | X | X
Hazard | Action Item | Timeline | Plan Goals Addressed
|  |  | Life Safety | Protect Facilities | Enhance Emergency Planning | Enhance Awareness and Education
Other Natural Hazards Mitigation Action Items
Short-Term #1 | Evaluate portable buildings to make sure that they are adequately tied down to resist high winds and implement mitigation measures, if necessary. | 1-3 Years | X | X | X | X
Short-Term #2 | Evaluate avalanche risk for the Washington Elementary School, which has a history of avalanche events near the campus. | 1-3 Years | X | X | X | X
Short-Term #3 | Evaluate alternative water supplies for the Lincoln Middle School which has a single water well and experiences low flow rates during dry years. | 1-2 Years |  | X | X | X
Hazard | Action Item | Timeline | Plan Goals Addressed
|  |  | Life Safety | Protect Facilities | Enhance Emergency Planning | Enhance Awareness and Education
Multi-Hazard Mitigation Action Items
|  | Ongoing |  | x | x | X
|  | Ongoing |  |  | X | X
|  | 1-2 Years |  |  | X | X
|  | 1-2 Years |  |  | X | X
|  | 1 Year |  |  | X | X
|  | 1-2 Years |  |  | X | X
|  | 3 Years | X |  | X | X
|  | 1 Year |  |  | X | X
|  | Ongoing | X | X | X | X