## PDWG_T&F_Groups_-_2020
PDWG Task and Finish Groups

	Task Group	HE Owner	Chair	Membership	Objective	Start Date	Finish Date	Current Status	Comments
	1. New CDM Standards - / DMRB Working Group	Dave Townsend	Dave Townsend	TBC	Develop replacement for IAN 105	TBC		Forming	List of potential names provided - DT to confirm arrangements
	2. Eliminating Risk from the outset (Risk Management)	Mike Boyland/Mike Wilson	Toria Thomas	Doug Potter / Roger Swainston / Liz Bennett / Paul Brown / Tim Goddard / Mark O'Riordan / Paul Boddy	Improve the Management of Design related Safety Hazards from the earliest stages in design development and maximise the use of digital technology to capture, inform and mitigate	Late January 2020	May-20	Forming	This links to an initiative being developed by Mike Wilson. Mike Boyland and Thomas Davies are to present on this at PDWG 15 (16/1/20). From which an action plan will be drawn up / CPD Opportunity
	3. Whole Life Design Safety Group	Richard Wilson	Andrew Finch	Tim Goddard / Ian Scott / Paul Brown / Martin Partington	Development of Design Manual to highlight examples of H&S issues that should be considered at the design stage to improve designer awareness and share lessons learned drawn from Safety Alerts etc	Apr-19	Feb-20	Design Manual in final development	DP to speak with AF with regard completion date
	4. RTB 26 Update	Ian Scott	Paul Browne	Tim Bowes / Tim Goddard / Pav Singh / Dave Owens / TBC	Improve current version of RTB 26 first developed in 2014 and subsequently updated in draft by PDWG in 2018	2018	TBC	This work is currently on hold pending feedback from Peter Mumford	Draft produced previously but on hold until better understanding of SCSLG position on this
	5. H&S delivery utilising BIM and Digital Delivery	Richard Wilson	Volunteer Required	TBC	Improve Risk Management by maximising the benefits of Digital Technology and sharing best practice from across the Supply Chain	Late January 2020	Sep-20	To be agreed at PDWG 15	Links with Eliminating Risk Group / To be focus of PDWG 16 in April / CPD opportunity
	6. SCSLG / - Accident Investigation	SCSLG Chair	Lesley Waud	Tim Goddard	Links with work PDWG have undertaken around root cause analysis	TBC		Awaiting further feedback from SCSLG	PDWG initiatives will continue in parallel
	_ Excavations and Temporary Works	SCSLG Chair	Lesley Waud	Jim Todd	Links with work TwF are undertaking around root cause analysis etc	TBC		Awaiting further feedback from SCSLG	PDWG initiatives will continue in parallel