## 2022 Dynamics Model Schedule
Task Name | Duration | Start | Finish | Abbreviation | Description | Year Definition | 2022 Series MDAG / 2023 ITP Model Selection
2022 Series MDAG Model Build Schedule (Dynamics) - PSS/E v34.8.2 Note: The SPP MDAG Model Development Procedure Manual 2021 v5.0 will be utilized for this model build. | 338 days | Tue 1/11/22 | Thu 12/15/22 | MDAG PF | MDAG Powerflow |  | Year | Season | MDAG PF | MDAG SC | MDAG DYN | ITP BR PF | ITP MPM F1 | ITP MPM F2 | ITP MEM F1 | ITP MEM F2 | ITP BR SC
Initial Data Update | 23 days | Tue 1/11/22 | Mon 2/14/22 | MDAG SC | MDAG Short Circuit | 1 | 2023 | Light Load | 1 |  | 1
Initial Data Update - Build and Post DYRE Files, WindFarm Data, Docureport, Most Severe TPL Fault Submission Template, and Uncacceptable User Models | 3 days | Tue 1/11/22 | Fri 1/14/22 | MDAG DYN | MDAG Dynamics | 1 | 2023 | Spring | 1
SPP Holiday -Dr. Martin Luther King Birthday Jr. | 1 day | Mon 1/17/22 | Mon 1/17/22 | ITP BR PF | ITP Base Reliability Powerflow | 1 | 2023 | Summer | 1 | 1 | 1 | 1
Initial Data Update -Members Submit Data Updates | 20 days | Mon 1/17/22 | Mon 2/14/22 | ITP MPM F1 | ITP MPM Future 1 | 1 | 2023 | Fall | 1 |  |  | 1
Initial Data Update - Member Data Due | 0 days | Mon 2/14/22 | Mon 2/14/22 | ITP MPM F2 | ITP MPM Future 2 | 1 | 2023 | Winter | 1 |  | 1 | 1
Transmisson Planner Most Severe TPL Fault Testing Submisson Data Due | 0 days | Mon 2/14/22 | Mon 2/14/22 | ITP MEM F1 | ITP MEM Future 1 | 2 | 2024 | Light Load | 1 |  |  | 1 | 1
Dynamic Model Adjusments | 29 days | Tue 2/15/22 | Fri 3/18/22 | ITP MEM F2 | ITP MEM Future 2 | 2 | 2024 | Spring | 1 |  |  | 1
Dynamics Adjustment (Dyre file, CMLD Load and User Defined Model Update) | 29 days | Tue 2/15/22 | Fri 3/18/22 | ITP BR SC | ITP Base Reliability Short Circuit | 2 | 2024 | Summer | 1 |  | 1 | 1 | 1 |  | 1 |  | 1
Member/Stakeholder Holiday -President's Birthday | 0 days | Mon 2/21/22 | Mon 2/21/22 |  |  | 2 | 2024 | Fall |  |  |  | 1
Lastest MMWG and MDAG Series Models | 0 days | Fri 3/18/22 | Fri 3/18/22 |  |  | 2 | 2024 | Winter | 1 |  |  | 1
MMWG Dynamic Models | 0 days | Fri 3/18/22 | Fri 3/18/22 |  |  | 3 | 2025 | Light Load | 1 |  | 1
Receive 2022 MDAG Powerflow Final Models | 0 days | Fri 3/18/22 | Fri 3/18/22 |  |  | 3 | 2025 | Summer | 1 |  | 1
Powerflow Model Adjusments | 24 days | Mon 3/21/22 | Fri 4/15/22 |  |  | 5 | 2027 | Light Load | 1 |  | 1 | 1 | 1 | 1
Powerflow Model Reduction, Powerflow Adjustments, Updates, Wind Farm Topology, X-Source | 24 days | Mon 3/21/22 | Fri 4/15/22 |  |  | 5 | 2027 | Summer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Dynamic Case Initialization | 33 days | Fri 4/15/22 | Wed 6/1/22 |  |  | 5 | 2027 | Summer Shoulder | 1
DC Tie Model Updates | 0 days | Fri 4/15/22 | Fri 4/15/22 |  |  | 5 | 2027 | Winter | 1 |  | 1 | 1
Case & Dyre File Corrections based on Initialization Messages | 33 days | Fri 4/15/22 | Wed 6/1/22 |  |  | 10 | 2032 | Light Load |  |  |  | 1 | 1 | 1
Build Initial Models | 40 days | Thu 6/02/22 | Thu 7/28/22 |  |  | 10 | 2032 | Summer | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
No-fault Testing | 10 days | Thu 6/02/22 | Thu 6/16/22 |  |  | 10 | 2032 | Winter | 1 |  | 1 | 1
Disturbance Testing | 10 days | Thu 6/16/22 | Thu 6/30/22 |  |  | Stakeholder Reviewed Total |  | 62 | 17 | 2 | 11 | 14 | 6 | 4 | 3 | 2 | 3
Command Line Testing | 5 days | Thu 6/30/22 | Thu 7/07/22
SPP Holiday - Fourth of July | 0 days | Mon 7/04/22 | Mon 7/04/22
Transmission Planner Submitted Most Severe TPL Fault Testing | 10 days | Thu 7/07/22 | Thu 7/21/22
Offline Wind Initialization | 5 days | Thu 7/21/22 | Thu 7/28/22
Dynamic Case Review and Finalization | 11 days | Fri 7/29/22 | Wed 8/10/22
Post Initial Models | 1 days | Fri 7/29/22 | Mon 8/01/22
Member Review of Initial Models | 10 days | Tue 8/02/22 | Tue 8/16/22
Member Final Data Submission Due | 0 days | Tue 8/16/22 | Tue 8/16/22
Data Update - Build Updated Models | 26 days | Wed 8/17/22 | Tue 9/21/22
Build Final Models | 15 days | Wed 8/17/22 | Wed 9/07/22
Post Proposed Final MDAG Models | 1 day | Thu 9/08/22 | Thu 9/08/22
Member Review of Proposed Final MDAG Dynamic Models | 10 days | Thu 9/08/22 | Thu 9/22/22
SPP Holiday - Labor Day | 0 days | Mon 9/05/22 | Mon 9/05/22
MDAG Finalization - Conference Call Vote | 0 days | Thu 9/22/22 | Thu 9/22/22
TPL Data Update - Build TPL Models | 72 days | Fri 9/02/22 | Tue 12/13/22
TPL Sensitivity Dispatch | 15 days | Fri 9/02/22 | Fri 9/23/22
TPL Data Update - Build Final Models including Board Decisions (NTC addition/withdrawals) | 45 days | Fri 9/23/22 | Mon 11/28/22
SPP Holiday - Thanksgiving Day | 2 days | Thr 11/25/22 | Fri 11/26/22
Post Final TPL MDAG Models | 0 days | Tue 11/28/22 | Tue 11/28/22
Member Review of Final TPL MDAG Dynamic Models | 10 days | Wed 11/29/22 | Tue 12/13/22
TPL MDAG Finalization - Conference Call Vote | 0 days | Thu 12/15/22 | Thu 12/15/22
Note: Friday data submission is allowed through the end of day the following Sunday. This schedule was jointly developed by SPP as the Planning Coordinator (PC) and each of its Transmission Planners (TPs) and the SPP Model Development Working Group (MDAG).