Type of Review: Annual Review

Project Title: Growth and Labour Markets in Low Income Countries

Date started:	August 2011	Date review undertaken: July 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID is supporting a substantial programme of research on labour markets in Low Income Countries (LICs) through the provision of £10 million over 5 years in a partnership with the Institute for the Study of Labor (IZA). The programme is running from August 2011 to July 2016.

What are the expected results?
The five year programme will deliver a significant new body of evidence on labour markets in LICs as well as the development of improved data on labour markets in LICs. The programme will also work to ensure uptake of the research findings by bring together researchers and policy makers to discuss the policy implications of the research. / The programme will focus on 5 key research areas in LICs including work on / Economic growth and labour market outcomes / Labour market institutions / Active labour market policies / Skills / Gender / Data on labour markets and growth in LICS will also be assessed, collected and made accessible to researchers across these five areas. In the longer term the data gathering exercise is expected to generate further investigation, analysis and research work on labour markets in LICs as the data is made freely available and accessible to researchers beyond the lifetime of the programme. / The logframe has the details of the expected outputs.

What is the context in which UK support is provided?
Labour is a key universal asset of the poor in Low Income Countries. The existence of a large informal sector suggests that labour is under-utilized in LICs, with implications for aggregate productivity (growth), poverty and inequality. A better understanding of how labour markets function and appropriate policies is critical both to facilitate growth and to ensure the benefits are shared. Demographics (a rising young population) in LICs will make it increasingly important politically, socially and economically to ensure that a growing number of people are able to benefit from growth through the labour market. We need better evidence on how to support labour markets to work effectively and deliver an increasing number of good quality better paid jobs. / The key partner in this programme – The Institute for the Study of Labour (IZA) – is the leading global research centre on labour markets. IZA provides scientifically founded advice to political and corporate decision makers. Its aim is to find sustainable solutions for the problems in today’s labour markets and to help actively shape tomorrow’s labour economics. In its role as a place of communication between economic science, political practice, businesses and society, IZA also offers information and expertise on labour market questions to a broader public. The institute works closely with other prestigious research centres and universities on national, European and international levels, with access to the largest network of labour economists worldwide / By tapping into the IZA network DFID will be able to gain access to a unique network of labour economists and policy makers through a well-established and sustainable network. The impact of the programme is likely to be sustained through the IZA network beyond the programme’s lifetime.

## Section A: Detailed Output Scoring

Output 1: High-quality research on labour markets and growth in LICs
Output 1 score and performance description: A / The program has selected 7 projects for funding, and another project has been offered seed money to develop a revised proposal. In total, 46 projects were peer-reviewed. The majority of selected projects focus on skills, trainings, and education. Very few proposals focused on labour demand and the macro research area ‘growth and labour markets’.
Progress against expected results: / Indicator 1: Number of research awards that meet the quality standards set by the Programme on a continuous basis. No milestone yet, but 7 projects have been selected for funding in the first round against an expected performance milestone of 18 projects by 2013. IZA are still negotiating the final contracts for the first 7 projects . IZA has recently issued its second call for research proposals, and is hopeful of achieving the milestone. Ultimately, however, achieving the milestone is dependent on high quality bids being received from the market, and will also depend on effective outreach by IZA to a wider set of relevant researchers. / Indicator 2: number of peer-reviewed articles, reports and conference papers produced by projects funded under the Programme. No milestone applicable, as research has yet to begin. / Indicator 3: Research conferences on labour markets and growth in LICs. No milestone yet, but IZA’s first conference will take place in November 2012. If this goes ahead as planned, IZA will achieve the 2013 milestone by end 2012. / Recommendations: / Efforts need to be made by IZA during the second call to reach new and a broader set of researchers on labour markets, following recommendations of the recent Programme Management Group meeting. / The project’s milestones are necessarily somewhat tentative in the first year or two, given this is a new area of work for both DFID and IZA. The milestones may need reviewing and adjustment after the second research call has concluded. / Impact Weighting (%): 50% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: Research use by policy makers in LICs
Output 2 score and performance description: A / No expected output at this stage of the projects, as research has yet to begin. All the selected research proposals have been asked to clarify their efforts for early engagement of policy makers. They have all responded positively and seem well connected to policy makers in LICs. All funded projects are in contact with DFID’s uptake advisor to advise on policy engagement and uptake approach in order to ensure progress against this output over the next few years.
Progress against expected results: / Indicator 1: Policy-oriented conferences on labour markets and growth in LICs / Indicator 2: Number of project-based events with policy makers to discuss existing evidence and research findings / Indicator 3: Book/ collected volume / Indicator 3: Policy briefs and synthesis products / Indicator 4: Survey of stakeholders – impact perception scores for the programme. / Recommendations: / Output and indicators still appropriate / Impact Weighting (%): 35% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 3: Capacity Building in LICs
Output 3 score and performance description: A / No expected output at this stage of the projects, as research has yet to begin. But see below for progress based on the project and budget proposals that have been selected for funding.
Progress against expected results: / Indicator 1: Number of southern researchers participating in the program. The engagement of southern researchers in proposed projects was lower than hoped for, but in the final selection of 7 projects, and after inviting some revisions, 6 projects have engaged LIC-based researchers (that excludes any local IPA staff, the NGO that carries out data collection for a number of projects) / Indicator 2: Training workshops in LICs. A first training workshop will be held in November 2012. If this goes ahead as planned, the project will have achieved the 2013 milestone by the end of 2012. / Indicator 3: Proportion of funds routed to southern researchers. Of the selected projects in Phase I, 5% of total funds requested are expenses for southern researchers, but it is not clear yet what proportion of funds will actually be routed to them. None of the selected projects are led by southern institutes. / Indicator 4: Start /end-of-program workshop. Milestone achieved: IZA organized a kick-off workshop in January 2012, which was focused on identification of research gaps. There were presentations and a panel discussion, based on 5 commissioned papers. The program website provides the presentations, papers, and a synthesis of the main conclusions of the workshop. / Recommendations: / Indicator 3 may need revision as it might not be realistic to expect 20% of the funds to be used by southern researchers. This will be reviewed after the second call and may then be revised . / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Low/Medium/High / Revised since last Annual Review? Y/N

## If the project involves more than 4 Outputs please copy the box above and paste below.
## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? N / 1.2 Overall Output Score and Description: A / Progress against the outputs has been in line with expectations. Since academic quality and policy relevance are the main criteria for selection of projects, the total number of grants may not be the most relevant output indicator (1.1). / 1.3 Direct feedback from beneficiaries / Not applicable at this stage.
1.4 Summary of overall progress / IZA organised the kick-off workshop in Paris, which resulted in 5 papers, presentations, and a synthesis of the main messages on the programme website. The first round of funding has almost been completed. In total, 47 proposals were submitted, of which 7 have been selected for funding.
1.5 Key challenges / The key challenge facing the programme is to encourage a wider range of researchers to apply and to look to route more of the research funding to southern researchers. From the first round of funding, it appeared the applications led by southern institutions were not competitive in terms of research quality. Training workshops will be used to address this challenge with the first due to take place in November 2012 in collaboration with IDRC (International Development Research Centre).
1.6 Annual Outcome Assessment / See 1.1 – 1.5. It is too early to make an assessment of progress against the project Outcome as the first research projects are just about to start.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / There is no indication that the total amount of research funding will deviate from the expected 9 million GBP over the entire programme duration. Approximately one third of the research funds will be spent on the projects selected for funding in the first phase, for which grant negotiations are just beginning. As such the exact timing of individual funding payments is not known yet. / 2.2 Key cost drivers / The major cost drivers for this project are the costs for funding research projects and uptake activities. To date there is no indication that there are will be any significant deviations. / 2.3 Is the project on-track against original timescale: Y / There is a 2-3 month delay compared to the planned commencement of the first research projects in June 2012. Grant negotiations with selected applicants are currently underway. There is however no indication that the current delay will affect the timely completion of the programme.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No changes in evidence. The program received a large number of high quality applications in the first round. Selected projects in the first round cooperate with local policy makers and other stakeholders, so there is some demonstrated interest in the program. / 3.2 Where an evaluation is planned what progress has been made? / N/A

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level / Low
Risk of funds not being used as intended / Low / 4.4 Climate and Environment Risk / Low

5. Value for Money
5.1 Performance on VfM measures / The selection process in the first round of funding was competitive (7 out of 47 applications were selected for funding) and involved external reviewing plus an internal review by the Independent Oversight Committee. / IZA is contributing a proportion of administrative costs / 5.2 Commercial Improvement and Value for Money / Besides competitive selection process and peer-reviews, continued payment of grants to funded projects will be conditional on a positive evaluation of interim reports. / 5.3 Role of project partners / The project partners IZA and DFID are playing their appropriate roles through the PMG / 5.4 Does the project still represent Value for Money : Y / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / None

7. Conclusions and actions
The project has made a good start. 7 strong proposals have been selected for funding with research work starting over the next few months. Call 2 has been issued and IZA will be making efforts to ensure a broader and new research community is made aware of the programme and encouraged to bid for the competitive grants. Efforts need to be made to increase the number and quality of southern researchers submitting proposals. A joint GLM-LIC and IDRC /World Bank event is planned in November.

8. Review Process
Discussions between DFID and IZA at the Programme Management Group two day meeting in June 2012. Review by DFID lead adviser, programme staff and IZA Directors and annual report.