Business Case and Intervention Summary

Intervention Summary

## Title: St. Helena Short Term Technical Co-Operation
What support will the UK provide?
DFID’s annual package of support to the St. Helena Government (SHG) includes provision of technical expertise in the form of personnel, advice, training and research where these needs cannot be fully met from local resources. This Business Case argues to increase the funding level available by £300,000 for SHG to access specific, time bound technical expertise (typically 4-6 months in duration but no longer than 24 months) and called Short Term Technical Co-Operation (STTC). The STTC project was first approved in November 2010 and provided £495,000 until the end of the 2011/12 financial year. Increasing funding by £300,000 at this time will allow SHG to continue work already in progress this year and to secure additional identified TC priorities. This increase brings the total budget for STTC to £795,000.

Why is UK support required?
SHG has long recognised capacity constraints due to the island’s remote location and small population. Between 1990 and 2008 the resident population on St. Helena declined from 5,750 to under 4,000. The small population and outward migration where key workers have sough employment overseas (namely in Ascension Island, the Falklands, and the UK) means that for many years SHG has not been able to meet its staffing and expertise needs from the local population. / In addition to these challenges, SHG ability to use its own revenue to buy-in technical expertise is currently very limited. The island’s low income base limits the volume of domestic revenue that can be raised and its isolation inflates the costs of providing a range of basic public services. HMG provides around 55% of the island’s recurrent expenditure, without which, SHG would be unable to provide for the reasonable needs of its citizens. / SHG and DFID are working to address long-term capacity by growing home talent through improving educational attainment levels and through activities such as scholarships, vocational training, on the job training and increased internet bandwidth for distance learning. Nonetheless in the short to medium term, SHG will continue to need support to be able to access short term technical knowledge from overseas that cannot presently been sourced locally and would otherwise be beyond the reach of its budget.

What are the expected results?
As a result of this project, SHG will gain crucial analysis and evidence to inform their policy making which will lead to more effective delivery of essential public services on the island. UK support will also augment SHG’s ability to design and implement reforms to open the island’s economy to greater levels of inward investment and increased tourism (as the Memorandum of Understanding led change agenda is now mainstreamed through SHG).[1] Finally, extra STTC will also result in a more efficient and effective SHG through work on systems and management.
[1] The December 2010 Memorandum of Understanding (MoU) between SHG and the UK Government outlined a series of reforms to open St. Helena’s economy to greater investment and tourism. Successful progress against the MoU was one of the Secretary of State for International Development’s four conditions for airport access in his July 2010 House of Commons Statement on St. Helena.

Business Case

Strategic Case

A. Context and need for a DFID intervention / Overseas Territories’ needs are not judged by the same criteria as those of developing countries. Citizens of the Overseas Territories (OTs) have the automatic right to British citizenship, and most of the OTs have achieved the MDGs. The International Development Act 2002 specifically exempts aid to the OTs from the poverty reduction criteria that apply to the rest of the DFID aid budget. With the exception of the EC, the UK Government is the only source of grant funding carries ultimate liability for the OTs. / Successive White Papers since the 1970s have committed the UK Government to meet the “reasonable assistance” needs of the OTs. The UK Government’s obligation to the OTs is also enshrined in the UN Charter: “to promote to the utmost … the well-being of the inhabitants of these territories…” The OTs are not explicitly mentioned in the Coalition Document. However the One World Conservatism manifesto document restates that the reasonable assistance needs of the OTs should remain a first call on the aid programme and that the ultimate goal is to move all of the OTs towards self-sufficiency. / The need for DFID support of STTC is based on two factors. First, there is very limited additional technical expertise in desired policy areas available from the small population on the island. Second, SHG’s own ability to fund needed technical expertise of a high quality international standard from their revenues is very limited. / While DFID assistance will continue to bridge budgetary gaps and ensure that reasonable needs are met, the overall objective of UK development assistance is to reduce St. Helena’s dependence on aid and set the island on a firm path to financial independence. This is the reason why the Government agreed in November 2011 to build an airport on St. Helena to provide the island with the best possible opportunity to build an economy which, in the long term, is expected to lead to financial self-sustainability. In time, it is expected that air access will facilitate the economic and social development of the island driven by a significant tourist industry that will increase local revenues to the point that budgetary aid will no longer be required. / To take full advantage of the economic opportunities that the airport will bring, SHG is making a large scale series of reforms to tax, investment, land, and immigration policies and legislation in order to encourage private sector activities and attract new investors. Significant progress has already been made in formulating the new policies and a significant amount of work remains for SHG to implement these reforms. / The need for £300,000 in additional resources over what was first allocated (£495,000) when the project was originally approved in 2010 has multiple causes. Among them are that SHG are beginning to improve their ability to benefit from STTC and to contract expertise more swiftly. There is also a significant need for technical expertise across the range of key areas this year (land, immigration, tax, investment) where SHG are designing and implementing policy and statutory reforms to open the economy ready for air access led growth. Finally, SHG’s Finance Directorate has increased need for support this year to fund finance system expertise and training as SHG transition to a new accrual accounting system which harmonises how all Directorates manage and input their budget information.
B. Impact and Outcome that we expect to achieve / In terms of impact, this project supports two of the three Pillars recorded in the Operational Plan of DFID’s Overseas Territories Department which is published on the DFID website. Specifically these high level priorities are: Pillar 1 – to meet the reasonable assistance needs of Overseas Territories citizens cost effectively; and Pillar 2 – to accelerate aid-dependent Overseas Territories towards self-sufficiency. / The desired outcome is improved capacity of the public sector in St. Helena where SHG’s policy making and implementation benefit from international high quality technical expertise across different sectors. / Planned specific outputs directly attributable to DFID include technical expertise in: / land control and development policies; / implementation of new Immigration Ordinance; / tax auditing function; / management of the SHG estate; / human resource; / telecoms & TV licensing; / Crown Council locum support; / welfare finance; / financial systems; / tax reform and investment; / accruals accounting and financial management training; / banking insurance and venture capital; and / tax modelling.

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / Option 1 – provide an additional £300,00 in support for STTC / Option 2 – provide less than an additional £300,000 in support for STTC / Option 3 – do nothing
B. Assessing the strength of the evidence base for each feasible option / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited / Option Evidence rating / 1 Strong / 2 Strong / 3 Strong / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C A / 2 B B / 3 A C / Option 1 minimises risks and maximising opportunities by enabling SHG to access independent technical expertise in climate change and environmental management if SHG requested and DFID judged this support to be value for money. This may be particularly pertinent in the context of land control and development policies and management of SHG estate where environmental considerations and the unique natural heritage of the island are integral to these issues. / Option 2 present medium risks and medium opportunities as SHG will have limited access to technical expertise in climate change and environmental management but only if these needs were considered of a higher strategic importance that other identified technical capacity gaps among SHG Directorates. In short, if STTC funds are more limited, environmental concerns would have to compete against other SHG prioritises for funding and would be less likely to get support. / Option 3 maximises risks and minimises opportunities as SHG would have no ability to access additional technical expertise outside of that which already exists on island. Given ongoing land reform, tourism development and that the unique natural environmental in St. Helena will be a key driver of tourism, this option is unacceptable.
C. What are the costs and benefits of each feasible option? / Option 1 – provide an additional £300,00 in support for STTC / An additional investment in technical co-operation of £300,000 will meet the remaining schedule of technical inputs this year that SHG and DFID judge to be necessary to buy-in technical advice immediately. This includes, land control and development, immigration, tax auditing, tax reform and investment, financial management and banking advice. The additional £300,000 is fully allocated for technical help across SHG Directorates and requests the minimal amount to cover needs with no unallocated funds. / Option 2 – provide less than an additional £300,000 in support for STTC / Providing less than £300,000 would mean that SHG would be unable to seek technical expertise across areas identified as an immediate priority for support. They would have to further cut what is already a highly prioritised list. Constraining SHG’s ability to buy-in technical support at this transformational time in the island’s history as it prepares for air access comes with high costs that policy is not fully developed across all areas and reforms are delayed and not successfully implemented. / Option 3 – do nothing / This option is excluded as it is essential that SHG are able to access technical expertise of an international standard. The high level risk of doing nothing is that the island sinks into further decline with failing services, higher costs of living, ineffective social welfare, and a further outward migration. Doing nothing could be seen as the UK breaking its obligation to meet the reasonable assistance needs of the OTs and would not capacitate St. Helena to prepare for air access opportunities.
D. What measures can be used to assess Value for Money for the intervention? / As this is an umbrella project, each request for individual STTC support is assessed for Value for Money. Approval for all short-term TC posts will need to be obtained by SHG from DFID in advance, with the provision of full Terms of Reference and a financial proposal. DFID will be kept informed on recruitment of Short-term TC posts through monthly monitoring reports and regular teleconference calls. The purpose of this Business Case is therefore to gain umbrella approval for an over-all sum; it does not remove the requirement for us to approve each proposed post on an individual basis judged against VfM. / It is also important to note that some elements of TC support are “spend to save” initiatives and lead to efficiency savings in the recurrent budget in future years. For example, TC support earlier this financial year supported SHG to harmonise financial data across Directorates which contributed to headcount savings as fewer staff now manage financial data.
E. Summary Value for Money Statement for the preferred option / The £300,000 cost to increase the capacity of SHG in this transformational year of reforms and airport contract signature represents value for money judged against the evidence base of previous performance of STTC inputs and the programme of priority inputs scheduled for this year. Constraining SHG’s ability to buy-in high quality international expertise this year would risk the reform agenda and ultimately the ability of St. Helena to lay the foundations to take full advantage the opportunities that air access will bring while improving their own efficiency and maintaining essential public services.

Commercial Case

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The proposed mechanism is Non-Budget Support Financial Aid. Until recent years, all TC was paid for and contracted directly by DFID. It was a shared DFID and SHG goal to localise recruitment of TC officers that had traditionally been recruited by DFID. In 2007, changes to UK employment law and pressure to lower DFID’s headcount numbers made it untenable for DFID to continue to recruit fixed term TC contractors. This necessitated a new approach to all TC posts and OTD has since delegated most recruitment and contracting directly to SHG.
B. Value for money through procurement / Overseas Territories Department’s (OTD) will work with SHG to ensure the “3 Es” – Economy, Efficiency and Effectiveness are followed when procuring services indirectly under this scheme and where appropriate competition will be sought. / Using the Terms of Reference and Financial proposal for each sought after technical input, DFID advisers will assure that ToRs are appropriate and represent only the highest priority inputs sought that could not be sourced on island. Financial proposals will be assessed by SHG HR, the Chief Secretary and finally DFID’s St. Helena Programme Team to ensure they are in line with market averages. If needed, advice will be sought from DFID procurement of average market rates in certain sectors. Additionally, SHG’s Terms and Conditions for contracting short term inputs are no more generous than DFID’s own and DFID will ensure this remains the case.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / DFID’s current STTC project was developed through 2010, approved in November 2010 and provided £495,000 to work up to the end of the 2011/12 financial year. Increasing funding by £300,000 this year will allow SHG to continue work already in progress and to secure additional identified TC priorities. / This is a cost extension to a two year project allocation of £495,000. Increasing the budget by £300,000 represents a 60% increase and brings the total budget to £795,000. Against the revised project total about 47% of funds (£376,500) were consumed in 2010/11 and SHG forecast expenditure of 53% in 2011/12 (£418,500). / Costs are forecast by SHG’s Human Resource Department and quality assured by the Chief Secretary and by DFID. DFID and SHG will work together to improve accuracy of forecasting. The newly arrived Chief Secretary will drive performance across SHG Directorates ensuring timely and efficient use of STTC funds.
B. How will it be funded: capital/programme/admin? / This funding will be met from OTD’s St. Helena programme resources.
C. How will funds be paid out? / DFID will reimburse SHG for STTC costs quarterly in arrears on receipt of their detailed and certified claim. Funds will be paid from DFID Accounts through Crown Agents Bank to SHG’s bank account.
D. What is the assessment of financial risk and fraud? / Risk is low as budgets will be agreed for all STTC inputs prior to each assignment and expenditure will be monitored throughout the year. Moreover, DFID will pay only in arrears based on SHG certified claims and DFID’s representative to St. Helena may perform spot checks on the documentary evidence that supports each claim if considered necessary. Finally, the Chief Auditor produces an opinion each year that covers Financial Aid to SHG.
E. How will expenditure be monitored, reported, and accounted for? / At a management level, SHG will maintain a monthly monitoring statement that will include: / approved budget by individual post; / actual spend to date by individual post; / forecast spend for the year by individual post; and / updated status for each post (e.g. post advertised/preferred candidate selected/contracts signed/in post, completed) with expected start date and contract end date. / This monitoring sheet will help the Chief Secretary drive performance and it will be shared monthly with DFID and teleconferences scheduled to discuss progress as necessary.

Management Case

A. What are the Management Arrangements for implementing the intervention? / The Chief Secretary will oversee and coordinate this assistance with support from SHG Finance Department and SHG Human Resources Department. Within DFID, the St. Helena Programme Team will manage the provision and performance of the project. The team will consist of an A2 Programme Manager, a B2 Programme Officer and a C1 Programme Assistant. Advisory input will be sought as necessary. The project team is accountable to the Head of DFID’s Overseas Territories Department. / In September 2010, a TC Protocol was agreed between SHG and DFID. This protocol sets out a standard management approach for the application of Technical Co-operation (TC) funding. It defines the different types of TC funding, and sets out the principles to be adopted for the approval of new posts, changes to budgeted posts, communication with DFID, approval within SHG and the monitoring of expenditure. It is reviewed annually at each DAPM to ensure it remains fit for purpose.
B. What are the risks and how these will be managed? / The overall risk assessment is low. Expenditure will largely be on small and relatively simple to administer discrete pieces of technical assistance. The Chief Secretary will oversee and coordinate this assistance with support from SHG Finance Department and SHG Human Resources Department.
C. What conditions apply (for financial aid only)? / Not applicable.
D. How will progress and results be monitored, measured and evaluated? / Monitoring of the performance and impact of technical assistance will be through routine reporting from SHG and through the DFID project review process. This reflects well-established practice. The St. Helena Programme Manager will conduct a PCR review at the end of the programme appropriate for projects of this total value.
Logframe / Quest No of logframe for this intervention: 3408517