Business Case

Tackling Visceral Leishmaniasis in South Asia and East Africa

March 2013

Contents

Acronyms and definitions

Active case detection	Health workers or village health workers go to communities and screen the population to find cases (see also ‘Passive case detection’).
AmBisome®	Commercial name of liposomal amphotericin B (see below), manufactured by Gilead. AmBisome is the only quality assured product currently available. In 2011 Gilead announced a donation for selected uses for VL over 5 years.
BMGF	Bill and Melinda Gates Foundation
CFR	Case fatality rate
CHAI	Clinton Health Access Initiative
C&E	Climate and Environment
Cutaneous Leishmaniasis	The most common form of Leishmaniasis. It usually produces ulcers on exposed parts of the body. The condition self heals but leaves scarring. Cutaneous Leishmaniasis (CL) is not addressed by this business case.
DALYs	Disability adjusted life years. A measure of the overall impact of a disease, which takes into account premature deaths and the length and severity of disability due to sickness. The number of DALYs lost as a result of a disease is calculated by estimating the number of years lost due to premature death plus equivalent years of ill health.
DDT	Dichlorodiphenyltrichloroethane - an insecticide. Its use for public health purposes (disease vector control) is strictly governed by the protocols of the Stockholm Convention on Persistent Organic Pollutants (POPs).
DNDi	Drugs for Neglected Diseases initiative which works on developing drugs for VL among other neglected diseases.
Elimination	Elimination as a public health concern (defined as fewer than one case per 10,000 population in affected areas).
GDP	Gross domestic product
GNI	Gross national income
HIV	Human immunodeficiency virus
IRS	Indoor residual spraying. A method of vector control involving application of a liquid insecticide with long lasting residual properties to the walls of a building (every 6 months for VL).
Kala azar	Commonly used name for VL, Visceral Leishmaniasis
Liposomal amphotericin B	VL medicine, currently recommended as first choice to treat VL in Asia by the WHO Expert Committee on the control of Leishmaniases (2010). Treatment is either for 3-5 days or a larger dose given in one day. It is being introduced in Africa for use in complex cases. Administered via intravenous infusion.
LLIN	Long lasting insecticide treated net
MDA	Mass drug administration involves distribution of medicines to vulnerable communities as a preventive measure. Used for other NTDs such as schistosomiasis and worms, but not relevant for VL.
M&E	Monitoring and evaluation
MF (miltefosine)	The only oral treatment available for VL (the other treatments require injections). MF needs to be taken for 28 days.
MOH	Ministry of Health
MOU	Memorandum of Understanding
MSF	Médecins sans Frontières
NPV	Net Present Value
NTD	Neglected tropical disease
OR	Operational research
Passive case detection	Detection triggered by patients seeking care for their illness from clinicians working in fixed health facilities. Reliance on passive case detection risks leaving many cases undiagnosed.
Phlebotomine sandflies	Insect vectors that spread leishmania parasites. In Asia, the sandflies live in and around houses and their numbers can be reduced with indoor spraying of insecticide (IRS). There is also some evidence of the value of insecticide treated nets. In East Africa, there are different types of sandflies involved, which tend to live in woods and in cracks in the ground and termite mounds. The impact and cost effectiveness of insecticide spraying or nets have not been demonstrated in this region.
PIC	Prior Informed Consent
PKDL	Post Kala-Azar Dermal Leishmaniasis. A complication of VL, it develops in some people following treatment for VL and such people may serve as reservoirs.
POP	Persistent Organic Pollutant
Pyrethroids	A class of synthetic pesticides (similar to the pyrethrum - a natural pesticide) used as an insecticide.
RDT	Rapid diagnostic test.
RK39	A rapid diagnostic test for VL. RK39-based tests are easy to perform, quick, cheap and give reproducible results; they can be used for early diagnosis of VL at both peripheral and central levels.
SSG+PM	Sodium stibogluconate + paromomycin: VL treatment recommended for first line use in Africa, administered as a course of injections over 17 days.
TDR	Special Programme for Research and Training in Tropical Diseases
UNEP	United Nations Environment Programme
VC	Vector control
VL	Visceral Leishmaniasis, also known as kala-azar
WHO	World Health Organization

Intervention Summary

Tackling Visceral Leishmaniasis in South Asia and East Africa

What support will the UK provide?

The UK will provide up to £27.3 million over 4.5 years in order to tackle the neglected tropical disease visceral leishmaniasis (VL), also known as kala-azar. The support will focus on the two regions that carry the heaviest burden of this killer disease: South Asia, where VL is concentrated in the border areas where Nepal, India (mainly Bihar state) and Bangladesh meet; and in East Africa, where it occurs in parts of South Sudan, Sudan, Ethiopia and on a smaller scale in Kenya, Uganda and Somalia.

VL is much neglected. This programme addressing VL is a groundbreaking UK initiative to help countries in these regions combat this very neglected disease. There has been very limited donor support for VL to date and unlike many other diseases there is no specific partnership to address VL. New, more effective tools for diagnosis and treatment are now available and need to be made more accessible to people affected by VL. A recent donation by a pharmaceutical company of one highly effective medicine for some affected countries has provided an impetus to expand treatment, but further support is needed to make effective use of the donation. In Asia, where there is public commitment to tackling VL, there is evidence of poor quality of efforts. VL particularly in Africa remains poorly understood and therefore a large operational research programme is built into the design.

DFID will support the efforts of India, Bangladesh and Nepal to make progress towards eliminating VL, and assist at least three African countries with expanding their capacity to detect and respond to VL. The support will be tailored to each country’s needs and integrated with existing programmes and health systems. In Asia it will include providing technical support; strengthening surveillance and training; and identifying cost effective methods to improve VL prevention and to expand access to diagnosis and treatment, while national governments and the donation will fund diagnostic tests, medicines and preventive services. In Africa it will include expanding surveillance, diagnosis and treatment of VL within national health systems, including procurement of the necessary medicines; operational research and piloting to identify effective methods of prevention; and response to emerging outbreaks.

The programme will result in a fall in the economic and health burden caused by VL in the two regions. It will help the South Asian countries make faster progress towards elimination of VL as a public health problem, while in East Africa it will reduce deaths from VL and build up the evidence on ways to prevent this disease.

This programme will be managed by the Health Services Team in London, and at country level will work closely with DFID offices, relevant programmes and other partners.

Why is UK support required?

VL is a disease that affects the poorest in society, typically in poor and remote areas of the country. It affects children and young adults and also displaced and migrant people. It is made worse by malnutrition and HIV. Left untreated, it kills the infected person. It causes suffering in terms of fevers and inability to work in the months or years before death. VL typically strikes agricultural areas, where loss of capacity among working household members is a significant blow to family income. Clustering of incidence means that particular communities may be devastated.

While data remains approximate, the annual incidence in South Asia is estimated at almost 240,000 cases, and in East Africa there are over 40,000 cases, and epidemics occur which can lead to much larger numbers of cases if not controlled.[1] Together the regions have 95% of the estimated global incidence of the disease.
[1] WHO Leishmaniasis worldwide epidemiology and access to medicines: an update 2012, www.who.int/leishmaniasis/resources/leishmaniasis_epidemiology_access_to_medicine/en/index.html

Until recently, diagnosis and treatment for VL were both painful and risky. New diagnostic tests have emerged which are quick and much easier to use. New treatments have transformed the potential for curing people with very high cure rates, good safety records and in most cases, shorter treatment periods[2] than 30 days of painful injections that were needed in the past.
[2] The newer medicine treatment regimes range from a single infusion of liposomal amphotericin B in Asia (Gilead’s AmBisome is the quality assured product) to 28 days oral treatment with miltefosine.

Yet there are people with VL who do not get access to these newer, better diagnostics and/or treatments. They may live in remote areas, lack funds for seeking treatment, or be given inappropriate treatment. Some providers lack training in VL and up to date medicines, particularly many private providers in India; and patients incur costs for inappropriate treatment and delays before reaching a provider who diagnoses and treats them correctly. Access tends to be limited among the poorest groups, and studies suggest women tend to have longer delays in access to treatment and are more likely to die from the disease.[3]
[3] Higher death rates among women were found by Alhuwalia IB, et al. VL: consequences to women in Bangladesh. 2004, with 14.7% deaths among women, 5.3% among men.

VL is a vector borne disease spread by insects (sandflies) whose ecology and behaviour is highly variable – in South Asia they mostly tend to live in cracks in the walls or floors of mud houses, while in East Africa, where sand fly behaviour is less well understood, they can breed in cracks in dried-out soil and trees. In Asia, indoor residual spraying with insecticide (IRS) is effective in reducing VL transmission and this is underway in India and Nepal (and to a limited extent in Bangladesh) but there is scope to improve the quality of spraying and better targeting in order to increase its impact. In Africa, indoor residual spraying and the use of bed nets appear to be less effective prevention methods and more research is needed on effective vector control. Other insecticide treated products have been developed, which need to be tested in a range of settings to see where they would be most useful.

To tackle VL effectively requires:

- awareness among community members and private health providers to refer suspected cases for diagnosis and treatment;
- more access to diagnosis at community or primary care level;
- capacity to provide the modern treatments as recommended by WHO and the national authorities;
- well targeted and high quality vector control to prevent transmission;
- with better surveillance and case recording so that outbreaks can be spotted and the affected areas targeted with active case finding and prevention activities,
- with emergency responses ready, particularly in Africa where there tend to be large outbreaks.

Modelling suggests that the programme is highly cost effective, with cost per death averted of £582 and cost per disability adjusted life year (DALY) of £37 (allowing for its impact over ten years).[4] Taking into account DFID’s share of funding of the programmes, the number of lives saved by DFID support is 47,000, with over 730,000 DALYs averted. The average annual number of deaths averted by the programme during its four years of operation would be the equivalent of almost half of the estimated global annual deaths.[5]
[4] Benefits are assessed over ten years to reflect continued impact after the programme in Asia, due to lower incidence of VL. Costs and DALYs are discounted at 10%.
[5] Using estimate of 30,700 deaths per year from Global Burden of Disease, which are based on 2004 data. Consistent mortality estimates are given in WHO 2012 Leishmaniasis Update (op cit) which estimates mortality in the range of 20,000 to 40,000 deaths per year, virtually all due to VL. The modelling estimates annual average deaths averted of 14,161 during the programme period.

In South Asia, the countries involved already have active programmes to address VL with the goal of elimination as a public health problem. The regional target date of 2015 may not be realistic, and the global elimination target set as 2020, is optimistic according to the modelling for this business case. The modelling suggests that incidence and the burden of VL can be reduced substantially and DFID support will help them bring elimination more than two years closer than would otherwise be the case. It will help to improve the quality and coverage of the interventions needed, including spraying homes with insecticide, case-finding and prompt and effective treatment of diagnosed cases. It will also enable better monitoring of progress, evaluate which strategies are most effective and help to improve management and procurement for these services. DFID’s inputs will complement governments’ which will fund the supplies and staff costs involved, and coordinate closely with the support from other partners. It is expected that the support will focus on Bihar state in India and affected districts in Bangladesh, with modest technical support for Nepal’s increasingly successful VL elimination programme.

In East Africa, DFID support will develop capacity for VL control, including expanding access to diagnosis and treatment in Sudan, South Sudan and at least one other country. This will reduce the death toll and suffering from VL and provide the evidence base for future control. Since VL is more epidemic in nature in Africa, with major outbreaks occurring every 5-10 years. DFID will support enhanced disease surveillance and build capacity for responding to outbreaks, in order to ensure early detection of disease outbreaks and minimise their spread and impact. DFID support will also increase knowledge of the incidence and epidemiology of the disease and the behaviour and control of sand fly vectors, with piloting and evaluating alternative preventive tools in different settings, including innovative methods such as cattle dips[6] and treated screens designed for people who sleep outdoors.
[6] In East Africa, domestic animals are thought to be reservoirs for VL, so there may be scope to reduce transmission through methods that target these animals.

What are the expected results?

The expected results are a significant reduction in the economic and health burden due to VL in East Africa and South Asia over the programme period. The benefits of the programme are summarised by region in Table 1. The programme includes DFID’s contributions and the inputs of other partners, notably national governments and the drug company Gilead, which has donated its highly effective treatment, AmBisome for some of the affected countries. DFID’s contribution is some 68% of the total programme.

It is anticipated that some 265,000 cases would be treated for VL over the programme period, of which 180,000 (68%) can be attributed to DFID support. Of these, some 5,000 cases are expected to be HIV positive.
Table 1. Summary of benefits by region (for the whole programme including both DFID and non-DFID funds)

Type of benefits	South Asia	East Africa
Health benefits during the programme	VL cases are identified more quickly and get good quality treatment. . An estimated 222,000 cases will be treated through the programme. / Better access to good quality care for women and poor VL cases, reducing disparity between male and female death rates from VL. / Better quality prevention and prompt management of cases expected to lead to 83,000 fewer cases of VL during the programme. / Estimated that 250,000 DALYs will be saved in 4 years, including 8,000 VL deaths averted.	Major increase in the proportion of VL cases detected and treated: coverage projected to more than double to 46% of annual cases, with over 43,000 cases treated under the programme. / Emerging outbreaks identified early (within 4 months[7]) and responded to effectively, leading to fewer cases and deaths.[8] It is estimated that 53,000 VL cases will be prevented by the programme. / Estimated to avert 48,000 deaths from VL, contributing to 520,000 DALYs averted.
Longer term benefits	Lower and declining prevalence of VL in each country is sustained beyond the end of the programme. This leads to an estimated 121,000 fewer VL cases and an additional 290,000 DALYs averted in the 6 years following the programme. / Capacity developed for more effective vector control (better quality, safer environmentally and better targeted). / Sound information on epidemiology of VL and strengthened monitoring systems support elimination efforts. / These benefits contribute to elimination as a public health problem at local level.	Methods for VL prevention identified, piloted and disseminated. / Capacity for VL detection and treatment developed within each country’s health system. / Sound information on epidemiology of VL and monitoring systems enable effective responses and guide future planning.
Economic benefits estimated from the programme	Shorter delays before treatment and fewer deaths result in £410m of productivity saved over 10 years.	Higher proportion of VL cases treated leads to £370m of productivity saved.
[7] A target of 4 months was suggested by WHO as achievable and realistic. In the past some outbreaks took a year to identify.
[8] VL epidemics are a frequent occurrence in East Africa, and history suggests that another is more likely than not during the programme period. The programme is expected to reduce the scale of epidemics and this will save lives. Conservative modelling of the programme’s benefits does not assume additional cases are treated during an epidemic, beyond the planned increase in numbers treated each year as VL services are scaled up.

Strategic case

A. Context and need for a DFID intervention

a) The scale and nature of the disease

Visceral Leishmaniasis (VL, also known as Kala-Azar) is one of the most neglected tropical diseases (NTDs). It affects poor communities in South Asia, East Africa and Brazil and on a much smaller scale in the Middle East and Europe. The current estimated number of cases of VL is in the range of 200,000 to 390,000 cases per year, with some 30-60,000 cases in East Africa and 160-310,000 cases in South Asia.[9] However one feature of it being neglected is that data on VL is incomplete, as many patients are not reached or recorded by the health system; in addition the numbers vary from year to year, with epidemics in East African countries every 5-10 years. This explains the wide range in the estimates.
[9] Source: Latest estimates based on country data, expert opinion and literature review, published in 2012, see Leishmaniasis worldwide epidemiological and drug access update, WHO website, and also published in PLoS-One: http://www.plosone.org/article/info%3Adoi%2F10.1371%2Fjournal.pone.0035671

Left untreated, VL leads to death in around 95% of cases, compared with 3-10% of treated cases.[10],[11] Even successful treatment can be associated with severe economic distress, for example for subsistence farmers.[12] For 2008 it has been estimated that VL caused some 30,700 deaths and loss of 785,000 disability adjusted life years (DALYs) in Africa and Asia[13], Numbers of deaths can increase significantly when epidemics occur in East Africa, where even in non-epidemic years most VL sufferers are not treated. VL tends to affect children and younger adults (who have not built up immunity).[14] VL interacts with HIV  people from VL endemic areas who are HIV positive are far more likely to become ill with VL and are harder to cure.[15]
[10] In a facility setting – up to 20% in a community setting. Source: WHO NTD department.
[11] Estimated from NTD Department, WHO.
[12] Due both to productive time lost and costs of seeking diagnosis and treatment. See Ahluwalia et al on Bangladesh for example “The long and short term costs to families are enormous. ...treatment requires borrowing money and selling or leasing land or animals, leaving the household destitute.”
[13] DALYs are disability adjusted life years and are a measure of the overall impact of a disease. Based on Global Burden of Disease estimates that used 2004 data. New estimates for 2010 are due soon.
[14] A multi-country study of patients presenting for treatment (not all cases). It found 40% were female overall. In Gedaref state, Sudan, 30% of patients were under 5 and 39% aged 5 to 15 compared with 10% under 5 and 39% 5 to 15 in Bihar, India (Harhay et al, Who is a typical patient with VL?, Am J Trop Med Hyg, 2011, 543-550).
[15] Alvar et al, The relationship between Leishmaniasis and AIDS: the second 10 years. Clin. Microbiology Reviews, Apr 2008, 334-359.

Table 2. Estimates of VL case numbers by region and selected countries

Country/Region	Average annual reported cases*	Estimated VL annual cases*	Estimated deaths and DALYs**
All South Asia	42,623	162,100 – 313,600	23,700 deaths; 400,000 DALYs
Bangladesh	6,224	12,400 - 24,900
India	34,918	146,700 – 282,800
Nepal	1,477	3,000 – 5,900
All East Africa	8,569	29,400 – 56,700	7,200 deaths / 385.000 DALYs
Sudan	3,742	15,700 – 30,300
South Sudan	1,756	7,400 – 14,200
Ethiopia	1,860	3,700 – 7,400
Kenya	145	610 – 1200
Uganda	288	350 – 520
Other regions ***	7,039	10,700 – 18,800
Of which Brazil	3,481	4,500 – 6,300
Total global	58,227	202,000 – 389,000	35,900 deaths

* Source: WHO, Leishmaniasis worldwide epidemiology and access to medicines: an update 2012. Note figures for East Africa are based on non-epidemic years; epidemics are expected to cause additional cases above these estimates.
** Estimates of deaths for 2008 from Global Burden of Disease estimates (based on 2004 data). Estimates of DALYs for Asia from WHO SEARO website and for East Africa from Reithinger et al 2007, Visceral Leishmaniasis in eastern Africa - current status. Trans R Soc Trop Med Hyg.Dec 101(12): 1169–1170.
*** Other regions are Americas; Middle East and central Asia, and Mediterranean.

Studies from Bihar in India, Bangladesh, Nepal, Kenya and Uganda show that VL affects the poor and the poorest.[16] The impact is through various mechanisms including poor housing conditions and lack of personal protection such as bed nets. VL is associated with poverty, illiteracy, malnutrition, and lack of access to health services. Poor nutrition accelerates the progression of the disease and mortality. People displaced due to war and economic migrants are vulnerable when they move into or through VL endemic areas. In Asia it is also shown that members of the household and neighbours of a VL case are far more likely to get the disease.
[16] Boelaert M, et al, The poorest of the poor: a poverty appraisal of households affected by VL in Bihar, India. Trop Med Int Health 2009; 14(6): 639-644. Adhikari SR, Maskay NM.The economic burden of Kala azar in households of the Danusha and Mahtlari districts of Nepal.Act Trop 2003; 88: 1-2. Anoopa Sharma D, et al. The economic impact of VL on households in Bangladesh. Trop Med Int Health 2006; 11:757-764.Kolaczinski et al, Risk factors of VL in East Africa: a case-control study in Pokot territory of Kenya and Uganda. Int J Epidemiology 2008; 1-9.

Lack of knowledge of the disease and its symptoms, poor physical and financial access to informed carers, and the poor availability of providers with the know-how and supplies to diagnose and treat VL, are significant barriers to treatment. One village based study in India found as many as 20% of VL cases died before their illness was diagnosed, and the fatalities were disproportionately among the poor and women.[17] It is estimated that the majority of cases in Asia are treated at some stage, while in Africa cases are more likely to have no treatment and die as a result. For example, in areas around Médecins Sans Frontières (MSF) clinics in southern Sudan in 1990-2002, it was estimated that 91% of VL deaths were undetected.[18] Evidence on epidemiology and about treatment is in general more available in Asia than Africa, so the proposed programme aims to address many of the most acute evidence gaps in Africa.
[17] WHO.Report of a meeting of the WHO Expert Committee on the Control of Leishmaniases. March 2010.
[18] Collin et al, Unseen Kala-azar deaths in Southern Sudan 1999-2002, Trop Med Int Health, 2006 Apr;11(4):509-12. http://www.ncbi.nlm.nih.gov/pubmed/16553934

There is unequal access to services by gender. A population based survey in Bangladesh found a case fatality rate from VL of 14.7% for females compared to 5.3% for males.[19] Women’s delayed care seeking in Bangladesh is linked to social norms and women’s low social status. Women reported that husbands are unwilling to spend money on their health care. Added to the social barriers to care is the weak nutritional status of poor women in Bangladesh. In both Asia and Africa there is a longer delay between symptoms and receiving treatment for females than men.[20] Addressing such gendered barriers to health care needs to be factored into the design of control strategies.
[19] Alhuwalia et al. 2004.VL: consequences to women in Bangladesh. Women’s Health (Larchmt) 13(4):360-4.
[20] Ahluwalia et al, 2004, as above.

The disease causes fever and reduces the patient’s ability to work. It can take up to 2 years to cause death. VL is not easy to recognise and diagnose clinically – patients’ fever and other symptoms can be mistaken for other diseases (such as TB). People may spend time and their limited resources on treatments that are inappropriate before they are diagnosed with VL and some treatments for VL are expensive for families. In India there is a particular problem with patients using private providers who may not diagnose VL correctly or who provide incorrect treatments. Combined with losing the productivity of the affected family members, this means VL contributes to household poverty.

When VL is treated, then people can be cured but a proportion go on to develop a (non-fatal) skin condition called Post Kala-Azar Dermal Leishmaniasis (PKDL), which is thought to exacerbate the spread of the disease to other people if left untreated.[21]
[21] PKDL skin lesions contain high concentrations of the parasite, so it is thought to act as a reservoir for parasites. In East Africa most cases of PKDL heal spontaneously, but this is not the case in India.

b) Prevention, diagnosis and treatment of VL

Prevention. The disease is caused by a parasite that is spread by bites of an insect vector, small phlebotomine sandflies. The pattern of disease transmission, progression and behaviour of the vectors varies by region, complicating the picture. In Asia, the sandflies live in and around houses, making it possible to reduce their numbers with indoor spraying of insecticide (IRS).Insecticide impregnated nets can also be protective. In East Africa, the sandflies tend to live in woods and in cracks in the ground, and cannot readily be reached with insecticide spraying, while people more often sleep outside, so making bednets less useful; optimal approaches to vector control are still being identified. Different types of sandflies are involved  with one type in Asia and four types identified so far in Africa. Further work is needed to identify cost effective and practical preventive measures that suit the diverse climatic and cultural contexts and ways of life in the areas affected in Africa.

Case finding and diagnosis. The recent development of rapid diagnostic tests (RDTs) have made diagnosis much easier and cheaper. The commonly used RDT at present is RK39, which works particularly well in Asia. In Africa it misses some cases, so a second diagnostic test is used. Work is underway to test other RDTs in Africa. The availability of RDTs makes active case finding more feasible, as health workers and trained community workers can visit an area with high risk of VL (for example, the home village of an existing VL patient) and test community members with relevant symptoms, rather than waiting for them to come to health services for treatment. Earlier detection and treatment means cases are infectious for a shorter time and people get treatment before their VL becomes very severe, as well as reducing the economic impact from productive time lost.

Treatment. In the past, the methods for treatment of VL involved invasive diagnosis and lengthy hospital treatments and the medicines were toxic in themselves. In addition resistance developed to these treatments in some areas. Newer treatment options have transformed the potential for treating more people, and greatly increased the effectiveness and safety of treatment. The newer treatments are also cost effective. There are currently different medicines used for treating VL in South Asia than in East Africa.[22] Trials are underway to test different combinations and treatment regimes of the various medicines available, so it is possible that countries will change their choice of first and second line medicines during this programme.
[22] Current medicines include: Liposomal amphotericin B (commercial name AmBisome) has recently been shown to be effective after just one dose in South Asia. The WHO Expert Committee on Leishmaniasis has recommended AmBisome as the first choice for Asia given its high efficacy, safety and high compliance with treatment,with one to three days recommended. The new donation programme provides for first line use of AmBisome in Bangladesh and for use in selected (more complicated) cases in East Africa. Bangladesh and India are currently studying the feasibility of introducing this regime in primary care facilities. In South Asia, miltefosine has been introduced as the first line treatment. It requires 28 days of medication taken orally. This avoids the need for painful injections and hospitalization but people may not take the full course of treatment. Incomplete treatment contributes to emerging resistance to the drug. Miltefosine should not be used by pregnant women and has resulted in some adverse events. (Report of the Regional Technical Advisory Group, 2011). In East Africa, first line treatment has moved to a combination of medicines, Paramomycin (PM) and sodium stibogluconate (SSG), which requires 17 days of injections (an improvement on the 30 days of treatment required in the past).

In endemic areas, treatment typically takes place in specialist units attached to larger primary or secondary public/NGO health facilities, especially when the treatment regime is one that requires admission. In South Asia, there is also significant treatment by the private sector, particularly in India, where it is estimated to provide half of all treatment, although this share is declining. However many private providers do not have the current first line treatment so use outdated medicines. As sandflies and thus VL are found largely in rural areas, transport to treatment locations is often a challenge.

Although VL is considered a neglected disease, it needs to be tackled differently from many of the other NTDs that are amenable to mass drug administration approaches. Whilst countries are developing an integrated approach to other NTDs that focuses on delivering drugs at community level on an occasional basis (e.g. once a year to everyone in the community), VL control cannot be fully integrated in these programmes as individual patients need to be diagnosed and treated. WHO classify VL into the Intensified Disease Management category which means that it cannot be treated by a single preventative annual dose (guinea worm disease is also in this category). There is scope for community involvement in VL case detection and in educating communities on the symptoms and prevention.

VL treatment needs to be integrated in health service delivery at primary and secondary levels in those parts of the country where the disease arises. This is in order to have the skilled health staff, diagnosis, medicines and laboratory tests available when the patients need treatment. There are likely to be opportunities for integrating surveillance and training with the systems for other diseases.

Elimination: In South Asia the disease is concentrated around the borders between Bangladesh, India and Nepal, and these three countries (and Bhutan) agreed to work towards regional elimination of the disease by 2015. Globally the date for elimination is now set as 2020. There has been some progress in reducing estimated numbers of cases but there is not yet sufficient effort or resources to achieve the aim of elimination as a public health concern (defined as fewer than one case per 10,000 population in affected areas).

Elimination is not yet considered feasible in East Africa, where there remain more unknowns about the best approaches to prevention, diagnosis and treatment and where the picture is complicated by the location of sandflies and the role of animals as a reservoir of the disease. The critical needs in East Africa are: to enable rapid detection of emerging outbreaks and put in place the case detection and prompt and effective treatment, in order to avoid large scale outbreaks; to increase access to diagnosis and treatment for cases in epidemic and non-epidemic years in order to reduce the suffering and economic losses due to VL; and to identify effective preventive measures.

c) Other international and country support for VL

The extent of donor support for VL is very limited, hence its neglected status:

- The World Bank has supported VL elimination in India as part of a wider vector borne disease control programme, since 2009, with approximately $42m earmarked for VL. The programme is due to end in 2013 and there are no plans for further funding for VL.
- Spain provided funds for leishmaniasis in East African countries and for WHO’s programme (some $2 million per year); the funds were managed by WHO and used for the response including drugs and diagnostics, mapping and training; the support is likely to end in 2012.
- NGOs have been engaged in VL control in South Asia and East Africa, most notably MSF which has provided diagnosis and treatment in outbreaks and contributed to development of tools and approaches for VL control. However NGOs tend to focus on small areas or districts and lack capacity or resources to scale up.
- The Gates Foundation is developing novel approaches to service delivery on a small scale in India, as well as supporting research. It also supports work in some districts of Bihar and is considering including strengthening the response to VL in this programme.
- WHO’s Special Programme for Research and Training in Tropical Diseases (TDR) was carrying out several research projects that addressed VL evidence gaps, but this is now being curtailed for budgetary reasons.
- There is a new donation of the drug currently recommended for Asian VL (AmBisome, from the manufacturer Gilead) for use in Bangladesh and for selected cases in East Africa over five years. At Gilead’s discounted price (see below), this donation of 445,000 50mg vials is equivalent to $8m. The donation does not cover the non-drug costs of diagnosis and treatment nor the necessary training.
- Since 2007, Gilead has reduced the price for AmBisome for use in VL cases to a ‘no-profit access price’ (currently $18 per vial, no end date specified). However it remains relatively expensive (around $126 for a single dose treatment for an adult in Asia; higher doses are needed in Africa) which has limited its uptake.
- The other major bilateral funder of NTDs at present, USAID, has decided not to address VL as they are focusing on diseases that require mass drug administration.
- DFID has been contributing to research and development partnerships for new diagnostics and drugs for VL.

There is significant current government commitment to prevention (particularly in India and Nepal) and treatment. In Africa, VL surveillance and control efforts have improved notably in Ethiopia, although VL has also shown a propensity to spread to new areas.

In this context DFID identified VL as a very neglected disease with the tools to make a difference but insufficient resources and capacity available at country level to achieve this without additional support. The burden of VL falls heavily on two regions that DFID supports - South Asia and East Africa. Whilst there are tools, there is not yet adequate experience to know how best to scale up efficiently and rapidly to reach those affected and at risk, and to prevent infection. Support from DFID at this stage can scale up access to life saving treatment while also helping to generate the knowledge, capacity and experience to progress towards elimination in South Asia and reduce the burden of the disease in Africa.

d) Rationale for selecting VL over other NTDs

DFID reviewed the relative burden and impact of support to NTDs that require individual treatment. The diseases assessed were Chagas Disease; Dengue Fever; Human African Trypanosomiasis (also known as sleeping sickness); Leprosy; Cutaneous Leishmaniasis and Visceral Leishmaniasis (VL). The diseases were assessed in terms of the following criteria:

- Burden of disease in regions that DFID supports (i.e. primarily Sub-Saharan Africa and South Asia) and in countries that are DFID priorities.
- Availability and cost effectiveness of preventive and curative measures.
- Making the most of contributions from other partners, particularly donated medicines.
- Scale  whether DFID’s contribution could make a significant difference in terms of reducing disease impact.
- Potential for elimination or eradication of the disease.

VL was identified as the highest priority for DFID support based on these criteria:[23]
[23] Walford & Crompton, Examining the case for which additional Neglected Tropical Diseases (NTDs) merit DFID support, HDRC, unpublished, December 2011.

- High burden of disease in South Asia and East Africa.
- Cost effective diagnosis and treatment options are available; also vector control is shown to be cost effective in Asia.
- The new donation of AmBisome needs supporting funding to maximise its impact  including training, technical advice and distribution of the medicines.
- DFID support can have an impact on the scale of needs in East Africa and South Asia.
- The plan for elimination of VL in South Asia has political, and to some extent financial, backing and needs further support to make it a reality.

DFID announced its intention to increase support for NTDs and to include support for VL at the London Declaration meeting on NTDs, 30 January 2012. Already DFID has committed £2.7 million to enable WHO to support the countries benefitting from the AmBisome donation (Bangladesh, Sudan, South Sudan and Ethiopia), as the donation is channelled through WHO. These resources help with planning for the use of AmBisome; preparation for its use including training and ensuring there is a cold chain (i.e. refrigerators, as this medicine needs to be kept cool during distribution and storage) and monitoring in the most affected areas.

In addition to this support which is helping to get treatment with donated AmBisome started, further efforts are required to move towards elimination in Asia and ensure control in East Africa.

B. Impact and Outcome expected

The goal of the DFID support is intended to reduce the number of deaths and the morbidity from VL in endemic countries in South Asia and East Africa. It will do this by supporting the scale up of VL control programmes, building the capacity within country health systems to manage the disease and increasing the knowledge available to enable future expansion of VL control.

The diagram below sets out the results chain, which is reflected in the logframe.

Figure 1. Results chain

Inputs
  - Technical support and operational research to improve quality of case finding, treatment, vector control and surveillance
  - Diagnostics and drugs for use in Africa
  - Country programmes tailored to country needs and context
Process
  - Developing skills and systems for case finding in the community and for delivering good quality treatment
  - Improving quality of vector control particularly indoor spraying delivered in Asia
  - Piloting, evaluation and scale up of innovative approaches
Output
  - Improved access to prompt diagnosis and effective treatment of VL
  - Improved coverage with effective and environmentally sustainable vector control in Asia. Evidence for vector control measures in East Africa
  - Capacity developed for surveillance, M&E, used to inform plans and respond to emerging outbreaks
  - Value for money monitored and demonstrated in VL control
Outcome
  - Progress towards elimination of VL in South Asia
  - Stronger capacity for an effective response in East Africa
Impact
  - Reduced economic and health impact of VL in South Asia and East Africa

Inputs and process
There are two main components to the support for VL:
1. A programme of support for South Asia, focusing on endemic areas in Bihar state in India, Bangladesh and Nepal
2. A programme of support for East Africa, to cover South Sudan, Sudan and at least one other country.

The context and theory of change for each region is discussed in the appraisal case.

The two regional programmes, whose management will be subject to competitive tender, will work with each country to support mapping, planning, service delivery, vector control, piloting innovative approaches, evaluating ways to improve services, operational research (OR) and monitoring and surveillance, as required and in a way that is tailored to each country’s context, needs and funding arrangements. The DFID support will complement and be coordinated with national funding for health services and for VL in particular. This could include contracting relevant NGOs, academic institutions, private providers and funding for government agencies, so as to encourage services integrated within existing systems and not vertical approaches. It can also include some procurement of commodities.

At the London Declaration on NTDs DFID made a public commitment to allocate £30m for VL (of which £2.7 m is already committed through WHO. This level of support will provide sufficient funds to support the scale up of prevention and treatment of VL. Given that this is the first significant support by any donor for implementation of VL programmes a higher level of support is not justified. There would be fewer economies of scale with a lower level of support.
This amount has been identified to take into account
- Interventions to improve the quality of VL prevention and treatment, especially in Asia. These should have a significant impact in VL control and make much better use of the resources from other funders including governments.
- The need for operational research, technical advice and surveillance in each region to improve understanding of how to prevent and control VL and to monitor the impact of interventions.
- The scale of the AmBisome donation (some £5 million) which provides one medicine but does not provide the necessary logistics, training nor the other costs for patients during treatment.
- Funding on a scale to achieve a marked reduction in numbers of VL cases – both in Asia where plans for elimination need support; and in East Africa where there are likely to be large scale outbreaks that can be prevented with early detection and rapid response.
- The plans for scaling up treatment especially in Africa are likely to be constrained by absorptive capacity, and by the complexity of operating in the countries concerned. This is reflected in assumptions of a gradual scale up of support over the programme period (rather than highly ambitious plans to reach all VL cases).
- More generally this is a new programme and addresses a complex and poorly understood disease in multiple countries. The approach is to build in significant flexibility to the programme at this stage and limit funding while further evidence is generated.

The key principles for the design are that:

1. All support is fully coordinated with existing programmes and institutions, including with national leishmaniasis, NTD and malaria control programmes and primary health care where relevant, with veterinary departments (in African countries) and with existing DFID programmes and providers of technical assistance. The support should be designed to build capacity and use existing health systems and domestic funding where possible, in order to build sustainability post-programme.[24]
  [24] This can include joint or integrated approaches, for example training in differential diagnosis of various diseases, not just training on VL diagnosis on its own.
2. The support should be tailored to each country’s context and needs while learning lessons from experience across countries.
3. The support will help pilot new approaches and evaluate this experience, with scope to scale up measures that are found to be effective.
4. There is flexibility in the design to allow for the changing context in VL control, including changes in partner government policy on recommended medicines and development of new tools such as new diagnostic tests.
5. There will be strong monitoring and evaluation of the programmes in each country, to learn lessons and demonstrate results. Results will be shared through regional and global fora.

This support will complement DFID’s funding to WHO to support implementation of the AmBisome donation (already approved). Close working with WHO will reflect its unique role in technical leadership and coordination.

The support will also complement other DFID support to NTDs, including – where relevant – joint approaches on mapping and surveillance, implementation and monitoring. In the case of South Sudan, where DFID plans an integrated NTD programme, there should be coordination between the programmes to identify opportunities for synergies and joint working. As noted above, the approach for VL is quite different for the other NTDs that use mass drug administration through community structures, rather than the facility based health system. There may be still scope for joint working, for example, for VL education and case finding at community level. The programme is expected to work with other DFID providers of technical support operating at country/state level (for example including support to health systems strengthening in Bihar and to NTD control and primary care in South Sudan).

Expected impact
The impact is expected to be a reduction in the numbers of VL cases due to better treatment and less spread of the disease, as well as less time suffering from the illness due to better access to faster acting treatment and fewer relapses. For South Asia it is estimated that this could reduce numbers of VL deaths by 20,000 and save 542,000 DALYs over 10 years. With a cost of £45 per additional DALY averted between 2013 and 2023, when modelled conservatively to cover vector control (VC), research and other costs, this can be considered a highly cost effective programme.

For East Africa the programme is expected to increase the proportion of VL cases that are diagnosed and receive treatment promptly. If an outbreak occurs (which tends to happen every 5 years or so) the programme will reduce the severity of outbreaks through earlier detection and prompt response; this will result in both smaller numbers of cases and fewer deaths than would otherwise be expected. It is estimated that this could reduce numbers of VL deaths by 65,000 and save 710,000 DALYs if there is an outbreak[25], and by 15,000 deaths even if there is no outbreak. With a cost of £30 per DALY saved, this can be considered a highly cost effective programme.
[25] The Base Case assumes only 2/3 probability of an outbreak, i.e. 48,000 deaths averted, 530,000 DALYs.

The benefit estimates are based on different approaches to modelling in each continent, reflecting the different conditions in each region and best estimates on impact. For Africa, modelling of benefits is based on number of cases treated, whereas in Asia it is driven by acceleration in the rate of decline of incidence. In both continents, a conservative approach is taken and no direct health benefits are assumed from programme investments beyond the programme’s end.[26] Taking into account the contribution of other funders (assumed to be £12.7m in Option 2 including the £5m AmBisome donation), and assuming the proposed activities would not otherwise be funded, the DFID results can be attributed based on its share of funding as 46,886 deaths averted (Asia and Africa combined).
[26] In the case of Asia, 2018-23 benefits are calculated through incidence there having been reduced to a lower trajectory during the programme. But no further direct reduction in incidence is assumed beyond the programme years. So, for example, the modelling projects lower incidence in 2020 than would otherwise be the case, but this is only because incidence was lower at the end of the programme, not due to any actions assumed post-2017.

The programme is expected to reduce the economic burden from VL on households in the affected areas, averting productivity losses equivalent to 24 times its cost.[27] This calculation involves multiplication of years of life disabled and lost by 2010 levels of national income per capita. Because VL affects the poorest families, these economic benefits will be gained by the poor. Fuller estimates of the economic benefits taking into account treatment costs would require further study, but are likely to be significant for both households and government/donors.
[27] Over ten years, with both costs and benefits discounted by 10%. If only over four years and with costs undiscounted, the productivity gain would be 14 times the cost of the programme.

In addition to these quantified benefits, the impacts are expected to include:

- Better capacity for surveillance, diagnosis, treatment and vector control into the future, both within individual afflicted countries and at regional level.[28]
  [28] Important as several cross-border areas are particularly affected by VL in both Africa and Asia.
- Better knowledge of where the disease is present and trends in incidence, as a basis for future planning.
- Evidence generated from operational research and piloting of different approaches, particularly methods of VL prevention in different contexts.
- Savings in the longer term if the disease is eliminated as a public health problem in Asia more quickly, as the costs of treatment to government and to households will fall.
- Financial savings for people who would otherwise have wasted their limited cash on inappropriate treatment; as they will have prompt access to good treatment.[29]
  [29] Beyond the individuals themselves, whole communities will be assisted as VL tends to strike farm workers in poor, farming-dependent areas.
- Indirect benefits to other vector-borne diseases, such as malaria, from VL vector control.

Taking into account the resources already committed to WHO to support implementation of the AmBisome donation (£2.7m), this programme will provide £30 million over 5 years and is expected to contribute to a major reduction in VL cases and deaths, as well as to elimination in South Asia.

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case?

a) Overview of the options
The following options were designed following extensive consultation with WHO and other experts involved in the response to VL, as well as DFID country offices.[30] Options of working in one region alone were considered but rejected, in the light of the needs for support and for further operational research to tackle the disease in both regions, and the cost effectiveness of the programme. Given the very limited donor support for VL to date this programme is ground breaking. VL particularly in Africa remains poorly understood and therefore a substantial operational research programme is built into the design. Much of the appraisal is therefore focused on the combination of interventions to be supported and the balance of the programme between East Africa and South Asia.
[30] See list of persons interviewed in developing VL BC.

The capacity and systems for addressing VL are at a different stage in each country whilst the nature of the disease and the evidence of what works varies between South Asia and East Africa. Therefore the DFID support needs to be tailored to regional context, as well as country priorities and needs. The appraisal has considered two main options for DFID support, which differ in the allocation of resources between South Asia and East Africa. This reflects the different conditions in each region and different views of the likely resources available from governments and other partners. The options are summarised in Table 3, and discussed in further detail in the next two sections.

Table 3: Summary of options appraised

	South Asia	East Africa
Counterfactual	No DFID support beyond existing support to health sector and via WHO for implementing AmBisome donation.	No DFID support beyond existing support to health sector and via WHO for implementing AmBisome donation.
Option 1	In Bangladesh:[31] / improve knowledge of locations with VL, expand active case finding and treatment to these areas; / expand and improve quality of vector control; / behaviour change interventions for health workers, community workers, and the public; / develop systems and capacity to monitor progress and adapt the response, with studies on issues e.g. the role of the private sector. / expansion of capacity for diagnosis and treatment (using donated AmBisome). / In India: / improve quality & impact of vector control; / increase VL case detection, diagnosis and referral and pilot approaches to improve access to treatment, including approaches for engaging with private providers; / behaviour change interventions to increase community awareness of VLtreatment and prevention, and ensure readiness to accept vector control; / strengthen monitoring and surveillance systems and capacity to make more reliable data available on VL. / studies including on effects of using DDT. / In Nepal: / provide technical support to improve quality of vector control, monitoring and treatment. / Across the region: / monitor progress, evaluate strategies applied and scale up pilots that work, assess costs and burden of VL, / disseminate research and lessons from experience, and / support elimination efforts.	In South Sudan, Sudan and at least one other country: / Ensure mapping and routine surveillance systems are in place and data is used for planning and to highlight possible outbreaks; possibly supplemented with sentinel sites to evaluate changes in epidemiology, responses to treatment and risk factors. / Establish additional diagnostic and treatment capacity within existing health services, through training, RDT and drug supplies and basic facilities, in order to increase access to active case finding, early diagnosis and treatment. / Study entomology of sandflies and pilot vector control methods in different settings to understand their acceptability, costs and durability. / Ensure capacity to respond to outbreaks in the region, such as funding, communications campaigns and buffer stocks of drugs and diagnostics. / Across the region, monitor progress, evaluate strategies applied, assess costs and burden of VL, disseminate research and lessons from experience. / Scale up of successful approaches and fill gaps in commodity supply. / Estimates of costs and benefits are based on five countries in this option (Sudan, South Sudan, Ethiopia, and on a smaller scale Kenya and Uganda).
Option 2	As for option 1 with more support for India to scale up treatment and improve prevention in more VL-affected districts. / More flexible funds for scale up of effective measures or for commodities as appropriate.	As for option 1 but reduce numbers diagnosed and treated by 33% (due to more limited resources available). Assume that apart from South Sudan, countries and partners make a contribution to treatment costs (e.g. for patient food). / Reduced funding for scale up of interventions compared to option 1. / Estimates are based on the same countries as option 1.
[31] These inputs will complement the existing support to the AmBisome donation through WHO.

Both options are good ways for DFID to address VL in East Africa and South Asia and both are highly cost effective. On balance, the recommendation is to choose option 2, for the reasons outlined below.

The estimated costs to DFID and other funders for the options are summarised in table 4 below. These are costed based on assumptions on the additional activities in each country, standard unit costs and allow for inflation (at 3%). The cost breakdown is discussed in more detail below and assumptions are explained in the economic annex. The amounts of support from DFID are the same for both options in order to facilitate comparison and to reflect the need to learn from experience and evidence under the programme.

This is a broad estimate of costs for the activities assumed, which will need to be refined in the proposals for programme management, which will need to specify activities for each country. The allocation of funds will also need to be flexible to how the country conditions evolve and programme findings during implementation (e.g. whether there is an emerging epidemic or a change in national drug policy).

Table 4. Summary of incremental costs to DFID and total additional costs estimated for the options

	DFID costs – Asia	DFID costs – Africa	Total DFID costs	Other non DFID funding *	Total option costs (DFID and non DFID)
Counterfactual	£ 0	£ 0	£ 0	£0	£0
Option 1	£ 8.0 m	£ 19.3 m	£ 27.3 m	£7.1m	£34.4m
Option 2	£ 15.9 m	£ 11.4 m	£ 27.3 m	£12.7m	£40.0m

* Other funding includes a) the AmBisome donation; b) contributions from Government and partners to health system costs including additional staff time allocated to VL; c) In India and Nepal it is assumed that Governments will fund the IRS, medicines and diagnostics required.

b) The counterfactual
Without DFID support it is assumed that there would still be country programmes on VL, but the support from Spain for VL in East Africa and from World Bank for VL in India will end as scheduled. This would lead to a drop in treatment access in East Africa, and slower progress towards elimination in India.[32]
[32] Both of these developments are incorporated into the modelling.

c) Options for DFID support for VL in Asia: the theory of change
VL in Asia is easier to detect and treat than in East Africa. The RK39 rapid diagnostic test works well and there is evidence that VL can be cured with a single treatment of AmBisome.[33] Even without use of AmBisome, there is an oral treatment (miltefosine) that cures VL successfully if taken for 28 days. Shorter combination treatments are being explored currently that would reduce risks of resistance and incomplete treatment. On the prevention side, the evidence shows the effectiveness of insecticide residual spraying (IRS) of people’s houses in achieving a large reduction in sandflies that carry VL, while use of insecticide treated bed nets also has protective value.[34]
[33] Sundar et al, Single dose liposomal amphotericin B for VL in India; N Engl J Med 2010, 362, 504-12, quoted in Matlashewski et al, Lancet, April 2011. Endorsed by WHO expert committee, 2010.
[34] See e.g. Joshi et al, Chemical and environmental vector control as a contribution to the elimination of VL on the Indian sub-continent: cluster randomized controlled trials in Bangladesh, India and Nepal, BMC Medicine 2009, 7:54. Sharma et al: Insect vectors of Leishmaniasis, J Vector Borne Dis, 208 45: 255-72.

If the interventions can be delivered properly, with cases detected and treated promptly and fewer infected sandflies in houses, then transmission will be reduced and the number of cases can be expected to fall. This will bring about both a reduction in illness and mortality due to VL among poor people and savings in diagnostic and treatment costs.

Based on this, the affected countries have concluded that elimination of VL as a public health problem is a realistic objective. Their joint memorandum of understanding aims for elimination by 2015, defined as incidence below 1 case per 10,000 population per year in affected areas. Experts consulted in development of this business case endorsed this objective, whilst 2020 was set as the global timetable for elimination. There are signs of progress: Nepal is reducing the number of cases each year. There has been some improvement in the uptake of treatment in Bihar, though the burden of disease there remains heavy (28,000 cases reported in 2008, which is likely to be a significant underestimate[35]) and signs of resistance to miltefosine are a concern. Bangladesh has started IRS and active case finding in parts of the district with most VL (Mymensingh district).
[35] Singh SP, et al (2006). Serious underreporting of visceral leishmaniasis through passive case reporting in Bihar. Trop Med Int Health 11(6):899-905, found under reporting by a factor of 4.2.

However there is evidence that the existing programmes have weaknesses:

- Poor quality of IRS, reducing its impact, especially in India. Problems identified include poor quality equipment; poor training, wrong concentration of insecticide etc.[36] as well as inadequate targeting to the most at risk areas and insufficient community mobilisation.
  [36] Huda et al, Toolkit for Monitoring and Evaluation of Indoor Residual Spraying for VL Control in the Indian Subcontinent: Application and Results, J Trop Med, 2011 www.hindawi.com/journals/jtm/2011/876742/
- People often seek treatment in the private sector (again, especially in India) where they often get the wrong diagnosis and/or spend money on inappropriate treatments, with delays before getting the right treatment.[37] Previously some 75% of cases started in the private sector although this is reported to be reducing in Bihar in recent years as community health workers and the population learn about the new treatment available from the public sector.
  [37] For example, Sarnoff et al. (VL supplement: the economic impact of VL on rural households in one endemic district of Bihar, India. Trop Med Int Health, 2010; 15 supplement (2): 1-8) found that VL patients in Bihar on average sought treatment after 10 days of high fever with 47% of cases seeking care from a private doctor and over 38% from non-physician rural practitioners in the first instance. Few patients were diagnosed with VL by their first care provider; and only 3% of those who visited a non-physician rural practitioner. Only 75% of VL cases in the study were diagnosed with VL during their second visit to a practitioner. Those visiting a government facility were most likely to receive a positive diagnosis (96%) but seeking care from a government facility was in the minority, with only 4.7% and 14.3% of first and second visits of VL cases seeking care from government providers.
- The numbers of cases and the risk factors remain unclear in most districts, with limited reporting and weak surveillance, so it is difficult to monitor progress in controlling the disease.
- There are insufficient public facilities available which have the knowledge, medicines and diagnostics for dealing with VL, especially at primary care level.

The goal of elimination requires strengthening the existing VL efforts in each country, tailored to the specifics of the country needs and gaps in its response. Figure 2 sets out the theory of change in diagrammatic form.

Figure 2. Theory of change - VL elimination in South Asia

Improving quality & targeting of vector control and testing innovative approaches
Increased coverage with effective vector control
Mapping, surveillance, active case finding, diagnosis and referral capacity developed
Improved access to and uptake of diagnosis
Effective & shorter treatment of VL&PKDL made available through more treatment centres
Increased coverage with full course of effective treatment, with fewer relapses and PKDL cases
Increased community understanding of prevention, diagnosis & treatment
Households accept/use VC, improve houses, seek diagnosis & treatment promptly, complete treatment course

Lower economic burden due to VL morbidity & mortality (now and in future)

Inputs
Activities
Outcomes
Impact
Outputs

DFID funding
AmBisome donation
Government expenditure & policy
private spending
other donors
 WHO leadership & coordination

Lower incidence of VL, with progress towards elimination as a public health problem

Increasing proportion of VL cases are detected & cured promptly, so infectious for less time; & less resistance

For the purposes of the business case, two options have been considered for South Asia:
Option 1: focus on strengthening vector control, community and private sector response, and overall surveillance in Asia.
Option 2: as for option 1 plus more intensive support to strengthen treatment access and quality especially in Bihar state, India.[38] Eighty per cent of all South Asian cases are in India.
[38] Also to a more limited extent in Nepal and Bangladesh.

No other donors are assumed (beyond the Gilead donation), though the Base Case assumes that governments will meet costs such as continuation of vector control and staff salaries for new treatment centres.

The specific inputs will be designed in detail when the programme is established in each country. The initial planning and consultation for the business case concluded that much of the resources should be allocated for providing technical support, management, training and supervision, behaviour change interventions, and piloting, evaluating and scaling up more effective approaches to vector control and treatment, while leaving the procurement of most commodities to the government health budget. This is expected to be affordable for Bangladesh and Nepal in view of the health sector support in each country and the AmBisome donation in Bangladesh. For India, if they decide to move to use AmBisome as the first line treatment, the costs may be high initially (although treatment costs overall may be no higher as shorter treatment means lower health service costs). Both options allow flexibility for some initial purchase of AmBisome if required to enable the introduction in selected sites. The flexible funding can also be allocated for scaling up of successful pilot initiatives.

Both options assume that VL prevention and control will build on and be integrated in the existing health system:

- Prevention and treatment will continue to involve the existing public sector health facilities and build up diagnostic and treatment capacity as part of the normal health services. As such, the programme will support and rely on the existing health system with the recurrent costs of health workers and running health facilities funded through normal budgets.
- The most appropriate roles for community health workers and where appropriate, private sector health providers need to be further defined and tested under the programme to see how they can be engaged to encourage prompt diagnosis and treatment. Some funding is included for piloting approaches such as referral incentives for private providers in India, with the objective that if successful and still needed, this could be taken over by the government.
- For vector control, there are already government departments responsible for this role, and the role of the programme will be to improve performance and build their capacity for the future, for example through technical advice; improving capacity for procurement, tendering, training, supervision and monitoring; and design of incentives.

c) Options for DFID support to VL in East Africa
There is a need to continue and expand diagnosis and treatment of VL in East Africa to reach more cases. Whilst the rapid diagnostic tests and drugs work less well than in Asia, and there are trials underway to devise better diagnostics and treatment regimes, there is clear consensus that the existing tools are good enough to expand coverage and avoid large scale epidemics that are a continuing threat.[39] The approach that has been adopted is to define a network of treatment centres which have facilities for diagnosis, inpatient treatment and laboratory capacity for diagnosis of VL cases and confirmation of cure, usually at secondary level hospitals. With the current first line treatment involving 17 days of injections (reduced from 30 under the previous regime), this kind of treatment centre with wards for patients will continue to be required unless a change in treatment regime alters the requirements (trials of single dose AmBisome and other combination treatments are underway). When there is an epidemic, additional treatment centres can be set up in the affected areas, as in the 2010/11 epidemic in South Sudan. Treatment centres in South Sudan are within existing facilities and extra centres have been set up in the past (e.g. in tents in refugee camps) when needed to tackle an outbreak. This support would go to existing facilities that need it, mostly to district hospitals e.g. to ensure that they have the medicines and other commodities that they need for an emergency response. Primary Health Care facilities would need the skills and materials for case finding and diagnosis which can be an integral part of service delivery in relevant geographic areas.
[39] For example see the MSF report, Fighting Neglect, which looks at the potential to address three NTDs, VL, Human African Trypanosomiasis and Chagas Disease (May 2012). www.msf.org.uk/MSF_report_Fighting_Neglect_20120611.news

On vector control (VC) there needs to be more research on effective and cost effective approaches in Africa. This could include entomological studies of the vectors as a basis for understanding how best to improve vector control. In addition some innovative tools have been shown to work in some settings, for example a tent-like insecticide-treated cover for people who sleep outside was tested and found acceptable in the Nuba region of Sudan and other materials such as treated sheets have been developed. The uptake of these types of approaches needs to be tested in different settings within countries, taking into account socio-cultural factors as well as factors such as temperature at night (people are unwilling to sleep under nets/covers when it is hot at night, but some areas are cool at night). Non-net based approaches also need further testing. The VL programme will allow for piloting in different areas to see what works where, with scope for scale up of feasible methods.

The options developed for East Africa are:

Option 1: As outlined above, the programme will be tailored to each country and include:
- improving monitoring of VL;
- expanding access to diagnosis and treatment to reach a larger proportion of cases;
- detecting and controlling outbreaks;
- developing knowledge on the vectors and methods of vector control.
- regional collaboration on surveillance and knowledge development; and
- evaluation.

Option 2: As for option 1 but assumes a slower scale up in treatment (33% fewer cases reached).

For both options it is assumed that the donation of AmBisome intended for second line treatment of VL and for PKDL will be almost sufficient, with scope for limited additional AmBisome funded by DFID. Further needs would have to be provided from other sources, or failing this, fewer people will receive this treatment (particularly for PKDL, which often self cures in Africa).

As for Asia, it is expected that the programme in Africa will work with and build up the existing health system in each country. This will involve working with the relevant government authorities. Since VL is concentrated in a few areas, this likely to involve relevant local government such as affected states in Sudan and regional governments in Ethiopia, (if included). It may also involve working with NGOs in some cases, for example in South Sudan where NGOs are contracted to enable delivery of primary health care services in each county. The programme will need to work with the relevant mechanisms and providers in each state and country, in order to build their capacity to plan, manage and deliver services as an integrated part of disease management in primary and secondary health care levels. This is in line with national policies to provide integrated health services in Sudan and South Sudan. It is also important to establish their responsibility for continuing control after the DFID programme ends.

The key feature of the theory of change in East Africa is that increased availability of diagnosis and treatment will reduce the burden of VL while the strengthening of surveillance and response capacity will identify outbreaks quickly and prevent the occurrence of large scale epidemics. On the prevention side, the theory anticipates that the programme will build evidence on effective methods of vector control that strengthen VL control in future. The theory of change (Fig. 3) is thus different from that for Asia.

Figure 3. Theory of change for VL Control in East Africa

Piloting innovative approaches to vector control in different settings & scale up
Evidence and start to increase coverage of effective vector control
Mapping, surveillance, emergency response, diagnosis and referral capacity developed
Epidemics detected early and responded to
Effective diagnosis and treatment of VL&PKDL made available through more treatment centres and outreach
Improved access to prompt diagnosis and treatment
Increased community understanding of prevention, diagnosis & treatment
Households use VC, seek diagnosis and treatment promptly

Lower economic burden due to VL morbidity & mortality

Inputs
Activities
Outcomes
Impact
Outputs

DFID funding
Ambisome donation
Government expenditure & policy
Private spending
Other donors WHO leadership & coordination

Lower incidence of VL, including avoidance of large outbreaks

Increasing proportion of VL cases are detected & cured promptly

B. Assessing the strength of the evidence base for each feasible option

Addressing VL should include a combination or package of the following types of intervention:

- Mapping to identify areas with VL.
- Surveillance of VL within the national disease surveillance system, to monitor progress and detect emerging outbreaks.
- Vector control to reduce transmission - through use of insecticides and developing other methods.
- Passive case finding - when people seek treatment from a health provider, the provider is able to diagnose VL and provide or refer for appropriate treatment.
- Active case finding - where the health system goes out to identify people who have the disease, for example, going to home villages of VL patients to check whether family members and neighbours are infected (as proximity to patients with recent VL is the major determinant of risk[40]). This enables early diagnosis and prompt treatment.[41] The priorities and best ways to target active case detection efforts need to be defined.
  [40] Alvar et al, Leishmaniasis and poverty, 2006. A study in Bangladesh found household members are 26 times increase in risk of VL - Bern et al. 2005, Risk factors for Kala Azar in Bangladesh, Emerging Infectious Diseases 11, 655-662
  [41] “Active case detection in villages in Bihar, Nepal and Bangladesh has identified increases in VL case finding of up to 60%, ... and reduced the time to treatment by about half compared with previous passive case detection”. Matlashewski et al, cit.
- Diagnosis, using an RDT as this can be used in primary care and potentially in the community (currently RK39 is in use, others are being tested). Also other diagnostic tests where needed.
- Treatment with one of the currently recommended types of medicines, and with second line treatment available if the first line treatment fails or is inappropriate.
- Social mobilisation, behaviour change interventions and community ownership to ensure effective vector control, and encourage uptake of VL diagnostics and treatment.
- Emergency response capacity to save lives and limit the spread of the disease, through better surveillance and communication, and buffer stocks of diagnostics and treatment commodities.
- Monitoring and evaluation and operational research, together with substantial piloting and evaluation of innovative approaches to specific problems, to learn from experience, improve efficiency and adapt to local cultural and climatic conditions, at both national and regional level

The individual interventions in this package for VL have been subject to various reviews and trials. There is strong evidence of the effectiveness of many interventions  well summarised in the Lancet paper by Matlashewski et al[42]. More specifically on the evidence:
[42] VL: elimination with existing interventions, Lancet, April 2011

- The RK39 diagnostic test has been tested for quality and accuracy and found highly accurate in Asia, although not sufficiently sensitive in Africa (where a positive test is indicative of need for treatment but the test may not detect all cases, so further diagnosis is needed).[43]
  [43] TDR: VL: Rapid Diagnostic Test Performance, August 2011, Diagnostics Evaluation Series no.4, www.who.int/tdr/publications/tdr-research-publications/vl-rdt-evaluation/en/index.html found 80-90% sensitivity of the RDT in East African settings.
- There are several drugs available that are over 95% effective and safer than the older medicines. This includes the oral medicine miltefosine (in use in Asia) and Paromomycin (PM).
- Liposomal amphotericin B was shown to be 96% effective with a single dose in hospital settings in Asia and is being tested in primary health care settings in India and Bangladesh. AmBisome is the only quality approved version currently available. It is thought unlikely to lead to resistance.[44]
  [44] http://www.who.int/tdr/news/2011/vl-treatment/en/index.html
- For patients co-infected with HIV and VL, liposomal amphotericin B has been shown to be safe and effective in India, but not in East Africa. Combination treatments of liposomal amphotericin B with miltefosine has shown promising results in Africa and will be studied further, as will secondary prophylaxis to prevent relapses after initial cure of VL in HIV positive patients.[45]
  [45] MSF, 2012, Fighting neglect op cit, (p 34).
- For PKDL it appears that AmBisome is an improvement over previous medicines, both in reducing its incidence and curing it more rapidly (although better evidence is needed for this finding).
- Prevention with IRS has been shown to be effective in Asia. Policy in India is to use DDT as the insecticide, and whilst there is resistance in some areas of India to DDT, pyrethroids remain effective and are in use in Nepal and Bangladesh. More broadly, the effectiveness of IRS is shown by the experience in India when widespread use of IRS to control malaria achieved dramatic reductions in VL in many states in both the 1940s and the 1970s. Bed nets can also be protective if they are treated with insecticide.
- Vector control in Africa is less well researched and the limited evidence is not conclusive for VL. However novel products such as insecticide treated plastic sheeting have been trialled in some contexts and could be piloted in more settings.

The evidence that an active control programme can limit the death toll of outbreaks is indicated by experience in South Sudan:

- In the 1984-94 civil war, there was no substantial VL response in place, and an outbreak is estimated to have caused around 100,000 deaths over 10 years (in a population of 280,000).[46]
  [46] Seaman et al, The epidemic of VL in Western Upper Nile, Southern Sudan: Course and Impact from 1984-1994, Int Journal of Epidemiology, 1996, vol 25
- Another severe outbreak took place from 2002-3, with around 10,000 deaths registered.
- In 2010/11, there has been another outbreak with 9-10,000 cases per year. Due to increased access to treatment (with 29 treatment centres opened in the affected areas offering diagnosis and treatment), the average case fatality rate was only 4%, much lower than previously reported case fatality rates of 30% in South Sudanese outbreaks.

There is less evidence on the practical aspects of how to ensure prompt and effective treatment. There has been some research on options for active case finding but more is needed for example on the role of community health workers in diagnosis and treatment. The demand side – what are barriers and how best to generate community willingness to take up diagnosis and treatment – could also be further studied. In Bihar there are plans to pilot approaches to ensure more effective community engagement in vector control (with support from DFID’s Sector Wide Approach to Strengthening Health in Bihar) that should generate lessons for this programme. Strategies to encourage integrated and cost effective service delivery also need further work, for example the use of integrated training in diagnosis in settings such as South Sudan where there is a need to differentiate VL from malaria and other infectious diseases. These types of issues will be explored through evaluations and operations research during the programme.

There remain issues where further research is needed, including the part that latent and asymptomatic infections play in transmission of VL, and continued research on prevention and better diagnostic tests and drugs for use in Africa (some is underway). However, there is broad consensus that there is strong enough evidence to make progress with control of the disease in East Africa and elimination in Asia with the existing tools.

In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited.

Option	Evidence rating
1: Improve vector control (VC) quality and test ways to improve prompt diagnosis and treatment in Asia; expand diagnosis and treatment and test preventive options in Africa; improve surveillance in both	Medium
2: Improve VC quality in Asia and increase treatment capacity in India; smaller scale up of treatment in Africa and test preventive options; improve surveillance in both	Medium

What is the likely impact (positive and negative) on climate change and environment for each feasible option?

Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation.

Option	Climate change and environment risks and impacts, Category	Climate change and environment opportunities
1	A	A
2	A	A
Counterfactual	B[47]	C
[47] Countries are currently at risk from poor quality vector control

Climate and environment issues surrounding this project concern:

- The disposal of medical waste (mostly needles) from clinical treatments.
- The control of sand fly vectors using insecticides in the home and immediate surroundings.
- The impact of climate change on the ecology of the vector and how that may affect the distribution of the disease.

Medical waste
There are significant, indirect risks associated with medical wastes such as used needles and vials whose inappropriate disposal puts humans at risk of harm. However by employing some simple management measures, such as training of users in safe disposal practices and the provision of appropriate sharps containers, diagnostic and drug administration procedures present a low risk of negative impacts on the environment. Safeguards can be put in place: e.g. outreach staff responsible for the delivery of supplies can be charged with returning the wastes. Good accountability for waste management is possible, even where local governance is weak (participating NGOs, charities and pharma take responsibility). The indicative programme budget has allowed for some funding for waste management at treatment centres.

Vector control
This intervention foresees the use of insecticides for indoor residual spraying. In South Asia, Bangladesh and Nepal use pyrethroids while India uses DDT. Pyrethroids are broadly classified by WHO and the US Environmental Protection Agency as Class II compounds i.e. moderately hazardous/toxic. Applied properly, the only risk of exposure to pyrethroids is through the dermal route (through touching sprayed surfaces). DDT is much more volatile for a short period of time and so exposure via both dermal and inhalation routes are possible. If used following appropriate guidelines and safety procedures, neither compound poses a direct threat to humans but there is some evidence that both have the potential to be endocrine disrupters (from massive dose/response tests on rats).

DDT belongs to a category of chemicals known as Persistent Organic Pollutant (POP) because of their physical and chemical properties and how they react with the environment and living organisms. For all intents and purposes bar one, DDT is an obsolete insecticide. It is only sanctioned by WHO under special circumstances – indoor use for disease vector control in authorised public health programmes. Countries that are signatories to the Stockholm Convention (prohibiting the use of POPs such as DDT) and the Rotterdam Convention on Prior Informed Consent (PIC) (no trade in hazardous chemicals without PIC) are unable to supply, trade, or use this organochlorine compound for other purposes. Any assistance for the control of VL using DDT can only be sanctioned by the UK if the target country is registered with the Secretariat of the Stockholm Convention for DDT exemption. India has been a signatory to the Stockholm Convention for a decade but continues to manufacture and use it for mosquito and sandfly control under the exemption (2006 onwards). No exemptions for VL have been registered by Bangladesh and Nepal where DDT is banned. DDT is also semi-volatile and can be expected to partition into the atmosphere as a result; it is highly toxic to aquatic animals including fish and especially shrimp, with ‘harmful presence’ values in the range of 0.4 μg/L; it also affects fish behaviour (Ritter, 1995; WHO, 1989). As a compound it is highly insoluble in water, which increases its persistence in aquatic environments and its harmful properties for all aquatic wildlife. DDT and its metabolite DDE are also acutely toxic to birds and have adverse effects on reproduction.The proven harmful effects of DDT to natural ecosystems, as well as birds and aquatic wildlife, further augments the need for caution and for introducing all possible safety measures and additional checks to ensure that no unnecessary or additional harm is caused to the livelihoods of people in neighbouring countries (especially Bangladesh and Nepal whose economies are so crucially dependant on fisheries and tourism).

These significant risks associated with insecticides can be mitigated and managed through appropriate measures, therefore it is of vital importance that gold standard procedures and safeguards are implemented for all DFID interventions and extended to those associated with it to ensure adherence to the basic principle of “doing no harm”. For this reason it is required that robust indicators be included in the logframe for this intervention to ensure that the abovementioned procedures and safeguards are implemented and monitored effectively. Any serious breaches of these should also warrant a robust response by DFID, including but not limited to a potential withdrawal or suspension of funding.

India is already using DDT for spraying, the problem is that the spraying is of poor quality and poses risks.[48] The role of the DFID support is to improve the quality of spraying and use of insecticides in India, Bangladesh and Nepal, making it safer for the people spraying and residents and improving the effectiveness through better targeting, ensuring correct concentrations and better equipment are used. The programme will not purchase any DDT.
[48] Huda et al, Toolkit for Monitoring and Evaluation of Indoor Residual Spraying for VL Control in the Indian Subcontinent, op cit. For example in the Indian sites reviewed, only 29% of spray squads mixed DDT and water properly.

It is planned that a study should be conducted as part of the programme. The study would collect data on potential DDT migration into the environment as part of indoor spraying as a way of determining whether this represented a long-term problem in India. The results should be published in a recognised peer-reviewed journal or similar publication and should be shared with the Indian Government as well as the wider research and scientific community.

Finally, it will be crucial for the DFID programme team responsible for the management and implementation of this programme to ensure appropriate monitoring of all actions and recommendations made in the Climate and Environmental Assessment by an accredited Climate and Environment (C&E) adviser. This will involve, but will not be limited to, including a C&E adviser in all annual reviews and the project completion review.

Climate
As with the other NTDs, their epidemiology and incidence is very likely to be affected by climate. In regions experiencing considerable climate change, increasing temperature and rainfall events can be expected to affect the spatio-temporal distribution of the sandflies and therefore the range, frequency and transmission rates of VL. Vector survival, reproductive rates and behaviour could also change, but there is little knowledge on transmission rates in relation to global warming (malaria is an exception).

The role of climate change in the expansion of Leishmaniasis has not been studied in depth. Such studies would need to identify clear climate-related patterns of inter-annual fluctuations in the populations of vectors and reservoir hosts and the incidence of VL, in each region affected.

C. What are the costs and benefits of each feasible option?

a) Breakdown of costs for the options
The assumptions for costs and benefits of both options are described in more detail in the Economic Annex that accompanies this document. The two following tables summarise the estimated costs of the options. Both options involve £27.3m of DFID funding over 4.5 years, split between payments to two programme managers (one each in Asia and in Africa) and modest provision for midterm and end term evaluation studies.

The costing is for the programme as a whole so also includes costs of the programme that are expected to be funded from other sources. A sensitivity analysis shows what difference it would make if none of these funds materialised. The programme is defined as activities that are additional to the counterfactual case. No costs are incurred following year 4, after which time to be conservative all direct benefits from commodities, equipment and training are assumed to end. However, in the case of Asia, there are fewer cases and deaths during years 5-10 due to incidence being on a permanently lower path, as a result of the programme (no reduction in incidence is assumed in Africa).

Table 5. Assumptions on allocation of costs for each option by country/component (£)

	Option 1	Option 2
Total, Option (DFID-funded)	27,300,000	27,300,000
Independent M&E including a vector control specialist	225,200	225,200
Asia
Asia regional	206,099	468,108
Bangladesh	940,329	1,274,053
India	3,911,351	7,373,410
Nepal	471,469	563,429
Contingency and pilot scale-up	897,795	3,593,045
Management and contractor M&E	1,499,221	2,520,940
Total, Asia programme (excluding independent M&E)	7,926,264	15,792,989
Share of independent M&E	112.600	112,600
Total, Asia (DFID-funded)	8,038,864	15,905,589
Asia Programme, not financed by DFID:
(Ambisome - Gilead donation)	3,423,133	3,267,536
(Ambisome - non-donation)	-	1,700,428
(MoH and others)	274,035	3,303,728

Total, Asia (non-DFID-funded)	3,697,168	8,271,692
Total, Asia	11,736,032	24,177,281

Africa
Africa regional	963,162	1,351,223
Ethiopia	2,341,113	779,320
Sudan	6,161,051	2,902,594
South Sudan	3,287,918	2,660,737
Kenya/Uganda	645,277	354,924
Contingency and pilot scale-up	2,632,928	2,086,638
Management and contractor M&E	3,117,086	1,146,373
Total, Africa programme excluding DFID M&E	19,148,536	11,281,810
Share of independent M&E	112.600	112,600
Total, Africa (DFID-funded)	19,261,136	11,394,410
Africa Programme, not financed by DFID:
(Ambisome - Gilead donation)	1,416,641	1,587,083
(Ambisome - non-donation)		-
(MoH and others)	2,026,905	2,872,667

Total, Africa (non-DFID-funded)	3,443,547	4,459,750
Total, Africa	22,704,683	15,854,160

Total, Option (all funding sources)	34,440,715	40,031,441

Notes: costs other than donated AmBisome have been inflated at 3% annually. Costs of donated AmBisome are included in these estimates. The cost modelling involves VL patients receiving a range of treatment regimes, based on their epidemiology and national guidelines.

Table 6. Profile of estimated costs over years for each option (£, allows for inflation)

	Inception	Yr 1	Yr 2	Yr 3	Yr 4	Total
Option 1 – DFID funding	1,816,492	5,187,240	6,168,320	7,060,086	7,067,862	27,300,000
Option 1 - all funding sources	1,993,572	6,382,460	7,737,769	9,188,436	9,138,478	34,440,715
Option 2 – DFID funding	1,699,459	5,011,494	6,285,580	6,718,273	7,585,193	27,300,000
Option 2 – all funding sources	1,940,797	7,211,277	9,138,213	10,417,596	11,323,558	40,031,441

b) Assumptions on commodity procurement

The commodities which it is estimated that the contractors would procure are estimated as follows (Table 7). These are indicative estimates as the requirements will emerge from detailed country specific plans and needs, including for example, whether there is an epidemic and its location and scale.

Table 7. Assumptions on commodities that would be procured with DFID funds (rounded to nearest £ ‘000)

	Option 1	Option 2
Rapid Diagnostic Tests	388,000	259,000
VL medicines [49]	3,643,000	2,124,000
Other medical supplies[50]	2,441,000	1,366,000
Patient nutrition[51]	1,628,000	288,000
Medical equipment	10,000	62,000
Sub-Total	8,110,000	4,099,000
Scale up funds (for successful pilots and for commodity needs) - assume 75% for commodities [52]	1,575,000	2,999,000
Total	9,685,000	7,098,000
[49] Estimate mostly procurement of SSG+PM for Africa, and limited Ambisome. It includes allowance for buffer stocks.
[50] These include other supplies needed to treat VL patients in East Africa, such as antibiotics and other medicines for their health problems apart fromVL.
[51] This is important in East Africa, where many patients are malnourished. The estimate is based on support for patients in South Sudan only.
[52] This is a ‘best guess’ of how the scale-up funds might be used, but the funds are intended to have the flexibility to respond to evolving conditions and outcomes of research and piloting, and so procurement with them is difficult to predict.

Note: funds are in £(2012), i.e. without inflation (added later), and include a 3% procurement charge.

c) Estimated benefits of the options
The benefits of the options have been modelled using the proposed levels of treatment and prevention in each option, combined with estimates of likely impact on incidence based on expert judgement. The approach differs between the two regions, reflecting the different situation for VL and objectives of the programme:

For Asia, the modeling assumes that the DFID support to VL programmes enables faster reduction in incidence of VL, due to more effective VC and faster access to effective treatment. This results in a longer term impact on the numbers of cases beyond the life of the programme and benefits are therefore considered over 10 years. It is also assumed that even in the counterfactual, 90% of VL cases in Asia receive treatment eventually and survive, but often with long delays and at high cost; the DFID support enables prompt and effective treatment.

For East Africa, the benefits are modeled based on numbers of VL cases treated, many of whom would otherwise have been untreated and would have died. It assumes the numbers of VL cases reached increase markedly due to the programme, more so in option 1 than option 2. It also assumes there may be an outbreak during the five years which would lead to large numbers of cases and deaths in the counterfactual, whilst the DFID support helps to enable early detection and control, and thus much lower numbers of VL cases in the outbreak. It assumes no direct benefits from programme activities in the five years after the programme ends in 2017. It is also assumed (conservatively) that the programme is unable to lower incidence in future years in Africa.

The modelling of the impact of each option and the counterfactual looks at the programme as a whole, not just the part that is funded by DFID. It looks at benefits for the programme period only (to 2017) and over 10 years (to 2023). Option 2 is a larger programme overall (including both DFID and non DFID funding), including more treatment activity in India, with total costs of £40.0m, compared to £34.4m for option 1. This contributes to the higher estimated health impacts shown below. The direct health benefits are estimated as follows:

Table 8. Aggregate estimated additional direct health impacts of VL programmes, both options

	Deaths averted	Deaths averted	DALYs averted	DALYs averted	Cases prevented	Cases prevented
	2013-2017	2013-2023	2013-2017	2013-2023	2013-2017	2013-2023
Option 1	67,833	72,925	807,016	932,851	87,484	138,402
Option 2	56,646	68,751	781,298	1,071,376	136,063	257,112

In the case of Asia, benefit is modelled through an assumed increase in the rate of decline in VL cases during the years to 2017. This model suggests that elimination of VL will not be achieved in Asia in either option by 2023, although Option 2 brings it more than two years closer compared to the counter-factual, and Option 1 brings it almost a year closer.[53]
[53] The model used does not show elimination will be reached during the modelled period (up until 2023), but Option 2 reduces incidence in 2021 to the level at which it stands in 2023 in the counterfactual.

These estimates of direct health impact are approximate for a number of reasons (see uncertainties and sensitivities section, below). In the case of Africa, based on expert advice that it will be highly unlikely that it would be possible significantly to reduce incidence until there is innovation in VC, the figures are based on numbers treated. The estimates ignore any potential benefits that may come from improved diagnostic, treatment and VC capabilities through the proposed pilots and their scale-up. At the same time, less experience, and without the top political level engagement on VL as in Asia, combinewith dangers of conflict to provide greater downside risk in Africa. In Asia, these factors may be considered to be subsumed within the overall forecast decline in incidence and the greater degree of knowledge about how to control sandflies and diagnose and treat VL means that there is less potential upside to pilot studies.

Taking into account the loss of working time due to illness and premature deaths, the approximate value of productive time which the two options might gain may also be quantified. The table below gives estimates of the value of the productivity losses averted, estimated from the reduction in working years lost multiplied by national Gross National income (GNI) per capita for 2010. The larger scale of option 2 contributes to larger savings in productive time.

Table 9. Value of lost productivity through illness and through deaths averted, both continents, £m (2012) (above the counterfactual)

	2013-17	2013-23
Option 1	574	670
Option 2	565	788

d) Other benefits, that have not been quantified
Other, unquantified, benefits would include:

- Averted costs to households, through out-of-pocket expenditures on transport and treatment with reduction in VL incidence and quicker access to effective diagnosis and treatment.
- Averted costs to governments/donors for VL care and e.g. care of orphans due to VL deaths (in contexts where VL causes premature death to adults with children).
- Indirect health impacts such as reduction of other vector-borne diseases due to vector control for VL; diagnosis of HIV enabling access to care beyond treating their VL.
- Equity effects, given that VL incidence is higher among the poorest and fatality rates are highest among women.
- Additional efficiencies through facilitation of sharing of knowledge and innovations between affected countries.
- An elimination effect which may be possible in the medium term in Asia and which could accrue indefinitely.
- It is also recognised that there may be negative benefits, including for current private providers of VL care, especially in India.

e) Cost-benefit analysis
Applying the costs and benefits from the modelling described above, gives the following cost-effectiveness ratios for the two options.

Table 10. Comparative costs per DALY, £, discounted at 10%

	Asia / 2013-17	Asia / 2013-23	Africa / 2013-17	Africa / 2013-23	Overall / 2013-17	Overall / 2013-23
Option 1	110.19	50.51	32.41	32.41	42.68	36.92
Option 2	95.96	44.61	29.95	29.95	51.24	37.36

Note that the costs applied are costs from all funding sources for the additional activities anticipated for this programme (DFID, AmBisome donation, MoH/others) and the DALYs are benefits of the whole programme.

Comparing any of these cost/DALY ratios to the respective countries GNI/capita suggests that both options are highly cost effective drawing on the commonly used rule of thumb suggested by WHO, which sees a cost/DALY ratio at or below the GNI/capita as highly cost-effective health activities.

The cost effectiveness ratios for the different options are very close, suggesting that there islittle difference in their overall cost effectiveness. This is mainly because some activities are similar across both options, with differences beyond these largely balancing each other out in terms of cost-effectiveness.

The African and Asian cost/DALY numbers are not fully comparable due to the different approaches taken to modelling the benefits in each case, necessary because of the very different situations and range of possibilities between the two regions. The figures for Africa are lower than for Asia, (i.e. slightly more cost effective in Africa), which reflects the modeling in Africa that assumes deaths will be averted in a higher proportion of cases, as the programme enables services to reach people who were previously untreated and also reduces the scale of an epidemic should one arise.

It can also be noted that due to the different ways in which benefits are modelled in Africa and Asia (i.e. with no change in incidence in Africa), the cost/DALY ratio improves beyond the programme period in Asia but not in Africa. In the case of Asia, this demonstrates the long term benefits from bringing about a faster decline in VL incidence during the programme years. This is a conservatively modelled result in the case of Africa, as it assumes that there is no lasting benefit beyond the programme years.

Table 11 considers the costs relative to deaths averted, giving a more limited picture of cost effectiveness than cost per DALY (which includes both deaths and illness averted). As discussed for cost per DALY above, the figures are lower for Africa, making it better value on this measure, and making option 1’s cost per death averted better value overall as DFID has relatively larger share of the programme in Africa. The estimates again suggest that both options offer very good value for money compared to many other interventions.

Table 11. Estimated cost per death averted, £(2012)

	Asia / 2013-17	Asia / 2013-23	Africa / 2013-17	Africa / 2013-23	Overall / 2013-17	Overall / 2013-23
Option 1	3,437	1,380	352	352	508	472
Option 2	2,922	1,186	328	328	707	582

Economic benefits
If the productivity losses associated with VL morbidity and mortality are taken as the sole measure of economic benefits, then both options are very good value, with costs (from all funding sources) equivalent to just 4-6% of expected economic benefits (depending on option and whether the programme or a 10 year period is used, see Table 12). Discounting for these calculations is at 10%.

Table 12. Cost benefit ratio (in % terms)

	2013-17	2013-23
Option 1	4.93%	4.22%
Option 2	5.80%	4.16%

This high economic value is reflected in projected net present values (NPVs), also discounted at 10%. For the programme period alone, Option 1 has an NPV of £545m, while Option 2 has £532m. For the period to 2023, Option 1’s NPV would be £642m and Option 2’s £755m. Thus on this measure of the economic return to VL treatment over 10 years, option 2 offers better value because of the continued impact in terms of lower numbers of VL cases and thus lower productivity lost over the 10 year period. Both options are a good investment on this measure.

f) DFID’s attributable share of net benefits
The table below estimates the share of programme benefits that can be attributed to DFID, taking into account DFID’s share of funding in the programme. It shows that Option 1 has slightly higher attributed benefits.

Table 13. Direct health benefits attributable to DFID, 2013-23

	DFID’s share of programme cost	DFID’s share of deaths averted	DFID’s share of DALYs	DFID’s share of VL cases prevented
Option 1	79%	57,805	739,440	109,337
Option 2	68%	46,886	730,639	175,351

Note that this assumes that other funders (e.g. Indian government, Gilead) will cover remaining share of programme costs. A sensitivity scenario (below) examines what would happen if they do not, beyond the agreed AmBisome donation.

g) Uncertainties and sensitivities
All economic analysis in the health sector is subject to uncertainty, but the lack of data on VL makes this appraisal particularly difficult to model. Particular issues are:
- The possibility and extent of an epidemic in Africa.
- The extent to which other partners (MoHs and donors) will meet the associated costs for both options (mainly staff inputs and in Asia, drug and IRS supplies).
- The likely effects of improved quality of vector control, surveillance and other activities such as behaviour change intervention and any change in treatment regime in reducing VL incidence in Asia, in both options.
- Potential political and civil instability in East Africa which may threaten the efficacy of programme activities in that region.

In order to assess the impact of different assumptions on the appraisal, the team subjected the Base Case (presented above) to a number of sensitivity analyses, which are presented in the following table:

Table 14. Sensitivity analysis for both options, in terms of cost/DALY 2013-23, £

	Option 1	Option 2	Difference / option 2 – option 1

Base case	36.92	37.36	1%

Higher volume of cases than expected
50% more cases	34.95	34.70	-1%

No epidemic
Epidemic does not occur	60.31	56.42	-6%

Rate of incidence decline in Asia
option 1 declines faster (14%/yr)	32.69	37.36	14%
option 1 declines slower (11%/yr)	39.59	37.36	-6%
option 2 declines faster (17%/yr)	36.92	34.14	-8%
option 2 declines slower (12%/yr)	36.92	44.09	19%
underlying trend is 5%	33.84	31.52	-7%

Change option 2 Case Fatality Rate (CFR) in Asia
CFR 3% (reduces current burden of disease)	39.67	43.68	10%

Discount rate
discount rate 6%	26.55	28.14	6%
discount rate 3%	18.77	20.51	9%

Other funders do not deliver
DFID reallocates funds to cover all commodity and salary costs, reduces numbers treated to compensate	38.93	40.91	5%

The margin of difference between the two options remains relatively small across all scenarios (from an 8% cost advantage to option 2 to a 19% cost advantage to option 1. The worst relative performance by option 2 is if it produces a slower decline in incidence in Asia than expected (while Option 1 produces a decline in Asia just as predicted). The highest absolute cost/DALY, £60, in the absence of any epidemic, remains relatively modest, even if more than 50% higher than in the base case. In the case of other funders failing to deliver, the number of DALYs saved falls from 1.07m to 783,000.

The results of the sensitivities, which are extreme variations on assumptions, all deliver cost/DALY well below national per capita GNI (a common rule of thumb for good value), which supports the attractiveness of both options on economic grounds.

h) Comparison with cost effectiveness of other health interventions
The following table offers comparative estimated cost/DALY ratios for a range of other health-related interventions for comparison, with figures adjusted to 2010 prices and converted to UK £. It should be noted that these estimates are for service delivery, while the VL programme includes operational research and other activities as well. Allowing for the difference in estimation methods, it suggests that the VL programme is in the same range as or more cost effective than these other key health interventions:

Table 15. Cost per DALY of health interventions in $ and £

Intervention	Cost per DALY saved / US$(2008)	Cost per DALY saved / £ (2010)
Insecticide-treated bed nets for malaria	13-20	9-13
Malaria prevention for pregnant women	29	19
TB treatment (epidemic context)	6-60	4-40
Modern contraceptive methods	62	41
Antiretroviral therapy (Africa)	252-547	167-363
BCG vaccination of children	48-203	32-135
Oral rehydration therapy	1,268	841
Cholera immunisation	3,516	2,331

Source: Singh et al (2009) Adding It Up The Costs and Benefits of Investing in Family Planning and Maternal and Newborn Health.

i) Conclusion on choice of option
The two options considered allowed for a different balance of inputs between Asia and East Africa. Both options are highly cost effective, have a good economic return and are therefore well worth investment.

Although option 1 (more for Africa) comes out very slightly better value on overall cost effectiveness, the results are so close that the choice of option should not be driven solely by the findings of the economic appraisal. The other criteria are set out in the table below with key issues summarised.

Table 16. Criteria and issues for choosing between the options

Criteria for assessing options	Case for option 1: more for Africa	Case for Option 2: more for Asia
Proven efficacy and cost effectiveness of interventions	Higher cost of interventions in Africa so requires more funding.	Interventions are more effective and cost effective in Asia than Africa
Scope to identify best practice in prevention	Major need for operational research and evaluation to identify best approaches to prevent VL in Africa.	VC already in place but IRS often poor quality - improving quality would leverage greater impact.
Leverage of other resources for VL and potential for sustainability	Asian countries have more capacity to afford interventions themselves, and other donors are involved (Gates Foundation in Bihar; sector support donors in Nepal and Bangladesh)	Greater scope for sustainable government support for VL in Asia.
Implementation risks		Risk of insecurity disrupting implementation in one or more affected countries in East Africa, much lower risk in Asia.
Scale of impact	Higher proportion of VL cases currently go untreated and die in Africa than in Asia. Option 1 increases certainty that full treatment will be available for them.	Larger numbers of VL cases need to be prevented and treated in Asia, so larger number of poor people benefit from programme.
Benefits for poor people	Prompt response to emerging outbreaks will reduce the numbers affected and benefit poor and displaced people. More DFID funding will ensure better treatment outcomes.	Longer term benefits of reducing incidence and thus accelerating elimination among the poorest, who are most likely to contract VL.

Taking these factors into account, on balance it is concluded that option 2, which allocates more to Asia than Africa, offers better value for money and less risk. The key factors in this recommendation are:

- It is the best way of meeting the overall objective of making a significant reduction in the economic and health burden due to VL.
- The risks to implementation (discussed later in the business case) especially risks of instability in the most affected African countries (Sudan and South Sudan) which could limit implementation of the programme in those countries. Instability could also arise in affected areas of other African countries.
- The uncertainty over total case numbers and hence to the estimated costs and benefits, especially in Africa where the extent of VL in communities is not well known.
- The longer term benefits of reducing VL incidence in Asia, which can build on and reinforce the political commitment to eliminate VL as a public health problem in the region. This is an opportunity to be grasped.
- The lower unit costs of treatment and availability of proven preventive measures in Asia, which gives confidence that the health and economic benefits will be achieved.
- The scope to leverage efficiency gains from improving quality of prevention and treatment, which would lead to better value for money from investments by other partners, particularly governments in Asia.

D. What measures can be used to assess Value for Money for the intervention?

All measures should be subject to a minimum service quality requirement and be compared across countries.

VfM at the Outcome level: Efficiency and impacts

- Cost per VL case detected
- Cost per VL case treated (1st line treatment)
- Cost per VL case treated (2nd line treatment)
- Cost per PKDL case treated
- Cost to households of VL diagnosis and treatment
- East African epidemics responded to in timely manner

VfM at the output level

- Cost per household of baseline survey
- Cost per health worker in endemic areas trained in VL/PKDL
- Cost per household protected by good quality IRS
- Cost per VL patient referred from private sector to Treatment Centre

VfM at the input level

The VfM focus here is with economy and assessing whether costs have been minimised. They should be benchmarked with other (for instance, vector-borne disease) programmes to in the two regions have a true understanding of whether they do offer VFM.

- Management to programme costs (should be within the 10% to 20% range)
- Incentive costs for private providers (who would otherwise wish to retain patients even though their treatment capabilities are weak) to refer patients to the public sector, or for health workers who contribute to case detection and treatment (in countries where this is common).
- Piloting costs
- Procurement costs for diagnosis: RDTs,
- Procurement costs for treatment: medicines (including AmBisome) and other supplies (e.g. nutrition, saline solution and other drugs)
- Unit costs related to construction/conversion and equipping of treatment centres
- Procurement costs for vector control inputs procured
- Evidence of scale or scope economies, or benefiting from sunk costs of existing infrastructure/cost sharing.[54]
  [54] For instance, demonstration that contractors shared unused capacity/costs with MoH where treatment centres are attached to public health facilities (which they very often will be).

E. Summary Value for Money Statement for the preferred option

The modelling against the counterfactual confirms that this programme offers excellent value for money. This reflects a) the contribution in Asia to improving quality and coverage with proven interventions, which should allow for an acceleration in the pace of reduction in VL cases and deaths that will be sustained into the long term as elimination as a public health problem progresses; b) the increase in access to treatment for people who would otherwise be untreated and die; and the avoidance of large outbreaks in East Africa which would have high mortality in the absence of an effective programme. There is also significant potential from a range of operational research and pilot activities on each continent that should have enormous positive impact for future programming.

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention

The direct procurement required by DFID is for programme management on DFID’s behalf; to secure value for money in the use of programme resources; and measurement of programme results.

The programme manager will be responsible for design work with each country, to decide in detail the interventions, funding arrangements and partners for the programme activities, delivered through sub-contracting arrangements in each country.

In addition the programme management will be responsible for the provision of products and supplies required for implementation while demonstrating value for money in procurement and ensuring quality assurance for medicines and diagnostics bought (such as inspection and batch analysis where relevant). WHO will advise on product specifications and most appropriate medicine and dosage in different contexts. If there is a need for procurement of liposomal amphotericin B medicine, the manufacturer, Gilead, has agreed to supply its quality assured product, AmBisome, at a greatly reduced price for use in VL treatment (compared to the market price for this product which is also used for other purposes). This reduced price should be available to the DFID VL programme.

Invitations to tender for the programme management role  one for South Asia and one for East Africa may result in two separate contracts to ensure capacity to work on both regions. One agency could win both contracts if they can demonstrate they can deliver both at once, to the required quality at a competitive price.

B. How does the intervention design use competition to drive commercial advantage for DFID?

The selection of the programme managers will take place through open international competition. The potential suppliers will compete in terms of their technical capacity in this complex technical area; their experience in programme management for a multi-faceted programme in several countries; and their understanding of the programme requirements and approach to them.

The design of the programme allows considerable flexibility for the contractor in terms of approach, design and implementation partners. Performance will be measured in terms of outcomes and outputs rather than activities and inputs, with additional monitoring of efficiency and economy aspects.

C. How is the market place expected to respond to this opportunity?

It is expected that experienced health or development management agencies will respond by forming consortia with technical experts, internationally and in programme countries, in order to bid. Given the relatively specialised and technical nature of the programme, it is envisaged there will be a limited number of bidders that pre-qualify for the tender.

DFID decided to have two tenders, one for each region, as this is expected to attract a wider range of competing agencies some of whom will have experience of one region only or lack capacity to deliver a programme in more than three countries. For East Africa, the requirement to operate in the somewhat unpredictable context of Sudan and South Sudan may limit the number of interested and qualified providers.

D. What are the key cost elements that affect overall price? How is value added and how will this be measured and improved?

Key cost drivers are the scale of the main programme activities such as vector control and training and supplies for diagnosis and treatment.

The choice of medicine is a major variable as AmBisome is significantly more expensive than the first line medicines used in East Africa, and may cost more than the miltefosine currently used in Asia (as miltefosine prices vary with order size[55]). Presently AmBisome is only used as second line treatment in Africa and has been donated. For Asia, there is a recommendation by the regional technical advisory group that AmBisome be used but it has not yet been adopted. It is not yet clear whether the DFID programme will need to procure AmBisome or another liposomal amphotericin B drug if there is one that achieves international quality standards (pre-qualification or stringent regulatory authority approval) or is recommended by a WHO expert committee. This depends on decisions of the Indian Government which are awaiting the findings of a trial. The costs for limited use of AmBisome in India have been included in the costing of Option 2, to allow for around 10% of cases to facilitate initial implementation or use for complex cases and pregnant women. India may decide on a different medicine or to use combination of AmBisome and another medicine.
[55] Indirect costs can also mean that even where the cost of miltefosine is less than the cost of AmBisome for an equivalent case total costs are higher for miltefosine due to higher staff costs associated with its application. Meheus F, et al. (2010) Cost-Effectiveness Analysis of Combination Therapies for Visceral Leishmaniasis in the Indian Subcontinent. PLoS Negl Trop Dis 4(9): e818.

Measures to keep pressure on costs and assure value for money include:
- competitive bidding for programme management with annual review of performance;
- cross country comparisons of programme costs to identify efficiency issues;
- programme managers will be required to demonstrate value for money in procuring supplies and sub-contractors, and
- use of negotiated low prices for medicines.

In order to address the uncertainty and increase competition in the medical commodities required, it is proposed that analysis be commissioned on the market dynamics and requirements to increase the number of quality assured suppliers, in coordination with other partners involved in this issue (DNDI and Gates Foundation).

E. What is the intended Procurement Process to support contract award?

Programme Managers will be invited to tender through OJEU. The tender document will leave significant flexibility for the bidders to demonstrate their approach.

Criteria for tendering will include:

- Experience in managing similar health programmes.
- Experience in the affected region and countries (especially desirable to demonstrate that implementers in Sudan and South Sudan have prior experience in those countries).
- Quality of technical approach and methods, including: plans to work with existing health programmes and systems; understanding of need to adapt programme to each country context; and quality of operational research, monitoring and evaluation proposed (in line with the design principles set out above in section B).
- Proposed/existing links with relevant institutions including existing DFID providers of technical assistance.
- Staff experience including in programme management, VL and evaluation, including arrangements for access to specialist expertise.
- Cost.
- Having a partner with experience of vector control (given that it is so specialised).

F. How will contract & supplier performance be managed through the life of the intervention?

The programme management produce an inception report within 6 months of contract award, setting out detailed proposals for implementation. This will be reviewed by the regional level advisory structure and DFID’s oversight committee for the programme. The contractors will present annual budget allocations and the contract will be monitored annually against planned activities and expenditures. This will involve an annual meeting of the oversight committee with each contractor to review their performance. The overheads and management inputs will be monitored and compared across the contracts.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting?

The 4½ programme budget is £27.3m. The programme managers will implement the programme based on annual work programmes for each country. The programme managers will forecast requirements on a half-year basis and sub-grant to the selected country partners.

The table below indicates how the funds will be allocated.

Classification	Cost elements included	Total DFID funding for all years
Commodities	Drugs; diagnostics; equipment; food[56]; 75% of scale up funds, procurement costs	£ 7.93 m
Technical support	TA; pilots; studies/OR; support supervision; annual country and regional reviews; contractor M&E; and contingency	£ 10.43 m
Delivery	Training and incentives for health workers; improvements to health facilities (where needed for basic ‘treatment centres’ i.e. ward and small lab space); distribution costs; consumables (e.g. syringes, fuel); design and delivery of behaviour change interventions; 25% of scale up funds	£ 6.08 m
Management costs	Management contractor costs; DFID managed mid term review and final evaluation	£ 2.86 m
Total		£ 27.30 m
[56] In the case of South Sudan, there is provision for hospitals to give food to inpatients. This is based on the information from key informants about the extent of malnutrition and the difficulty for patients to get food for themselves

The amounts required for each stage are estimated as follows (from Table 4 above):
Inception phase (6 months): £ 1.7 m
Year 1: £ 5.0 m
Year 2: £ 6.3 m
Year 3: £ 6.7 m
Year 4: £ 7.6 m

The annual funding profile is based on the assumption that contracts will be awarded in the third quarter of 2013. The profile by DFID financial year is estimated as (up to):
2013/14  £ 1.7 m (6 month inception stage ).
2014/15  £ 5.0 m ( year 1 budget )
2015/16  £ 6.3 m ( year 2)
2016/17  £ 6.7 m ( year 3)
2017/18  £ 7.6 m (year 4 and evaluation)

This funding will be made available on Aries through budget centre P0372.

This funding is not politically sensitive, novel or contentious and so does not require HM Treasury approval.

B. How will it be funded: capital/programme/admin?

This project will be funded from Programme funds, in budget centre P0372.

Requirements annually by funding type are as profiled above.

There are no contingent or actual liabilities.

Payment timing across financial years will be forecast annually to meet DFID requirements.

C. How will funds be paid out?

Payment will be Six-monthly or Quarterly in arrears. The final decision will be taken in negotiations with the preferred programme manager(s).

D. What is the assessment of financial risk and fraud?

The programme managers will be responsible for establishing financial management arrangements for implementation and for monitoring financial as well as technical performance. The agencies will themselves have to demonstrate their capacity to manage as part of the selection process.

The risks of misuse of funds arise in terms of faking of activities (e.g. training courses); another risk is diversion of commodities such as insecticides which can be sold on for agricultural use. This will be addressed through the monitoring responsibilities of the programme managers and by monitoring of impact of training and of vector control.

For most of the VL medicines and diagnostic tests there are limited risks of diversion as they are not useful for other diseases and VL is concentrated in restricted parts of the country/state. However for AmBisome there is a high value market for the drug. If substantial amounts of AmBisome are purchased, the management agency will be expected to develop mechanisms for the country to monitor its use, such as specific packaging requirements and tracing of supplies. For the AmBisome donation, WHO is setting up systems to monitor drug use and these may be applicable to other countries.

E. How will expenditure be monitored, reported, and accounted for?

Each programme manager will report on expenditure 6 monthly against plans and budgets, with explanation of variances. They will be expected to provide financial accounts 6 monthly including audited accounts annually for the programme.

Management Case

A. What are the Management Arrangements for implementing the intervention?

The management, lesson learning and oversight mechanisms have been designed to fit with existing structures as far as possible, while retaining DFID’s fiduciary and performance oversight roles. There are two types of management and oversight required: programme management oversight and broader technical oversight and coordination.

DFID will contract a programme manager for each region (South Asia and East Africa). That agency will be selected based on international tender. The programme manager will work with the national government and other in country partners to identify the implementing partners and subcontract them to provide support.

At global level there should be a VL Programme Oversight and Performance Review Committee that is responsible for performance management of the contractors, steering the programme as a whole, commissioning and reviewing the Mid Term and Final Evaluation and receiving the financial reports. The members should be from DFID policy and regional departments and WHO NTD department should be invited to join. There could also be an independent external expert in VL. The Committee would meet each contractor independently at the end of the inception phase and then once per year. The Committee terms of reference include:

- Approving the inception phase report and subsequent workplans
- Receive and review the annual report from each contractor
- Review value for money in contractor performance
- Agreeing changes to the logframe or contractor performance metrics
- Assessment of progress and any changes of course following the midterm review
- Agreeing on use of contingency funds which have been held back pending key policy decisions or evaluations of piloting
- Signing off the annual scoring of programme results.

Figure 4 summarises the programme management and financial reporting structure.

Figure 4. VL Programme management and financial reporting arrangements

DFID VL Programme Oversight & Perfomance Review Committee
Asia Programme manager
India
programme
Bangladesh
programme
Nepal programme
Africa Programme manager
South Sudan programe
Sudan programme
Country 3 programme
Country 4 programme?
The technical oversight, review and lesson learning will be fully integrated with national structures and with regional and global oversight structures. This is to ensure that the lessons are fully incorporated into wider efforts to address VL and the programme adapts to emerging findings such as results from trials.

In each country there will be a national coordination mechanism that covers VL. This need not be a new body nor specific to VL: as far as possible the programme should use existing structures for planning and coordination. Where there is a VL committee or national task force, then this can be used, or existing NTD or health sector structures. For India, the plan is to focus on Bihar state so a state level structure would be required, preferably with engagement of the National Vector-Borne Disease Control Programme. The coordination mechanism is expected to include key partners involved in service delivery and agencies that conduct vector control. It would review progress of the VL programme at least annually, preferably twice a year. This will provide some accountability to national partners and help to support coordination of efforts within VL, with other programmes (such as malaria) and the broader health system.

There are already regional meetings in Asia to support the elimination objectives, which are usually called by WHO. This sort of regional forum could also be used to provide guidance to and share experience from the programme. When reporting on progress and lessons for VL control/elimination, this would include activities supported by the DFID programme. This is intended to identify what works and where there are barriers or issues for further evaluation or improvement, and build up the collaboration and lesson learning from experience. It is envisaged that there will continue to be at least one regional progress review each year involving national officials.

If WHO establishes a similar regional forum for East African countries this could provide a mechanism for lesson learning, dissemination of evidence and discussions on policy. Review of all VL efforts including this programme would be an agenda item for meetings of national officials.

WHO reports annually on progress on VL, and the reports will identify DFID’s contribution. Reports will be reviewed by the global NTD follow up mechanism established following the London Declaration. This global level reporting is intended to maintain partner focus and coordination on VL and ensure there is a forum to address the needs of VL and an exit strategy for when DFID support ends.

B. What are the risks and how these will be managed?

Seven main risks have been identified and are discussed with mitigation strategies below.

a) Instability in programme countries: in particular, Sudan and South Sudan are both fragile states with instability in specific areas, internally displaced and cross border movements of people and risks of military confrontation between them. This is also affecting neighbouring countries that might also be included in the programme (Ethiopia, Kenya, Uganda, Somalia) and there are also risks of instability in border areas between these countries. This sort of instability could affect the programme in terms of changes to the numbers and locations of people at risk, with extra risk of outbreaks in populations that have no immunity moving into or through VL endemic areas, and when populations are malnourished. Secondly the programme activities could be disrupted if there is fighting or destruction of facilities such as hospitals.

Risk mitigation measures for this are 1) to strengthen the surveillance systems to monitor where there are cases and have the capacity to follow up actively and quickly to stem a potential outbreak. 2) To work with the existing health system and NGOs already active in country, including those working with displaced people, to build on their risk management and response arrangements. 3) To build up epidemic preparedness in the region including some buffer stocks of medicines and diagnostics in preparation for possible outbreaks.
Assessment: Medium probability, medium impact on affected areas in Africa (with effective mitigation).

b) Limited political interest and commitment in programme countries: a key risk especially in Asia, where the programme assumes the governments will provide leadership and resources to strengthen the response, including allocating most of the resources required for purchasing commodities for diagnosis, treatment and vector control, as well as operational costs for staff etc[57]. In Bangladesh and Nepal, there is substantial donor support to the health sector budget (including from DFID) and there is judged to be adequate resources to procure the necessary supplies, while in Bihar state in India DFID is providing support to the health sector and there is rapid growth in public funding that can be used for health. In Bihar state, lack of commitment in the past has been reported as a barrier to expanding VL control and making it more effective; however there is recent interest suggested by the Chief Minister establishing a steering committee on VL.
[57] Apart from Bangladesh, which has the offer of AmBisome as a donation for 5 years, with supporting funding from DFID through WHO for its introduction.
In Africa, where there is experience of dealing with major outbreaks of VL, there is recognition of the need to address outbreaks but VL competes for attention and resources for routine control. Past WHO support has helped to generate interest and started to develop VL services in Sudan, South Sudan and Ethiopia.

Risk mitigation measures include: 1) Strong coordination among the partners active in India and Bihar to keep VL on the political agenda (Gates Foundation, World Bank and WHO are all engaged and keen to work together). 2) DFID staff and consultants based in country in Bihar, Bangladesh and Nepal can help to keep the resource needs of VL control on the agenda in sector wide discussions. 3) The funding already committed to WHO for VL will enable regional meetings and advocacy efforts led by WHO, and the programme will enable additional regional interaction to keep up the momentum towards elimination in Asia. 4) The programme will build modern VL diagnosis and treatment methods into existing health services so that it can be delivered as an integral part of services in relevant parts of the country, and not require separate funding commitments or service delivery mechanisms.
Assessment: Medium probability, high impact on programme especially in Asia.

c) Capacity of health systems to incorporate VL control: adding VL diagnosis and treatment in a wider range of health facilities may be a challenge for the weak health systems in the countries concerned, especially those in post conflict settings in Africa. This includes the assumption that the system has capacity to deliver the medicines and diagnostics to where they are needed and to keep stocks of AmBisome at the right temperature.

Risk management measures include: 1) Studies are already underway to look at feasibility of using AmBisome in primary care settings in India and Bangladesh; 2) the programme will work with national programmes and coordinate with partners to address barriers to implementation and strengthen key elements of systems.
Assessment: Medium probability, high impact on programme.

d) Sustainability of VL control after the programme ends: For East Africa, the programme assumes DFID needs to provide some of the drug requirements and diagnostics, while much of the predicted requirements for the second line drug (AmBisome) are provided under a 5 year donation. The prospects for African countries to continue funding these recurrent requirements in the most affected countries, Sudan and South Sudan are hard to predict at this stage, and requirements may change if drug regimes change or new diagnostics are adopted that have different cost consequences (e.g. if short course AmBisome is shown to be effective in Africa, as in Asia). In particular, sustaining use of AmBisome if the donation ends could be a challenge at current prices. Thus there is likely to be a continued need for international funding for VL commodities for Africa. For Asia, the prospects of elimination mean that the costs of treatment can be expected to fall as there will be fewer cases, which will help sustainability. There may be difficulty in sustaining expertise to maintain the quality of vector control and treatment developed under the programme as elimination approaches.

Risk mitigation in this area includes: 1) work by partners to agree lower prices and secure supply for critical commodities; this is likely to include technical inputs on market dynamics. 2) Identifying approaches to training, supervision, case finding, diagnosis and treatment that are cost effective and where possible, integrated into primary and secondary health care, to minimise the costs of maintaining service delivery. 3) Strengthening planning and policy functions at national/state level and service delivery, training, supervision and monitoring protocols and practices at district and sub-district level to ensure capacity for surveillance and service delivery can continue after the programme. 4) Improving quality and thus cost effectiveness of prevention activities to reduce the incidence of VL. 5) Links to the global NTD partners’ forum being set up following the London Declaration on NTDs in January 2012 to keep VL funding under review and encourage continued or expanded donations.
Assessment: high probability, high impact in Africa; medium probability, low impact in Asia.

e) Funding requirements for medicines may be higher or lower than anticipated. There could be several reasons for this, for example:
- if there are several substantial outbreaks in Africa, especially in areas where there is high HIV prevalence, then treatment costs could escalate. Additional AmBisome would be required as well as first line drugs.
- Treatment costs may be higher if substantially more cases are identified than assumed in the funding estimates (which are based on the mid-point in the range of case estimates).
- Indian (Bihar state) and Nepali governments may find difficulty in funding their drug requirements for VL drugs, especially if they change drug regimes (although non-drug costs may fall if they move to a shorter treatment regime);
- The programme costing assumes there may be an epidemic but this is not certain - if there is not, then needs for medicines will be reduced, resulting in lower costs.

This will have most impact on the programme in Africa which assumes DFID will be the major source of funding for diagnostics and VL drugs, apart from AmBisome (which is used for some 10% of cases).

Mitigation of this risk is through: 1) flexibility in the budget to allow for changes in priorities and switch between uses within the programme as it develops. 2) Emergency funding could be secured for epidemics among displaced communities from humanitarian sources. 3) If there is insufficient funding for drugs, then their use can be prioritised, for example PKDL cases would not be treated with AmBisome if case numbers are much higher than estimated. 4) During year 3 of implementation in East Africa, case numbers can be reviewed and if there is surplus funding for treatment and no signs of an epidemic emerging, then funds can be reallocated to other purposes within the Africa regional programme.
Assessment: high probability, low impact (if programme adapts in response to developments)

f) Capacity of programme managers to develop and manage programmes in countries: the role of programme management will be challenging, to bring together aid management and technical skills and to work with global and local partners to deliver a response tailored to each country’s needs. Risk management measures include: 1) offering two contracts, one for each region, with the intention of attracting a wider range of bidders and making the task more manageable (with 3 countries in Asia and 3-5 in East Africa). 2) Building in a role for WHO to provide technical support and coordination. 3) Country level review of the programme and global level review of contractor performance, with requirements to get approval for annual budgets and use of contingency funds.
Assessment: low probability, medium impact

g) Epidemiology of VL: VL has shown the capacity to migrate to new geographical areas, as well as for incidence to increase rapidly in localised epidemics (mainly in Africa). The need and value for money for particular interventions (such as active case finding) will also change with changes in disease prevalence. The programme design has sought to address this through 1) improved surveillance and mapping in order to obtain a constant flow of information regarding incidence. 2) The programme contains a high degree of flexibility through its scale-up funds, which can be deployed in response to such developments.
Assessment: medium probability, medium impact (as programme is flexible to respond)

Overall the risk assessment is a medium-high risk programme, reflecting the limited knowledge of this very neglected disease, particularly in Africa where there are also other challenges. The programme has been designed with this in mind, to include substantial investments in improving understanding of the disease, its incidence and how it can be prevented in different settings; and flexibility to programme the funds in response to emerging experience, technical developments and disease patterns.

C. What conditions apply (for financial aid only)?

N/A

D. How will progress and results be monitored, measured and evaluated?

Monitoring progress
Progress will be monitored at four levels, using activity and log frame indicators:
Monitoring implementation progress of project activities: the programme will have annual workplans for each country and for regional level activities; and these will reflect the plans for individual interventions agreed with sub-contracted implementing agencies. Progress against these workplans will be monitored routinely by the programme manager, and by the national level coordination forum that covers VL at least once a year.

Performance monitoring against programme outputs and outcomes: this will be reviewed annually for each country, using data available. The first annual review will check that all baselines that are needed for the logframe and performance monitoring have been collected and agreed. The annual review after the second year of implementation will be a more comprehensive midterm review that will consider whether the programme is on track or whether it requires revision, due to issues faced in implementation or to exogenous changes (such as changes in drug policy or new evidence on diagnostics or vector control).

Progress will be reviewed at regional level as described above under A (management arrangements).

Monitoring the performance of the programme managers will be the responsibility of the VL Programme Oversight and Performance Review Committee. This group will meet with each of the contracted managers annually to review their performance and any issues in the implementation process including reviewing and approving changes that have been proposed from the country and regional reviews. They will scrutinise value for money.

Measurement of results
Results will be measured through a range of data collection and analytic methods:

- Beneficiary surveys: Sample surveys of households that have had a VL case /VL patients at baseline and end of programme will collect information on the costs of VL to households, sources of treatment (e.g. use of private providers), economic impact on families (e.g. time off work) and time lags between symptoms and diagnosis, diagnosis and treatment. The baseline findings will be fed back to improve targeting and design of country programmes.
- Cost analysis : Collection of cost data on Government and donor inputs to services will be used for identifying programme costs and analysing unit costs, to assess procurement efficiency and value for money.
- Economic impact assessment: VL programme cost data will be combined with data from beneficiary surveys to assess impact in terms of reduced economic burden of VL.
- Modelling to estimate cases prevented: and for estimating savings to families and the health system due to reduction in case numbers and prompt coverage with effective treatment (in the economic impact assessment).
- Numbers of VL cases detected; case fatality rates; proportions treated by location, age and gender; and time lags between diagnosis and treatment will be collected through routine surveillance systems and health information systems (HIS) which will be strengthened as part of the programme. This requires data collection at treatment sites and from active case detection (outreach) efforts, and reporting to district and national/state level. Sentinel sites could also be established. Specific processes will depend on national (and sub-national) settings, as the programme will seek to integrate the surveillance with the existing system where this is practical and likely to be effective.
- Estimated numbers of VL cases will be based on epidemiological studies and mapping that should improve the existing estimates of numbers of cases and their breakdown by caste/socio-economic group and gender. Estimates can be refined each year as surveillance data improves. This will be used to assess coverage for different groups (as relevant in country), both to monitor equity in access to services and to better target interventions. In Asia this data will also be used to assess progress against elimination targets at sub-district or district level.
- Quality and coverage of vector control will be measured through applying the toolkit developed by TDR and country researchers for IRS.[58] This will be complemented by data from supervision and evaluations including entomological impact (how much has VC reduced sandfly numbers).
  [58] TDR, 2010, M&E Toolkit for IRS, Kala-azar elimination in Bangladesh, India and Nepal. available to download from the TDR website.
- Capacity for case detection and management will be assessed through monitoring the quality of services at treatment centres. WHO will define standards for treatment centres that include issues such as: trained staff in post, drugs and RDTs in stock, cold chain, wards of basic standard, safe waste disposal, etc. Impact of training and the resulting service quality delivered will also be monitored, including through support supervision.

Evaluation and operational research (OR)
This programme will not conduct an experimental impact evaluation. Rather the evaluation efforts will focus on the impact of specific strategies to identify the lessons for improving programme strategies in each region and provide evidence for the theory of change where this is lacking. The specific strategies and methods for evaluation will be decided as part of the proposal and detailed planning process. At this stage it is envisaged that there should be evaluations or OR in the following areas as an integral part of the programme:

- Evaluate strategies to target IRS in India and Bangladesh to maximise impact in VL prevention
- Evaluate strategies to improve quality and community acceptance of IRS and other preventive measures.
- Evaluate methods to engage private health providers of different types in case detection, diagnosis, treatment and referral (probably just in India).
- Evaluate strategies to involve community health workers in case detection and diagnosis.
- Review of diagnostics and how they can be used at each level of the health system with a view to improving diagnostic algorithms in East Africa.
- Evaluate effectiveness, acceptability, durability and costs of innovative VC tools in different East African settings.
- Evaluate impact, costs and cost effectiveness of active case detection options in different contexts, including screening of high risk populations.
- Evaluate approaches to ensure integration of training, monitoring/surveillance and service delivery for VL within the health system to maximise sustainability and efficiency.
- OR on the factors influencing the level and timing of community take up of diagnostics and treatment, and adherence to treatment; and how behaviour change interventions can contribute to improving demand for early diagnosis and prompt treatment.
- OR on the entomology of sandflies in Africa to identify implications for VL prevention.
- Study on environmental implications of the use of DDT for VC in India.

It is expected that there will be compilation and dissemination of evaluations and OR through regional meetings, with the focus on practical use for programme improvement and progress towards elimination as the priority (alongside, but not waiting for, any academic publications).

As discussed above under management arrangements, there will also be an independent mid term review and an independent evaluation at the end of the programme, which will be used to assess the results and make recommendations on follow up. This evaluation will draw on the data collected for country monitoring and results measurement to draw conclusions on the impact; contributions to evidence and capacity building; and value for money achieved. It is assumed a limited scale evaluation will be required to draw together the findings and make an overall assessment.[59]
[59] Evaluation and MTR budget each estimated at up to £50,000 for each region plus inflation. This allows for including experts on vector control in monitoring and evaluation.

Logframe

Quest No of logframe for this intervention: 3995807