# Annual Statement of Progress (Fiduciary Risk Assessment)
#### ASP for Vision 2020 Umurenge Programme, Rwanda
Date ASP due	31 December 2013	Date ASP completed	2 January 2014	Date ASP submitted to FCPD
Does the FRA relating to this ASP draw on a PEFA? (Yes/No)					Yes
If No, was the FRA based on the 8 Good Practice Principles and 15 Benchmarks? (Yes/No)

### Overall situation
Current level of fiduciary risk (L, M, S, H)	M	Comparison to previous FRA/ASP (Improving, Stable or Worsening)	Stable
Specific assessment of corruption risk (L, M, S, H) / NB This assessment is drawn from the FRA which uses a different framework for assessing corruption risks than DFID Rwanda’s anti-corruption risk matrix used for portfolio management.	M	Comparison to previous FRA/ASP (Improving, Stable or Worsening)	Stable
Is a full FRA update required? [Yes: likely to be needed where risk levels have worsened / No: where the situation is stable or improving]			No

### Progress against key fiduciary risks identified previously
List all key fiduciary risks identified previously in the FRA or in the previous ASP to this one, if later. / Include: a brief description of the risk; planned measures to address it during the period of the ASP; and progress achieved. Where progress is off-track, outline remedial measures which have been/will be taken.
Risk 1	Risk: There are inclusions and exclusions of beneficiaries (substantial) / Description: The VUP has used community social mapping (Ubudehe) as the basis for the selection of the beneficiaries. The FRA found evidence of inclusions and exclusions of beneficiaries and concluded that these were due to poor quality data, rationing as a result of limited financial resources for implementing the programme and absence of potential beneficiaries from community meetings when categorisation takes place. / Planned measures: Targeting, Exit and Graduation guidelines committed to check targeting data through applying a balanced scorecard approach and to pilot test this by April 2013. / Progress: Scorecard designed but not piloted. / Ubudehe categorisation now under revision. DFID is providing technical assistance to GoR’s work on revising Ubudehe (led by Social Protection Division, Rwanda Local Development Support Fund), alongside UNICEF and WB. / Re-categorisation of population into new categories planned by September 2014.
Risk 2	Risk: Financial services fungibility risks (substantial) / Description: Financial services resources not used for purposes agreed and authorised by VUP staff. / Planned measures: Concept note on partnership with SACCOs developed to address the risk of delays in payments and to strengthen financial literacy of participants in financial services. / Progress: Concept note has been developed and is currently with Cabinet for consideration.
Risk 3	Risk: Environmental and social impacts of the public works activities (moderate) / Description: Limited evidence of assessment of social and environmental impacts of public works projects, which absorb more than 50% VUP resources. / Planned measures: To remind local governments of the policy on environmental impact assessment and to emphasise it during planning and budgeting process. Continued monitoring by RLDSF. / Progress: Environmental impact assessments of some public works projects undertaken and impact assessments have been emphasised in Budget Call Circular, article 17. / This issue was also highlighted in the design of DFID’s recently approved social protection programme, and in the project completion review of support to VUP. A new Capacity and Policy Development Facility to be supported under DFID’s new programme (expected to be operational July 2014), will enable review of the approach to conducting social and environmental impact assessments of public works programmes.
Risk 4	Risk: Capacity limitations at the centre (moderate) / Description: Some vacant posts at the centre and lack of TA undermining capacity / Planned measures: Commitment to fill vacant posts (financial officer and social analyst) and to procure TA as part of restructuring of RLDSF. / Progress: Two out of three TA posts (M&E and financial management) have been filled. The Capacity and Policy Development Facility will provide medium term TA on policy and programme development.
Risk 5	Risk: Capacity limitations at district and sector levels (moderate) / Description: Overstretched district staff, covering 2-3 sectors, lacking transport facilities. / Planned measures: Ongoing institutional restructuring (civil service reform led by MIFOTRA) includes local governments. Newly elaborated staffing strategy for VUP (supported by DFID TA) will address capacity bottlenecks. / Progress: Institutional restructuring approved but VUP staff continue to work on contracts and not yet fully integrated into District and Sector structures. / VUP staffing and capacity building strategy to be implemented now that restructuring complete. / Under the wider fiscal decentralisation programme, in 2013-14 sectors have been given devolved financial authority and each sector will be recruiting one accountant.
Risk 6	Risk: Staff turnover creating capacity gaps (moderate) / Description: Low salaries compared to counterparts in government and short contract periods contributing to turnover. / Planned measures: Wider institutional restructuring to cover central and local government; newly elaborated staffing strategy will address turnover. / Progress: VUP staff sector contracts extended from one to two years. / Now that restructuring complete, VUP staffing strategy will be implemented.
Risk 7	Risk: Loan repayment is very low (substantial) / Description: Low repayment rates; risks of increased vulnerability of poor as a result of proactive lending and proactive repayment management. / Planned measures: Planned partnership with SACCOs, including role for Rwanda Development Board (RDB) in financial literacy training. Stronger monitoring of financial services component by Districts and RLDSF. See risk 2. / Progress: Concept note on transitioning financial services to SACCOs (Partnerships with SACCOs) has been developed and is currently with Cabinet for consideration. / Under DFID’s new programme DFID funds will not be used for implementation of financial services component.
Risk 8	Risk: Consistency of the payrolls and attendance sheets for public works (moderate) / Description: Lack of adequate staff capacity may result in ineligible persons being included on public works payroll sheets. / Planned measures: RLDSF disagreed with this risk. In the FRA action plan they noted that “currently the list is prepared by the team leader whereby each team has between 30-50 people, verified by the committee in charge of implementation, approved by a contracted person in charge of supervision, and cross checked by the VUP staff before preparing the payroll.” / Progress: This system is continually emphasised within the public works component.
Risk 9	Risk: Graduation benchmarks (substantial) / Description: Premature graduation of beneficiaries. / Planned measures: Targeting, graduation and exit guidelines in place and dissemination has begun. Training of key staff planned by end June 2013. / Progress: Training of Vice Mayors for Social Affairs at District level and of Executive Secretaries at Sector level conducted. / Graduation will be a special area of focus for MINECOFIN under EDPRS2 in 2014/15, and a international graduation conference planned to take place in Kigali in May 2014 will provide a further opportunity to consider graduation in practice.
Risk 10	Risk: Planning Monitoring and Evaluation capacity is limited (moderate) / Description: Inadequate capacity in PM&E Unit to meet VUP’s needs risks undermining VUP / Planned measures: RLDSF agreed with the assessment but disagreed with proposed mitigating actions in the FRA (the establishment of a separate M&E unit within VUP). A team of data monitors formed to follow up on reports from Districts and Sectors. Recruitment of M&E TA. / Progress: M&E TA recruited and in contract. / Financial management TA recruited and in contract. / RLDSF team conducting quarterly routine monitoring in the districts.
Residual risk 1 (from FRA 2009)	Risk: training needs assessment at all levels needed / Planned measures: Rwanda Governance Board undertaking training needs assessment of local government. / Progress: In addition RLDSF has trained district engineers and sector staff on RLDSF programmes and monitoring tools. / First round of social protection training of trainers delivered by Institute of Development Studies/MINALOC, with participants from Districts and Sectors.
Residual risk 2 (from FRA 2009)	Risk: capacity limitations of the MFIs (SACCOs) / Planned measures: RLDSF disagreed with this risk. They noted that SACCO capacity building is ongoing and is supported by Rwanda Cooperative Agency, National Bank of Rwanda, Access to Finance Rwanda and Rwanda Development Board. / Progress: Inter agency meetings within GoR on SACCO capacity building are ongoing. / Issues of SACCO capacity are subject to discussion in Financial Sector Development Sector Working Group. / DFID has supported meetings between AFR and RLDSF to discuss AFR’s potential role in SACCO capacity building.
Residual risk 3 (from FRA 2009)	Risk: Multi-step fund transfer mechanisms resulting in delays and gaps in District’s financial management capacity / Planned measures to address: Ongoing institutional restructuring led my MIFOTRA includes local governments. VUP staffing strategy will address capacity bottlenecks. / Progress: Institutional restructuring approved and VUP staffing strategy to be implemented. / Under wider PFM reform, and DFID’s new programme of support to PFM (under design), attention will be paid to PFM capacity at decentralised levels. / Financial management TA within RLDSF now recruited and will focus on financial management capacity at District levels, including timeliness and quality of reporting to RLDSF. / Design of RLDSF M & E MIS underway (supported by GIZ), which should improve timeliness and quality of both financial and programme reporting.
Have any new risks been identified? [Yes/No] If Yes, include a brief description of the risk and planned measures to address it.			No

Is there a credible PFMA reform programme? [Yes/No]. Whatever the answer, give brief details below to justify that opinion.			Yes
A new PFM Sector Strategic Plan 2013-18 was approved in June 2013 in the context of EDPRS2, replacing the previous 2010-2013 PFM reform strategy. This is supported by donors, including DFID, through a PFM basket fund 2010-2014. The recent independent annual review (Dec 2013) of the basket fund concludes that “both components of the PFM Reform Programme are performing well against the agreed workplans for the fiscal year 2012-13”.
Is donor support for PFM aligned behind a single government-led action plan? [Yes/No]			Yes
Is there a single multi-annual plan of PFM diagnostics agreed by the Government and donors? [Yes/No]			Yes
Can you cite examples of positive progress to report which could feed into DFID external publications? / Useful examples could include successful delivery of key reform programmes or activities, quantified fiduciary or anti-corruption achievements (e.g., increased tax collection rates, reductions in the number of ghost workers, or savings made in procurement programmes)
NA

### Sources used in preparing this ASP
[Tick / add date as appropriate]
Regular Govt/donor monitoring processes		Govt-produced reports
PAF indicators		Quarterly Budget Reports
Budget Support Group/PFM Group meetings / Sector Group meetings		Annual Financial Statements
		Annual audit reports / Insert date of most recent audit report	OAG audit 2011/2012; PWC audit Dec 2013.
Other		Other	FRA action plan update Oct 2013
DFID bilateral meetings		DFID project documents
Meetings with government officials	Yes	Data from annual programme and project performance reviews	Yes PCR, Dec 2013
Meetings with CSO contacts	No
Meetings with other donors / others	Yes
PFMA diagnostics produced in the ASP period		Corruption diagnostics
PEFA /PER, etc. [state relevant sources]		TI CPI / Public Integrity Index, etc. [state relevant sources]	CPI 2013

Submitted by: Samantha Yates

Date: 2 January 2014

Note: When complete, send by email to FRA-ASP Central Scrutiny