Type of Review: Annual Review

Project Title: Global Legal Empowerment Initiative (GLEI)

Date started:	June 2011	Date review undertaken: January 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
In December 2012, the Department for International Development (DFID) awarded a grant not exceeding £1,500,000 to Namati to support Global Legal Empowerment Initiative activities between 1 January 2013 and 31 March 2015 for the areas of building the evidence base for legal empowerment, strengthening the Global Legal Empowerment Network, and exploring the possibility of a global funding mechanism. / Namati is a fully independent organisation established by the Global Legal Empowerment Initiative (GLEI) under the first year of DFID funding to the Open Society Institute (OSI) from 2011-2012. Namati works in partnership with OSI to implement GLEI’s vision. Namati has developed its organisational capacity and governance structures, in line with a DFID Due Diligence assessment completed in 2012. GLEI will continue to be jointly implemented, with Namati leading on the network, research and innovative programming and OSI leading on donor coordination.

What are the expected results?
The ultimate goal of GLEI activities is greater and more effective legal empowerment programming and policies worldwide. / What are the planned outputs of the project attributable to UK support? / Evidence gathering, particularly on the socio-economic benefits of legal empowerment; piloting, expanding, or refining innovative legal empowerment models; cultivating a global community of practice; building the capacity among network members through technical advice (including DFID staff), promotion of knowledge-sharing, and co-ordination of best practice. / How will we determine whether the expected results have been achieved? / Results are measured against agreed outputs. The logframe for this programme was revised twice in 2012: by Namati staff in October 2012, which then formed the basis of a subsequent revision by DFID staff in November that year. The logframe was approved at senior level in DFID, and although it was shared with Namati at the time, there is no evidence to suggest that it was ratified by Namati. DFID’s revisions aimed to synthesize the outcomes of the Namati logframe, bringing them in line with the impact statement. Although the content of Namati’s October 2012 logframe and the DFID November 2012 logframe is the same, the information is laid out differently to fit with DFID’s corporate requirements. This issue came to light just as the Annual Review information was being collated. The two logframes are reinforcing, and milestones are consistent, however the definition of what constitutes an Outcome and an Output within the logframe needs to be clarifed with Namati. DFID will urgently address once this review has been completed. / This review aims to capture all results from the programme this year, including those results achieved against the overall outcomes of the programme to ensure metrics from both logframes have been taken into consideration. Despite this logframe duplication, the outputs for this programme have been successfully met and milestones have been exceeded against most of the indicators found in both logframes. Nevertheless, the Outcomes in the revised logframe will need to be altered to capture the over-arching impact of the programme as we move into the final year of DFID funding. A meeting will be held with Namati to discuss revisions to the logframe in mid-February. A revised logframe will be approved at Senior Level in DFID and agreed with Namati by the end of February.

What is the context in which UK support is provided?
The UK recognises that legal empowerment is a promising approach to strengthening access to justice and producing developmental outcomes. It needs to be better understood and recognised. We need to know whether, when and how legal empowerment approaches work for the poor. / Legal empowerment approaches use the law to benefit the disadvantaged. They involve community-based justice services, such as paralegals, alternative dispute mechanisms and street and mobile courts. These efforts tend to be accessible and accepted in communities and respond to the needs of the poor and vulnerable. They can assist people in protecting their rights, pursuing their economic interests and demanding accountable and responsive governance from public institutions. / DFID’s growing programme experience in this area in countries such as Malawi, Nepal and Bangladesh indicates that legal empowerment initiatives can produce significant development benefits. Although the approach has received some international attention, for example by the UN Commission of Legal Empowerment of the Poor in 2008, there has been little systematic documentation of impact and methodologies. As a result, donor policy and practice has tended to neglect community-based legal empowerment approaches, favouring state-based institutional justice reforms, often at the national level. / In view of the above, the UK decided to support the establishment of the Global Legal Empowerment Initiative (GLEI), an international collaborative formed to develop the emerging field of legal empowerment. While GLEI is jointly led by Namati and the Open Society Institute (OSI), DFID funding supports the activities undertaken by Namati. Namati works in three ways: 1) implementing innovative grassroots legal empowerment interventions that address five issues of pressing global significance. Namati researches and evaluates each intervention rigorously, to ensure that learning from these experiments inform practice worldwide; 2) convening a network of practitioners to foster dialogue, collaboration, and learning across borders; and 3) advocating for policy changes that grow from grassroots data and experience. / Substantial evidence points to a range of socioeconomic benefits of legal empowerment for women and girls in particular. As a result of including women in Namati’s by-law drafting process for managing communal land in Liberian communities, for example, women actively challenged discriminatory rules, rejuvenated customary norms to protect women’s land claims, and changed perceptions in favour of women’s participation in town decision-making committees. In Bangladesh, legal education and raising awareness of women’s rights has made the local justice providers (Shalish) more gender sensitive, resulting in more women taking claims to court, more women victims allowed to speak at Shalish, and an increasing number of women accepted as Shalishkars, or judges. In Sierra Leone and Mozambique, 50-65% of the clients served by Namati-trained paralegals are women. / Supporting GLEI actively promotes DFID’s wider work on the rule of law/security and justice and fits with several commitments set out in DFID Business Plan 2011-15: 1.2. Support actions to help achieve the Millennium Development Goals, 2.4. Focus on results and evidence, 3. Boost wealth creation and property rights, 5.1. Lead international action to empower girls and women. It was directly endorsed by the Secretary of State (SoS) in several meetings with George Soros. It has led to a strong institutional relationship with Open Society Foundation (OSF) on justice and legal empowerment, helping to advocate for their inclusion in the post 2015 development framework, a crucial part of the UK Prime Minister’s vision on open economies and open societies. OSF-DFID collaboration on justice is an integral part of an emerging broader OSF-DFID partnership.

## Section A: Detailed Output Scoring

Output 1: Better understanding of the impacts of legal empowerment and the most effective mechanisms for achieving them (described in Namati Oct 2012 logframe as Outcome 1)
Output 1 score and performance description: A / Outputs met expectation.
Progress against expected results: / Namati has developed innovative, scale-able legal empowerment interventions in partnership with governments and civil society organizations in eight countries. These efforts address five issues: delivering quality legal aid at scale, protecting community land rights, fulfilling the right to citizenship, closing the enforcement gap in environmental law, and ensuring that essential services like healthcare are accountable to local communities. Namati has researched and evaluated each intervention’s impact with the aim of informing best practice worldwide. The data collected from Namati’s work in these countries provides the evidence base from which Namati draws to advocate for large-scale policy changes. / Number of internal targets for each intervention achieved / 2013 Milestone: 75% / Actual: on track / Namati’s internal targets aim to improve the scope, quality, and impact of grassroots work across its 5 themes. Virtually all targets for 2013 were achieved. Where targets were not achieved Namati revised its strategies accordingly to account for these obstacles. / Highlights of progress toward internal targets include: / Legal Aid 2.0: In Sierra Leone and Burma, Namati worked to demonstrate models of providing justice services that are scalable, empowering, and responsive to context. Namati’s network of community paralegals in Sierra Leone resolved 4,106 cases. Cases addressed abuse of power by local authorities, accident compensation, unpaid wages and a lack of basic services like clean drinking water, among other issues. Namati successfully advocated for a legal aid law that endorses the scale-up of community paralegals and is assisting with implementation of the new law at the request of the Ministry of Justice. In Burma, Namati partnered with law firms and civil society organizations to develop a community paralegal approach that draws on international experience but is tailored to Burma’s socio-legal context. / Community Land Protection: Having developed and tested a community land protection model in 58 study communities across Liberia, Uganda, and Mozambique, Namati and local partners began work in 156 additional communities. Drawing from research and experience, Namati also supported the Liberian and Sierra Leonean governments in their processes for drafting community land documentation policies. Liberia’s policy embraces the model that Namati and its partners developed for documenting and protecting customary land rights, and adopts specific language that Namati proposed. Namati’s key policy recommendations were also incorporated into Bioenergy Investment Guidelines now before the Sierra Leone cabinet. / Accountability of Health Services: In Mozambique and Sierra Leone, Namati is combining social accountability and legal empowerment approaches to generate improvements in the delivery and accountability of services. Namati piloted a grievance redress mechanism under which community-based health advocates have registered 228 cases of health rights violations. Nearly 65% of reported cases have been resolved, with over 50% of these resolutions taking place under 25 days. Advocates have succeeded in improving several health centres with water and sanitation facilities, increasing access to life-saving diagnostics, ending requests for bribes, and resolving shortages for essential drugs. / Environmental Justice: In India, Namati’s efforts with the community in Mundra to ‘ground truth’ environmental violations has resulted in the publication of a 50-page report on violations and the establishment of a body of concerned citizens called the Mundra Hitrakshak Manch (Forum for the wellbeing of Mundra). The forum committed itself to taking up activities and training programmes on laws and policy, as well as engaging more actively with the government on issues that affect them. / Citizenship: Namati began work with local partner organizations in Bangladesh and Kenya to train community paralegals to help stateless populations understand citizenship and documentation requirements, and to assist them in navigating bureaucratic process for ID documents, trade licenses, or passports. Uptake of paralegal services far surpassed original targets: in 2013 across both countries, paralegals assisted 1796 clients. Of those 898 cases have already been successfully resolved, meaning they resulted in valid legal identity documents. The other cases are ongoing. / Number of civil society organizations or governments trained in, advised on, or adopting our models or methods / 2013 Milestone: 30 / Actual: 127 / Namati works closely with civil society partners to implement all of its country-level interventions. It conducts trainings for communities and civil society as a means of encouraging greater use and understanding of legal empowerment methods. It advises governments on how to craft and implement policies and laws that advance legal empowerment. / Namati provided follow-up training to 64 paralegals from 5 different organizations in Sierra Leone through on-site mentoring provided by seconded and lead paralegals. As a result of Namati’s work in this area, it now assists the Ministry of Justice with implementing the 2012 legal aid law as a key member of Sierra Leone’s Legal Aid Task Force. Meanwhile, Namati’s land program provided technical capacity-building assistance to over 65 land rights organisations at symposiums and regional meetings in Thailand, Kenya, and South Africa. The Liberian land policy reflects Namati’s input and embraces its community land protection model. Namati’s training of Mozambican provincial land administrators on alternative methods of supporting community land delimitation efforts resulted in the successful and rapid award of almost all of the land certificates applied for. / Number of references of GLEI knowledge products in media and journals / 2013 Milestone: 50 / Actual: 61 / Namati seeks to raise the profile of legal empowerment among professional, academic, and general audiences. References to Namati’s work in journals, research papers, international and mainstream media, local news sources, development blogs, and at international conferences enhance the visibility of legal empowerment worldwide. Highlights include a discussion in the World Bank Legal Review of Namati’s multi-country randomized experiment on community land titling; discussion of Namati’s work in the Boston Globe, Foreign Policy, and Freedom House reporting; extensive coverage of Namati’s work with paralegals in the Huffington Post, AllAfrica.com, and the Sierra Leone Express; references to Namati’s paralegal model in Conflict, Security & Development, the Journal of Refugee studies, and a study by the International Development and Law Organization; discussion of Namati's grassroots approach to legal empowerment on a Council of Foreign Relations panel and blog, at the World Justice Forum, and at the World Bank conference on Land and Poverty; inclusion of the Global Legal Empowerment Network in a UNDP/UNEP toolkit on community conservation; and reporting on global network events in various local and regional news sources. A piece on the work of Namati and its partner Timap for Justice in Sierra Leone is forthcoming in the Stanford Social Innovation Review. / Number of knowledge products produced or translated by Namati or Open Society Justice Initiative (OSJI) / 2013 Milestone: 15 / Actual: 48 / Community Land Studies: Following the publication of the comprehensive results of a two-year, multi-country randomized experiment on community land titling in Uganda, Mozambique, and Liberia, Namati released two country reports offering in-depth analysis of key findings from Uganda and Liberia. In Liberia, the new land policy has embraced the model Namati has demonstrated for documenting customary land rights. Namati also consolidated learning from this research into two low-literacy “how to” guides, which help communities strengthen their land protection efforts and improve their ability to negotiate with investors. Namati is currently partnering with the School of Natural Resources and Environment at the University of Michigan to undertake a longitudinal randomized controlled trial of the impacts of community land protection in Liberia. The research team is on the ground and will soon be interviewing respondents for baseline data. / Justice Initiatives Indicators Special Edition: OSF and Namati produced a legal empowerment edition of Justice Initiatives, featuring introductory essays by George Soros and Justine Greening MP, UK Secretary of State for International Development. The issue’s 11 chapters explore various legal empowerment approaches and highlight eight case studies that look closely at legal empowerment in action: from paralegals resolving disputes and reducing conflict in Liberia to villagers fighting for their land in Indonesia, to an NGO using citizen-generated data to fight corruption. / 6-country paralegal study: Namati coordinated, with partners, a six-country empirical study on the impact of community paralegals. Research has been completed in Indonesia, the Philippines, South Africa, Liberia, Sierra Leone, and Kenya. Papers have been published on Indonesia, South Africa, and Liberia; the Philippines paper is being published in February 2014. The team is pursuing publishing all six studies plus a comparative chapter as a book. / Evidence Review: Namati was commissioned to prepare a Legal Empowerment Evidence Review – a paper on the state of the evidence of legal empowerment, analysing a wide-range of existing documentation on the impact of legal empowerment. In addition to establishing a baseline of current knowledge, the final product will also identify gaps and propose a framework for future research. In 2013, Namati expanded the call for evidence and research efforts to include studies in Arabic, French, and Spanish to complete a comprehensive review of existing evidence. Namati presented findings to the legal empowerment donor collaborative in November 2013; donors are using it to scope a common research agenda. The paper will be published in February 2014. / Recommendations: / In August 2012, DFID recommended that Namati should develop realistic milestones to measure the effectiveness of pre-existing approaches and initiatives. In subsequent months, Namati revisited and consolidated its workplan, redefining annual milestones for the rollout or refinement of its innovative models. / This Annual Review has demonstrated to DFID that this Output and relating indicators are not sufficiently challenging or robust to effectively measure the success and innovation of these interventions. It is essential that DFID captures the impact that Namati’s knowledge products have had on the countries or communities of practice for which they are produced. Similarly, providing training and producing knowledge products are relatively low risk, highly scalable outputs. In reviewing the logframe, DFID and Namati will need to agree how best to capture the overall impact of these outputs both at the community grass-roots level and in strengthening the field of legal empowerment at a strategic and global level. / In relation to the issues surrounding the logframe, DFID and Namati also need to refine what constitutes a knowledge product as opposed to a research initiative or training resource owing to potential crossover with other indicators in the current logframes. Next year, we would like to see how Namati responds to the gaps that have been identified in the evidence review. / Impact Weighting (%): 30% / Revised since last Annual Review? Yes / Risk: Medium / Revised since last Annual Review? No

Output 2: Improved interconnectedness, knowledge sharing and access to programming and training resources for legal empowerment practitioners, donors, and policy makers. (described in Namati Oct 2012 logframe as Outcome 2)
Output 2 score and performance description: A + / Outputs moderately exceeded expectation.
Progress against expected results: / Number of tool downloads: / 2013 Milestone: 650 / Actual: 2948 / Namati’s Tools Database is an open-source resource library that features materials and evidence on best practices in legal empowerment. Resources range from case intake forms, monitoring and evaluation tools, case studies, and examples of laws and policies relevant to legal empowerment practitioners. Namati’s building the world’s largest database of tools and evidence on legal empowerment. Network members can contribute their own resources and rate the resources they use. / Over 1,130 downloads by network members were recorded in the past year. After the US and the UK, most users who download tools are located India, Kenya, and South Africa. / The most popular tools downloaded over the past year have been: / A guide produced by Network Guidance Committee member Stephen Golub, “Legal Empowerment Evaluation: An Initial Guide to Issues, Methods, and Impact.” / Timap for Justice’s Case Management Form and Community Paralegal Manual / Namati’s Community Guide to Protecting Community Lands and Resources, produced in partnership with the Sustainable Development Institute (Liberia) / Number of returning visitors / visits / 2013 Milestone: 3000 returning visitors / 2000 returning visits / Actual: 8,295 returning visitors / 37,186 returning visits. / In 2013, over 24,000 unique visitors accessed the Namati website. Nearly half of all recorded visits were return visits. On average, people spent over 4 minutes on the website - indicating that they are reading content rather than simply passing through. The top twenty countries from which Namati’s site is accessed are: United States, India, United Kingdom, Kenya, Canada, Hungary, South Africa, Burma, Uganda, Australia, Sierra Leone, Netherlands, Germany, Italy, Bangladesh, Nigeria, Switzerland, Indonesia, and Tanzania. / Number of legal empowerment organizations represented in the network / 2013 Milestone: 300 / Actual: 300 / As of 2013, more than1600 people have registered as members on the network’s online platform, representing 300 legal empowerment organizations or institutions around the world. Registered members hail from over 115 different countries. / Number of participants in network events & GLEI capacity building opportunities: / 2013 Milestone: 200 / Actual: 425 / Namati convenes a global network to foster dialogue, collaboration, and ultimately a stronger international movement for legal empowerment. Since the formation of the network, Namati has convened over 166 member organizations from 72 different countries at regional meetings in Dhaka, Kampala, Buenos Aires, Jakarta, Amman, Accra, Nairobi, and Cape Town. / These include six major international meetings or trainings since August 2012. Each meeting addressed areas in which network members had identified a strong need for guidance but a dearth of regional resources. Themes included: Health and Legal Empowerment; Strengthening Paralegal Programming in Gender-based Violence Cases; Legal Empowerment Methods for the Promotion of Socioeconomic Accountability; Community Land and Natural Resources Protection. Regional meetings took place in Latin America and South East Asia on legal empowerment and strengthening paralegal programming respectively. / At the African regional meeting in 2012, more than 50 organizations adopted the Kampala Declaration on Community Paralegals, which calls on governments to recognize paralegals and invest in the scale-up of paralegal services. The Declaration has been used by paralegal organizations to advocate for legal aid reforms in Zambia, South Africa, Tanzania, and Rwanda. / A Network Guidance Committee (NGC) composed of accomplished legal empowerment practitioners from around the world, forms the nucleus of the global network. The NGC met in late 2013 to take stock of this past year's progress; set priorities and initiate a proposed work schedule for the network for the coming year and contribute to an ongoing dialogue on justice in the post-2015 development agenda. A number of network members have stepped up to campaign for the inclusion of justice in the post-2015 agenda at their national level. Namati is supporting national partners in forming coalitions, preparing talking points, and devising advocacy strategies in Kenya, India, and Argentina, and have begun coordinating with network members in several other countries identified as playing an influential role in the crafting of the post-2015 development framework. / Number of tools in database and toolkits / 2013 Milestone: 300 / Actual: 321 / The website hosts the world’s largest database of tools and evidence on legal empowerment. As of December 2013, there were 321 tools available online. Namati is currently producing curated toolkits that highlight seminal tools in five areas: starting a paralegal program, monitoring and evaluation, legal aid legislation and recognition of community-based paralegals, community land protection, and strategies for handling cases related to gender-based violence. Namati also experimented with a variety of methods for enhancing virtual collaboration. In 2013, Namati made refinements to an online multilingual platform that allows network members to share resources, including research, training materials, monitoring and evaluation tools, case management systems, and advocacy strategies. / Recommendations: / In August 2012, DFID recommended that Namati should continue to explore how best to make the Global Legal Empowerment Network a useful and interactive tool for discussion, sharing and dissemination of best practice. Namati’s continued progress in encouraging knowledge exchange among network members, curating and developing useful legal empowerment tools, shows a continued commitment to this goal. The Network’s active and collaborative advocacy for the inclusion of justice issues in the post 2015 discussions also demonstrates a growing sense of community. / Clearly Namati are meeting previously untapped demand for knowledge and information on legal empowerment. However there is no evidence of how practitioners have used the tools and information Namati have provided. As users are able to rate the information they found, Namati should assess whether they found it to be of good quality as well as how it addressed their needs. Similarly, it would be good to understand to what extent donors and partner countries are absorbing this knowledge and adopting legal empowerment methods. As a result, it is difficult to attribute results and impact against the milestone indicators beyond the figures reached. / The revised indicators for this Output should include a greater degree of feedback from users on the tools that Namati is producing in order to get a sense of the impact these services are having on practitioners’ work. We will address this in our revisions to the logframe, and aim to have a finalised version by the end of March 2014. / Impact Weighting (%): 35 / Revised since last Annual Review? Yes / Risk: Medium / Revised since last Annual Review? No

Output 3: Greater and smarter investment in legal empowerment (described in Namati Oct 2012 logframe as Outcome 3)
Output 3 score and performance description: A / Outputs met expectation.
Progress against expected results: / Percentage of engaged donors who report increased investment in legal empowerment / 2013 Milestone: 20% / Actual: approximately 25% / Namati have found the percentage of engaged donors who report increased investment in legal empowerment difficult to gauge because of a lack of firm baseline figures and incomplete or inconsistent self-reporting by donors. However, informal exchanges of information indicate that more than 25% have taken on additional legal empowerment programming or have identified legal empowerment as a new priority. Given the difficulty of collating data on this indicator, DFID is content that there has been sufficient interest amongst engaged donors in increasing their investment in legal empowerment. For example, AusAid, UNDP, DFID, and OSF have committed to legal empowerment funding via the Global Legal Empowerment Initiative whilst legal empowerment investment is consistently a high priority for Swiss International Development Cooperation Agency (SIDA). / Number of OSF projects enhanced with respect to legal empowerment by consultation with GLEI / 2013 Milestone: 7 / Actual: 21 / Due to OSJI’s support and technical advice, OSF projects in Burma, Cambodia, China, Pakistan, Nepal, Ukraine, Indonesia, Czech Republic, Hungary, Macedonia, Tajikistan, Kazakhstan, Macedonia, Greece, and Kyrgyzstan, Sierra Leone, and Liberia, as well as projects of the Law and Health Initiative and the International Women’s Program now encompass legal empowerment programming. / Namati worked with OSF to engage in direct advocacy with members of the High Level Panel (HLP) and the Office of the Secretary General; to produce factsheets about the role and impact of justice in development; and to host roundtables on legal empowerment at the final High Level Panel meeting in Bali, Indonesia. A number of GLEI’s policy asks relating to access to justice, legal identity, access to information, participation, and land tenure were explicitly endorsed in the final report of the High Level Panel, laying solid groundwork for continued advocacy on the issue. Two of the HLP’s 12 illustrative goals feature rule of law and justice issues. Targets for Goals 10 and 11 envision universal legal identity, ensuring “that people enjoy freedom of speech, association, peaceful protest and access to independent media and information”; increasing public participation in political processes; guaranteeing the public’s right to information and to access government data; reducing bribery and corruption; and ensuring that justice institutions are “accessible, independent, and well-resourced, and respect due-process rights; reducing external factors that lead to conflict, such as organized crime. / Number of interested donor participants / 2013 Milestone: 10 / Actual: 12 / In September 2013, OSF and DFID convened a meeting of 11 donors and policy makers, hosted by UNDP. Participants included the Ministry of Foreign Affairs; Ministry of Foreign Affairs, Denmark; DFID and DEFRA (UK); Ministry of Foreign Affairs, Sweden; Ministry of Foreign Affairs, Netherlands; GIZ; OSJI; Montpelier Foundation; Omidyar Network; UNDP; World Bank (with regrets from AusAid and EuropeAid). The meeting aimed to strengthen the coherence and impact of efforts to increase access to justice for the poor, and proposed the establishment of a Policy Collaborative on Access to Justice and Legal Empowerment. The collaborative identified priorities in the following areas: (1) advocating for the inclusion of justice in the post-2015 development agenda, (2) establish a learning forum to share evidence, programming tools, and other resources, and (3) mapping research interests so as to coordinate on addressing gaps. / Namati engaged with the US Department of State and the US Mission to the United Nations on key advocacy priorities, including the promotion of legal empowerment within the post-2015 development agenda, the establishment of a funding mechanism, the protection of community land rights, and supporting the scale-up of basic justice services. / Number of guidance documents distributed at the request of donor / 2013 Milestone: 4 / Actual: 2 / Namati developed a background paper for UNDP’s Global Dialogue on Rule of Law in the Post-2015 Agenda, which outlined sample justice-related goals, targets, and indicators. A discussion note presented these proposals to the Network in an online consultation. Over 40 Network provided substantive feedback on the proposed goals. The results of the consultation informed an advocacy statement that will be endorsed by network members and launched at the meeting of the Open Working Group in 2014. / Namati also shared recommendations for supporting the field of legal empowerment with the U.S. State Department’s Bureau of Democracy, Human Rights, and Labor. OSJI is currently undertaking a survey of the resources donors have or desire, after which it will facilitate distribution of existing documents and initiate development of guidance documents together. / Number of research initiatives brokered / 2013 Milestone: 4 / Actual: 43 / In March 2012, at the suggestion of a number of donors, Namati was commissioned to prepare a Legal Empowerment Evidence Review – a paper on the state of the evidence of legal empowerment, analysing a wide-range of existing documentation on the impact of legal empowerment. Namati presented on the findings of the complete version to the donor group in November 2013, and will publish the paper in February 2014, in advance of next donor group meeting. In February Namati will also submit the paper for publication in a peer-reviewed journal. Publication has taken longer than Namati hoped, because of the decision to search for non-English studies, and because of a problem with coding data that was discovered during drafting, and that required re-coding of a third of the studies in the review. In 2014, Namati will also publish on the Network website an open source database of all studies and evaluations that were reviewed, so as to create a searchable, living collection of evidence going forward. / In 2013, OSJI joined Mott foundation in supporting research with South African umbrella organisation Nadcao, on the cost effectiveness of South Africa’s community advice office, at the request of the government which is considering financing them. Results will be available in 2014. / The World Bank Justice for the Poor program is evaluating Namati’s experiment in Sierra Leone that explores the potential synergies between legal and social strategies for improving the accountability of healthcare services. The World Bank is using the qualitative case tracking method that Namati piloted in its 6-country study on paralegals. / The International Development Research Center issued a grant to cover joint research initiatives undertaken by four institutions, convened by Namati. IDRC will play an active role in designing and monitoring the various investigations undertaken by each of the partners. / Namati helped to broker additional funding for a longitudinal randomized controlled trial of the impacts of community land protection from Cloudburst Development. One of the aims of Cloudburst’s investment is to ascertain from research findings whether community land protection is a viable strategy that merits further USAID support. / Recommendations: / In 2012, DFID noted, “The evidence review will help to develop a more structured research programme on the impacts on poverty reduction and broader development outcomes. Namati should consider how it can respond to the research gaps identified over the next two years.” / Namati has targeted its research to address gaps identified in the evidence review. The review found little to no evidence on the impact of legal empowerment efforts in repressive regimes—Namati developed a program in in Burma in part to contribute to filling that gap. The review also called for longitudinal studies, to examine longer-term impact. Namati aims to track all our efforts over time. For example, Namati has embarked with colleagues from the University of Michigan on a 10-year, multi-country study of its work in community land protection. Finally, the review called for more evidence on the impact of community paralegals on development outcomes. Namati is researching possible development impacts in several interventions, including citizenship, accountability of health services, and land. DFID need to understand better the evidence review that has been produced in order to assess its impact against the milestone indicator. / Output 3 is jointly led by OSJI, and Namati are key contributors. OSJI’s leverage and advocacy are vital to changing donor behaviour and investments; however, Namati needs to consider how to liaise with OSJI to ensure that data is sufficiently captured in narrative reporting ahead of the Annual Review process. DFID is agreeable to discussing revisions to the logframe, however it is noted that capturing the information in these outputs should be achievable once a mechanism for reporting results between Namati and OSJI is formalised. DFID has previously recommended that Namati consider a Memorandum of Understanding with OSJI on this basis and this should be addressed over the next reporting year. / OSJI have requested to alter indicator 1 to include information on the work it has been undertaking to ensure legal empowerment and access to justice become an integral part of the post-2015 agenda. OSJI proposes the indicator should measure the number of governments who are making a contribution to advocacy on getting legal empowerment into the new agenda. DFID is agreeable to this and alterations can be made during the logframe discussion that is required as a result of this review. / Impact Weighting (%): 35% / Revised since last Annual Review? Yes / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? / Yes - the logframe was updated in October 2012 and November 2012. Owing to changes in personnel in DFID, Namati has been working towards the outputs it proposed under the October 2012 logframe. The milestones for the different logframes are reinforcing, however, the logframe will need to be revised again to meet both DFID corporate requirements, and to match Namati’s areas of operation. A review of the logframe will take place in mid-February, with a final version approved at senior level in DFID and agreed with Namati by the end of February. / 1.2 Overall Output Score and Description: / The overall output score is A / In most areas, results are significantly better than expected. Namati surpassed almost all projected 2013 milestones. These include, for example, the number of civil society organizations that were trained in, advised on, or adopting Namati models or methods, rates of website usage and network membership, and the number of knowledge products produced or translated. However, it is difficult to attribute the overall impact of Namati’s work at both the community grass-roots level and also the global level. The indicators by which DFID and Namati are measuring the success of their work in the current logframes will be investigated and amended where necessary. This will be done in order to capture how Namati’s interventions are serving the communities it assists; the impact that Namati is having on the overall field of research; as well as the results attributable to investments in legal empowerment initiatives. / 1.3 Direct feedback from beneficiaries / -Citizenship- / Yusuf Mahmoud, 19 years old, Resident of Mako’ngeni in Kibera: For three months Yusuf tried to get through the birth certificate application process on his own. He repeatedly went to the relevant government office in order to submit his application – each attempt was met with more requests from the officials for additional documents - the officials may have made the process more difficult in order to increase their chances of a bribe. He finally received a birth certificate with the assistance of a paralegal, trained by Namati. “It was the happiest day” – Yusuf plans to apply for a passport and also wants to search for new work and feels this additional documentation will help him get a good job. / -Essential Services- / “The community and hospital relationship greatly improved after the start of this project. Now the people of this community know how to claim their rights. Before it was impossible to complain. There was no room for it.” - Traditional authority, Changalane / -Environmental Justice- / Since Namati started work in India, we have received feedback from government officials at the Fisheries Department in Uttara Kannada and the Gujarat Pollution Control Board. Officials from these departments have participated in community meetings organized by Namati, have described our interventions as “valuable” and are willing to advance our reports and advocacy points through their offices. / -Global Network- / At the Latin American Regional Meeting on Legal Empowerment, a majority of participants found the content of the training to be “very useful” (5/21) or “extremely useful” (13/21). The momentum generated at the meeting resulted in the formal establishment of a regional sub-network for legal empowerment. / At the training on gender-based violence for paralegal programs in Africa, pre-tests and post-tests were administered to measure participants’ understanding of strategies for addressing cases of gender-based violence. / Overall, the average pre-test mark for participants who attended the training in full was 26% and the average post-test mark was 51%. / The participant who demonstrated the most improvement scored 34% initially and 77% after the training. / -Direct Feedback from UNDP on the Global Network / UNDP praised Namati’s ability to forge relationships with like-mind NGOs / Reflections included the need for a clearer vision on what exactly Namati wants to achieve through developing a strategy of work that defines the role of the secretariat, and that of the members of the guidance committee. Namati should align its strategy to these roles within its regional workshops and events to avoid a discussion on legal empowerment in general terms and to better focus attention on what Namati aims to achieve.
1.4 Summary of overall progress / GLEI has had a productive second year. The global network almost doubled in size, and substantially more network members benefitted from capacity-building and dialogue-enhancing opportunities in 2013. Namati also published a variety of resources that explain and analyse their models and methods. In partnership with both government and civil society, Namati has succeeded in replicating and scaling up these models in several countries.
1.5 Key challenges / An important programme management challenge in conducting the review of progress against anticipated results this reporting year was having two different versions of the logframe. Despite this DFID is satisfied that results against the logframe approved in DFID at senior level in November 2012 have been met. / The logframe will be reviewed and revised with Namati by the end of March following this Annual Review, to ensure that: / The logframe captures the outcomes/impact of Namati’s work sufficiently, as well as activities; / The indicators are sufficiently rigorous and challenging; / The outputs are framed in such a way that Namati is accountable for their delivery; / The logframe reflects DFID corporate requirements in relation to Outcomes and Outputs, is aligned with DFID’s priorities; and / The logframe accurately reflects Namati’s areas of operation against its new workplan. / 2012 DFID Recommendation: “As described, some aspects of the original workplan have not been completed as expected in Year 1. For example, joint research with International Women’s Partnership for Peace and Justice (IWP) on the gendered impact of legal empowerment has been on hold awaiting funding from IWP; international pro bono and crowd-sourcing proposals are also on hold. Conversely, opportunities for pilot interventions have been identified in Bangladesh, Kenya and Nepal. I appreciate that any new initiative needs some degree of opportunism and related flexibility in the workplan. However, GLEI should consolidate the workplan for Years 2 and 3, to ensure that there is sufficient capacity to deliver the key outputs.” / In September 2012, Namati revisited and consolidated its workplan, with the aim of more effectively leveraging our resources in pursuit of its mission. All its work now falls under five primary themes, for which Namati has developed both an overarching vision and distinct targets and goals. A further challenge is balancing country-level innovation with global evidence gathering, networking and influencing. In 2014, DFID would like to discuss the workplan, ensuring that it responds to the evidence priorities set out in the evidence review and in the donor policy collaborative. / 2012 DFID Recommendation: “Technical support: In Year 1, GLEI has provided technical support to several organisations and is providing research capacity for a group of donors. However, the business case stated that GLEI would provide technical assistance to DFID programmes. We would like to encourage greater engagement and technical assistance to DFID programmes directly, on issues related to implementation, evaluation and research. The Security & Justice team will need to actively explore opportunities in other countries such as Nepal, Bangladesh, Ethiopia and Nigeria.” / Namati’s collaboration directly with DFID in country is growing, but Namati has requested increased support from DFID in London in making contact with country offices. In Sierra Leone, Namati’s team leader serves on the steering committee for a multi-year DFID-supported justice reform project. Namati is also implementing a large portion of the project’s work on community justice services. In Mozambique, Namati had several meetings with DFID staff and hopes to collaborate in 2014. In Burma, Namati advised and collaborated with Pyoe Pin, DFID’s civil society strengthening program. The DFID-funded Community Legal Services Project in In Bangladesh, The DFID-funded Community Legal Services Project drew on Namati’s data collection tools for paralegals in developing similar tools for Bangladesh paralegal organizations. The project also invited Namati to speak at a national meeting on access to justice it’s convening in Dhaka in February 2014. / In 2012, Namati CEO Vivek Maru presented at DFID’s inter-ministerial advisory group and gave a talk for DFID staff. Iris Krebber invited Vivek and Program Director Rachael Knight to present on land protection work in 2014 to DFID staff, and to the land donor group that DFID convenes. Namati has applied with Oxfam for a DFID innovation grant to support adaptation of its community land protection model in two new countries. Namati has also coordinated with DFID on post-2015 advocacy. This work demonstrates that Namati has established itself as a source of expertise and excellence. evidence / 2012 DFID Recommendation: “Capacity: Namati is a new organisation, with good organisational capacity and governance structures. However, it will need to continue to establish itself and ensure that it has the right systems and capacity to fulfil an ambitious vision and associated workplan. In particular, it needs a mixed skill set to deliver both research and a diverse portfolio of pilot interventions. Some initiatives are already well established such as primary justice services in Sierra Leone. However, new pilots will be more demanding, so will need to be thoroughly considered.” / Namati achieved progress in a number of organizational capacity and management areas in 2013. It now has a global staff of over 25 individuals and partnerships with over 12 organizations in eight countries, surpassing original projections. Recent hires have strengthened its core financial and administrative capacity. In addition, Namati maintains contractual relationships with several outside consultants for technical assistance in program areas, including website development and monitoring and evaluation. Namati has Board-approved personnel policies, conducted a market evaluation to inform salary recommendations and contracted with several vendors to offer employees a competitive and comprehensive benefits package. / 2012 DFID Recommendation: “OSI’s role: GLEI will continue to be led jointly by OSI and Namati. The intention is for Open Society Institute (OSI) to lead on donor coordination and activities with other Open Society Foundation (OSF) network members, and to contribute to the network and evidence gathering where appropriate. The partnership with OSI will need to be well defined, to make sure that the division of labour is strategic, making the most of OSI’s profile and size. OSI and Namati are drawing up a memorandum of understanding to respond to these concerns.” / In January 2013, Namati and OSI met to collaboratively define the nature of their partnership. Both parties discussed and agreed on complementary geographic and thematic areas of focus. A follow-up planning session is scheduled for February 2014, to account for OSF’s recent global strategy-setting process. Namati and OSI will also seek to develop a more systematic approach to data-sharing so as to enhance accountability and coordination. The parties will also clarify goals and timelines relating to the joint Justice 2015 campaign, to improve the impact of their advocacy. . / 2012 DFID Recommendation: “Funding: The main funders of GLEI and now Namati are OSI, DFID, and AusAid. OSI have committed to matching all funding (from between 30-50%). Namati will need to find other sources of funding, particularly as the AusAid funding is coming to an end.” / Namati is diversifying its funding base. In addition to core support from DFID, OSF, AusAid, Echo Street Foundation, and Yolo Foundation, Namati attracts grants to support specific projects. A fraction of all project-specific grants are reserved for core operational costs. Funding sources include UNDP, Wellspring Advisors, the International Development Research Center, the American Jewish World Service, DAI, Echo Street Foundation, the Yolo Foundation, Humanity United, and a range of private donors. The Echo Street and Yolo foundation grants were untied core support. All the grants included a fraction for core operational costs.
1.6 Annual Outcome Assessment / In Year 2, GLEI made significant progress towards a better understanding of the impacts of legal empowerment and the most effective mechanisms for achieving them. Namati’s models are being monitored, researched, and tested in a variety of contexts, with a variety of partners. Data and learning from grassroots experimentation have been shared across a wide range of practitioners in diverse formats, from academic articles to low-literacy community guides. Through global network programming, Namati has built the capacity of network members to monitor their work and gather greater and more reliable impact evidence. / A key challenge going forwards will be showing how increased evidence and learning is actually influencing policy change at the national level and at the international level. Over the next year, Namati should focus on how its work at grass-roots level and their reconfigured workplan are facilitating and enhancing the overall strategic impact anticipated from this programme.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: / Yes. Namati is paid in advance with quarterly financial disbursements set out in the DFID Accountable Grant. All request for funds give detailed information on anticipated expenditure and the forecast financial disbursements match the figures set out in the Accountable Grant. / 2.2 Key cost drivers / Primary costs supported by the DFID grant include costs associated with meetings of the Global Legal Empowerment Network and Network Guidance Committee, grants provided to Namati’s in-country partners, and personnel and travel costs for Namati staff. / 2.3 Is the project on-track against original timescale: / Yes.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / During the review and consolidation of Namati’s work-plan, Namati revised unrealistic targets. For example, instead of undertaking joint research with IWP, Namati conducted a more practical training workshop on gender-based violence for African paralegal programs, and is currently supporting these organizations’ efforts to implement lessons learned at the workshop into their daily programming. Namati adjusted the pace of the launch schedule for citizenship interventions in Bangladesh, Kenya, and Nepal, which are now all operational. Full scoping of crowd-sourcing and private social enterprise options led to a re-prioritization of these activities. In light of the complex legal, technical, and financial obstacles involved, Namati shifted its focus from crowdsourcing for network members to developing a base of small donors for Namati’s work. Namati continues to explore avenues for micro-philanthropy for network members as well as social enterprise. Should workable solutions arise, it will reintroduce these initiatives to its work. / 3.2 Where an evaluation is planned what progress has been made? / N/A

4. Risk
4.1 Output Risk Rating: Medium / Namati are proving to be reliable and effective in achieving outputs against the logframe as well as in their ability to clearly demonstrate value for money. However, Namati is a relatively new organisation that is still establishing itself and the risks below indicate the continued relevance of the current risk rating. / 4.2 Assessment of the risk level / The overall risk rating is Medium. The following risks were originally identified and mitigated against: / The profile of GLEI remains limited and legal empowerment approaches continue to be neglected. GLEI and Namati have raised their profile through media outputs and coverage, as well as growth of the Network; wide dissemination of research and best practice tools; a diverse portfolio of pilots; engagement with a wide group of donors at both working and political level. The Justice 2015 campaign in particular has attracted global and high-level attention to GLEI and the crucial role of legal empowerment in achieving development outcomes. / The legal empowerment approach may encounter resistance from national governments and donors focused exclusively on state justice provision. GLEI has made clear that legal empowerment is not exclusively about civil society initiatives, but also state-led approaches which increase people’s understanding of the law and their rights. In its innovative country-level interventions, Namati has demonstrated a clear capacity to build positive relationships with government actors engaged in state justice provision. / The initiative may prove financially unsustainable. To date, GLEI has had sufficient funding, with both OSI and DFID committing multi-annual funding. OSI has committed to providing matching funds to Namati. Namati has succeeded in attracting funds from a range of other donors in support of specific projects; it will need to continue to look for other funding sources.
Risk of funds not being used as intended / Low-there is minimal risk of misuse. Namati engages qualified external auditors to review all financial activity and render an independent opinion. Audits are performed in accordance with generally accepted accounting principles and audit standards. As a new organization Namati has completed the first audit for the fiscal year ended December 31, 2012 and received an unqualified opinion and a “clean” report. / Internal controls: Namati has implemented policies procedures related to segregation of duties and management of financial resources. In addition, the accounting system is geared to segregate costs and to ensure that expenditures are made in accordance with the terms of grants and contracts. / Leadership responsibility: Namati’s Board of Directors, the CEO and CFO have fiduciary and legal responsibility for the integrity of the financial system and implementation of sound practices. The CFO is primarily responsible for the day-to-day control of the organization’s assets and control over all financial transactions. / Grant monitoring: Namati’s managers are also assigned responsibility for the financial management of grants and contracts under their supervision. Managers are closely involved with the control a use of financial resources in accordance with grant terms and donor expectations. Namati’s program staff either works alongside or regularly visits the offices of in-country partners to which Namati provides grants. In this way, Namati is able to verify the appropriate use of funds by its partner organizations through personal observation or confirmation. Namati also requests annual audits from its in-country partners. / Insurance: Customary to most NGOs in USA, Namati protects its assets, including monies related to grants, through insurance policies that provide coverage for losses arising from malpractice. / 4.4 Climate and Environment Risk / N/A

5. Value for Money
5.1 Performance on VfM measures / As this is the first year that Namati has received funding as a fully independent organisation, Namati underwent a full due diligence questionnaire, which includes commercial aspects. Funds are paid in advance to Namati with clear quarterly disbursements set out in the Accountable Grant agreement with DFID. / In terms of financially reporting, Namati have kept their request for funds within the parameters set by the Accountable Grant agreement and account for both actual expenditure and forecasted expenditure in their statement of accounts each quarter. Namati underwent an independent annual audit of their accounts and it was found that all statements fairly reflected Namati’s financial position. In this audit, and throughout the funding year, DFID has been able to attribute clearly DFID’s funding to Namati’s activities. / Namati are aware of value for money principles and are seeking to find ways to ensure cost effectiveness is an underlying baseline by which to measure their overall impact in this field. Based on the achievements set out over this annual review period and Namati’s clear financial reporting to date this programme is demonstrating value for money, and is on target to achieve all indicators set out over the programme. / Owing to the fact that the majority of logframe indicators have been significantly exceeded during this review period, DFID staff will review the milestone indicators with Namati to ensure that the indicators for 2015 are sufficiently rigorous. / 5.2 Commercial Improvement and Value for Money / Namati’s commitment to data collection and evaluation allows it to leverage its impact in two ways. Firstly, Namati uses the data to translate grassroots efforts into large-scale policy improvements. It has succeeded to do so Liberia and Sierra Leone, and is aiming to do so in all the other countries where it works. Secondly Namati shares the evidence it generates with the legal empowerment network. The network provides a vehicle for taking innovations to scale. Namati includes cost effectiveness as a factor in evaluations in order to study impact against opportunity costs and monitors its staff’s financial accountability through annual performance reviews. / 5.3 Role of project partners / Namati works closely with local partners to implement all of its country-level interventions, e.g. in Sierra Leone, Uganda, Liberia, Mozambique, Kenya, India, Burma, and Bangladesh. Namati trains local partners in its models and methods, and jointly strategizes, implements, and monitors activities with partners. Namati also undertakes joint fundraising with local partners to support collaborative work. / Open Society Institute (OSI) and Namati work together to fulfil the goals and targets set out for GLEI, as described in the GLEI logframe. This requires constant coordination and information-sharing. A number of initiatives aimed at developing the network or advocating for international policy are also undertaken jointly. / 5.4 Does the project still represent Value for Money : / Yes / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
Namati has built innovative legal empowerment experiments on the ground in eight countries and is researching each of these efforts rigorously. Namati is using this evidence in three ways: to advocate for large-scale policy changes, to enrich the knowledge base from which other efforts can draw, and to encourage greater and smarter investments in legal empowerment. / Namati should consider how to balance these 3 areas of work to enhance its strategic vision through consolidation of evidence, increased output of research initiatives and co-ordination with like-minded donors. This should focus attention on the significance of Namati’s legal empowerment interventions and create a platform to advocate for increased investment and interest in legal empowerment initiatives from the international donor community as well as achieving important results on behalf of communities at the regional level. / A main conclusion of this review is the need for a single revised logframe which captures the outcomes and impact of Namati’s work sufficiently. It is essential that revisions to the logframe are reinforcing to the new Namati workplan and enhances Namati’s strategic vision and impact. DFID and Namati will need to test the assumptions that were made against the current indicators and milestones to capture results more effectively and define output products more clearly. Adjustments should be made to the milestone indicators to ensure they are sufficiently rigorous and challenging. / Overall, this has been a successful first year for Namati with many of the outputs meeting expectations or exceeding them. However, there is a need for a more rigorous logframe to have greater confidence in these ratings. The revised logframe will seek to improve upon these achievements as the programme moves into its final year of DFID funding next year.

8. Review Process
This review was undertaken by the Deputy Programme Manager and Senior Governance advisor, in the Security and Justice Team, Conflict Humanitarian and Security Department, DFID, utilising narrative and financial reports provided by Namati.