Type of Review: Annual Review

Project Title: Web Foundation

Date started:	October 2012	Date review undertaken: Oct-Nov 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is providing up to £1.25 million to the World Wide Web Foundation from 2012-14, to continue to pilot the generation of an annual “Web Index” that captures the economic, political and social impact of the Web in over 100 countries. The UK is also contributing to the Alliance for Affordable Internet, a public-private coalition hosted by the Web Foundation, which aims to increase Web access through regulatory reform.

What are the expected results?
The intended impact to which the project will contribute is More inclusive policies, services and business models, underpinned by a more cost-effective and accessible World Wide Web / The intended outcome of this support is Better information on readiness, access, use and development impact of the web available to inform efforts to reduce costs of accessing the internet through policy and regulatory reform / The planned outputs are: / The production of an annual Web Index, with data about Web Readiness, Web Use, and the Impact of the Web / The Web Index is produced with high quality research and rigorous methodology standards are applied / Web Index data is released in accessible formats that are easily usable by academics, policy makers, and other relevant stakeholders / The Alliance for Affordable Internet coordinates efforts on the regulatory and policy changes required to reduce the cost of web access / Support and engagement of NGOs, academia, policy makers etc. at the local and regional level to help shape policy and programming.

What is the context in which UK support is provided?
In order to graduate from poverty, poor people must be able to make informed choices, take actions for their own development, influence decision makers and hold them to account. Successful economic and social progress depends on creating the environment where people living in poverty can be actively involved in overcoming the challenges that they face, overcoming structural barriers to participation through the creation of channels and opportunities to have greater control over their own development. / For the last decade or so, there has been increasing attention to how new technologies can support more inclusive development processes through promoting openness and transparency, and empowering people living in poverty to engage more fully in economic, social and political life. The impact of the World Wide Web in fostering more open societies since the 1990s has been dramatic. The Web has also created new platforms for social and political relationships, improved access to information and supported more effective service delivery in a number of contexts. / However the impact of the Web has been unevenly felt both within and across countries. The digital divide which occurs in relation to wealth, gender, and geography shows us that the current impact of the web largely reflects existing global inequalities and that the web can further reinforce such patterns of access to resources. Clearly there are large, albeit reducing, differences in terms of access based on affordability, availability and individual and institutional capacity between developed and developing nations. Beyond this, there is the further question of how Web access translates into economic and social benefits for users based on the quality, relevance and utility of the opportunities that it provides. / Until recently, nobody had attempted to design a simple, comparative instrument to allow policy-makers and citizens alike to understand at a glance the uptake and development utility of the web. Beyond high-level statistics on the “digital divide”, there has in fact been relatively little analysis or public debate on the reasons why some countries have moved faster and more effectively to harness the Web as an accelerator of economic and social development, or its impact on different groups within society. Many of the indicators that already exist only measure quantifiable metrics, such as the number of Web users, speed of access, total number of pages and number of searches per subject, and this is often not publicly available. / To address this gap, The Web Foundation has created an Index that uses both quantitative and qualitative data to rank countries on the progress and social utility of the web. The Index is both an analytic tool and a resource for policy advocacy. It has 3 key dimensions: (i) web readiness - communications and institutional infrastructure; (ii) web content and use and (iii) political, economic and developmental impact of the web. / In addition, the Web Foundation is spearheading an Alliance for Affordable Internet with the ultimate goal of increasing adoption and use of broadband in low-income countries. By creating the conditions for open, competitive and innovative broadband markets, regulatory and policy reform can pave the way for very large increases in internet access.

## Section A: Detailed Output Scoring

Output 1: Web Index produced annually, with new and better data
Output 1 score and performance description: / A- Outputs met expectation / Indicator 1.1: Number of primary indicators in expert assessment survey Milestone: 60 Achieved: 90 fielded, of which 83 used across the index and pull outs Indicator 1.2: Improved data on censorship and surveillance in the Index Milestone: Development of secondary indicators on censorship and surveillance Achieved: 2 indicators on privacy, 2 on cybercrime and 1 on censorship / Indicator 1.3: Improved data on gender and poverty gaps in Web use and benefits Milestone: 7 indicators on gender, 1 on literacy and 3 on affordability Achieved: 10 gender, 2 education, and 21 affordability indicators / Indicator 1.4: # indicators on the use of the web as related to the environment Milestone: 2 Achieved: 5
Progress against expected results: The Web Foundation has exceeded all of the milestones relating to the inclusion of new and better indicators for the Index. However, with regards to the achievement of the overall output, it should be noted that at the time of the Annual Review the Index had not yet been published. The Web Foundation rescheduled the launch date to 22 November to allow more time for quality checking the scores against the available evidence. This means that we have been unable to gather detailed feedback on the improvements in the 2013 Index from policy-makers and other stakeholders. / Improvements to the Web Index 2013 include: / Addition of 13 new indicators to the Index since 2012 and refinement of a further 7 to strengthen the available data on censorship and surveillance, affordability, literacy, and gender. As a result, there will be three pull-out indices produced from the Web Index – an Affordability Report, an Open Data Barometer and (data permitting) a Gender Report. / The Web Index has also been restructured into four sections with a view to enabling it to better provide clear, actionable policy recommendations. / The 2013 Index includes data from 20 new countries. The availability of data from across a wider range of countries will add nuance and regional perspective to the broader Index, adding to its value as a global public good. / Stakeholder feedback confirms that the comprehensive range of data across countries and thematic areas provided by the Index is relevant and needed. Although it is too soon to point to specific evidence of impact, several stakeholders reported that the Web Index is making a distinctive contribution as a public good because it provides data on issues which are not covered by any other research; and because it aggregates the data in a way which allows a more comprehensive national assessment and cross-country comparison. Over the next year it will be important to get feedback from policy makers as to whether the new format facilitates policymakers to identify relevant findings following the launch of the Index. / Recommendations: To strengthen monitoring and support learning, it would be helpful to clarify the difference between fielded indicators and those included in the final index. / The milestones for indicators 1.1 and 1.4 have already been exceeded. However, noting that ‘better’ data isn’t necessarily achieved by collecting more data the Web Foundation should consider how to strengthen qualitative reporting in relation to these indicators next year. / The Web Foundation should track changes made to the indicators over time. This will help maintain oversight of how the Index is changing – both to ensure that indicator quality is being prioritised over quantity, and that the volume of changes does not compromise data consistency to the extent that results cannot be monitored over time. / Action 1: In addition to reporting on the milestones for Output 1, in 2014 the Web Foundation will provide additional information in next year’s annual report on: / Indicators fielded vs those included / Changes to the indicators and structure of the Index over time / A qualitative narrative on how Index quality and relevance has improved in relation to the above points. / Impact Weighting (%): 30 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Web Index data released in accessible formats to relevant stakeholders
Output 2 score and performance description: C- Outputs substantially did not meet expectation / Indicator 2.1: Number of accessible formats published on the site Milestone: 7 Achieved: 0 published (7 in development) / Indicator 2.2: Average number of unique website visitors per day Milestone: 2750 Achieved: 1000 / Indicator 2.3: Number of visualisations, infographics, data mash-ups independently produced by others using our data Milestone: 6 Achieved: 2
Progress against expected results: The Web Foundation has made significant progress with the design and construction of the website. However at the time of the Annual Review this output had not been delivered, due to the extended research period and rescheduled launch. / The Web Foundation reports that a beta version of the website will be available for testing at the end of October which will offer at least 7 different formats to access the data (as per the milestone). / Similarly, due to rescheduling of the Index launch, the Web Foundation has achieved less than half of its expected website visitors per day and fewer independent visualisations of the data than anticipated. The Web Foundation estimates that these milestones would have been achieved had the launch of the Index occurred within the reporting period, based on activity following the Alliance for Affordable Internet launch. As such it is likely that this milestone will be met in the next quarter. / Recommendations: In order to more effectively assess the extent to which the Index is informing more inclusive policies, services and business models, Web Foundation should consider how to improve information about who is accessing the data sets, what they are looking at, and (ideally) how they are using it. However, it is important to ensure that any collection of such metrics does not create obstacles/ deterrents to users accessing the data and is proportionate in terms of cost and effort. / The Web Foundation could also think more broadly about the different ways in which stakeholders access and engage with the data beyond the website. In particular, the Web Foundation could use social media more actively to both promote the Web Index data and to monitor its use. Tools like Storify could be a good way to try and record this. There are limits to what this information can reveal but it would help strengthen other monitoring data. / Monitoring this type of access and engagement with the data might be more relevant to the overall outcome than prioritising the production of another format for data download (indicator 1.1). / Action 2: Web Foundation will explore additional methods for tracking the use of the Index data as provided and accessed on the website. Web Foundation to update DFID on possibilities at the mid-year meeting (March 2014). / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Promotion of data-based advocacy and policy influence
Output 3 score and performance description: / B- Output moderately did not meet expectation / Indicator 3.1: Number of policymakers, academics, CSO representatives, etc. reached via the policy engagement and capacity building events on how to construct and use the Index Milestone: 60 Achieved: 100 / Indicator 3.2: Number of private sector representatives reached via the "opinion-maker engagement events" Milestone: 40 Achieved: 22 / Indicator 3.3: Number of regions in which CSO engagement / hackathons / competitions are supported Milestone: 2 Achieved: 2
Progress against expected results: / The Web Foundation has engaged directly with over 100 stakeholders, with roughly equal representation across the spectrum of target groups in Africa and Asia. However, the broad scope of what constitutes ‘engagement’ here and the number of stakeholder groups involved makes it difficult to identify particular lessons about how this work is contributing to the overall outcome and impact objectives. It is also difficult to assess whether certain stakeholder groups are easier to reach or are more responsive to the index in comparison with others. / Stakeholder feedback has been positive about the utility of the events, and DFID recognises the added value of having an emerging network of in-country research capacity for peer-peer learning and support, consolidating national ownership, as well as for rapid response work. One stakeholder specifically fed back that this network of field researchers made the Web Index “human” in a way that most other indices aren’t. / The Web Foundation has also provided support to 7 local organisations in Africa and Asia, either through small grants or support for participation in regional fora. However, no stakeholder feedback has been received on this approach. / Similarly, there is limited evidence available at this stage about the efficacy of engagement with policy makers. Web Foundation directors, including Sir Tim Berners-Lee, met with high-level government stakeholders in South Korea, Japan, Brazil and India to discuss their country Web Index scores and produced briefing notes about how to improve those scores. Web Index staff also met with government officials and representatives in South Africa, Indonesia and Ghana about how to strengthen national efforts to use the Web for positive development outcomes. / While the Web Foundation exceeded the milestone for stakeholder engagement in general, it fell short of the milestone for Private Sector engagement. The Web Foundation reports that, due to scheduling difficulties, they only held one private sector engagement event rather than two. Although no stakeholder feedback was received in this regard, the Web Foundation is in follow up discussions on further engagement with a number of participants from that event. / Recommendations: It would be helpful to revisit the theory of change for output 3 to better articulate why the Web Foundation is working with different stakeholder groups, and test how effective their interventions are achieving their desired outcome. / Stakeholder ‘engagement’ as captured under indicator 3.1 is very broad and could be made more meaningful by revising all three indicators to focus more on the qualitative changes expected from different groups e.g. an indicator about building in-country research capacity, or drawing on private sector expertise to strengthen index indicators. / This would also help the Web Foundation to develop stronger systems for gathering evidence about the influence the index is having on those different stakeholders, and how this is contributing to the overall expected outcome of providing an evidence base for policy. / The indicators as currently set out seem to separate out engagement with various target groups (private sector, civil society) rather than looking at the possibilities of building coalitions across stakeholders to promote change. In particular the Web Index could potentially capitalise on the A4AI country coalitions which have broad membership across different sectors. / Action 3: Web Foundation will incorporate learning from Year 1 of the project regarding stakeholder engagement and update the theory of change at the annual strategic review in December 2013. They will share insights and progress with DFID in the next quarterly report by end January 2014. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 4: Alliance for Affordable Internet (A4AI)
Output 4 score and performance description: B- Outputs moderately did not meet expectation (Please note that this score has been calculated differently to the other Output scores. Although the reporting period is live until December 2013, this score has been generated on an estimation of progress by the end of the reporting period. For the 2014 Project Completion Review, this will not be an issue as reporting dates will be aligned and achievements under Output 4 to December 2013 will be accurately reflected). / Milestone 1 exceeded / Milestone 2 not achieved – preliminary work to establish coalitions achieved in 2 countries including signing MoUs, however no coalitions actively carrying out advocacy efforts Milestone 3 – achieved and exceeded (100% of best practices not 50%)
Progress against expected results: / Indicator 4.1: Number of coordinated actions to influence policy debates (eg. open letter to newspaper, letter to minister, joint press release / Milestone: 2 by December 2013 / The total number of coordinated actions completed by the end of October was 8 - 2 press releases for the launch, 2 open letters to papers and 4 letters to Ministers. The Communications report issued by the A4AI shows that the press releases were extremely successful in getting regional and global coverage. / Indicator 4.2: Number of in-country coalitions, comprised of local businesses and civil society that are contributing voices, experience, and needs to the in-country advocacy efforts. / Milestone 2: 3 by December 2013 / 3-4 target countries have been selected and approved by the A4AI Advisory Committee. / The A4AI team secured a meeting in New York with the Nigerian Minister of Communications, and signed a Memorandum of Understanding (MOU) with Minister in Abuja. / An MoU has also been signed with the Ghanaian government. / Two additional MoUs were prepared following several meetings with government officials, and are awaiting final details and signature from respective Ministries. / These MoUs are seen as the key first step in forming in-country coalitions as it is important to first get the buy-in of the government. / The team has identified a first set of coalition stakeholders in each target country and is currently developing a strategy to reach out to local and global partners to engage with during the initial missions to the countries. These in-country missions should take place by the end of the year in the first 2 countries – Nigeria and Ghana. / This milestone has therefore not been reached by October 2013. By the end of the year, progress towards it should be made, but it is unlikely that the 3 in-country coalitions will be fully formed. / Indicator 4.3: New research and data on internet affordability and new policy recommendations for achieving markets that are both socially and economically efficient / Milestone 2: At least 50% of Alliance best practices have been translated into measurable indicators; annual report on affordability sub-index released / All of the A4AI’s best practices have been converted into measureable indicators. The affordability report is due to be published during the first week of December in Cape Town. Working groups have also been established to peer reviewing the report and provide feedback on research results and findings. / Recommendations: / To reduce transaction costs, the Web Foundation should discuss bringing the DFID logframe indicators in line with the work plan and internal log frame of A4AI, which is being monitored and shared with the Advisory Council (including other donors) on an ongoing basis. / Action 4: DFID A4AI lead to review the new A4AI reporting framework and recommend how the DFID project milestones can be updated to reflect these by the mid-year meeting (March 2014). / Impact Weighting (%): 25 / Revised since last Annual Review? n/a / Risk: Medium / Revised since last Annual Review? n/a

Output 5: Index methodology
Output 5 score and performance description: B- Outputs moderately did not meet expectation / Indicator 5.1: External independent verification of Index Methodology Milestone: External report completed Achieved: Incomplete / Indicator 5.2: Depth and breadth of expertise represented on the science council Milestone: 12 members across specified fields Achieved: 12 members across specified fields, except education and health
Progress against expected results: The Web Foundation has made good progress but has not been able to deliver the expected output within the reporting period. A reviewer from the EU has been identified but due to availability constraints, the independent assessment is not expected to be completed before February 2014. / The membership of the Science Council has been transformed over the last year to include more expertise from developing countries (4 members) and a more equal gender balance (5 women, 7 men). The members bring strong expertise from the fields of Web Science, Economics, Statistics and the Law. The Web Foundation had also planned to include expertise from the fields of education and health within the membership but this is not currently represented. / Recommendations: / The milestone for indicator 5.2 could be revised to target the education and health expertise that had previously been identified as a priority area but that is not currently represented on the Science Council. (This might not necessarily require identifying new members e.g. if existing members have sufficient expertise in these areas). / Indicator 5.2 could also be made more meaningful by providing more evidence about the contribution that the Science Council makes to the work of the Web Foundation. / Likewise, for indicator 5.1, it would be helpful to provide additional qualitative information responding to the recommendations made by the independent assessment to improve their work. / Action 5: Web Foundation to review current Science Council for expertise and report back to DFID on any proposed changes/additions to the Science Council by the next quarterly report (January 2014). / Action 6: Web Foundation to include a qualitative assessment of (i) the contribution of the updated expertise Science Council and (ii) responses to the recommendations of the EU external report in next year’s annual report. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? N / This is the first review / 1.2 Overall Output Score and Description: / B – Outputs moderately did not meet expectation / 1.3 Direct feedback from beneficiaries / This review has taken into account feedback from target groups (civil society, government and private sector stakeholders) in the sections above. However as this is a high-level research and policy initiative it does not have clearly defined ultimate beneficiaries.
1.4 Summary of overall progress / The 2013 Web Index is in the final stages of production and is due to be launched on 22 November. The Web Index team have worked to improve various elements from last year particularly in terms of indicators and content on issues such as gender and the environment. The product is likely to be more relevant for key stakeholders including greater emphasis on concrete policy actions that will improve the impact of the Web. / However, the rescheduled launch of the 2013 Index has resulted in many milestones being missed across the grant – for example on delivering accessible products to increase the uptake of Web Index research, and/or finalising the external assessment of the methodology. While it has been important to get the products right and Web Foundation did reschedule with significant notice, this brings significant challenges for demonstrating impact within the 2-year time period (see section 1.5 on challenges). / In terms of outreach and engagement, the activities completed this year have been very much about exploratory work to build interest in the Web Index and Web Foundation’s work and to understand the needs of groups such as civil society to be able to engage effectively on this agenda. There seems to be significant appetite for the Web Foundation’s work. However the range of engagement has been quite broad across this grant and to see more concrete impact at policy change there is a need to be clearer on priorities for policy change, the best routes to influencing (global, national) both as Web Foundation and with partners and coalitions – including some analysis of which global debates to focus on and how this project would aim to shift them. Using an M&E system such as Outcome Mapping might support better articulation of priorities and the ability to track shifts over time.
1.5 Key challenges / The Web Foundation is a very new and dynamic organisation. However organisationally they have faced some capacity challenges over the past year. The first has been around delayed delivery due to recruitment of the new team taking more time than anticipated. The second (related) challenge has been around planning and delivery of work. The budgets and workplans have shifted several times over the year in a way in which it has been very difficult for DFID to get a good sense of whether activities represent value for money. There is a need to ensure that this is improved based on the experience gained over the past year. / Web Foundation have provided feedback to DFID as part of the review that they have found the financial reporting requirements this year to be heavy and a strain on capacity (quarterly financial reports, monthly update on spend against forecast, project lifetime forecasting exercise, due diligence review and updated budget and core costs for the mid-year meeting and for the annual review). They also feel that feedback has been delayed and instructions not always clear in relation to financials. A further complication has been that The Web Foundation has faced delays in funding from other sources which has required the need to balance priorities, seek in-kind support and to re-allocate DFID funds. / Action 7: DFID and Web Foundation finance managers to meet to resolve any outstanding financial issues by mid-December 2013 (relating e.g. to underspend) and to agree reporting process for 2nd year of the grant. / Since the 2013 Web Index launch was rescheduled from September to November, it was difficult to provide evidence of achievement within the timeframe for the first Annual Review (undertaken during October-November). If DFID policy requires a second annual review to be undertaken in November 2014 as well as the project completion review in early 2015, there will be a need to develop specific milestones for this Annual Review which take into account the new annual Index launch dates. The overall project targets will remain the same. / Action 8: DFID to confirm by mid-year meeting (March) whether an annual review is required in 12 months’ time, and if so to agree with Web Foundation the review milestones to be added to the results framework. / The overall challenge on this grant is the time-frame. Given that little more than 12 months remain, and with the delays that have occurred during this year, it is not clear whether this project will contribute to concrete policy changes within the lifetime of the grant. It is appreciated that the theory of change does not necessarily say that the Web Foundation would directly work for policy change. However it was agreed during Business Case development that there should be some, limited, examples of work being taken up to influence policy change – almost as a proof of concept. This will be particularly important for bringing other funders on board and sustaining the Index beyond 2014. / It seems likely that DFID’s funding will support establishment and exploratory phases of this work, and as such make a contribution towards what is essentially a global public good, but without demonstrating any specific upstream impact. Some of this may be mitigated by more targeted policy actions (e.g. by the Alliance for Affordable Internet) over the next 12 months based on the 2013 Index. However based on progress to date, this does seem ambitious within the current timeframe. As such both DFID and the Web Foundation need to discuss how DFID’s investment during this period is used best to support sustainability of the Web Index. / Action 9: Web Foundation and DFID to discuss sustainability issues based on the updated strategy and workplan at the mid-year review (March 2014).
1.6 Annual Outcome Assessment / Project Outcome: Better information on readiness, access, use and development impact of the Web is available to inform efforts to reduce the costs of accessing the internet through policy and regulatory reform / Indicator Milestone Achieved / Number of Web Index citations in publications and strategies 6 4 / Number of media mentions 700/900 22 / Number of requests for engagement 26 6 / Number of target country governments engaged in policy dialogue with Alliance members N/A N/A / This project has under-performed at outcome level largely due to the rescheduled publication of the Web Index in 2013. None of the outcome indicator milestones were achieved. / Based on coverage of the Alliance for Affordable Internet launch in October 2013, the media mentions target is likely to be met following the launch in late November. Web Foundation has also determined the level of media coverage including a target for coverage on the 2013 Web Index in international top-tier outlets. We propose that updated information is provided to DFID at the mid-year meeting in March 2014. / In terms of citations, four of the examples submitted to this review were deemed to be sufficiently relevant to the outcome. These include Web Index/Web Foundation ‘mentions’ in an Avaaz campaign on free internet, and in the Internet Policy Review. It is expected that the content of the 2013 Index will lend itself slightly better to this milestone given the greater focus on specific policy recommendations. While it is appreciated that the methodology and quality of the work on the Web Index has been documented and will support levels of trust in the product, ultimately there is a need to agree the scope under which these citations relate to the impact chain set out in the results framework. / Regarding stakeholder engagement, again the target was missed however there are some good examples of emerging relationships including significant engagement with ICANN, participation at 2 internet governance fora (Africa and Asia) and perhaps most promisingly, conversations with Internet New Zealand on creating a regional Web Index for the South Pacific. / However as has been observed under Output 3, the strategy for informing and influencing stakeholders and essentially increasing uptake of the index, remains unclear. It is understood that in the first year much of this will be exploratory and/or opportunistic. However, following the 2013 launch, there is likely to be a higher level of interest from all sides in the Index and there is a need for a stronger sense of how to prioritise to ensure that the impact indicators can be addressed i.e. concrete policy change – linked to recommendations coming out of the Web Index. This should build on learning from the past year. It should also set out more clearly how the Web Foundation should work to achieve change with limited resources in terms of direct policy engagement, and what it should be doing through partners and coalitions, and the relative balance of efforts at global and at national level to be able to effect change. / Recommendations / Web Foundation to share updated influencing strategy for policy change that shapes priorities for the project outcomes in terms of stakeholder engagement by the mid-year meeting. / There is a need for better systematic tracking of mentions, citations and requests for next year’s review (including a scoring system) as well as a better qualitative sense of the achievements in relation to this outcome in next year’s review. We recommend that Web Foundation propose a system for doing so to DFID after this review. DFID can share similar systems used in other Annual Reviews if required.
Action 10: DFID to provide examples to Web Foundation of a tracking and scoring system for uptake and engagement by stakeholders by December 2013. / Action 3: Web Foundation to update DFID on theory of change and project strategy following their annual review meetings with the next quarterly report (January 2014).

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N / Overall project budget / The original budget and forecasts have been updated several times throughout the year and continue to change. As a result there has been re-profiling of a number of budget lines although the overall budget for year 1 has remained the same. / The initial overall project for year 1 for the Web Index was $733K which was revised to $1.1m during the year. Based on this budget the project is currently significantly under-spent in relation to both forecast and budget including $380K costs for the 2013 launch which Web Foundation is proposing to push back to Q1 of the 2nd year of the budget. / After launch costs are factored in, expected spend is $948k which is an under-spend of $163k on the revised budget. The main budget lines which under-spent is are follows; / Policy & Capacity $40k / Civil Society & Advocacy $36k / Opinion Maker Engagement $30k / Programme Manger $19k / Communication officer $16k / DFID funding implications / For DFID funding this means (i) a request to carry-over of $150K to year 2 for the launch and (ii) an under-spend of $55K on our contribution. With the rescheduling in the project the budget for year 2 will need to be looked at to see if the activities planned and the associated costs are still feasible. / Action 7: DFID and Web Foundation finance managers to meet to resolve any outstanding financial issues by end-December 2013 (relating e.g. to underspend) and to agree financial reporting processes and standards for 2nd year of the grant. / The production costs have increased by $55K and communication/capacity building has decreased by $55k. However most of the capacity building work has been carried out and some cost-savings were realised in this area. / 2.2 Key cost drivers / Key cost drivers remain ‘Data Analysis’, ‘Expert Assessment’ and the costs of project staff. Further details are provided in the VFM section below. / 2.3 Is the project on-track against original timescale: N / The launch of the 2013 index was rescheduled which has impacted on milestones and outputs. However, it is likely that the 2014 Index will be on track and the milestones for the project completed by the project end date (December 2014).

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The evidence base was rated as ‘limited’ in the business case. This project seeks to contribute to the evidence on how the Web can be used to promote more inclusive policies, services and business models through the development of a Web Index. / The debate on how and why countries are able to leverage the web as a tool for developmental change has increased over the last year. This is in part due to assessment of the metrics available on the web and also due to the increased availability of quantitative data that can be used in economic modelling (there has been a need for data time series to catch up with the pace of change in the sector). / In certain areas, gender and, censorship and surveillance, on-going study either global or regional specific has added to the quality of data. However, clear lines of causality and statements on thresholds remain contentious. As the Web Foundation, we are currently positing that a 30% penetration threshold seems to be critical for uptake of the web in areas such as the economy and or social and political empowerment. This does still need to be tested. / Key reports released in the last year include: / Intel/Dalberg study on Women and the Web; Freedom House’s Freedom on the Net 2013: A Global Assessment of the Internet and Digital Media. (covering 60 countries); / UN Human Rights Council, 2013. “Report of the Special Rapporteur on the promotion and protection of the right to freedom of opinion and expression, Frank La Rue”; / Research ICT Africa’s ‘Understanding Broadband Demand in Africa: Internet Going Mobile’ and, Dalberg’s Impact of the Internet in Africa - Establishing conditions for success and catalysing inclusive growth in Ghana, Kenya, Nigeria and Senegal. / The Web Foundation continues to engage other research groups and foundations as such information is released and began the second project year with a conference on ‘Known-Knowns and Unknowns about the Internet: Measuring the Economic, Social, and Governance Impact of the Web’ interrogating what measurement challenges remain on this issue including issues of definition, standardisation of metrics and the availability of sufficient data. / 3.2 Where an evaluation is planned what progress has been made? / No evaluation is planned.

4. Risk
4.1 Output Risk Rating: Medium / In May 2013 DFID completed a baseline due diligence assessment of the World Wide Web foundation and rated them as medium risk. The organisation has a risk framework and a risk matrix which is reviewed by the Board at least once every year. The risk assessments have risk owners who are responsible for managing the risk. / The organisation is new to DFID and the project has just finished its first year so the organisation has still to provide evidence that they have the ability to deliver outputs as agreed. There have also been delays in confirming overall funding for the index in respect of funding from SIDA. It has also taken longer than expected to recruit the full team which has contributed to delays. / 4.2 Assessment of the risk level / There are risks inherent in the production of the Index. These take the form of the robustness of the methodology and institutional continuity as well as the delivery of contractors. Some of the actions the World Wide Web Foundation is taking to minimise risk are; / The Web Index staff team meets on a bi-weekly basis to review progress against timelines, troubleshoot problems and discuss programme operations. / The Programme Development Advisor, responsible for monitoring & evaluation of the project, periodically reviews progress against logframe/milestones with the Web Index staff and ensures that appropriate documentation is in place. After each event, a post-event outcomes report is written. / The World Wide Web Foundation’s senior leadership (CEO, senior programme staff) also meet bi-weekly to address any significant issues with regard to contracts, funding, timelines and objectives. / The Web Index science council meets twice per year to review the quality and rigour of the research framework and data collection process. / An external evaluator reviews the Index methodology and data quality annually.
Risk of funds not being used as intended / DFID recently completed a due diligence assessment of the organisation and DFID was satisfied that there were adequate management controls in place to ensure that finances were spent and audited appropriately and funds would be spent on activities as originally agreed. / Web Foundation has recently received notification of funding for this project from SIDA. Web Foundation will need to provide a clear breakdown of how this impacts on the project so as to avoid double-funding. / Action 11: Web Foundation to inform DFID of any implications to our funding in light of the SIDA funding by next quarterly report (January 2014). / 4.4 Climate and Environment Risk / Risks associated with this project are carbon emissions and environmental footprint associated with regional meeting and with paper conference outputs. Such types of activities are unlikely to have any major negative environmental impacts. Where possible Web Foundation have combined trips and events to reduce environmental impact and financial costs. / The Web Index project provides an opportunity to explore how policies and business models can promote the role of the Web in relation to climate change mitigation and adaptation from local to international levels.

5. Value for Money
5.1 Performance on VfM measures / The Web Foundation has produced and plans to launch the 2013 Index in line with the resources allocated in the budget. / It is hard to measure the value for money of this project at this stage. The rescheduled launch of the 2013 Index has resulted in milestones not being met and as such it is not possible to evaluate evidence of impact against resources spent. / In terms of unit costs, staffing remained the same as in the business case. Some costs savings have been recognised particularly around outreach, engagement and events, as anticipated by DFID at the mid-year review. These new lower unit costs should be used as a benchmark for activities in 2014. / Management fees represent approx. 19% of project expenditure in the past year within this total overhead is 10% which is quite high. / On DFID funding 5.7% overhead has been charged, compared with the 5% agreed in the business case, due to the lower actual spend during the first year. This should come down to 5% by the end of the next quarter but the Web Foundation need to monitor to ensure that the total overhead charged to DFID does not exceed 5% over the lifetime of the project taking into account any future underspends. Overheads for the Alliance for Affordable Internet are included in the basket fund contribution. / 5.2 Commercial Improvement and Value for Money / The Web Foundation has their own internal procedures for procurement of goods and services, which they have provided to DFID. The Web Foundation has agreed to cost controls for example economy flights, DFID’s no-per diem policy. / The Web Index is not produced in-house but involves two main consultancy contracts to Global Integrity and Telecom Advisory Services. The Web Foundation has outlined the procurement process that was used award these contracts. At the mid-year review it was noted that one of these contracts in particular involved high daily rates which are above what DFID would usually pay for such work. Web Foundation staff were asked to provide more detail on the added value/rationale for paying these rates at the year-end review. This would enable a decision on to what extent they would be justified for the 2014 Web Index and could be covered by DFID. / It was noted in the course of this review that the Web Foundation do not require partner organisations to provide a narrative of work completed by consultants when invoicing and therefore were unable to provide sufficient analysis on this point. This makes it very difficult to understand the specific contribution by consultants at higher rates and to what extent this would be required for replicating the Index going forward. However Web Foundation report that they feel that the contracts offered value for money and that partner organisations had provided more time than indicated in the initial agreements. / Action 12: Web Foundation to provide a clear narrative on the value added of the high daily rates under consultancy contracts (based on billing info/narratives from partners) by January 2014. Based on this DFID will decide whether such costs represent Value for Money and can be included in next year’s DFID budget. / 5.3 Role of project partners / Outreach, engagement and support for civil society advocacy in the first year of the project took the form of engagement with over 100 stakeholders through events in Europe, Asia (Jakarta, Indonesia) and Africa (Durban, Kinshasa and Ghana). / The unit costs per roundtable / workshop were lower than forecast, down from £19.5k to £8.5k, which was due to which was due to savings on logistics and cost sharing with other Web Foundation projects, Actual reach and impact needs to be quantified to get a better understand of how these activities contributes to the value for money of the project. These lower costs should also be used as benchmarks for similar activities going forward. / 5.4 Does the project still represent Value for Money : Y / The Web Foundation have delivered in line with the budget however without seeing whether the Web Index is a useful product that can support policy engagement and reform it is impossible to carry out analysis on this issue. / 5.5 If not, what action will you take? / n/a

6. Conditionality
6.1 Update on specific conditions / No specific conditions.

7. Actions
Output 1 – Production of the Web Index / Action 1: In addition to reporting on the milestones for Output 1, in 2014 The Web Foundation will provide additional information in next year’s annual report on: / Indicators fielded vs those included / Changes to the indicators and structure of the Index over time / A qualitative narrative on how Index quality and relevance has improved in relation to the above points. / Output 2 – Accessible data/formats / Action 2: Web Foundation will explore additional methods for tracking the use of the Index data as provided and accessed on the website. The Web Foundation to update DFID on possibilities at the mid-year meeting (March 2014). / Output 3 – Stakeholder engagement and capacity building / Action 3: Web Foundation will incorporate learning from year 1 regarding stakeholder engagement and update the theory of change at the annual strategic review in December 2013. They will share progress with DFID in the next quarterly report by end January 2014. / Output 4 – Alliance for Affordable Internet / Action 4: DFID A4AI lead to review the new A4AI reporting framework and recommend how the DFID project milestones can be updated to reflect these by the mid-year meeting (March 2014). / Output 5 – Quality assurance of the Web Index / Action 5: Web Foundation to review current Science Council for expertise and report back to DFID on any proposed changes by the next quarterly report (January 2014). / Action 6: Web Foundation to include a qualitative assessment of (i) the contribution of the updated expertise Science Council and (ii) responses to the recommendations of the EU external report in next year’s annual report. / Results and value for money / Action 7: DFID and Web Foundation finance managers to meet to resolve any outstanding financial issues by end-December 2013 (relating e.g. to underspend) and to agree reporting processes and standards for 2nd year of the grant. / Action 8: DFID to confirm by mid-year meeting (March) whether an annual review is required in 12 months’ time, and if so to agree with Web Foundation the review milestones to be added to the results framework. / Action 9: Web Foundation and DFID to discuss sustainability issues based on the updated strategy and workplan at the mid-year review (March 2014). / Action 10: DFID to provide examples to Web Foundation of a tracking and scoring system for uptake and engagement by stakeholders by December 2013. / Action 11: Web Foundation to inform DFID of any implications to our funding in light of the SIDA funding by next quarterly report (January 2014). / Action 12: Web Foundation to provide a clear narrative on the value added of the high daily rates under consultancy contracts (based on billing info/narratives from partners) by January 2014. Based on this DFID will decide whether such costs represent Value for Money and can be included in next year’s DFID budget.

8. Review Process
This review was carried out by DFID officials in the Politics, State and Society team. The Web Foundation submitted evidence to DFID which was reviewed alongside feedback from a limited number of stakeholders.