Type of Review: Annual Review

Project Title: Carbon Market Finance (CMF) delivered via the World Bank’s Carbon Initiative for Development (Ci-Dev)

Date started:	March 2014
Date review undertaken: February 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK provides £50m from 2013 to 2025 to increase the flow of international carbon finance to Least Developed Countries (LDCs) – with a focus on Africa – to support climate change mitigation and poor peoples' access to clean energy and other poverty reducing technologies. In the short to medium term, this programme will deliver direct climate and poverty reduction benefits on the ground in poorer countries through clean energy projects such as household solar, biogas and micro-hydro systems. By channelling this support through the carbon market, the programme will increase the ability of poorer countries to access and benefit from carbon finance in the medium to long term, if and when the market recovers. / The CMF is a joint DFID and DECC programme, with both Departments providing funding from their share of the UK Government’s International Climate Fund (ICF). DFID will provide £15 million and DECC £35 million. All UK ICF funds are classified as Official Development Assistance (ODA). These funds are used to: / Develop innovative methodologies and models that enable the international carbon market to finance projects with high development benefits in Least Developed Countries, as well as reduce carbon emissions. These methodologies will be for low carbon technologies that deliver community and household level results, such as, but not restricted to, biogas, household solar and micro-hydro power. / Use a results-based approach to support pilot projects that test new applications of carbon finance models in practice. The programme will purchase emission reductions credits from pilot projects. Because ICF funds are classified as ODA, all credits purchased by the UK will be cancelled and not used for compliance with UK greenhouse gas reduction targets. This is clarified in legal agreements with the World Bank Carbon Finance Unit implementation partner for CMF. Progress in developing the portfolio of pilot projects is reflected in Output 3. / Influence the future carbon market so that poorer countries, especially in Sub-Saharan Africa, can receive a greater and fairer share of carbon finance that results in both high development benefits and reduced carbon emissions. This will be accomplished through disseminating the new methodologies and models that reduce the red tape and the results of their practical application. Replication of the programme’s innovative models through the carbon market, if the market recovers, would transform the access of poor people to carbon finance. / Evaluate the potential of these innovations to enable the carbon market to (i) deliver direct development benefits at the same time as emissions reductions; (ii) reach poor households in LDCs – and deliver appropriate technologies cost effectively and (iii) attract finance and innovation from the private sector in distributing the technologies through replicable business models. / The programme is implemented through the World Bank Carbon Finance Unit (CFU) and its Ci-Dev Initiative. Ci-Dev implementation is designed to be consistent with the UK funded CMF programme and its business case. Purchase of emissions reductions is through the Ci-Dev “Carbon Fund”, and methodologies and approaches are developed through the Ci-Dev “Readiness Fund”. Sweden and the Swiss Cent foundation also contribute to the Ci-Dev Carbon and Readiness Funds. Sweden and the Swiss Cent foundation contribute €20m and €20m respectively to the Carbon Fund and €3m and €3m respectively to the Readiness Fund. A donor steering group oversees progress on a quarterly basis.

What are the expected results?
IMPACT: / Carbon financing reduces greenhouse gas emissions and poverty in less developed countries. / Indicator 1: M tonnes CO2 reduced by all international carbon finance projects drawing on CMF developed methodologies. / Indicator 2: Number of people with increased access to clean energy, as a result of international carbon financed projects drawing on CMF developed methodologies. / Indicator 3: Level of installed capacity of clean energy (MW) from all international carbon finance projects drawing on the new methodologies. / OUTCOME: / Increased carbon finance flows to poor countries for low carbon energy and other poverty reducing technologies. / Indicator 1: £x of private/public finance mobilised for investment in CDM projects that use the new methodologies directly supported by the CMF programme / Indicator 2: M tonnes CO2 reduced through projects directly supported by the CMF programme. / Indicator 3: Level of installed capacity of clean energy (MW) in CMF programme directly supported locations / Indicator 4: Number of people with increased access to clean energy from all projects in CMF programme directly supported locations

What is the context in which UK support is provided?
Carbon trading is a tool for reducing the emissions that cause climate change. Driven by internationally agreed caps on carbon emissions (set currently by developed countries), the international carbon market is an instrument for governments and large private sector emitters to cost-effectively meet their caps. Through the international carbon market, emitters can buy offsets to cover a proportion of their emissions, and so help meet the overall cap on emissions. This creates a price for carbon based on market demand and incentivising emission reductions at the lowest possible cost. Selling emission offsets can also facilitate technology transfer, sustainable development and provide substantial carbon finance flows to developing and Least Developed Countries. / The international source of carbon credits is the Clean Development Mechanism (CDM), the UN regulated system for selling “certified emissions reductions” – generated from emissions reducing projects in developing countries – to buyers in other countries to meet their international mitigation commitments. Currently, developing countries participate in carbon markets through the Clean Development Mechanism (CDM). The CDM also links national and regional carbon markets, for example connecting the EU’s European Trading Scheme (EU ETS), the largest scheme worldwide and to date the main source of demand for CDM credits, with the international carbon market / The UK is committed to the expansion of carbon markets in both developed and developing countries. A global carbon market enables economies to undertake cost effective emission reductions and therefore increases the likelihood that the world will be able to deliver emission reductions consistent with two degrees / Carbon finance could make clean energy and other low carbon technologies more affordable for poor people in LDCs. This would help expand energy access to the 80% of the world’s population without electricity – through community and household based off-grid renewable technologies (like solar, biogas and micro hydro). This will be particularly important given the challenges of increasing grid connection in sub-Saharan Africa – where distances are large and energy demand already exceeds supply. Off-grid renewable technologies have excellent benefits for poor households, but have received almost no carbon market support in LDCs to date. / Carbon finance flows for these poverty reducing technologies remain minimal – particularly to the LDCs that need them most. This is because: (i) the cost to demonstrate carbon reductions for carbon market finance is currently particularly prohibitive for small scale projects; (ii) uncertain returns from the technologies discourages investment; (iii) a gap in skills and experience in poorer countries; and (iv) the uncertainty in the carbon market is causing very low prices. This programme will test new methods and approaches specifically designed to help LDCs access carbon finance, ensuring they are well placed to participate in the future carbon market and develop along a low emissions pathway

## Section A: Detailed Output Scoring

Output 1: New methodologies (standardised baselines and programmatic approaches) and streamlined processes approved by the CDM Executive Board (EB).
Output 1 score and performance description: A / Methodologies are starting to be developed that can be used in some of the pilot projects (described in Output 3) and that could influence the future of the CDM and future carbon markets. The World Bank CFU has involved the CDM EB in its work so that it is consistent with Board intentions to reform the CDM and so that such reforms can be informed by new methodologies produced by the programme. The CFU has already started to submit proposals to simplify CDM processes to the EB that can facilitate more effective of use of the CDM for household and community applications.
Progress against expected results: / Indicator 2013 Baseline First milestone end 2014 End 2015 milestone Achieved results / (not UK attributable) Indicator score / (eg “Met expectation”) / Output 1.1: Number of new methodologies submitted by the programme and approved by CDM Executive Board (EB) 0 No methodologies 2 one CDM EB submission Met expectations / Output 1.2: Number of new methodologies and other reform measures developed 2 4 5 Mapping exercise to identify areas for improvement in methodologies Met expectations / OUTPUT 1 SCORE Met expectations / Indicator 1.1: / Although it was not expected that the CFU would have yet submit any methodologies, one CDM EB submission was made for simplification of the project cycle as part of the exercise to review CDM modalities and procedures, and another submission is expected to be made as part of the forthcoming call for inputs on CDM modalities in April 2014. / In addition, a submission was made proposing alternative approaches to standardized baselines for establishing baseline emission factors more fitted to realities of low income countries. / Also, a submission is being prepared so that two separate CDM methodologies, one for off-grid and one for grid extension in rural areas, can be used in combination, simplifying their application. This combination would be used in a proposed Uganda energy access pilot project (see Output 3). This submission will be made to the EB in April/May 2014. In parallel, the CFU will also explore the scope for the development of a standardized baseline for this same Uganda program. Additional opportunities may arise in relation to the pre-PINs received as part of the recent call for project ideas. / Indicator 1.2: / The CFU work plan includes a number of actions to modify and adapt methodologies that could later be submitted to the EB and used by projects in the Ci-Dev initiative. / This includes work to streamline monitoring and verification, and to improve CER issuance. / A CDM project business model study is being implemented to assess the role of carbon finance for investing in energy access, to develop a carbon pricing approach and to identify CDM reform that will promote energy access projects. Further new measures targeting CDM reform will be developed based on the outcome of the study. / A mapping exercise has been conducted to identify the areas for improvement in the methodologies that are applicable to Ci-Dev projects. Submissions will be made to the UNFCCC according to needs of the pilot projects (Output 3) selected for implementation. / Recommendations: / The CFU should continue with a focused methodology work plan. Methodologies should be developed that are most applicable to the pilot projects. This includes drawing on the mapping exercise to identify the most appropriate type of methodologies to develop. / Impact Weighting (%): 15% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

Output 2: Communities, private sector and government with increased capability to use standardised baselines and programmatic approaches
Output 2 score and performance description: A / The limited programme experience to date, for example on methodologies being developed and the methodology mapping study, is being disseminated to potential users. Dissemination and consultation events are combined with other stakeholder gatherings, such as the annual Carbon Expo meeting.
Progress against expected results: / Indicator 2013 Baseline First milestone end 2014 End 2015 milestone Achieved results / (Not UK attributable) Indicator score / (eg “Met expectation”) / Output 2.1: Number of activities (e.g. workshops, key publications) to disseminate programme experience. 0 3 5 1 Met expectations / Output 2.2: Number of Designated National Authorities (DNAs) submitting standardized baselines for approval by the EB in target countries 0 0 1 First anticipated submission to the EB from a DNA is expected in 2015 Met expectations / OUTPUT 2 SCORE Met expectations / Indicator 2.1: / At this early stage, there is limited scope to disseminate programme experience. However the CFU and Ci-Dev has engaged a range of stakeholders in support of CDM reform and to build understanding in Africa. A two day workshop was organized in Bonn in October 2013 to explore options for using the CDM as a framework to deliver results-based approach and to facilitate discussion among key CDM reform negotiators in preparation for the December 2013 (COP 19) climate change negotiations conference in Warsaw. / A workshop with representative African negotiators is planned during first week of April 2014 to support their ability to suggest improvements to CDM modalities and procedures. / A CDM reform working group of stakeholders to contribute to improve the CDM is being established to specific terms of reference agreed with donors, and its first meeting is planned in conjunction with Carbon Expo 2014 at the end of May 2014. A workshop to disseminate the findings of the business model study (Indicator 1.2) will be implemented during the Africa Carbon Forum 2014. Another workshop to help African DNAs influence CDM negotiations is planned before this year’s climate change COP conference in Lima, Peru in December 2014. / Indicator 2.2: / The first anticipated submission to the EB from a DNA is expected in 2015, in line with the milestone. / The “methodology mapping” study of indicator 1.2 provides a number of recommendations and suggestions for developing standardized baselines. Discussions will continue with country DNAs in countries where pilot projects might be located and other multilateral and bilateral agencies active in standardized baseline development. This will also help to develop standardized baselines that could be applied in potential pilot projects (Output 3). / Recommendations: / The useful stakeholder working group should remain focused on helping identify how the programme can influence CDM reforms. / The WB CFU should continue to actively disseminate the growing number of programme findings during 2014. / The WB CFU should identify potential DNA’s that would be willing to submit standardised baselines and identify what areas of support those DNA’s may require. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 3: Practically demonstrate financial viability of standardised baselines (SB) and programmatic approaches (PoAs).
Output 3 score and performance description: A
Progress against expected results: / Indicator 2013 Baseline First milestone end 2014 End 2015 milestone Achieved results / (Not UK attributable) Indicator score / (eg “Met expectation”) / Output 3.1: Number of CDM projects registered with the CDM Executive Board in focus countries that use the new CDM methodologies 0 0 1 The first milestone can only be achieved when pilot projects have been developed and are ready for registration. Met expectations / Output 3.2: Number of project models developed that apply new methodologies 0 TBA TBA 29 project ideas that has so far resulted in 9 pre-PINs. Met expectations / Output 3.3: CDM projects developed and registered with the CDM Executive Board are consistent with guidelines for stakeholder engagement 0 Guidelines agreed All developed projects consistent Draft Guidelines prepared in October 2013. Met expectations / OUTPUT 3 SCORE Met expectations / The CFU is developing a pipeline of potential pilot projects to test models that enable the international carbon market to finance projects with high development benefits. Potential projects are assessed against selection criteria. It is anticipated that UK and other donor contributions will be sufficient to support around 20 or so pilots. Achievements to date against indicators for this Output demonstrate good progress. / Indicator 3.1:. / The first milestone can only be achieved when pilot projects have been developed and are ready for registration. This would not be expected until 2015 and when progress has first been made on Indicator 3.2. / Indicator 3.2:. / end 2014 and 2015 milestones were to be agreed when the business case was approved in March 2013. See recommendations on milestone targets. / This indicator is intended to monitor progress in the development of a pipeline of pilot projects. The CFU has developed a process to assess proposals against the project selection criteria agreed by the UK and other donors. The stages are: / a preliminary pre Project Identification Note (pre-PIN) - assessed against the selection criteria / successful Pre-PIN developers submit a more detailed Project Identification Note (PIN) for more assessment. / the best PIN developers are selected and enter into a CDM emission reduction purchase agreement (ERPA) with the CFU for the project. / The CFU kick started the programme through initial publicity in mid-2013. This resulted in a range of proposals. The CFU received enquiries for 29 project ideas that have so far resulted in 9 pre-PINs. These pre-PINS include: off-grid energy in Ethiopia and Uganda; grid connected energy in Uganda, biogas in Ethiopia and Tanzania; water purification in Uganda, Rwanda and Bangladesh; and ethanol cooking in Madagascar. (The Bangladesh pre-PIN is because the CFU Ci-Dev programme can support projects in Asian LDCs as well as Africa, although the majority are expected to be in Africa.) Uganda water purification and Madagascar ethanol cooking were rejected because they are not a priority according to the selection criteria. Other developers will be invited to submit PINs. It can be expected that these PINs will result in at least one ERPA before the end of 2014. / In addition, a more formal call for projects resulted in more than 100 pre-PINs. They will be filtered by the CFU and then tested against the selection criteria. / In the light of programme experience to date the wording of this indicator is not a good measure of progress in developing a pipeline. Therefore a change in the indicator wording and associated milestones is recommended below. / Indicator 3.3: / A draft of the “Guidelines for Stakeholder Engagement” was prepared in October 2013. Comments and suggestions from the UK and other donors will be addressed to produce final guidelines for donor approval in May 2014.the guidelines will be provided to project developers so that theey are implemented. / Recommendations: / Change the wording of indicator 3.2 so that it is better suited to measuring progress of the pilot project pipeline. The new wording and milestones would be: / Indicator 3.2 Baseline 2013 End 2014 End 2015 End 2016 End 2019 End 2022 End 2025 / Number of: / pre-project identification notes (PINS) received and assessed / emission reduction project agreements (ERPAs) agreed with project developers 0 / 0 15 / 1 25 / 3 35 / 8 50 / 20 50 / 20 50 / 20 / - Continue to develop the pipeline of projects to ensure the pool of pre-PINs is large enough to develop the required amount of PINs that meet the Ci-Dev goals. / - The World Bank should ensure the work on the Guidelines for Stakeholder Engagement continues, with the goal of having the guidelines finalised and agreed by December 2014. / Impact Weighting (%): 30% / Revised since last Annual Review? No -this is the first annual review / Risk: Medium / Revised since last Annual Review? No -this is the first annual review

Output 4: Results Based Financing (RBF) effectively incentivises private investment in technologies that deliver emission reductions and poverty reduction.
Output 4 score and performance description: A
Progress against expected results: / Indicator 2013 Baseline First milestone end 2014 End 2015 milestone Achieved results / (not UK attributable) Indicator score / (eg “Met expectation”) / Output 1.1: Value of CER credits contracted from projects supported through CMF using the RBF mechanism. 0 £2m £5m CER credits will be contracted through ERPAs agreed for pilot projects, so none expected yet. Met expectations / Output 1.2: Number of events to engage potential project developers for CER contracting. 0 2 4 1 Met expectations / OUTPUT 4 SCORE Met expectations / Indicator 4.1: / CER credits will be contracted through ERPAs agreed for pilot projects. As in Output 3, the pipeline of potential pilot projects has made good progress over the last few months. At least one, and possibly more, ERPAs could result in 2014 with a CER credit value of £2m or more. This puts the fund on track to achieve the milestone. / Indicator 4.2: / Initial publicity to kick start the programme included a specific event at the Africa Carbon Forum in July 2013 in Abidjan, Cote d’Ivoire, and the fund was also featured one of the sessions of the Forum. This contributed to receipt of initial pipeline proposals and pre-PINs. The 2014 Carbon Expo and the 2014 Africa Carbon Forum will include similar events. / Recommendations: / - Future Indicator 4.1 milestones should be increased to reflect expected higher value of CER credits given the additional funding by Switzerland compared with the original logframe. / Impact Weighting (%): 35% / Revised since last Annual Review? No -this is the first annual review / Risk: Medium / Revised since last Annual Review? No -this is the first annual review

## If the project involves more than 4 Outputs please copy the box above and paste below.
## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? / No. But adjustments are recommended for Output Indicator 3.2.as described above. / In addition the original logframe, 2015 and 2016 milestones for Outcome Indicators 2, 3 and 4 were still to be determined when information on the type of initial pilot projects became clearer. Milestones have now been identified as follows: / Outcome Indicator Baseline 2013 End 2014 End 2015 End 2016 End 2019 End 2022 End 2025 / M tons CO2 reduced through all projects directly supported by the CMF programme. (Attributed to UK) 0 0 0.1 0.2 0.5 1.6 2.6 / Level of installed capacity of clean energy (MW) in all projects directly supported in CMF programme. (Attributed to UK) 0 0 2 6 55 130 165 / Number of people (‘000) with increased access to clean energy from all projects directly supported in CMF programme. / (Attributed to UK) 0 0 150 300 1,700 3,700 4,300 / 1.2 Overall Output Score and Description: / A - Outputs met expectation. / 1.3 Direct feedback from beneficiaries / As it is still very early in the programme no direct feedback from the beneficiaries has been sought. Feedback from potential project developers and the CDM Executive Board has been favourable. Contact with developers, such as at the Africa Carbon Forum (see Output indicator 4.2) demonstrated keen interest in the programme. The good response for project ideas and pre-PINS (see Output 3) also demonstrates significant interest in using the programme to support household and community level projects. The CDM Executive Board is open to learning from the programme as informing CDM reform.
1.4 Summary of overall progress / All of the 2013 output indicators have achieved expectations. If the programme’s performance continues at its current pace, it is likely to remain on track to meet its 2014 indicators. / The development of a pipeline projects has made good progress over the past 12 months. This has led to the analysis and discussion of 9 pre-PINs, of which 7 have been approved for further processing. As part of this process, all potential projects are screened for opportunities to develop new methodologies or revise existing methodologies, in addition a CDM reform working group will be established in 2014. / Based on the pipeline, the programme appears on track to start generating emission reductions in calendar year 2015, with a progressive ramp-up as more projects are added to its portfolio. / A draft of the “Guidelines for Stakeholder Engagement” were prepared and shared with Ci-Dev donors in advance of the first quarterly progress meeting early October 2013. The draft is on track to be finalised and approved in 2014.
1.5 Key challenges / There has been a good initial response for pilot project ideas, and the submission of project pre-PINs. Many are consistent with the project selection criteria. The quality of the PINs and underlying projects is yet to be tested. This includes the quality of projects in delivering benefits to poorer groups and communities, as well as delivering emission reductions. / The WB CFU has a challenge to assess the potentially high number of pre-PINs resulting from the call for ideas, to ensure the best pilot projects are selected and that ERPAs are signed and pilots started to schedule. / Setting the right price to be paid for CERs through the ERPAs has also yet to be tested in practice. This is important for programme value for money. / The development of new methodologies and approaches (Output1) should inform the type of pilot projects (Output 3) leading to the achievement of Outcome indicators, such as numbers of people with increased access to clean energy, and tonnes of carbon dioxide reduced. The WB CFU should continue to ensure there is an appropriate connection.
1.6 Annual Outcome Assessment / Progress indicates the Outcome is on course to be achieved. For example, good progress in the project pipeline indicates that sufficient pilot applications will be implemented to achieve the indicators. As described in Section B 7 below, the 2015 and 2016 milestones for Outcome Indicators 2, 3 and 4. In the business case logframe were still to be determined while information on the type of initial pilot projects became clear. Milestones are now recommended, as in Section B7. / Outcome Indicator 1: private/public finance mobilised for investment in CDM projects that use the new methodologies directly supported by the CMF programme. ICF KPI 11 and KPI 12: UK attributable) / Public and private finance should be mobilized through the pilots, although each will vary. Some pilots pure private-sector initiatives with little public support. Others are likely to be part of national programmes for energy access. The volume of public finance mobilized is likely to be higher (and earlier) than the logframe targets. The volume of private finance for 2014 and 2015 appear achievable, with a potential underachievement of the 2014 target, should ERPA signature dates slip beyond end December 2014. / Outcome Indicator 2: million tons CO2 reduced through projects directly supported by the CMF programme. ICF KPI 6; UK attributable / Based on the pipeline in development, this indicator should be on track to start generating emission reductions in calendar year 2015, with a progressive increase as more pilot projects are implemented. / Outcome Indicator 3: / Level of installed capacity of clean energy (MW) in CMF programme directly supported locations. ICF KPI 7: UK Attributable / Expectations are as for Indicator 2. / Outcome Indicator 4: Number of people with increased access to clean energy from all projects in CMF programme directly supported locations. ICF KPI 2: UK attributable / Consistent with the project selection criteria, the pipeline includes a majority of energy access programs. The type of initial projects will have implications for both this and indicator 3 and there is potential for some slippage against the milestone, although the 2014 and 2015 milestones are achievable. / 1.7 Project’s contribution to corporate results for the year covered by this review: / Operational Plan Headline Results: / Output Indicator 4 contributes towards the OP result of “people with improved access to low carbon energy”. As originally anticipated, the programme has not yet contributed any results. But the end 2015 milestone of 150,000 people could contribute towards the target by the end of the CSR. / DFID Results Framework Indicators: / Output Indicator 4 could also contribute towards the DRF result of “people with improved access to low carbon energy”. But the end 2014 milestone is zero people, because of the timing in implementation of the initial pilot projects. Therefore no contribution to this DRF indicator by the end of the 2014/15 CSR period is currently estimated. However, if some initial pilots are implemented sooner than anticipated the programme might contribute towards the indicator. / ICF KPIs (climate projects only): / All the Output indicators contribute towards ICF KPIs as shown above. The milestones are as described in Section B 7. / 1.8 How are corporate results contributions calculated from project level indicators? (eg indicators included, DFID funding share used to calculate attributed results) / Corporate results are directly taken from the Outcome indicators as described above. Attribution is calculated and reported by the World Bank CFU based on UK funding share with other donors. / 1.9 Did ARD’s March 2012 gender review make recommendations for this project?: Y / 1.10 If yes: What progress has been made in considering and implementing these recommendations? / The review recommended that Output indicator 4 on “Number of people with increased access to clean energy from all projects in CMF programme directly supported locations” should be considered for gender disagregation. This is being discussed with the World Bank CFU in the light of the type of pilot projects that will be implemented.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / The DECC finance is a contribution to the Ci-Dev Carbon Fund via a promissory note that will be drawn down according to need to purchase emission reductions according to signed ERPAs. / The DFID finance is a contribution to the multi-donor Ci-Dev Readiness Fund with contributions by Sweden and Switzerland. Payment is in arrears and according to the needs of the Fund. Other donors are able to make up-front payments, rather than in arrears, reducing the need for a UK payment to the Fund which can make financial forecasting more difficult and careful adjustment. DFID will work with the World Bank CFU to make sure forecasts are as predictable as possible. / 2.2 Key cost drivers / The CFU works with the the World Bank Group’s Corporate Procurement Unit to ensure value for money in terms of price, fitness for use, operating costs, delivery and payment terms. These activities are accomplished applying the highest level of ethical standards for fair and equitable treatment of suppliers providing goods, works and services to the Bank Group. This particularly applies to procurement through the Readiness Fund. At this early stage indications are that the CFU is performing as expected. / Carbon price paid for projects is an important cost driver for the Carbon Fund. No ERPA has yet been signed with any project. There is therefore no concrete data on this indicator at this stage. Based on the pre-PINs for the first projects under review for possible inclusion in Ci-Dev’s portfolio, it appears that the price range envisaged at the outset ($9 to $14) remains relevant for this first batch of projects. A study has been commissioned to provide guidance and inputs into to negotiation of a price for future ERPAs. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / They have been no changes in evidence and implications for the project since the business case of March 2013. / 3.2 Where an evaluation is planned what progress has been made? / The evaluation plan and ToR’s have been drafted and are pending DECC senior management clearance (expected 2nd quarter 2014). They will also be quality assured by DFID through the DFID evaluation process. It is expected that the evaluation will be tendered during the middle part of 2014.

4. Risk
4.1 Output Risk Rating: Medium / The risks and mitigation measures remain as in the business case of March 2013. / The key risk that the carbon market does not recover and that this would lead to limited scope that the programme is still high. International climate change negotiations were not expected to have provided an indication of change in risk by this first annual review. However, the European Commission has proposed that the EU adopts a 40% domestic GHG target for 2030 on 1990 levels. They have also proposed that, if international negotiations require it, the EU can go further than this, including through international carbon credits. The UK Government is for a 50% reduction, which can include international credits. The Commission proposals make it less likely that there may not be a functioning market for international credits after 2020, whilst not affecting any of the direct results expected from this programme. / Implementing pilot projects that produce good benefits in their own right and not just because of their demonstration effect for a future carbon market remains a way to mitigate the risk. As in Output 3 there has been good progress in developing such a project portfolio. / 4.2 Assessment of the risk level / As in the business case, the programme is judged as overall medium risk at this first annual review. The high risk that the carbon market does not recover is noted above.
Risk of funds not being used as intended / As in the business case there remains a low risk of mismanagement of funds by project developers contracted by the World Bank, or that emissions reductions purchased by the programme are not genuine. The Readiness Fund will adhere to well established World Bank procurement Guidelines, and there will be close supervision by WB of emission reductions. All payments for emission reductions from the Carbon Fund will be disbursed after CERs are certified by the UNFCCC. / Climate and Environment Risk / The climate and environment risks remain as in the business case of March 2013. For example, the types of pilot projects emerging from the portfolio will reduce carbon emissions. Some of the low carbon technologies, such as micro-hydro or biomass, could be vulnerable to climate and environment impacts such as reduced rainfall or changes in agricultural productivity. World Bank environmental safeguards will be applied to pilot projects that should reveal such risks and identify mitigation measures.

5. Value for Money
5.1 Performance on VfM measures / At this first annual review, some of the vfm measures in the business case can be reviewed. Others remain as in the business case of March 2013. / Economy (Input) Measure / Project design costs, including CDM validation and registration. The programme will track the costs of supporting demonstration projects. Some of the initial pilot projects are likely to be at a relatively advanced stage (validation started, completed, or even program registered). This should lower the project design costs / Effectiveness (Output to Outcome) Measure / Carbon price paid for projects through the Carbon Fund. The programme will support projects that require a carbon price that is within the likely prospects for the future carbon market. This has a bearing on how well the programme can demonstrate that pilot projects are financially attractive at a price realistic of a future carbon market and could be replicated. No ERPA has yet been signed with any project. There is therefore no concrete data on this indicator at this stage. Based on the pre-PINs for the first projects under review for possible inclusion in Ci-Dev’s portfolio, it appears that the price range envisaged at the outset ($9 to $14) remains relevant for this first batch of projects. A study has been commissioned to provide guidance and inputs into to negotiation of a price for future ERPAs / 5.2 Commercial Improvement and Value for Money / The Trust Fund procurement for the Readiness Fund follows the World Bank Group’s procurement guidelines. These procedures ensure competitive selection where necessary and measure each procurement option on technical and financial capabilities. This process will be overseen by the World Bank’s Carbon Finance Unit which is also responsible for financial management, ensuring proper execution of trust fund activities and fiduciary responsibility. At this early stage indications are that the CFU is performing as expected. / 5.3 Role of project partners / Partners for pilot projects have yet to be selected so there is value for money compared with the business case is not possible at this annual review. / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / Financial aid conditionality does not apply to this programme.

7. Conclusions and actions
The overall output score for this Annual Review is: A / The programme is on course to deliver the Outputs and Outcome. Good progress is being made in developing a portfolio of pilot projects that is capable of delivery direct benefits. These direct benefits are emission reductions through the purchase of CERs and benefits to poorer people, including increased access to energy. The CFU will need to carefully assess portfolio project ideas and proposals against the selection criteria to make sure the best projects are selected. The CFU should maintain good and timely communication with donors and act on clear donor recommendations in the selection of projects. / Pilot projects have yet to be implemented. It is too early to know how far they can act as good demonstrations for potential replication through a future carbon market. But they are consistent with the selection criteria that were designed to optimise their replication potential. / Methodologies are starting to be developed that can be used in some of the pilot projects and that could influence the future of the CDM and future carbon markets. The CFU has developed good relations with the CDM Executive Board to facilitate the programme’s influence on reform. / The key risk that the carbon market does not recover and that this would lead to limited scope for the programme is still high. International climate change negotiations were not expected to have provided an indication of change in risk by this first annual review, but there have been some proposals from the European Commission. Implementing pilot projects that generate benefits that produce good benefits in their own right and not just because of their demonstration effect for a future carbon market remains a way to mitigate the risk. As in Output 3 there has been good progress in developing such a project portfolio. / Changes are recommended to the logframe in the light of experience in the first year of the programme. These are: / Change the wording of indicator 3.2 so that it is better suited to measuring progress of the pilot project pipeline. The new wording and milestones would be: / Indicator 3.2 Baseline 2013 End 2014 End 2015 End 2016 End 2019 End 2022 End 2025 / Number of: / pre-project identification notes (PINS) received and assessed / emission reduction project agreements (ERPAs) agreed with project developers 0 / 0 15 / 1 25 / 3 35 / 8 50 / 20 50 / 20 50 / 20 / Include 2015 and 2016 milestones for Outcome Indicators 2, 3 and 4. In the business case logframe these were still to be determined while information on the type of initial pilot projects became clear. Milestones would be: / Outcome Indicator Baseline 2013 End 2014 End 2015 End 2016 End 2019 End 2022 End 2025 / M tons CO2 reduced through all projects directly supported by the CMF programme. (Attributed to UK) 0 0 0.1 0.2 0.5 1.6 2.6 / Level of installed capacity of clean energy (MW) in all projects directly supported in CMF programme. (Attributed to UK) 0 0 2 6 55 130 165 / Number of people (‘000) with increased access to clean energy from all projects directly supported in CMF programme. / (Attributed to UK) 0 0 150 300 1,700 3,700 4,300 / To update the 2014/2015 values of outcome indicator 1 to reflect the changes in the initial mix of private and public sector projects within the portfolio. / The risk rating that has been given to this project is medium.

8. Lessons learnt
8.1 Summarise three key lessons learnt from this annual review: / 1) There has been significant interest by potential developers in support offered through CMF for pilot projects. There were an initial 29 enquiries with project ideas, and a call for proposals resulted in more than 100 further for ideas. / 2) Based on the experience of pre-PINs to date, the CFU will need to carefully assess portfolio project ideas and proposals against the selection criteria to make sure the best projects are selected. / 3) Donors, including the UK, should make clear recommendations on the selection of projects on the basis of pre-PIN analysis by the World Bank CFU.

8. Review Process
This review is based on quarterly reporting by the World Bank CFU and progress discussions by DECC and DFID with the CFU. / Sources Used: / CMF Business Case. / CMF Logframe. / World Bank Quarterly reports. / ICF Management Tool