Type of Review: Annual Review

Project Title: Anti-Corruption Together Project

Date started: 12 May 2014	Date review undertaken: 20 May 2014

Acronyms: / ACC Anti-Corruption Commission / ACT Against Corruption Together project / APNAC African Parliamentarians Network Against Corruption / GRZ Government of the Republic of Zambia / MDA Ministry, Department or Agency / NACP National Anti-Corruption Policy / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The Anti-Corruption Together (ACT) project is a £6.3m (2010 – March 2015) investment targeted at reducing the occurrence of corruption in Zambia. The project supports two institutions: / The Anti-Corruption Commission (ACC) in its work to prevent, investigate and prosecute corruption, as well as educating the public on the issue. / Zambia Chapter of the African Parliamentary Network Against Corruption (APNAC) in its work to strengthen Parliamentary engagement in anti-corruption initiatives. / This annual review covers the period July 2013 to June 2014.

What are the expected results?
In line with the National Anti-Corruption Policy, the impact of DFID’s ACT programme is to contribute to Zambia and its people being zero tolerant to corruption. The programme will support this by enhancing the capacity of two Zambian institutions, ACC and APNAC, to implement and monitor anti-corruption initiatives which will help reduce occurrences of corruption. / What will change as a result of our support? / DFID support will contribute to the Anti-Corruption Commission achieving the following results by 2014: / Sensitise 45,000 Zambian citizens on a yearly basis in anti-corruption initiatives. / Successfully improve its prosecution to at least 70 persons for corruption in the courts / Strengthen anti-corruption controls in at least 12 government Ministries and agencies. / What are the planned outputs attributable to UK support? / There are 6 priority outputs that are attributable to UK support through this programme: / Effective coordination and monitoring of National Anti-Corruption Policy implementation. / Sector specific anti-corruption initiatives facilitated and monitored by ACC in selected public institutions. / Increased effectiveness in corruption investigations and prosecutions. / Increased citizen involvement in and oversight of anti-corruption initiatives. / Increased institutional capacity of ACC. / Increased engagement of parliamentary and political actors in anti-corruption initiatives.

What is the context in which UK support is provided?
Experience of corruption is a relatively common part of everyday life in Zambia. The 2012 Zambia Bribe Payers Index reveals that more than 9.8% of Zambians pay a bribe at least once a year. Out of 1,908 respondents taking part in the survey, 38.4% reported they were asked for a bribe by a government or a parastatal employee in the previous year. 21.3% said they took part in corrupt behaviour by offering a bribe to a public employee even without being asked. / As per the assessment from DFID’s Zambia Anti-Corruption Strategy “high level corruption is hard to measure but there is increasing judicial evidence of widespread elite corruption” over the last few years. Over a 15 year period there is evidence of larger corruption scandals. Both elite and ‘petty’ corruption have undermined citizens’ ability to access basic services and distorted policy decisions. / According to the World Bank Governance indicators, Zambia shows some improvement in the control of corruption from 20.90 in 2002 to 45.95 in 2012 on a 0 to 100 scale. A similar positive trajectory is reflected on Transparency International’s Corruption Perceptions Index where in 2013 Zambia scores 38 on a 0 (very corrupt) to 100 (very clean) scale compared to a score of 26 in 2002. The improvements in scores in the main governance indicators suggest Zambia has made progress in the fight against corruption in the last decade. The legal and institutional frameworks have been strengthened; there have been good efforts to reduce red tape and bureaucratic procedures and some progress on investigating and prosecution of corruption cases including those involving high ranking officials.[1] However, despite the progress, corruption remains a serious issue. / Addressing corruption is among DFID’s highest priorities. The ACT programme was commissioned in 2009. It builds on the previous ACCES (2001 – 2009) programme’s success in strengthening the ACC’s systems and capacity. Support to the ACC focuses on strengthening delivery of ACC’s core functions of prevention, investigation and prosecution of corruption. The project also supports education and awareness raising around corruption by working directly with civil society and Zambian citizens. Support to APNAC focuses on strengthening the capacity of APNAC Secretariat, and Parliamentary members, and includes various outreach activities.
[1] Chene, M (2014), Zambia: Overview of corruption and anti-corruption, U4 Expert Answer

## Section A: Detailed Output Scoring

Output 1: Effective coordination and monitoring of national anti-corruption policy (NACP) implementation
Output 1 score and performance description: A (Outputs met expectations) / This output seeks to strengthen Cabinet office and the ACC’s capacity to disseminate the National Anti-Corruption Policy (NACP) in a systemic and target-audience specific way, to prioritize and sequence implementation goals, to establish and manage a coordination mechanism for dialogue with a wide array of public and private stakeholders and to design and implement a simple but effective NACP monitoring framework. It further aims at enhancing the capacity Cabinet Office to perform its political and policy oversight function over the NACP.
Progress against expected results: / Indicator 1.1: tracks the implementation of National Anti-Corruption Policy (NACP) / Milestone: 70% of key annual milestones attained / Progress: 67 % of milestones in the policy were met during the period. / 16 of 24 milestones (67%) were reached in the last year and so moderately did not meet expectation. The majority of milestones not met are to do with reviews of laws to strengthen anti-corruption measures in the private sector. Government also has yet to develop guidelines to improve administrative sanctions for corruption in the public sector. The best performance was on milestones related to embedding anti-corruption measures in public institutions and increased sensitization of the public on corruption. / Indicator 1.2: measures the cumulative number of Ministries, Departments and Agencies (MDAs) that are regularly monitored for experience with corruption in service delivery. / Milestone: At least 6 MDAs (from a baseline of 0 in 2009) / Progress: 9 MDAs / National Institute for Public Administration (NIPA), Department for Immigration, National Road Fund Agency, Zambia Revenue Authority, Pensions and Insurance Authority, Zambia Information, Communications and Technology Authority (ZICTA), Medical Stores Limited, and Pensions Service Fund have been regularly submitting monitoring reports. This result has moderately exceeded expectation. / The tool used to monitor corruption in service delivery reviews the ability of the institution to prevent corruption (improved systems and strengthened internal checks and balances), educate and sensitise (so that all stakeholders fully understand everything that it’s trying to do to stem corruption) and enforce sanctions (suspected cases of corruption are dealt with and no one is “immune” to sanctions). / The reports reviewed showed good progress on prevention (e.g. increased use of online payments for tax transactions by ZRA, payments for services at the National Registration and Passports Office). There was similar evidence for education with most of the institutions having carried out staff integrity awareness activities and launching codes of ethics. However, even though the scores for enforcement showed improvements for most of the MDAs, the reports did not provide any examples of cases where staff had been sanctioned. / Observations of the annual review team / There appears to be increasing momentum to implement the National Anti-Corruption Policy. The Steering Committee (Secretary to Cabinet, Permanent Secretaries and Chief Executives of semi-autonomous public institutions) met in July 2013 and agreed important actions including that the Secretary to Cabinet issue a memo instructing all government departments to include expenditure for anti-corruption initiatives in their 2015 budgets. The memo has since been issued. There is also growing focus on delivering results and the planned mid-term review of the NACP implementation will help to review progress. / But the lack of data on a number of indicators exposes the weaknesses in the monitoring system. Further, while there is increased acceptance of the policy by stakeholders there remain challenges of coordination between ACC and other agencies. / There has been good progress on regularly monitoring MDAs for experience with corruption in service delivery. Although the monitoring is currently all completed in house with quality assurance from ACC, there is evidence that the findings are being used to improve service delivery. For instance in order to curb inflation of prices for goods/services (for kick-backs) the National Road Fund Agency (NRFA) has developed a supplier database and benchmarked prices for items frequently procured. There is also a strong drive to implement service charters which will ensure the institutions have customer complaints and feedback systems. / Recommendations: / R1: Anti-Corruption is still seen as an ‘ACC’ issue. ACC needs to come up with a guide and tool kit on how to implement anti-corruption initiatives for the MDAs. This should go beyond awareness campaigns. / R2: For a number of institutions monitoring corruption appears to have become routine. However there is need to strengthen the collection of evidence and to ensure that findings are used to strengthen interventions. DFID should also quality assure the evidence as part of the end of programme evaluation. / Impact Weighting (%): 20 / Revised since last Annual Review? N [We recommend that this weighting be adjusted downwards to 10%] / Risk: High / Revised since last Annual Review? N

Output 2: Sector specific anti-corruption initiatives facilitated and monitored by ACC in selected public institutions
Output 2 score and performance description: A+ (Outputs moderately exceeded expectation) / This output involves enhancing the ACC’s capacity to work with select line ministries and public agencies in order to identify key corruption vulnerabilities and then to design mitigating measures.
Progress against expected results: / Indicator 2.1: assesses the % of respondents asked for a bribe to obtain a public service, license or permit in targeted MDA’s / Milestone: Reduced rate in all by 20% from the baseline (Baseline: Ministry of Health: 14%, Road Traffic Safety Agency (RSTA) 15%, Ministry of Lands 20%, Local Councils 8%). / Progress: N/A / The Bribe Payers Index is conducted every other year and the next results are expected in the first quarter of 2015. This indicator is therefore not scored for this Annual Review. However, it is worth noting that the 2012/13 Annual Review found that the 2012 Bribe Payers Index results showed an average 19% reduction in the bribery scores across the target institutions from the baseline. The overall aggregate bribery score also showed a downward trajectory, 9.8% in 2012 from 14% in 2009.[2] / Indicator 2.2: tracks the cumulative number of MDAs in which corruption vulnerability assessments and anti-corruption measures are implemented / Milestone: 9 MDAs / Progress: 14 MDAs[3] (plus 1 extension of assessment in ZRA to Chirundu Border) / The Corruption Vulnerability assessments are used to identify the ‘hot spots’ for corruption in institutions and to come up with recommendations to mitigate the risks. / Corruption Vulnerability assessments were conducted in the Judiciary, Ministry of Mines, Energy and Water Development, Workers Compensation Board, National Registration, Passports and Citizenship Office, Livingstone City Council and Zambia Revenue Authority (additional sites visited). The milestone was substantially exceeded. / The review team was also shown evidence that the ACC has been able to monitor the implementation of recommendations from corruption vulnerability assessments.[4] See Table 1 for examples of hotspots and action taken. / Observations of the annual review team / Indicators 2.2 and 1.2 are closely linked and can easily be mixed up. In hindsight, it might have been better for one to focus on the roll out of the anti-corruption initiatives (Integrity Committees) and the other on monitoring the implementation of their anti-corruption plans. There has been quicker than expected progress on the roll out of Integrity Committees[5] to MDAs thanks to the Anti-Corruption Act of 2012 which made it mandatory for every public institution to have anti-corruption initiatives. But this carries a risk if the Integrity Committees are rolled out too quickly because quantity can overshadow quality. This risk was highlighted during a visit to Ndola City Council where officials felt the ACC was no longer able to support the Integrity Committee as effectively as before. This observation was repeated by Kitwe City Council and National Road Fund Agency. / Good progress has been made on monitoring the implementation of anti-corruption plans. But more can be done to improve the quality of action plans to ensure the most essential activities/recommendations are being implemented. There are usually too many activities planned and there is a risk that the scores for implementation are pushed up by institutions only completing the ‘low hanging fruits’. / Table 1 Selected examples of action to mitigate corruption in identified ‘hotspots’ / Institution Hotspot Key Actions Completed / RTSA Examination and licencing of vehicles and drivers / Bribes due to long queues / High costs to motorist to go to examination centres, bribes cheaper Road tax pay points and examination decentralised and outsourced / Department / of Immigration Service Centre/ Issuance of permits - Informal red tape so applications not dealt with on a first in first out basis Computerised Zambia Immigration Management System being piloted at HQ / Ndola City Council Land allocation - multiple allocation of plots and abuse of office by politicians not following procedures Complaint handling mechanism developed but not consistently implemented / Dissemination of Code of Ethics and reporting of cases to enforcement agencies[6] / The team also met the Officer in Charge of the Kitwe Central Police. This meeting exposed the challenge of getting ownership in the police for the integrity committee initiative but also the need to ensure that prevention measures are tailored and not ‘blue print’. The police feel that the Police Public Complaints Authority already does what the integrity committee should be doing. There is need for the ACC to rethink their strategy with the police and they should also consider working more closely with the Police Public Complaints Authority. / Recommendations: / R3: Given that the milestones for roll out of Integrity Committees (ICs) have been exceeded, over the remainder of this programme, more effort should be put in supporting existing ones to develop and implement robust action plans rather than establishing more ICs. This work should include a review of what model of integrity initiative is rolled out to different institutions. / R4: Building on the 2012/13 recommendation that DFID Advisers should discuss the work of the integrity committees with their partner institutions, we suggest DFID programme teams consider supporting ICs within sector programmes. This will build ownership as well as raise the anti-corruption agenda within sectors including monitoring action on Auditor General’s findings. / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N
[2] ACT Annual Review 2013, pg. 5
[3] Inclusive of National Roads Fund Agency, Kitwe City Council, Lusaka City Council, Medical Stores Limited, Zambia Police Service and Ministry of Education reported in the 2012/13 Annual Review.
[4] Recommendations implemented -Road Transport and Safety Agency-RTSA (69%); Ndola City Council (60%); Ministry of Lands (69%); Department of Immigration (56%); Road Development Agency (90%) and Ministry of Health (59%).
[5] So far 32 against a target of 12
[6] Stakeholders feel there is still inadequate sanctioning

Output 3: Increased effectiveness in corruption investigations and prosecutions
Output 3 score and performance description: B (Outputs moderately did not meet expectation) / This output strives to enhance the ACC’s capacity for investigations and prosecutions of corruption cases.
Progress against expected results: / Indicator 3.1: measures the % of completed investigations leading to prosecutions/administrative action / Milestone: 50% / Progress: 35 % of cases were investigated and led to prosecutions or administrative actions. / Number of active cases in 2013 Cases investigated Cases carried forward to 2014 Progress against milestone / 1080 223 / 35 referred to court / 43 referred for administrative action / 145 closed with no further action 857 78 of 223 cases led to prosecution /administrative action representing 35% which moderately does not meet expectation. / Indicator 3.2: measures the % of convictions of cases completed in a particular year / Milestone: 70% / Progress: 58% / In total, 114 cases were before the courts in 2013. Of these cases: / 25 led to convictions / 7 were acquittals / 11 were withdrawn / 71 were still pending / This represents a success rate of 58% of concluded cases which moderately did not meet expectation. / Indicator 3.3: measures the % of corruption cases in audit report investigated by ACC / Milestone: At least 90% / Progress: 82% / 68 corruption related cases were identified from the 2011 Auditor General’s Report[7] of which 49 were authorised for investigations and 7 were referred for action to other agencies. The milestone was moderately not met. / Indicator 3.4: tracks the % of citizens who submitted a complaint who receive feedback within 5 days. / Milestone: 70% of feedback to citizens within 5 days. / Progress: 73% / A total of 490 reports were received out of which 451 (92%) were responded to. However, only 330 where responded to within 5 days which still marginally exceeds expectations. / Observations of the annual review team / Investigations / The team observed that in real terms the ACC increased the number of cases cleared from 132 in 2012 to 223 in 2013. This is a positive development. However, it is a concern that 65% of the cases investigated were terminated and also that 857 cases (up from 682 in 2012) were carried forward from 2013 to 2014. This suggests either a capacity gap or that perhaps too many cases are being authorised for investigation. The review meetings picked up the need for training and improved investigations management. But there was also a strong feeling within the Commission that there are still too many cases being approved for investigations. This has been a recurring problem for the last couple of years. There is an urgent need for ACC to review this situation. / Prosecutions / The ACC does not include the withdrawn cases in its calculation of the success rate of the prosecuted cases. As a result their own assessment is that in 2013 they attained 78% success. We would argue that withdrawn cases should be considered as unsuccessful. It should be a concern for the ACC that 42% of cases failed. / There was a concern in the last Annual Review about the backlog on the investigation cases that the legal team needed to process. The statistics provided show that as at 31 December 2013 the legal department had 67 legal opinions pending. At the time of the review only 23 cases are awaiting assessment. However, there is a lack of clarity on the numbers within the ACC. This may suggest that the current manual tracking system on the status of each open case is inadequate. / Management of investigations and prosecutions / The case management system currently in use in the ACC is porous and leads to inefficiencies and inadequate accountability. The case has been made over the years for an electronic case management system and this review supports that view. However, expectations should be managed as the electronic system will not be a ‘magic bullet’. There is also need to strengthen the ‘back room’ management and accountability structures so that staff performance can be better monitored.[8] There also continue to be issues in coordination between the legal and investigations department which prevent effective team work. / Further, there is also an urgent need to review processes within the Commission so that decisions are taken at the lowest competent level. At the moment a lot of decisions are left to the Director General, which is understandable for investigations authorisation given the provisions of the law. However, there are other decisions that could be delegated to cut waiting times. For example, even though Kitwe has a resident Senior Prosecutor, files still need to be sent to HQ for legal opinions. Such management issues will not be sorted by simply installing an electronic case management system. / Recommendations: / R5: To improve ACC effectiveness continued training and mentoring support is required to ensure full and effective investigations and prosecutions. Consideration should be given to TA that helps officers move through select cases from end to end. DFID should consider extending the IDR case management consultancy. / R6: ACC needs to review its investigation authorisation process so that cases do not overwhelm staff. More cases may need to be referred for administrative action to ensure ACC concentrates on the most strategic (not necessarily high profile) cases. / R7: ACC does not include the withdrawn cases as part of the total cases in court when it calculates of the success rate of the prosecuted cases. ACC’s assessment is that in 2013 it attained 78% success (i.e 25/32 rather than 25/43). DFID would argue that withdrawn cases should be considered as unsuccessful. It should be a concern for the ACC that 42% of cases failed. / R8: Case management needs to be improved so that the status of each case can be clearly tracked. / R9: ACC needs to improve the timeliness of its decisions on investigations and prosecutions. Management should consider delegating authority (as appropriate) to lower levels in the organisation. / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N
[7] Released in 2013
[8] This view is also well articulated in the IDR Consultancy report

Output 4: Increased citizen involvement in and oversight of anti-corruption initiatives
Output 4 score and performance description: A+ (Outputs moderately exceeded expectation) / This output aims to support partnerships between the ACC and civil society organizations to undertake anti-corruption sensitisation activities.
Progress against expected results: / Indicator 4.1: counts the number of cumulative partnerships or outsourcing contracts that ACC has established with Civil Society Organisations / Milestone: 9 / Progress: 83 / The ACC exceeded the target for this indicator by establishing 83 partnerships with civil society organisations by the end of 2013. The civil society organisations carried out anti-corruption sensitization activities targeting a range of stakeholders including women groups. There is also evidence that some of the civil society groups engaged on specific sector issues. / Indicator 4.2: tracks the number of citizens engaged in anti-corruption initiatives per annum / Milestone: 40,000 / Progress: 211,215 / In partnership with the supported civil society organisations, the ACC’s community education initiative managed to exceed the target for this indicator. The outreach initiative involved partnerships with community radio stations in 9 provincial capitals, targeted lectures (including to 25 traditional leaders) and a youth festival. The key messages included the manifestation of corruption and how to spot it, channels to report corruption and encouraging stakeholders to report suspected acts of corruption. / Observations of the annual review team / The ACC has done well in engaging civil society to support its efforts to sensitize people. This is a massive step for an organisation which only a few years ago was considered inaccessible. However, the partnerships are generally short term and largely delivered one-off activities. This may be a missed opportunity to build sustainable partnerships which both strengthen civil society and as well as promote a concerted anti-corruption campaign. There was little evidence of prioritisation of the sectors civil society organisations worked on which would have helped to compliment prevention efforts in high risk sectors. Further, it was clear in meetings with civil society groups that there was no coordination between them. Again this is a missed opportunity to build reform coalitions which are necessary to bring about change. / On the content of there was a concern from stakeholders (including ACC staff) that sensitization materials needed to be updated to be relevant for the times and tailored to specific sectors. / Recommendations: / R10: ACC now needs to build longer term partnerships with fewer civil society organisations. The partnerships should also be approached strategically so that they cover both the geographical reach and sector focus. These strategic partnerships should include private sector stakeholders. / R11: ACC needs to think more specifically at the drivers of corruption in each sector and identify the risks in the ‘delivery chain’ then develop educational materials that are relevant. Both prevention and education initiatives need to address “the different faces of corruption” especially in high risk sectors. / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 5: Increased institutional capacity of ACC
Output 5 score and performance description: A (Outputs met expectation) / This output involves the further strengthening of key institutional functions (including regional offices), and the enhancement of the required technical skills.
Progress against expected results: / Indicator 5.1: counts the number of operational staff trained according to a competency framework and Learning and Development Plan / Milestone: 60 trained / Progress: 170 officers were trained / 63 staff including senior management attended a 3 day leadership and management training programme run by CMEUK. The training was practical and tailored to the needs of the ACC after a needs assessment. More importantly the training ensured staff applied the learning by completing ‘live’ projects within the ACC. 10 investigation officers underwent training in intelligence gathering and surveillance skills. Another 50 underwent further training in investigative methods including on financial crimes and forfeiture of proceeds of crime. 44 officers attended supervisory management training. 3 other officers attended training to enhance their monitoring and evaluation skills. Finally 3 others were trained on corporate communication to enhance the ACC’s public relations. The milestone for the year was substantially exceeded. / Indicator 5.2: measure the extent to which an electronic case management system is developed and implemented / Milestone: Case management system fully operational / Progress: After a needs analysis, the ACC has now produced the specifications for the business processes which are under consideration by DFID. / Indicator 5.3: counts the number of media briefings conducted annually / Milestone: 4 / Progress: 4 / The ACC held all four media briefing as planned and met expectations. There was evidence that there is increased coverage of the briefings by private media houses. The Corporate Affairs Unit also responded to press queries and conducted daily monitoring and analysis of news and feature articles on corruption in the media. / Indicator 5.4: counts the number of regional offices with work plans and budgets / Milestone: 4 / Progress: 9 - The ACC is now able to maintain budget lines for the regional offices within each of the departments. / Observations of the annual review team / The ACC has made good progress on developing a generic competency framework which now serves as a basis for skilling up staff. There was also evidence that the training has had impact within the ACC. But there is still no objective way of distinguishing what skills are needed at different grades particularly in the technical departments. For instance, rather than time served in the Commission, it is not clear what skills distinguish a Senior Investigator from an Investigator. Such a competency will also help to encourage officers to specialise and become experts in their field.[9] / As stated earlier, the review team agrees with the need for an electronic case management system. However, expectations should be managed and there are critical management issues that will need to be addressed for the system to make a difference.[10] / At the moment the Regional Manager serves more a coordination rather than a management role. Officers in regions largely work to the departmental priorities rather to tackling regional issues as a team. For example, in Kitwe staff thought procurement and land allocation where the main corruption areas on the Copperbelt. However, their education programme was focussed on tracking examination leakages. The review team is of the view that regional offices must have control over their resources and be held accountable for agreed results. The budgets can be ‘virtual’ and still be managed from the centre (to comply with Ministry of Finance regulations) but the priorities and decision making should lie with the Regional Offices. / Recommendations: / R12: ACC needs to consider developing technical competency frameworks for all technical cadres. / R13: ACC should consider devolving more authority to the regional offices to plan and implement activities then hold them accountable for results. / R14: The implementation of an electronic management system (with the caveats noted) should be prioritised. / R15: ACC needs to develop a leadership and organisational development strategy. The current training approach (while much improved) is still ad hoc. ACC and DFID should consider extending the relationship with CMEUK and other relevant institutions to take this forward. / Impact Weighting (%):10 / Revised since last Annual Review? N [We recommend that this should be revised to 20%] / DFID and ACC should consider increasing the weighting on this output to 20 and decrease the weighting on Output 1 accordingly. Increasing the institutional capacity of the ACC particularly in the regions will be critical in improving the effectiveness of the ACC. / Risk: Medium / Revised since last Annual Review? N
[9] See also IDC consultancy on the need for a skills development framework
[10] Ibid

Output 6: Increased engagement of parliamentary and political actors in anti-corruption initiatives
Output 6 score and performance description: Not scored / This output provided support to African Parliamentarians Network Against Corruption (APNAC) to enhance its capacity to influence the political agenda on corruption. This work involved building the capacity of APNAC members to propose legislative reviews, amendments or new laws to strengthen the anti-corruption legal framework. It also sought to enhance MPs’ skills to oversee the executive and strengthening their ability to promote ethics and integrity among Parliamentarians and within Parliament. / Observations of the annual review team / This output was not scored against the logframe as DFID funding stopped in June 2012. APNAC priorities changed in line with a new Strategic Plan which was agreed with the Embassy of Finland and GIZ. / At the start of the DFID programme APNAC had about 30 members. This number has now grown to 88 (55% of the Zambian Parliament). There was recognition from stakeholders including Transparency International Zambia (TIZ) that parliamentarians where more engaged on corruption issues as a result of APNAC activity. The key risk for APNAC is the lack of multi-year funding which means activities can only be planned from year to year. This is the security that DFID funding provided in its set up. It is our considered view that APNAC remains a viable stakeholder and partner in the fight against corruption. Progress will be slow and even face reversals, but APNAC remains the main platform to engage parliament on corruption issues. / Breakdown of membership by party / PARTY/INDEPENDENT MEMBERS / Alliance for Democracy and Development (ADD) 1 / Forum for Democracy and Development (FDD) 1 / Movement for Multiparty Democracy (MMD) 17 / Patriotic Front (PF) 45 / United Party for National Development (UPND) 23 / Independent 1 / Total 88 / Recommendations: / R16: DFID should make a decision on the future of its engagement with APNAC. Given there is less than a year left on this programme this may be more relevant in thinking around DFID’s long term engagement on anti-corruption. / Impact Weighting (%): 10 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

Has the log frame been updated since last review? Y / Indicator 4.2 was revised from ‘number of citizens engaged’ to ‘number of citizens sensitized’. We do not recommend further changes at this time given the period remaining on the programme, apart from the minor revision to impact weighting described on page 13. / 1.2 Overall Output Score and Description: A / The ACT programme has overall met expectations for this reporting period. / 1.3 Direct feedback from beneficiaries / This Annual Review includes direct consultation with ACC and APNAC. The review team also met beneficiaries from civil society including PRISCA, NMAC and AVAP. We also met members of the Integrity Committees from Ndola and Kitwe City Councils and the National Road Fund. We also met the Officer in Charge of Kitwe Central Police, officials from the Director of Public Prosecutions and Transparency International Zambia. In all cases stakeholders were very supportive of the ACC but felt the institution needed to continue improving. There was divided opinion on the government’s political will to fight corruption. While some felt the government was supportive others felt the fight against corruption was still selective.
1.4 Summary of overall progress / Figure 1: 2013 Logframe Output Milestone Achievement / Output 1 Output 2 Output 3 Output 4 Output 5 Output 6 / Indicator 1 B B A+ A++ / Indicator 2 A+ A++ B A+ C / Indicator 3 B A / Indicator 4 A+ A+ / Score A A+ B A+ A+ / The ACC has made progress to improve management and operational capacity. However, there are still a number of structural challenges including sustainability of funding, understaffing and limited regional offices capacity. In spite of these challenges, stakeholders believe the institution has made notable improvements.[11] The initiation of investigations against serving government officials and the ruling party’s MPs has received particular commendation (See TI Zambia press statement, 9 April 2014 – Zambia Daily Mail 2014).[12] There still is cynicism towards the ACC as a number of citizens believe the investigations are political, and offending senior officials remain free during lengthy appeals (Freedom House 2011 and 2013). / Against programme objectives ACC has made good progress but going forward the focus on such activities should be on their impact i.e. the changes they produce. The review team observed that there are a number of areas which continue to present recurring challenges. The failure to hit targets on investigations and prosecutions should be examined more closely. While there is certainly a case to improve the skills of staff, ACC may need to review its investigation/prosecution authorisation processes. There appear to be too many cases being authorised compared to the number of staff. Case management and collaboration between investigations and prosecutions also needs to be strengthened.[13] / The ACC also needs to be better joined up. There is still little correlation between education and prevention initiatives. The ACC needs to be clear on the drivers of corruption and seek to tailor its education and prevention to tackle those.
1.5 Key challenges / The key challenges identified in the 2012/13 review remain relevant. Investigative and legal team capacities, as well as the need to improve management and performance still need to be tackled. While training will help, more needs to be done to change the organisations work culture as well, if these challenges are to be overcome. Focus must shift from fulfilling processes to staff being held accountable for results. / Political Will: High-level Government of Zambia political will to support anti-corruption efforts is difficult to determine. There have been some encouraging signs of the ACC trying to bring senior officials to book. But there have also been public statements by senior government officials that undermine the authority of the ACC. ACC cannot succeed in the absence of committed political leadership. / Inter-agency and multi-sectoral coordination: The fight against corruption is still considered an ACC baby. But without other MDAs playing their part (particularly in enforcing administrative action and prevention measures) and joined up efforts with other enforcement agencies, ACC will struggle to meet expectations.
1.6 Annual Outcome Assessment. / The ACT programme has made some progress towards its outcome “decreased occurrences of corruption by enhancing the capacity of Zambian intuitions to implement and monitor anti-corruption initiatives”. The 2012 TI Zambia’s Bribe Payers Index shows improved scores on the two indicators used to measure progress. On the first indicator, 38% (compared to 57% in 2009) of respondents reported an experience of corruption (bribery). On the second indicator 74 % of respondents (compared to 5% in 2009) knew where to report corruption. / The Anti-Corruption Commission has improved its strategic and operational capacity. This is particularly evident in the prevention and education scores. However, ‘acceleration’ in the roll out of initiatives in the absence of approaches/processes being sufficiently embedded in the first place presents risks to longer-term sustainability. On the other hand progress has been slower on the enforcement side but there is clearly evidence that the ACC has increased the number of cases investigated and concluded as well as in the number of prosecutions and convictions. The challenge remains in ensuring that cases are concluded timely and that ACC is seen to prosecute suspects regardless of their standing in society. This will enhance the confidence in the organisation. / We agree with the last Annual Review that there is a significant gap between ACT programme outcome and its impact “A nation and its people that are zero tolerant of corruption”. As that view concludes, even a strengthened ACC can only make a modest contribution to this high level goal. However, we do not see the advantage of revising the impact of the programme at this late state.
[11] Chene, M (2014)
[13] See also IDC Consultancy report

2. Costs and timescale
2.1 Is the programme on-track against financial forecasts: Y / The total revised budget for the entire ACT programme is £6.3 million broken down as follows: / Financial Aid to the ACC was £4.49 m / An accountable grant to APNAC £0.36 / DFID managed technical assistance £1,421,142 / So far all the funds to APNAC have been disbursed and £3.5 million or 79% has been disbursed to the ACC. There still remains a challenge in ACC’s funds utilization due to a lag in procurement while funds remain in bank accounts. But this is in line with Zambian procurement law that requires funds to be in an account before commencement of any purchases. Overall, the ACC remains on track with its financial forecasts and has improved in its spend rate over the last year. / The TA component has been underspending but it is expected that some remaining funds will support the implementation of the Case Management System if that takes off. / 2.2 Key cost drivers / This programme was designed before the incorporation of cost drivers in the design process. However, the key cost drivers are staffing (fully covered by the Government of Zambia), travel and training costs. / 2.3 Is the programme on-track against original timescale: Y / ACC remains on track against the timings set out in the Programme Memorandum.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The programme continues to build the evidence base upon which its design rests. For example, as part of its strategic planning process the ACC has embarked on embedding M&E processes to assess its own performance. The ACC has also been jointly funding the TI Zambia Bribe Payers index. The collection of statistical information on the reports received is now entrenched. However, it remains an open question whether the institution is effectively using the data that can now be more readily collected. / There has been less progress on higher level evidence gathering. The ACC still relies on the Governance Baseline Survey of 2003 to understand the drivers of corruption. This may now be outdated. There is also need to strengthen systems for monitoring of the impact of interventions within sectors. / 3.2 Where an evaluation is planned what progress has been made? / An evaluation will be commissioned at the end of the programme.

4. Risk
4.1 Output Risk Rating: High / The output risk rating remains “High” / 4.2 Assessment of the risk level / ACC has benefited from DFID long term funding which has delivered progress on management and operational capacity. However, low capacity (including understaffing, inadequate management and limited funding from government) and an ambitious mandate are a key risk. This is compounded by limited commitment from other institutions to enforce recommendations for administrative sanctioning of erring officials. Together with mixed signals of political support these factors means the environment for ACT remains high risk overall.
Risk of funds not being used as intended / DFID has helped to build robust financial mechanisms in the ACC and funds are controlled and disbursed by the programme team and the associated regional offices. The programme undergoes external audit by the Auditor General every year. The programme emerged from this scrutiny with a clean bill of health. / Climate and Environment Risk / As noted in the previous annual reports, the climate and environment risk associated with ACT remains low.

5. Value for Money
5.1 Performance on VfM measures / VfM measures were not mandatory during the design of the ACT programme and no specific development was undertaken of VfM measures at the time. The review considered 3 questions: / Does the ACC spend its money wisely? (Economy) / How effective is the ACC in achieving outputs and outcomes at the lowest possible cost? (Efficiency) / How effectively do the actions of the ACC lead to impacts in Zambia – is there an increase in the percentage of people who think the government is effectively tackling corruption? (Cost-Effectiveness) / Economy: DFID funding goes into core funding for the ACC, so we cannot isolate any specific items to attribute to DFID – we have to judge the economy of all ACC spending. Whilst specific indicators for economy are not available, the unqualified audit by the Auditor General suggests ACC is using its money for the intended purposes and within agreed budgets. The report notes that ACC follow government procedures and have effective systems for controlling cost, and achieving economies through market analysis and aggregation of purchasing to seek volume discounts. / Efficiency: The review found that ACC continues to deliver against milestone indicators which formed the basis of DFID’s investment. But the review was not able to determine whether these outputs could have been achieved at lower cost. Feedback from staff suggests that there may be areas where ACC can get better return for their investment, particularly in investigations and prosecutions. In some cases the costs (staff time and travel expenses) seem higher than the return (prosecution of low value crimes). However, there is a counter argument that some low value crimes may have high impact (e.g. a police officer who lets off a murderer for a small bribe puts a lot of lives at risk). It is clear that there is a gap in evidence as ACC has not as yet made any attempt to assess how efficiently the project is turning inputs to outputs, or how to maximise performance from its resources. / Cost-Effectiveness: Every year, Zambia loses millions of dollars’ worth of public money which is misappropriated, stolen or grossly mismanaged. In 2011 for example it is estimated that US$98 million may have been lost to corruption.[14] There are therefore substantial potential economic gains from reducing corruption. All the major governance indicators[15] and the Zambia Bribe Payers Index seem to confirm a positive trend over the last 10 years. It is very difficult to judge how much of the improvement in governance indicators can be attributed to the ACC. / The ACC is the main institution legally mandated to investigate and prosecute cases of corruption. It is therefore unlikely that any alternative organisations would be as effective at reducing corruption, as action is needed within Government. This forms part of the justification for providing support to the ACC. A successful ACC therefore will make a significant contribution to fighting grand corruption and saving Zambia much needed funds to reduce poverty. / 5.2 Commercial Improvement and Value for Money / The majority of expenditure on the programme to date is through Government of Zambia systems. DFID sits on the Project Management Team which approves budgets, which works to improve value for money throughout DFID’s investment. DFID also provides additional control by giving a ‘no objection’ to purchases and Terms of Reference as appropriate. / 5.3 Role of project partners / DFID’s contribution to the overall ACC budget in 2013 was 10% and 26% of the discretionary budget[16]. As a percentage of the overall budget, DFID’s contribution has reduced consistently by 1% yearly since 2010 (12% in 2010 and 11% in 2011). DFID’s contribution to the discretionary budget dropped by 15% (from 41% in 2012 to 26% in 2013). Increased funding from government provides a higher likelihood that the ACC will be more sustainable in the longer term once DFID support finishes. / 5.4 Does the project still represent Value for Money : Y (but qualified) / This review finds that at the moment not much was known about costs of inputs and the average cost per unit of delivery. There is a positive trend in terms of attainment of outputs and outcomes that represent, qualitatively, good efficiency, because costs are within budget, outputs are being delivered, and outcomes are noted. However, there are significant gaps in evidence which make it difficult to provide a comprehensive assessment. / 5.5 If not, what action will you take? / In the remaining period actions should be taken to enhance VFM particularly to develop better metrics for efficiency and effectiveness. We recommend that DFID should support the ACC to carry out a comprehensive review of: i) how ACC has spent its money to make a judgement on economy and (ii) a more detailed breakdown of the ACC’s budget to see if we can link how much they have spent to achieve each output in the logframe – this would allow DFID to create efficiency measures. The planned evaluation should review how the ACC’s work is impacting on perceptions of corruption amongst Zambians.
[14] US Department of State, 2013
[15] World Bank Governance Indicators, Transparency International Corruption Perceptions Index and World Bank Enterprise surveys
[16] Discretionary budget includes all expensed except for staff costs.

6. Conditionality
6.1 Update on specific conditions / No conditionality is applied to this programme.

7. Conclusions and actions
ACT has delivered an important set of results which have the potential to contribute to reducing corruption in Zambia. But corruption remains a significant problem and political environment remains challenging. As a response, the following key actions are proposed: / For the remainder of this programme DFID should focus its support to ACC on the following areas: / improving the ACC’s performance on investigating and prosecuting cases - both civil and criminal. / improving the case management system but this should go beyond introducing a computerised system and include strengthening management accountability processes. / developing leadership and management skills of ACC staff. / ensuring more empowered and better functioning regional offices. / DFID could help to embed a culture of accountability in the public service by investing in the integrity initiatives through sector programmes. This will ensure that anti-corruption is mainstreamed across the DFID portfolio. / Finally, and as part of the planned evaluation, DFID should undertake a thorough review of the Value for Money achieved through the programme. / A list of recommendations for both DFID and ACC is summarised below: / DFID / There is need to strengthen the collection of evidence and to ensure that findings are used to strengthen interventions. DFID should quality assure the evidence as part of the end of programme evaluation. / DFID programme teams should consider supporting integrity committees within sector programmes with their partner institutions as this will build ownership as well as raise the anti-corruption agenda within sectors including monitoring action on Auditor General’s findings. / DFID should consider extending the IDR case management consultancy in order to improve ACC effectiveness. / DFID should make a decision on the future engagement with APNAC, with less than a year left on this programme this may be more relevant in thinking around DFID’s long term engagement on anti-corruption. / DFID and ACC should consider increasing the weighting on output 5 to 20% and decrease the weighting on output 1 to 10%. Increasing the institutional capacity of the ACC particularly in the regions will be critical in improving the effectiveness of the ACC. / ACC / ACC needs to review its investigation authorisation process so that cases do not overwhelm staff. / ACC needs to build longer term partnerships with fewer civil society organisations, have partnerships that cover the geographical reach and consider strategic partnerships with private sector stakeholders. / ACC should consider devolving more authority to the regional offices to plan and implement activities then hold them accountable for results. / ACC needs to come up with a guide and tool kit on how to implement anti-corruption initiatives for the MDAs which should go beyond awareness campaigns as Anti-Corruption is still seen as an ‘ACC’ issue. / ACC need to develop and implement robust action plans for existing Integrity Committees rather than establishing more and review what model of integrity initiative is rolled out to different institutions. / ACC need to improve case management so that the status of each case can be clearly tracked. / ACC needs to improve the timeliness of its decisions on investigations and prosecutions. Management should consider delegating authority (as appropriate) to lower levels in the organisation. / ACC needs to think more on the drivers of corruption in each sector and identify the risks in the ‘delivery chain’ then develop educational materials that are relevant. / ACC needs to consider developing technical competency frameworks for all technical cadres. / The implementation of an electronic management system (with the caveats noted) should be prioritised. / ACC needs to develop a leadership and organisational development strategy. The current training approach (while much improved) is still ad hoc. ACC and DFID should consider extending the relationship with CMEUK and other relevant institutions to take this forward.

8. Review Process
This review was carried out by Wilf Mwamba (Governance Adviser) with support from Doreen Manda (Project Officer Governance), Florence Mabandhla (Programme Manager) and David Lloyd-Davies (Acting Lead Adviser). The team carried out a review of documentary evidence and interviewed range stakeholders including civil society, Office of the Director of Public Prosecutions, and representatives of integrity committees. The team also undertook a field visit to Ndola and Kitwe.