Annual Review - Summary Sheet

Title: Forest Governance, Markets and Climate (FGMC)
Programme Value: Business case value £250 million (£163 million currently approved, up to March 2018)		Review Date: August 2014
Programme Code: 201724	Start Date: August 2011	End Date: August 2021

Summary of Programme Performance
Year	2012	2013	2014
Programme Score	A	A	A
Risk Rating	M	M	M

Summary of progress and lessons learnt since last review
Overall progress is on track. A larger than expected number of countries are negotiating Voluntary Partnership Agreement (VPAs), with more expressing interest. There are good prospects for both Indonesia and Ghana to export FLEGT (Forest Law Enforcement, Governance and Trade) licensed timber in early 2015, showing the way forward for countries still working to negotiate or implement their agreements. The EU Timber Regulation (EUTR) is now in place, reinforcing existing demand-side measures. Programme partners are generating a strong body of knowledge and evidence to support further work, and are beginning to apply lessons to other commodities associated with deforestation. A key lesson is the sensitivity of programme delivery to changes in the political context, to changes in security, and unexpected events such as the Ebola epidemic in West Africa. This underlines the importance of strengthening the flexible, responsive and technical management of the programme over the medium term which will now be secured through outsourced programme management arrangements with strengthened DFID oversight, particularly on political and strategic matters.

All key recommendations arising from the 2013 AR have been completed (where relevant).
- Programme management: Transition arrangements implemented, and a tender process commenced to secure outsourcing management arrangements by early 2015.
- Monitoring and evaluation (M&E). Programme logframe revised, improvements made to accountable grant reporting templates, and introduction of a new financial reporting format.
- Grantee coordination, monitoring and learning. Annual conference for grantees strengthened and standardised reporting introduced.
- Efficiency of procurement. Tender for outsourcing programme management underway, to be completed early 2015.

Summary of recommendations for the next year
1. Programme management: strengthen management arrangements to cope with rising demands as the programme grows in complexity by securing a competent outsourced programme manager, with DFID retaining oversight on political and strategic issues (by January 2015).
2. Lesson learning: develop a strategy to enhance programme lesson learning to include reviewing additional platforms ensuring that these complement those already in use and which have proven to be effective, such as biannual Chatham House stakeholder meetings, the annual EU FLEGT week, and annual FGMC grant partners’ meeting (by March 2015).
3. Programme assumptions: research, analyse and test key assumptions in the programme theory of change to enhance the evidence base in order to assess, during the anticipated final phase of the programme from 2018-21, whether FGMC has succeeded in meeting its impact and outcome objectives, and in particular building the evidence to demonstrate poverty impacts of partnership agreements (by July 2015).
4. Gender: build on gender integration efforts by implementing mechanisms to allow gender impacts arising from current interventions to be clearly reported, where possible; encourage partners to explore how to increase the impact of programme interventions on girls and women; ensure that future calls for proposals give greater emphasis to gender (by March 2015).
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3718415.docx
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4445967.xlsx

Outline of the programme

Approved in 2011, Forest Governance, Markets and Climate (FGMC) is a 10-year programme of up to £250 million. The initial programme budget over 2011-15 is £79 million. In June 2014 a second tranche of £84 million was approved for 2015-18, bringing the total approved budget to £163 million. Funded through the International Climate Fund (ICF), FGMC is DFID’s flagship forestry programme, designed to tackle illegal logging and support forest governance reform.

Corruption and weak governance allows illegality to flourish in the forestry sector in many developing countries. Illegal logging undermines the rule of law and leads to the loss of significant tax revenues, and is most likely to persist or increase where governance is poor, where forests have timber values that attract attention of markets, and where alternative economic opportunities are lacking. These circumstances are found in some regions of many countries, but are particularly prevalent in Central and West Africa, the Amazon basin and Central America. These circumstances are also found in parts of Russia, especially in the Russian Far East.

The FGMC programme is designed to tackle illegal logging by increasing transparency through tracking timber from point of harvest, supporting reforms to clarify and improve the law, providing market incentives for legal timber, and linking small firms to global markets. The programme will coordinate efforts with the EU Forest Law Enforcement Governance and Trade (FLEGT) action plan, as part of a global effort to tackle deforestation, and enables compliance with the EU Timber Regulation (EUTR).

Expected results as expressed in the programme logical framework are as follows.

## Impact statement: Improved management of forests for poverty reduction, biodiversity conservation, and climate protection. Progress indicators are:
G.1. Deforestation and degradation rate in developing countries
G.2. Value from forests accruing to forest dependent people in developing countries
G.3. % of trade in illegal timber and selected other forest risk commodities
## Outcome statement: Governance and market reforms that reduce the illegal use of forest resources and benefit poor people. Progress indicators are:
P.1. Progress towards self-sustaining, nationally owned, deliberative multi-stakeholder process in Voluntary Partnership Agreement (VPA) countries
P.2. Progress with adopting and implementing pro-poor forest sector governance reforms at national level
P.3. Progress with adopting and implementing pro-poor land tenure reforms at national level
P.4. Progress with adopting and implementing market reforms addressing deforestation and forest degradation at national and international levels
## The programme has four outputs. Details of these and the progress indicators for each output are set out in section C, along with the progress achieved against each.

The programme context is changing as a result of the decrease in timber trade between producer countries and the EU, the growing importance of emerging markets in the timber trade, and the role of other commodities in driving deforestation. FGMC is responding to these changes by supporting advocacy and facilitation that aims to encourage new consumer countries (such as China) to create policies and laws governing the purchase of timber and other commodities to reduce illegal trade. There have also been a number of changes of context in individual countries where FGMC operates, specifically in Central Africa Republic following the outbreak of civil war, and in Liberia programme activities have been disrupted as the result of measures put in place to contain the Ebola virus outbreak. The programme is responding to and managing these changes within the limits of DFID’s control.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The programme is contributing to the achievement of the outcome, and progress is on track towards 2015 milestones. A brief summary of progress against each outcome indicator is provided below.

Indicator P1: Progress towards self-sustaining, nationally owned, deliberative multi-stakeholder process in VPA countries. There has been overall progress towards this indicator, with the situation varying by country. Indonesia has been building a multi-stakeholder process since 2000 which currently has strong national ownership. Civil society is playing a key role in monitoring the partnership agreement and the private sector is an active participant, but there is less ownership at sub-national levels of government. In Liberia and Ghana, multi-stakeholder processes have been reinvigorated and are functioning well. Multi-stakeholder processes are at an early stage in Vietnam and Cote d’Ivoire; have been advancing only slowly in Guyana, Republic of Congo and Cameroon; and have been impeded by weak capacity and insufficient government engagement in the Democratic Republic of Congo (DRC). Overall the participation of the private sector (in particular small and medium-sized enterprises), forest communities and local governments remains weak, and efforts will therefore be directed towards ensuring that these categories of stakeholders are included.

Indicator P2: Progress with adopting and implementing pro-poor forest sector governance reforms at national level. The programme is clearly contributing to the achievement of this indicator. Out of eight countries analysed , three countries (Republic of Congo, Cameroon, Ivory Coast) have developed forest sector governance reforms which are expected to be adopted by their national parliaments in the coming year. Ghana, Liberia and Indonesia are also in the process of implementing reforms. Transparency has contributed to the reform process in Indonesia, with the globally scrutinised audit process required by FLEGT licensing requiring a higher degree of professionalism in the Ministry of Forestry. Vietnam is still at an early stage, but the government has asked a national network of non-governmental organisations to engage in a review of the Forest Protection and Development Law. In the DRC, a draft arrête developed for local community forest concessions has been stalled.

Indicator P3: Progress with adopting and implementing pro-poor land tenure reforms at national level. Progress is slow in this area and significant work is still required. Out of eight countries analysed, Liberia has developed a new draft land law which is being presented for consultation; Cameroon and DRC are making very slow progress with land tenure reforms; and in the DRC and Republic of Congo, governments are preparing laws on indigenous people, albeit slowly. In Indonesia, there is pressure to implement a 2013 constitutional court ruling on indigenous land rights.

Indicator P4: Progress with adopting and implementing market reforms addressing deforestation and forest degradation at national and international level. There has been progress with adopting and implementing market reforms during the review period, but significant work is still required, particularly with regard to developing adequate enforcement systems for the EUTR in all EU Member States. The EU Timber Regulation came into force in March 2013, and all EU Member States have nominated competent authorities, following advocacy by programme grantees. Some Member States, such as the UK and Germany, have established enforcement systems, but many others have yet to do so. Programme partners are actively fostering the sharing of lessons amongst competent authorities to develop a consistent set of best practices, and are also fostering cooperation between EU and US authorities. Indonesia and Ghana have both adopted timber procurement policies favouring FLEGT-licensed timber. There is also clear evidence of increased awareness among some EU companies about the connection between illegal logging and regulatory and financial risks, in response to campaigning by FGMC grantees.

Overall output score and description
The programme is assessed as ‘A’, i.e. outputs met expectations. Output level indicators are largely on track towards the next set of milestones in 2015. A brief summary of progress is provided below.

Output 1: Engagement by multiple stakeholders increased and sustained in targeted producer and processing countries. The programme has been instrumental in building the capabilities of various stakeholders, in particular government institutions, civil society organisations and to some extent the private sector and forest communities. Effective facilitation is enabling multi-stakeholder dialogue and governance reforms. There is progress with developing timber legality assurance systems in Indonesia and Ghana, both of which are likely to commence licensing of legal timber products in 2015. Systems to monitor the impact of voluntary partnership agreements are under development

Output 2: Public policies and private business standards that tackle trade in timber and other commodities from illegal forest practices. Programme partners have fostered shared understanding of the EUTR amongst industry, civil society, service providers, and regulators. This will underpin the strong operation of the EUTR as well as efforts to develop coherent measures internationally. Targeted financial institutions are becoming more aware of the need to address risks associated with illegal practices in timber supply chains.

Output 3: Increased knowledge and momentum for change. Good progress overall. Evidence is increasingly relevant, and of good quality. This will serve to build and sustain momentum for change. There are issues to consider in relation to accessibility, usability and the setting of research agendas, all of which would benefit from an increase in the representation of processing and producer countries.

Output 4: Coherence between programmes on forests and deforestation at national and international levels. Evidence suggests that the EUTR and voluntary partnership agreements can be directly leveraged to combat forest conversion to agricultural commodities. This is gaining attention in policy discussions. FGMC-funded research and advocacy is resulting in changes in investor policies and behaviour relevant to deforestation. Country experiences have shown that land use planning, tenure reforms that better recognise community rights to land and forest resources, and better governance and procedures around land allocation to private sector are fundamental to the success of both FLEGT and efforts to reduce greenhouse gas emissions from deforestation (REDD+).

Key lessons
FGMC demonstrates the importance of political (and economic) engagement to bring together the global and local actions that are necessary to catalyse change. It is beginning to provide evidence of the impact which can be generated through improvements in the capacity of the different stakeholder groups to negotiate and engage in major legal and policy reforms. As the EU’s market influence diminishes in relation to emerging economies, there are signs that new consumer countries, notably China and India, are beginning to respond to the problems of illegal logging and agricultural deforestation, encouraged in part by FGMC-funded efforts. There is also some evidence of behaviour change in the private sector, in the timber industry and in the palm oil sector, particularly in Liberia. Support for small and medium-sized enterprises engaged in these supply chains is urgently needed to ensure that shifts towards verified legality do not have perverse impacts on rural livelihoods. The programme will address this.

All these outcomes remain fragile and sensitive to political change, underlining the importance of continued engagement to consolidate and build on these gains. Changes in security in some countries, and unexpected events such as the Ebola outbreak in West Africa, underlines the importance of securing outsourced management arrangements which are flexible, responsive, and where DFID retains significant oversight, particularly on political and strategic matters (see recommendation 1).

Key actions
- Programme management: appoint outsourced service provider to support management of a growing programme (by January 2015).
- Lesson learning: develop a strategy to enhance programme lesson learning (by March 2015).
- Programme assumptions: initiate research to test key assumptions in the programme theory of change, to support evalution of impact and outcome objectives during the anticipated final phase of the programme from 2018-21 (by July 2015).
- Gender: ensure gender impacts arising from current interventions are clearly reported; encourage partners to explore how to increase the impact of programme interventions on girls and women; ensure that future calls for proposals give greater emphasis to gender (by March 2015).

Has the logframe been updated since the last review? Yes. The programme logical framework was revised during the course of the reporting year and now provides a stronger basis for reporting results against a 2013 baseline and milestones for 2015 and 2020.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Engagement by multiple stakeholders increased and sustained in targeted producer and processing countries
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicators	Milestones (2015)	Progress
Indicator 1.1: Capability of national stakeholders to participate effectively in deliberative processes in order to deliver political reforms in relation to market, forest, and land tenure in VPA countries.	Detailed country specific milestones (set for 2015) for the 8 countries are listed in the logframe.	All participating countries are on track aside from Cameroon and the Central African Republic. In Cameroon Implementation has been slower than expected due to deterioration of relations between civil society organisations and the Government. Work has been suspended in the Central African Republic due to the security situation.
Indicator 1.2: Effective FGMC-funded facilitation of VPA processes	Detailed country specific milestones (set for 2015) for the 8 countries are listed in the logframe.	On track. Effective facilitation led to the ratification of the voluntary partnership agreement with Indonesia in February 2014. More broadly, partnerships where DFID has taken a lead in supporting facilitation – Indonesia, Ghana and Liberia – are at the most advanced stage of implementation.
Indicator 1.3: Progress towards effective Legality Assurance System development and effective implementation	Detailed country specific milestones (set for 2015) for the 8 countries are listed in the logframe.	Overall, the programme is on track although there are some delays in the implementation of systems in the Republic of Congo and Cameroon.
Indicator 1.4: Status and quality of governance, poverty and livelihoods impact assessment of VPA processes (and related forest sector governance reforms).	Detailed country specific milestones (set for 2015) for the 8 countries are listed in the logframe.	The programme is generally on track to reach 2015 milestones; however more research and evidence is needed on the poverty reduction impacts arising from forest governance reforms.

Key Points
The programme has been instrumental in building the capabilities of various stakeholders, in particular government institutions, civil society organisations and to some extent the private sector and forest communities. Effective facilitation is enabling multi-stakeholder dialogue and governance reforms. There is progress with developing timber legality assurance systems in Indonesia and Ghana, both of which are likely to commence licensing of legal timber products in 2015. Systems to monitor the impact of voluntary partnership agreements are being jointly developed with national stakeholders.

A number of delivery risks have arisen over the last year in Central African Republic (CAR) and Liberia. In CAR this has centered on the outbreak of civil conflict, whereas in Liberia the recent outbreak of the Ebola virus has curtailed operations. Measures have been taken in both instances to manage and mitigate the situation (see section E).

Summary of responses to issues raised in previous annual reviews
The 2013 Annual Review included recommendations to: revise the programme logframe (completed); consider whether country theories of change and results frameworks are required (completed); strive to link accountable grants to country implementation plans (ongoing); ensure that accountable grants adopt a consistent use of activity based budgets and reporting of results (completed).

Recommendations
Ensure enhanced gender impacts through strengthening focus on gender issues, particularly through programme activities that contribute to indicators 1.2 and 1.4 above.

Output Title	Public policies and private business standards that tackle trade in illegal timber
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicators	Milestones (2015)	Progress
Indicator 2.1: Understanding of EUTR requirements on the part of economic operators, timber suppliers, and service providers such as monitoring organisations, third-party certification schemes, and trade federations.	See logframe	On track towards 2015 milestones. Good progress has been made with raising awareness of the requirements of the EUTR. Grantees have collaborated to ensure an accurate and consistent presentation of key issues and have rigorously engaged with stakeholders, including regulators and service providers, to confront confusing and conflicting messages about EUTR requirements. This has resulted in significant progress towards a common understanding of the EUTR requirements.
Indicator 2.2: Competent Authorities’ awareness of EUTR enforcement roles and responsibilities.	See logframe	On track towards 2015 milestones. The programme has made a substantial contribution towards consistent enforcement of the EUTR across the EU. Programme activities have helped competent authorities to better understand the requirements for effective implementation, built capacity through facilitating lesson sharing between competent authorities, and focussed attention on where the EUTR has not been properly implemented or enforced.
Indicator 2.3: Progress with implementing policies and measures to reduce consumption, trade in illegal timber globally.	See logframe	On track towards 2015 milestones. The programme has made substantial contributions towards policies and measures to reduce consumption and trade in illegal timber globally.
Indicator 2.4: Change in targeted financial institutions’ policies and practices related to illegal practices in acquiring and implementing timber rights, including forest land conversion rights.	See logframe	On track towards 2015 milestones. In some cases, programme activities have prompted targeted financial institutions to change their policies, behaviour, and practices to address these risks.

Key Points
Programme partners have fostered shared understanding of the EUTR amongst industry, civil society, service providers, and regulators. This will underpin the strong operation of the EUTR as well as efforts to develop coherent measures internationally. Targeted financial institutions are becoming more aware of the need to address risks associated with illegal practices in timber supply chains. Exposés and related advocacy work by programme partners have caused targeted financial institutions to recognise the need to be more transparent in relation to their management of risks associated with illegal logging, violation of land rights, and other illegal practices in timber supply chains.

Summary of responses to issues raised in previous annual reviews
The 2013 Annual Review included recommendations to: review the theory of change, and indicators and baselines should be revised to more closely represent programme results and to reflect the right level of ambition (completed); consider whether to commission further research to quantify the links between procurement policies and production practices to facilitate more precise monitoring of results (ongoing).

Recommendations: None specific to this output.

Output Title	Increased knowledge and momentum for change
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicators	Milestones (2015)	Progress
Indicator 3.1: Availability and communication of evidence for and about governance, market and tenure reform.	Evidence continues to be relevant and accessible; / Main priorities for future research have been identified	On track towards 2015 milestones. The overall evidence is increasingly relevant and of good quality. Funding entities are actively seeking opportunities to identify main priorities for future research, often with a geographical focus..
Indicator 3.2: Size and diversity of community of practice.	Increase in size and diversity of community of practice	On track towards 2015 milestones, although work would benefit from an increase in the representation of processing and producer countries and other sectors.
Indicator 3.3: Communication and engagement to sustain political momentum globally.	Increase in effectiveness of communication and engagement with influential political decision-makers	On track towards 2015 milestones. A large majority of survey respondents felt that there was effective engagement with political decision makers to sustain momentum for change

Key Points
There has been good progress towards achieving Output 3. Evidence is increasingly relevant, and of good quality. This will serve to build and sustain momentum for change. There are issues to consider in relation to accessibility, usability and the setting of research agendas, all of which would benefit from an increase in the representation of processing and producer countries.

Grantees’ reporting indicates widespread improvements in evidence and this is backed up by quantitative results from the illegal logging stakeholder perception survey and a survey of alumni from the Centre for International Development and Training’s (CIDT) International Forest Governance Course.

Community of practice meetings reached at least 810 stakeholders. Returns from the illegal logging stakeholder perception survey suggested that 68% of respondents reported good performance on indicator 3.2, while only 15% indicated bad performance (17% did not know). However the composition of survey respondents was heavily weighted towards the UK and other consumer countries, with only 19% of respondents based in producer countries, and only 5% in processing countries.

The CIDT alumni survey indicated that 88% of the 69 responding alumni stated improved knowledge about forestry governance issues. Skills were improved for training of trainers for improving forest governance (75%) and alumni experience a shift in their perception of the importance of effective enforcement of forest laws (74%). 57% of alumni stated that they or their organisation had taken practical steps to improve forest governance (9% had not), particularly by addressing key challenges.

Output 3 risk was increased from low to medium during the logframe revision to reflect the challenge around the flow of knowledge leading to measurable increases in knowledge and change.

Summary of responses to issues raised in previous annual reviews
Logframe indicators for this output have been revised based on a recommendation in the 2013 Annual Review. The indicators now better reflect the aim of funding research, generating and disseminating evidence.

Recommendations
Lesson learning: develop a strategy to enhance programme lesson learning (by March 2015).
Programme assumptions: initiate research to test key assumptions in the programme theory of change, to support evalution of impact and outcome objectives during the anticipated final phase of the programme from 2018-21 (by July 2015).

Output Title	Coherence between programmes on forests and deforestation at national and international levels
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones (2015)	Progress
Indicator 4.1: Change in policy alignment between REDD+, FLEGT and other processes dealing with forest land use	Recognition within country REDD+ programmes that good governance is essential for REDD+ progress.	On track towards 2015 milestones. The programme has contributed to research, awareness raising and dissemination of the potential and actual linkages between REDD+ and FLEGT processes.
Indicator 4.2: Awareness of lessons from FLEGT on how to apply trade and investment measures to other forest risk commodities	Appropriate research and analysis from FLEGT have been debated and used in policy discussions on how the EU, Member States, and producer countries can address other forest risk commodities.	On track towards 2015 milestones. Programme partners are bringing lessons from FLEGT into policy discussions about new EU measures to address forest risk commodities
Indicator 4.3: Changes in business standards, compliance and behaviour of investors in relation to reducing deforestation.	Systems being developed by civil society and local communities to monitor and report compliance with business standards for forest risk commodities; demonstrated change in awareness and capacity in relation to compliance with palm oil standard; Approximately 200 major businesses and 230 investment companies whose portfolios impact on tropical forests acknowledge the risks of deforestation and attempt to measure and manage those risks.	On track towards 2015 milestones. FGMC-funded research and advocacy is resulting in changes in investor policies and behaviour relevant to deforestation.

Key Points
Evidence suggests that the EUTR and voluntary partnership agreements can be directly leveraged to combat forest conversion to agricultural commodities. This is gaining attention in policy discussions.

Country experiences have shown that land use planning, tenure reforms that better recognise community rights to land and forest resources, and better governance and procedures around land allocation to private sector, are fundamental to the success of both FLEGT and efforts to reduce greenhouse gas emissions from deforestation (REDD+). The recent focus of FGMC on illegal forest conversion for agriculture in Asia and central Africa has brought the links between REDD+ and FLEGT into sharper focus in the frame of VPAs in Laos, Cameroon and Indonesia.

The number of companies disclosing their impacts on forests increased to 139 in 2013, a rise of 39% from the previous year. This reporting initiative is endorsed by 184 investors with US$13 trillion in assets under management.

Summary of responses to issues raised in previous annual reviews
The 2013 Annual Review included recommendations to: in countries where there are different institutional homes for REDD+ and FLEGT (e.g. DRC), encourage all development partners to work with the government to encourage greater collaboration and coordination across these two instruments (ongoing); continue to explore the potential to use both instruments to reinforce effort around critical issues and reforms at a country level (ongoing).

Recommendations
Ensure enhanced gender impacts through strengthening focus on gender issues, particularly through programme activities that contribute to indicators 4.3.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
Key cost drivers for the programme centre on overhead and management costs associated with the grantees, Memorandums of Understanding, and service contracts with companies and individuals, and on the cost of overall programme management.

- Grantees: A standardised budget reporting template has been introduced, providing clarity on cost distributions across grantees. Management and overhead costs continue to be assessed and negotiated before grants are issued to drive down costs where possible. For example, the memorandum of understanding with one programme delivery partner was negotiated leading to a cost reduction in fees from 13% to 7% of total budget, generating a saving of £84.5k.
- Service contracts: All new contracts issued during the year (e.g. in China and Guyana) were subject to full competitive tendering where selection was based on both technical and commercial criteria. Post-tender negotiations have led to cost saving, in one case leading to a £1m (50%) reduction in fees, and in another leading to an estimated £96.5k (10%) saving. Services provided under FGMC are a fairly niche market which at times leads to reduced levels of competition with the potential to drive costs upwards. Rigorous negotiations have managed to keep costs within acceptable levels. The Framework Agreement established to speed-up the tender process has not achieved the anticipated gains in time and therefore savings in transaction costs as originally anticipated.
- MOUs: Savings achieved through negotiations to establish MOU with FAO; MOUs with AFD (Republic of Congo) and Government of Norway (Guyana) leverage additional funds from the donor partners; MOU with Government of Ghana drives value through strong performance-linked triggers; MOU with EFI extends DFID support and influence across all FLEGT countries.
- Programme management: From April 2012-14 the programme was managed by an externally-appointed facilitator on a non-renewable two-year fixed term staff contract. The demands of a growing programme now require additional management inputs, and therefore a tender process to appoint an outsourced programme manager has been initiatied. This is in line with recommended management arrangements described in the programme Business Case. The tender for the supplier is being run outside of the Framework Agreement to maximise market access and value for money.

VfM performance compared to the original VfM proposition in the business case
The economic cost-benefit analysis in the original Business Case provides some time-weighted metrics that indicate the worth of the benefits from the programme relative to the money spent on it. The total incremental environmental, climate change and social benefits are estimated to have a benefit-cost ratio of up to 52:1. The discounted net present value of the additional forest revenue captured by exchequers in developing country forest nations is estimated at up to £13 billion, if illegally-logged timber is harvested legally, for an investment of £250 million. It is not possible to assess performance against this metric at this stage of the programme, however progress across contributing indicators are on track.

Assessment of whether the programme continues to represent VfM
Since the last annual review, FGMC delivery has moved towards a state of maturity with activities in train in all programme countries, and the grantee portfolio delivering and providing lesson learning. The programme is achieving good intermediate results and has the potential to offer value for money against the Business Case measures over its ten-year funding period and beyond. FGMC is also central to the delivery of the EU FLEGT Action Plan, leveraging inputs from other donors (e.g. DFID contribution to the total value of the Guyana contract is 12%) and coordinating efforts.

Quality of financial management
The time taken for tendering and procurement, and Memorandum of Understanding (MOU) and grant issuance, through in-house processes has led to a reduction of up to 15% in the forecast budget for the financial year relative to the original approved budget. More efficient contracting, and grant awarding and management by the outsourced supplier has the potential to bring the programme forecast budget back in line with the approved budget. All service providers and grantees have met financial reporting including audit requirements. Fiduciary risk is considered to be low. Although the programme works in a number of challenging countries, funds are managed by service providers with established track records, and robust corporate governance; or by grantees subject to prior due diligence assessments. All funds are subject to regular audit.

Date of last narrative financial report	Varies for each accountable grant, MOU and service contract
Date of last audited annual statement	Varies for each accountable grant, MOU and service contract

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk
FGMC is a large and innovative programme operating in some diverse political environments. To achieve programme objectives and to allow delivery through, and by, different partners and co-funders, FGMC currently operates 17 accountable grants, 4 Memoranda of Understanding, and 8 service and individual contracts. DFID has general programme oversight, and standard DFID procedures are used to manage generic delivery and fiduciary risks. Oversight and governance of grantees is supported through an annual conference, designed to share lessons and review the portfolio as a whole. The majority of service contracts with companies cover individual country/ regional delivery components in support of output 1, and are monitored individually. To strengthen oversight and monitoring, a number of field visits by DFID programme staff have been conducted, including in Liberia (multiple visits), Ghana, and China. Visits to DRC and Guyana, and a further visit to Liberia is planned.

The programme is growing in scale and complexity. Careful design and selection of outsourcing programme management arrangements will help strengthen both management and oversight across the entire portfolio of interventions

Key risks that may affect programme delivery, and mitigation measures, are as follows.
- Programme management strains as programme grows in size and complexity: DFID to conclude tender for outsourced management arrangements for future phase of the programme and establish strong performance management for this contract, alongside clear roles and responsibilities.
- Changes in the EU timber market: Continue to track timber patterns and ensure enforcement of partnership agreements. Strong enforcement of the EUTR will also assist in sharpening the demand for FLEGT licensed timber.
- Failure to enforce the EUTR: The programme will continue to invest in encouraging and supporting the strong and consistent enforcement of the EUTR across the EU.
- Country specific risks: Take action to mitigate risks to programme delivery from the effects of shifting goverance and political contexts, and from the impacts of conflicts and events on programme delivery. The outbreak of civil conflict in CAR and the Ebola epidemic in west Africa required operational adjustments in-year; and while activities have been postponed in Liberia due to Ebola, all 3 service providers are continue to operate remotely.

To strengthen focus on delivery by service providers, 5 of the 8 current service delivery contracts are paid on the basis of output milestones reached, rather than inputs. A 6th contract will move to output based payments by the end of 2014. The remaining 2 contracts, for West Africa VPA facilitation, and facilitation of UK/China collaboration on forest governance, necessarily need to be remain more flexible and responsive to changes in demand, and therefore remain input based. All grant payments are contingent on satisfactory quarterly progress reporting, with independent verification of effectiveness from FGMC’s monitoring and evaluation service providers. More than half of the grant recipients are paid in arrears; advance payment schedules for the remainder conform with DFID rules. For MOUs, output-based payment triggers are used where possible.

Outstanding actions from risk assessment: None, other than those outlined above.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe: Yes. Progress against logframe indicators is on track. Financially, despite some slippage due to delays (see earlier), FGMC is broadly on track against the budget forecast set out in the Business Case. The budget through to 2014-15 in the Business Case was forecast to be £60 million. In 2012 a £19 million budget uplift was requested to cope with increasing demand, bringing the total approved budget to 2014-15 to £79 million. This allowed DFID to enter into commitments to provide support to the countries where the UK is a lead donor, and to enter into related contracts for the provision of these services. By the end of the current FY the programme is forecast to have spent a total of £69 million. A combination of the longer than expected lead-times to establish grants and contracts – ensuring that value for money is secured through these – and in negotiating related cooperation agreements with partner goverments, has led to the downwards revision of the budget forecast from that anticipated in 2012. All service providers have been appointed in close cooperation with developing country government partners, helping to cement strong and positive working relationships, creating additional value for the programme.

Performance of partnership(s): Considered satisfactory, and actively managed. The nature of some partnerships will change once the outsourced programme management arrangements are in place. Maintaining effective partnerships will continue to be key role for the DFID lead adviser.

Asset monitoring and control: Non-disposable programme assets are generally low value. Management of these by grant recipients and service providers is considered satisfactory.

G: CONDITIONALITY (½ page)

Update on partnership principles: Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
A strong independent team has been appointed to monitor and evaluate the programme on a continuous basis. This is providing critical review and analysis of programme interventions; this year - through specific interviews, two bespoke surveys and seven country visits. The evidence base for assessing programme progress is strengthening as a result.

The independent review team in conducting their assessment of progress against logframe indicators for this Annual Review, concluded that the FGMC’s theory of change remained relevant within the changing programme context defined by a) the decrease in timber trade between producer countries and the EU, b) the growing importance of emerging markets in buying tropical timber, and c) the increase in other forest risk commodities such as palm oil driving deforestation.

Forthcoming reviews and evaluations scheduled for the second half of 2014 include: a) an evaluation of European Forestry Institute’s FLEGT Facility; b) EU Food and Agriculture Organisation’s FLEGT Programme’s mid-term review; and c) the Independent Commission for Aid Impact (ICAI) review of the International Climate Fund, which will capture FGMC. Three relevant reviews are planned for 2015: a) ,review of the EUTR,b) a review of the EU FLEGT Action Plan, and c) EU independent court of auditors review of EU FLEGT actions.

Monitoring progress throughout the review period
The independent monitoring team which supports the programme has interviewed stakeholders in the UK, other EU countries and in beneficiary countries. The team concluded from these interviews that the programme is highly valued by policy makers in partner countries and the EU, as well as by NGOs and the communities interviewed. Stakeholders widely recognise the importance of the programme in maintaining momentum on forest governance and market reforms.

DFID prepared this review based on input and analysis provided by the independent review team (ITAD and Triple Line Consulting Ltd). The review team undertook the following work: documentation review; two surveys; interviews with funded organisations, DFID staff and key informants; four country visits covering Indonesia, China, Guatemala and Vietnam; and a review of demand side measures as applied to the international trade in timber and other commodities.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process