Annual Review

Title: Global Open Data for Agriculture and Nutrition
Programme Value £ (full life): £4,780,000		Review Date: Review Date: 11/11/18
Programme Code: 203202	Start Date: 01/11/14	End Date: 31/10/19

Summary of Programme Performance
Year	2015	2016	2017	2018	2019
Programme Score	A	A+	A	A+
Risk Rating	M	Moderate	Moderate	Minor

DevTracker Link to Business Case:
DevTracker Link to Log frame:

A. Summary and Overview

Description of programme
The Global Open Data for Agriculture and Nutrition (GODAN) initiative is a partnership of national governments, non-governmental, international and private sector organisations that has committed to a joint vision to support the sharing of open data to make information about agriculture and nutrition available, accessible and easy to use to deal with the urgent challenges in agriculture and nutrition (see www.godan.info).
The UK is providing funding of up to £4.8 million over five years (November 2014-October 2019) in support of the GODAN initiative.

	2014/2015	2015/2016	2016/2017	2017/2018	2018/2019	2019/2020
Programmed Spend	£400,000	£520,000	£783,804	£1,165,450	£1,388,500	£522,246

GODAN was officially launched by the Secretary of State at the Open Government Partnership (OGP) Summit in October 2013. GODAN is jointly funded by the governments of the UK, Netherlands and the United States, the Centre for Agriculture and Biosciences International and the U.N. Food & Agriculture Organisation. The main activities of GODAN are:
1. To increase coordination, mapping, impact documentation, knowledge management and advocacy amongst agriculture/nutrition partners which are working on open data through the establishment of an Executive Secretariat (GODAN Secretariat). The secretariat is jointly funded by all the main partners;
2. To conduct research and capacity building projects (GODAN Action), funded through a specific UK contribution;
3. To conduct on-going monitoring and two independent evaluations which will allow for an independent assessment and will ensure lessons are learnt from the investments in GODAN.

Summary supporting narrative for the overall score in this review
Overall the Global Open Data for Agriculture and Nutrition (GODAN) programme is slightly exceeding expectations.
The GODAN has made good progress over the last year. In 2018, it has:
- Grown the GODAN partnership by 215 to 815. New partners are being added at a rate of around 11 a month and this is expected to continue.
- Contributed through talks and workshops at 14 events.
- Reached an estimated 9 million individuals through its website, social media platforms and media coverage.
- Produced nine policy-relevant papers.
- Built a map of standards, an online database capturing standards and vocabularies which are used in the exchange of agriculture and nutrition data.
- Performed three impact case studies on weather data.
- Created a wide range of training material such as
- Trained over 5000 people through online courses, webinars and face to face training.

Output	Output Title	Output Weight	Score	Risk
1	Mobilizing key actors to collaborate and commit to actions that will lead to a strengthening of the open agricultural and nutritional data ecosystem in developing countries.	35%	A++	Moderate
2	Collecting & compiling tools, stories, case studies, and papers that equip key actors to strengthen the open agricultural and nutritional data ecosystem in developing countries	20%	A	Minor
3	Improved standards and interoperability for open data for agriculture and nutrition.	15%	A	Minor
4	Impact evaluations and impact methodology	15%	A	Minor
5	Building capacity to use open data for agriculture and nutrition	15%	A++	Minor

Overall Output Score			A+	Minor

Recommendations for the year ahead

Summary of key recommendations for the remainder of the project
Output 2	The GODAN secretariat to keep DFID informed on development in hosting arrangements and potential funding models to inform action in 2019.
Output 2	The GODAN secretariat should translate more website material into French, Spanish and Arabic.
Output 2	The GODAN secretariat to explore whether partner profiles are leading to greater engagement.
Output 3	GODAN Action to provide a strategy for understanding how well these activities are working including developing a user survey which will then feed into a revised methodology for indicator 3.2.
Output 5	GODAN Action to track and improve understanding of the longer term impact of training.

## B: DETAILED OUTPUT SCORING

Output Title	Mobilizing key actors to collaborate and commit to actions that will lead to a strengthening of the open agricultural and nutritional data ecosystem in developing countries.
Output number per LF		1	Output Score	A++
Impact weighting (%):		35%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of major and other key agriculture and nutrition open data events organised or significantly contributed to by the GODAN secretariat.	10	14 events
1.2 Number of GODAN partners recruited	700	815 partners (215 new partners 2018)
1.3 Number of new products or services developed through agricultural/nutritional open data hackathons or innovation schemes.	2	9

Overall this output has exceeded expectations.
Indicator 1.1: This milestone was exceeded. In 2018 the GODAN Secretariat and GODAN Action organized or made substantial contributions to 14 events.
The major events were:
- GFIA, Utrecht (June 2018) and Abu Dhabi (February 2018);
- GODAN Rwanda High Level meeting (September 2018);
- International Open Data Conference 2018, Argentina (October 2018);
- IGF Conference, Geneva (December 2017);
- NNedPro Summit, Cambridge (July 2018);
- Ag-SUM Conference, Tokyo (June 2018);
- 2nd United Nations WTO World Conference on Smart Destinations, Spain (June 2018);
- United Nations World Challenge, Finland; including NASA (August 2018);
- RUFORUM 2018, Kampala (August 2018)
- CGIAR Platform for Big Data in Agriculture Convention (October, 2018);
- IGAD/RDA Conference, Berlin; (March 2018);
- Fourth IAALD Africa Conference, (May 2018);
- Digital Economy Forum, Vietnam (October 2018);
- ICT Agri Conference, Copenhagen (November 2017);
Participation in these events has strengthened the awareness and working knowledge of open data in the areas of agriculture and nutrition. For example, the RUFORUM 2018 event developed knowledge of open data for agriculture and nutrition amongst universities and learning institutions in East Africa. The Digital Economy Forum led to senior officials of the Vietnamese government requesting training for their ministry of agriculture and research establishments, so that they can understand the steps needed to develop an open data policy to assist agriculture and nutrition.

Indicator 1.2: This milestone was exceeded. The number of partners rose by 215 to 815, which is more than three times the original target for the lifetime of the initiative. New partners are being added at a rate of around 11 a month and this is expected to continue. This continued growth indicates the relevance of GODAN and suggests there is a growing demand for knowledge about open data for agriculture and nutrition. Africa is the region which now has the greatest number of partners (297) and the private sector has the greatest number of partners (270).
 Indicator 1.3: This milestone was exceeded.
The GODAN Secretariat sponsored and helped plan two major agricultural/nutritional open data hackathons. Firstly, the Freetown Student Entrepreneurship Competition Hackathon in Sierra Leone which had approximately 500 participants from Sierra Leone, the diaspora, and neighbouring countries. The event created three trial products related to agriculture. The winning and runner-up teams based their projects on: water use in regional farm support projects; use of geospatial information for weather reporting; and plant data for improved crop development
Secondly, GODAN was invited to host a webinar, with 23 researchers, on open data for the INSPIRE Hackathon at the INSPIRE Conference 2018 in Antwerpen. This helped in raising awareness and helping them prepare open data proposals.
GODAN Secretariat hosted the following seven webinars which had 1964 views, which can be viewed on: https://www.youtube.com/playlist?list=PLv8yRTnf9h7j-5SoKRs6lEsdI1EyzM8Cc

- Sharing open data and capacity development experiences from RCMRD (November 2017)
- Agri GEOSS GRSS soil moisture and agriculture support project (February 2018)
- How open data on land & property rights can inspire global food security & nutrition (April 2018)
- GEOGLAM - Improving the use of EO for agricultural monitoring (June 2018)
- Data interoperability: the land portal experience of open data management (July 2018)
- Agricultural development: Role of open data in ending poverty (August 2018)
- Farmers rights on data and ownership (September 2018)
Summary of responses to issues raised in previous annual reviews (where relevant)
The previous annual review recommended that “the GODAN secretariat should explore how to focus on deepening strategic relationships and report on this as part of their interim report on programme next steps by the end of January 2018”. The GODAN secretariat produced the GODAN 2.0 report on the 1st on February 2018 that explored how to focus strategic relationships. During 2018 GODAN secretariat deepened its strategic relationships with a total of 97 planned interactions with partners which helped to support open data policy-making, use of open data standards and regional initiatives.
For example, as a member of the Group on Earth Observations board, GODAN has been made a member of the Committee on Earth Observation Satellites, comprised of national space agencies. GODAN supports capacity building in the area of agricultural information dissemination and provides free and open tools to access open data, particularly for developing countries. Additionally, supporting working groups (WG) is a developing commitment which leverages greater engagement with partners. The working groups are made up of members drawn from the GODAN partnership and supported by the secretariat. This includes ongoing activities with: the Capacity Development WG; Food Systems Vocabulary WG; Inter-governmental African WG; GACS WG; Soil data WG; SDG2 Accountability Framework WG; Data rights & responsible data WG; Data ecosystem Working Group; GOFair Implementation Network Working Group.
Lessons identified this year, and recommendations for the year ahead linked to this output
- In order for organisations to implement open data policies they need to implement changes to their underlying digital systems, organisational processes and to change organisational culture. Therefore changing organisational open data policies is challenging and takes time.
- With over 800 partners the magnitude and diversity of needs cannot be maintained unless greater emphasis is placed on encouraging linkages between partners and a high commitment to self-help. This pathway necessitates growing support to working groups and strategic alliances who under their own initiatives implement practical goal orientated activities.
GODAN’s two-pronged strategy is working well as it allows them to focus more on depth and a small number of high impact initiatives alongside continuing to play a supporting role in building working groups and strategic alliances.
Recommendations
No recommendations

Output Title	Collecting & compiling tools, stories, case studies, and papers that equip key actors to strengthen the open agricultural and nutritional data ecosystem in developing countries
Output number per LF		2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Creating an effective repository of tools, stories, case studies and papers.	2nd phase of website incorporates partner profiles.	Partner profiles accessible, more relevant content, greater optimization between social media platforms drives readers to resources and engagement.
2.2 Number of advocacy focused policy-relevant papers produced or commissioned by the secretariat.	4 advocacy focused policy relevant papers commissioned	9 advocacy focused policy relevant papers commissioned and 1 reference in important policy influencing report
2.3 Communication and governance of the Secretariat.	Finalise governance structure of GODAN partnership	Business plan created / Hosting/funding process underway / Way Ahead process communicated

Overall this output met expectations
Indicator 2.1: This milestone was exceeded. The website has been redesigned to incorporate partners profiles and there have been upgrades to the backend of the service. This has resulted in:
- More effective links which are leading to greater engagement. With improved quality of content on the website, partners are viewing more often than they have done so previously. The relevance of content to partners has meant with a smaller number of articles and papers GODAN is receiving a higher number of views than in previous years.
- More traffic to GODAN’s social media platforms; and
- Increase in the number of event reports which has led to a higher level of interactions between partners, principally by enhancing the newsletter, but more broadly by increasingly effective linkages from Twitter, LinkedIn and Facebook.
During 2018 GODAN reached a large audience through several different channels.

GODAN Reach	November 2017 - October 2018
Twitter Reach (total number of people seeing content)	7,467,168
Twitter followers (unique individuals)	5,500
Facebook	95,942
LinkedIn	15,829
YouTube	12,800
Website	78,660
Website downloads	6,000
Media Coverage Reach	1,402,535

GODAN’s website has been accessed by users in every country in the world (195). The site has had around 80,000 visits this year, a 33% increase from the previous reporting period. Referral traffic is now the main driver to the website generating 60% of users. Social media reach: Facebook, 95,942 followers; Twitter, 7,467,168 follows/likes; LinkedIn, 15,829 individuals; YouTube, 12,800 views.
The Secretariat estimate that 55 GODAN-related stories were published in 2018 with a readership of 1.4 million. This is an increased readership on last year. Sample of articles: Tapping open data to boost agricultural productivity, Business Daily, May 2018; Could Open Data help Solve World Hunger? Forbes,June 2018; How will access to data boost agricultural productivity? Food Navigator, June 2018; New partnership to advance open data in Rwanda’s agricultural sector, New Times, Kigali September 2018
Indicator 2.2: This milestone was exceeded.
GODAN Secretariat has produced nine policy-relevant papers during 2018:
- Open Data and Open Access of PUSH Universities, May 2018.
- Big Data in Agriculture. IFPRI/CABI, November 2018.
- Open Up Guide for Agriculture, October 2018
- State of Open Data - Agriculture Sector (reviewed, and to be published December 2018)
- Promise and reality of Open Data for SDG2 (final draft completed)
- GODAN’s impact 2014-2018, Improving Agriculture, Food and Nutrition with Open Data, August 2018
- Recommendations for filling identified gaps: weather data, May 2018
- Digital & Data-Driven Agriculture: Harnessing the Power of Data for Smallholders, May 2018
- Global Agricultural Concept Space paper, Nature, August 2018 (commissioned by GODAN)
Indicator 2.3: This milestone was met.
The GODAN Secretariat produced the following documents:
- GODAN Steering Committee minutes – April 2018;
- GODAN 2.0 document, outlining strategy & presented to the Steering Committee, July 2018;
- Business Plan 2019 - 2022 presented to partners at the Road Ahead event, July 2018; and
- Request for Proposals, new hosting and funding document, September 2018.
These documents were uploaded to the website for broader distribution and access.
The GODAN steering committee met in April 2018. The focus was on the future of the GODAN secretariat and GODAN partnership and what the range of options were for continued action from 2020. The future options for the GODAN partnership have implications for the governance structure, so while the current steering committee was agreed, there is a need for continued discussion on this topic.
Summary of responses to issues raised in previous annual reviews (where relevant)

Lessons identified this year, and recommendations for the year ahead linked to this output
Social media is important to growing an effective and diverse partnership and building social media presence requires constant engagement. During 2018 GODAN showed a substantial increase in its social media presence which was made possible by using a strategic combination of social media channels. Facebook is driving engagement from Africa and LinkedIn is increasing connections to decision-makers. Adding keywords has attracted a growing level of policy-makers to the GODAN website. YouTube has become an effective repository of news events and presentations, receiving 12,800 views. There is a need in 2019 to cater for French, Spanish and Arabic on the website. The intention is to share resources in more languages.
Recommendation
Output 2	The GODAN secretariat to keep DFID informed on development in hosting arrangements and potential funding models to inform action in 2019.
	The GODAN secretariat should translate more website material into French, Spanish and Arabic.
	The GODAN secretariat to explore whether partner profiles are leading to greater engagement.

Output Title	Improved standards and interoperability for open data for agriculture and nutrition.
Output number per LF		3	Output Score	A
Impact weighting (%):		15%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Awareness of standards (Awareness that standards exist and acceptance that they are a good thing; Awareness of the specific standards relevant to the particular stakeholder.)	n/a	The map of existing vocabularies for the exchange of data in the field of food and agriculture contains: / 215 food & agriculture related / 65 geospatial/weather data and farm management related / 63 land & nutrition related / (399 data standards in total) / 3,775 users / 15,563 page views
3.2 Adoption of standards (discoverable through a global online map of standards) in general, and used in pilot interventions in particular	n/a	n/a

Overall this output has met expectations
In order to improve standards and interoperability for open data in agriculture, GODAN Action have been building a map of standards https://vest.agrisemantics.org/ , an online database capturing standards and vocabularies which are used in the exchange of agriculture and nutrition data. The purpose of the map is to help those working with open data in the agriculture and nutrition sectors to identify, use and improve existing data standards and to reduce duplication in the creation of new standards. In 2018, GODAN Action built on their 2017 work which focused on weather data by working on the land and nutrition issues. They made good progress on developing the map of standards and supporting the adoption of standards. However, being able to provide a monitoring strategy for understanding how well these activities are working should be a priority for 2019.
Indicator 3.1: The milestone was met.
GODAN Action have added a total of 399 standards added to the Map of Standards covering food, agriculture, weather, land and nutrition. GODAN Action have promoted the map, helpdesk and the importance of standardising data that is published, used and shared, through citations in partner products, presentations, blog posts and European and international open data initiatives. GODAN Action have attracted 3,775 users to the map to date.
Indicator 3.2:
GODAN Action have not developed a milestone for this indicator. This is because measuring the adoption of standards has not been possible so far. The key challenges are that data on adoption of standards is often not available and even when it is available it is hard to find, of variable quality and not documented. Accessing experts the experts who use food and agricultural data standards is also challenging. A survey of the users of the Helpdesk and the Map of Standards is intended for 2019 to provide an understanding of standard adoption. It should be noted that adoption of standards can take time, due to cultural and technical barriers, and is closely linked to capacity building.
However, GODAN Action have made good progress on achieving greater adoption of standards through supporting the use of those standards. GODAN Action have:
- Established an online helpdesk, intended to provide peer-peer technical support in using data standards to the 3775 users of the map of standards;
- Produced a gap analysis on the availability and use of data standards for land and nutrition data;
- Provided practical recommendations to data publishers, data users and standards developers to encourage the adoption of standards ; and
- Reviewed the barriers to the adoption of standards across weather, land and nutrition data to produce specifications for tools that will support the adoption of standards.
Summary of responses to issues raised in previous annual reviews (where relevant)
GODAN developed two new indicators in a response to a recommendation in last year’s annual review that they should “develop an appropriate indicator and method to measure output 3”. GODAN will conduct a survey of Helpdesk and Mapping Standards users to collect information on the impact of this work. This should also provide insights on how using standards will change behaviour.
Lessons identified this year, and recommendations for the year ahead linked to this output

Output 3	GODAN Action to provide a strategy for understanding how well these activities are working including developing a user survey which will then feed into a revised methodology for indicator 3.2.

Output Title	Impact case studies and impact methodology
Output number per LF		4	Output Score	A
Impact weighting (%):		15%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of impact case studies performed and documented (by GODAN Action for testing its impact evaluation framework, or by independent stakeholders/communities initiated/guided by GODAN Action)	3	3

Overall this output met expectations.
Indicator 4.1: The milestone was met.
GODAN Action has produced a review of the range of different approaches for understanding impact in open data projects and has developed a method for understanding the impact of open data projects in weather, nutrition and land data.
This impact methodology has been used to understand the impact in three case studies:
Weather data projects in Ethiopia, Bangladesh and the United States were analysed and their impact narratives were documented in this synthesis report:
- Ethiopia - The CommonSense initiative: use of weather data to provide farm management advice to Ethiopian smallholders
- Bangladesh - The GeoBIS initiative: use of weather data to provide weather information and farm management advice to smallholders in Bangladesh,
- National Oceanic and Atmospheric Administration (NOAA) – Opening up NOAA weather and climate data in the US.
The Ethiopia and Bangladesh cases describe interventions that still under development and that are typical for the conditions in a developing context. They show impact of weather data for agriculture in hybrid situations, where combinations of open and closed data are used. They also demonstrate typical barriers for achieving impact. The US case is well-developed, with clearly stated impacts among others in agriculture, and can be used as an example of how open weather data can benefit society and economy under good conditions, for example for advocacy purposes.

Summary of responses to issues raised in previous annual reviews (where relevant)

Lessons identified this year, and recommendations for the year ahead linked to this output
- Open data efforts do not seem to follow a clearly defined path aimed at achieving impact, and that generally no systematic monitoring of effects is in place. This reinforces the need for a clear common framework for understanding how impact is achieved through open data.
- Political economy is an important consideration for open data projects. This came out especially strongly in GODAN Action’s work on land and weather data.

Recommendations
No recommendations

Output Title	Building capacity to use open data for agriculture and nutrition
Output number per LF		5	Output Score	A++
Impact weighting (%):		15%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 Number of people - by gender and sector - that have benefited from the delivery of capacity development activities (including e.g. online, face-to-face,seminars, workshops))	200	5137
5.2 Media products: number of articles, booklets, brochures, videos and innovative training products developed as a result of capacity development activities (uploaded through the GODAN Action programme and the GODAN capacity development working group webpages)	20	65

Overall this output exceeded expectations.
The Land Portal Foundation is part of the GODAN Action consortium and their experience in working with local information providers determined that data management practices are generally poor and that a local level, there is little to no capacity, both in terms of financial- and human resources, to publish information or to publish in a way that allows for it to be discoverable online. Therefore the training approaches have focussed on addressing data sharing and publishing practices. The Global Nutrition Report (GNR) partners indicated that lack of capacity is an issue in the creation, curation, analysis, and interpretation of nutrition datasets.
Indicator 5.1: The milestone was met.
Capacity Development activities
1. Delivery of four Massive Open Online Courses for target user groups such as intermediaries, researchers and policy makers (3110 participants);
2. Delivery of face-to-face training at two key events (63 participants); and
3. Delivery of seven open data webinars to support the GODAN working group on Capacity Development (1964 views).
Massive Open Online Courses
Four Massive Open Online Courses were delivered between November 2017 and October 2018 with a total of 3110 participants from more than 115 countries. The participants are mostly from the nutrition sector (25%), with the land and weather following at 19% and 13% respectively. The majority of the participants (44%) are from other Agriculture related fields. The courses overall have seen representation of women at approximately 30%.

	Nov 2017	Apr 2018	June 2018	Oct 2018	Total
Weather Data participants	26	108	152	128	414	13%
Land Data participants	92	129	170	193	584	19%
Nutrition Data participants	80	192	249	253	774	25%
Other Agriculture related data participants	15	441	498	384	1338	43%
Total	213	870	1069	958	3110

Face-to-face workshops
Two face-to-face workshops were delivered:
Partnership for Action: Information Ecosystem for Land Governance Workshop 17-18 March 2018. Washington, D.C.
The feedback survey indicated that the workshop was well received. Even though the topic of open data at times still felt abstract to some of the participants, the role of data and the importance of open collaboration and clear communication and coordination between different initiatives became clearer.
Land Data and Managing Open Data Repositories Workshop 31 May 2018, South Africa
The workshop was a collaboration of GODAN Action and the Network of Excellence on Land Governance in Africa. The aim was to provide an understanding of the requirements of efficiently managing an open data repository including interoperability and data exchange. Twenty-one (21) infomediaries participated in the workshop with 47% of them being women. The participants were mostly land data professionals from countries in Southern Africa intending to establish or already working on a data repository from the region. Feedback showed that the workshop highlighted the importance and challenges when it comes to data licensing and copyright to the participants, especially with a controversial topic such as land data.
Open data webinars to support the GODAN working group on Capacity Development
The webinars have continued to be delivered for the wider agriculture open data community through the GODAN working group on Capacity Development between November 2017 and October 2018.
1	Sharing open data and capacity development experiences from RCMRD - 29/11/17
2	AfriGEOSS GRSS Soil Moisture and Agricultural Support Project - 08/02/2018
3	How open data on land and property rights can improve global food security and nutrition - 23/04/18
4	The Gender and Open Data Intersection - 16/05/18
5	Improving the use of EO for Agricultural Monitoring - 15/06/18
6	Agricultural Development: Role of Open Data in Ending Poverty - 22/08/18
7	Farmers rights on data and ownership issues 18/09/18

Overall the training interventions are well received. On average 95% of the respondents to evaluation surveys of the MOOCs indicate that the course content met their needs and expectations and more than 90% of respondents on average indicate that they would recommend this course to their colleagues.
Indicator 5.2: The milestone was met.
Sixty-five resources have been produced between November 2017 and October 2018 including:
- Online courses: Open Data Management in Agriculture and Nutrition
- Curriculum: Curriculum on open data and research data management in agriculture and nutrition
- Leaning note: Approaches to developing capacity for open data
- Webinar: Open Land Data
 The role of various partners’ networks, such as FAO’s AIMS, e-Agriculture, ICT4Ag, ODI Trainers Network, RDA and others has been significant in supporting the dissemination.
Summary of responses to issues raised in previous annual reviews (where relevant)
None.
Lessons identified this year, and recommendations for the year ahead linked to this output
None
Recommendations
Output 5	GODAN Action to track and improve understanding of the longer term impact of training.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change and any major changes in the past year
This programme aims to:
1. Mobilise key actors to collaborate and commit to actions that will lead to a strengthening of the open agricultural and nutritional data ecosystem in developing countries;
2. Collect and compile tools, stories, case studies, and papers that equip key actors to strengthen the open agricultural and nutritional data ecosystem in developing countries;
3. Improve standards and interoperability for open data for agriculture and nutrition.
4. Develop impact evaluations and impact methodology; and
5. Build capacity to use open data for agriculture and nutrition.

The main assumption is that key actors are able and willing to enact changes that will lead to a strengthening of the open agricultural and nutritional data ecosystem in developing countries. Potential risks include:
- Organisational unwillingness to be transparent due to fear of reputational risk;
- Organisational unwillingness to open data due to perceived loss of value or control;
- Organisational inability to open data due to lack of resources;
Addressing these risks is part of GODAN’s activities. Over the course of the last year it has become clearer that there is a real demand from organisations for openness but also that these organisations are struggling to enact the necessary changes.
Through these outputs this will help to achieve:
Outcome: An open agricultural and nutritional data ecosystem that facilitates increased supply and use of agricultural and nutritional open data for enhanced accountability and transparency, improved service delivery, innovation and economic growth.
Impact: More efficient, effective and sustainable use of agricultural and natural resources leading to enhanced economic growth and better nourished societies.
There have been no major changes to the theory of change in the past year.
Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
An open agricultural and nutritional data ecosystem that facilitates increased supply and use of agricultural and nutritional open data for enhanced accountability and transparency, improved service delivery, innovation and economic growth is more mature as a result of the outputs of the GODAN programme but there is still a long way to go. This is because changing organisational policies and upgrading their systems is challenging, takes time and is hard to monitor. It is linked to the broader challenge of digital transformation of organisations. Open data policies are often part of a suite of changes that are needed for organisations to change their digital and transparency strategies. Other major challenges include changing an organisations digital and data culture and their capacity to use data. It is also especially challenging in politically charged sectors like land data.
In order to respond to this challenge, GODAN should make sure that it is working on closer links with other organisations involved in the broader challenge of digital transformation and data for the global goals.
Describe any planned changes to the logframe as a result of this review
There are no planned changes to the logframe as a result of this review but the indicator methodology for indicator 3.2 will be developed as part of understanding the adoption and use of data standards (see recommendation 3).

## D: VALUE FOR MONEY
Assess VfM compared to the proposition in the Business Case, based on the past year
Key cost drivers and performance
The key cost drivers on the delivery of the project continue to be aligned with the following three funding components and related activities. Currently two programme components are being implemented; the GODAN secretariat and GODAN Action. Component three (independent evaluation) has yet to start.
Component one - £2,460,000 in support of establishment of an independent Executive Secretariat for GODAN. This contract was procured through a competitive process. The main cost drivers are staffing costs. Value for money is achieved through staff being funded by several other interested parties in addition to the funds being provided by the UK and US. The Government of the Netherlands pays for one secretariat member of staff. The Food and Agriculture Organisation provided a secondment of 50% of a member of staff for two years. The German Federal Ministry for Agriculture and Nutrition is funding a German researcher in the GODAN Secretariat for 3 years who will focus on responsible data use in agriculture and nutrition. In addition, Global Forum on Agricultural Research (GFAR), CABI, the CGIAR consortium, CTA and the Open Data Institute have all provided in kind support such as for office space, travel and event planning.
Component two - £2,080,000 in support of GODAN Action an agricultural/nutritional open data research and capacity-building project which is a UK-specific contribution to GODAN objectives. This is being funded solely by the UK government. The main cost drivers are staffing costs and expenses. Value for money is achieved through competitive tendering and expense claims are checked by DFID before being signed off.
Component three - £240,000 in support of procurement of two independent evaluations and other ongoing monitoring activities to allow for independent assessment and lesson-learning from GODAN funding investments. The main cost drivers here would be consultant’s fees and expenses. This is due to be commissioned in 2018/19 and will draw on experience from a DFID Research and Evidence Division Evaluation Adviser.
VfM performance compared to the original VfM proposition in the business case
Measuring value for money for Open Data is challenging, in part because a significant part of the value proposition is that anyone can then use that data for any purpose and because some of the benefits are qualitative in nature (e.g. the value of greater citizen engagement with government or value of data preservation).
Economy
- The business case was reviewed and approved by the UK Government Digital Service (GDS) and DFID’s DG Corporate Performance to ensure compliance with the Government design principles, use of AGILE[1] methodologies, to benchmark cost of salaries and capital investment and utilisation of previous infrastructural investments and to promote use of open source tools and software where feasible).
  [1] https://www.gov.uk/service-manual/agile
- Both the GODAN secretariat and GODAN Action went through competitive procurement process that was used to drive value for money and commercial advantage including negotiation on management overheads.
- Value for money will also be achieved through regular oversight meetings, DFID representation on the GODAN Secretariat Steering Committee, a break clause after the inception phase as well as an independent evaluation towards the end of year four.
Efficiency
- Both the GODAN secretariat and GODAN Action have been better able to perform the tasks of raising awareness, tackling key barriers and building capacity by being collaborative. Both work with a wide range of organisations and work well together allowing them both to draw on deeper well of experience and expertise and larger networks than otherwise possible.
- As mentioned in the key cost drivers section, the GODAN secretariat has as additional co-funders the Government of the Netherlands, the Food and Agriculture Organisation, the Global Forum on Agricultural Research (GFAR), CABI, the CGIAR consortium, CTA and the Open Data Institute.
Effectiveness
- There is a growing body of evidence that open data has a high rate of return[2]. Open data increases transparency and helps to reduce corruption, it can make public services and resource allocation more efficient, enable more informed decision making, fostering innovation and promote economic growth and job creation. In the agriculture and nutrition sector there are good examples of success e.g. using open data to help farmers secure better prices for their produce and level the playing field in price negotiations between farmers and buyers in Ghana.[3][4]
  [2] http://odimpact.org/
  [3] http://odimpact.org/case-ghanas-esoko.html
  [4] https://theodi.org/how-improve-agriculture-food-nutrition-open-data
- It is challenging to tell to what extent the GODAN programme is the right route to encourage this. The GODAN secretariat has created a GODAN partnership of over 800 partners. Even a small subset of these partners, if influenced by the work of the GODAN secretariat and GODAN Action to raise awareness and reduce key barriers, have the potential to make a very large difference to the open data ecosystem for agriculture and nutrition. Feedback from the second partner assessment survey suggests that these efforts are working e.g. the Nairobi Declaration, and GODAN has managed to reach over 9 million people through its website, social media platforms and media coverage. Both the GODAN secretariat and GODAN Action are working on improving the ability to measure the effectiveness of the programme.
International development organisations and national governments together spend billions of pounds on agriculture and nutrition projects. If improvements in open data can realise even a fraction of percentage point of efficiency gains through better coordination of funding, better access to data and better use of data then this will have paid for the investment in the GODAN programme.
Assessment of whether the programme continues to represent value for money
Yes it does. The theory of change and value for money presented in the GODAN business case still hold.
Quality of financial management
DFID funds for the GODAN Secretariat (component one) are being disbursed through a Delegated Cooperation Agreement (DCA) with the US government Department of Agriculture (USDA). USDA will ensure regular scrutiny of invoices and submit an annual financial statement as at 30 September confirming the DFID funds received and expended for the project, including any fund balance. This statement will be certified by the USDA financial office and submitted to DFID by the 31 March. They will also produce the annual USDA Agency Financial Report which will include an independent auditors report as at 30 September and likewise submit this to DFID by the 31 March.
Advice from DFID’s Risk and Control team has confirmed that no due diligence assessment is needed on the US government as the level of financial risk and fraud is low. However, the US government have conducted their own version of a due diligence assessment on the Secretariat prior to disbursement of funds to ensure they have sufficient financial controls and procedures in place.
For the Research and Capacity Building Programme (component two), funds are being disbursed through a direct Contract with a Supplier. Payments are linked to achievements of pre-agreed milestones.and expenses reports, as determined in the Contract. RED will approve and release payments in line with DFID requirements based on narrative progress reporting on evidence of achievement

Date of last narrative financial report	Last financial statement from USDA was received in March 2017 (relating to the period up to 30 September 2016). / The GODAN Action consortium have provided quarterly financial reports the next annual financial report is due in January 2018.
Date of last audited annual statement	Last audited report from USDA was received in March 2017 (relating to the period up to 30 September 2016).

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
The GODAN programme is producing valuable outputs that are contributing to improving the agriculture and nutrition data ecosystem. A healthy open data ecosystem is needed more than ever due to the increasing challenge of a growing digital and data ecosystem and of food security.

E: RISK
Overview of programme risk (noting the rating from p.1) and mitigation
Overall risk rating: Minor
Overview of programme risk
The main risk to the successful delivery of the programme is a risk that a lack of engagement amongst the global stakeholders who collect and use agricultural and nutrition data. This could happen because of broader political trends around agriculture, nutrition, transparency or data protection and could result in no improvement in the open agricultural and nutritional data ecosystem despite the efforts of the GODAN programme. This is mitigated through activities like the partner survey that enable better understanding of partner engagement. The second partner assessment showed that of the 193 organisations responding the following numbers were interested in applying open data for or in the context of: Advocacy (51); Capacity Building (64); Creating Data (46); Interoperability (32); Publishing data (66); Social change (20); Applications, Using Data (59); Research (67); Community development (46); and Policy (25). This suggests that there is an appetite to improve open data for agriculture and nutrition amongst global stakeholders. The partner survey continues to be refined to improve understanding of partner engagement and of the outcome level results of the GODAN programme.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Performance of partners and DFID, notably on commercial, and financial issues
Delivery against planned timeframe
Project delivery is on track with agreed timescales
Performance of partnership (s)
GODAN Secretariat (CABI)- component one
As a lead donor, we are satisfied with our overall level of dialogue and working relationship with our partner United States Department of Agriculture (USDA) on this project. UK funding is being disbursed through a Delegated Cooperation Agreement (DCA) with USDA.
We are also satisfied with the overall level of dialogue in the GODAN partnership steering group that consists of DFID, USDA, FAO, the Government of the Netherlands, the German government, GFAR, CABI and CTA. The steering group met in April 2018 and has strategic oversight of the Secretariat including both a supporting and challenge function. The proposed workplans of the Secretariat need to be approved by the Executive Committee on an annual basis.
GODAN Action – component two
DFID undertook a competitive procurement process, resulting in a contract with the GODAN Action (Joint Venture) consortium. This consortium consists of:
- Alterra;
- Agroknow;
- Land Portal;
- Open Data Institute; and
- Technical Centre for Agricultural and Rural Cooperation.
In addition, the consortium has been given consent to appoint the following sub-contractors:
- United Nations, Food and Agriculture Organisation;
- Institute of Development Studies; and
- AidData.
Oversight of the Programme will be as per standard DFID programme management processes. Funding will be on the basis of both milestones and expenses. A detailed annual technical and financial report is required as part of the reporting process. GODAN Action have met all their milestones to date.
Monitoring and Evaluation - component three
The independent evaluation will be procured centrally through a competitive procurement process, drawing upon the advice and appropriate instruments of PCD and RED’s Evaluation Advisor. Final payment will be dependent upon satisfactory and timely completion of the evaluations including relevant quality-assurance mechanisms.
To promote co-ordination and synergies between the first two components of the programme, there are regular conversations between the GODAN secretariat and GODAN Action as well as joint participation in key events and a coordinated approach to comms and research uptake.
Asset monitoring and control
As per its financial procedures, the GODAN Secretariat (CABI) maintains a physical inventory record of all fixed assets purchased by the Organisation.
CABI can confirm that no equipment with an individual value in excess of £1000 has been purchased using DFID funds.

Date of last narrative financial report(s)	The GODAN Action consortium have provided quarterly financial reports the last annual financial report was received in March 2018.
Date of last audited annual statement (s)	14 November 2018 https://www.usda.gov/sites/default/files/documents/usda-fy18-agency-financial-report.pdf

G: MONITORING, EVIDENCE & LEARNING
Evidence and Evaluation
DFID will centrally procure an independent evaluation for the Secretariat, and Research and Capacity Building components of the programme in FY 2018/19 which will be the penultimate year of operations for both component one and two. Retaining control of this budget line centrally will enable DFID to take advantage of in-house procurement and evaluation expertise to enable quality-assured products and will also allow for a degree of independent verification of findings reported by the Secretariat host and successful commercial bidder for the research and capacity-building programme. This budget line will also be used to enable DFID staff (Data for Development team) to participate in regular monitoring missions, including but not restricted to annual reviews and annual meetings of the Secretariat steering committee as well as travel costs to participate in other relevant lesson-learning events and workshops organised by GODAN stakeholders.
Women and Girls and the Digital Divide
The GODAN secretariat has developed a gender mainstreaming approach, clearly outlining an approach to reducing gender inequality, acknowledging gender-related differences in need. This includes CABI's Project and Programme Gender Strategy and CABI's Workplace Gender Strategy, as well as referencing specific elements of CTA’s Gender Strategy and DFID’s Business Case: UK Support to the ‘Global Open Data for Agriculture and Nutrition’ (GODAN) initiative.
The GODAN Summit attendees were 46% female (366 women and 426 men) and the panellists were 39% female (45 women and 71 men).
Four Massive Open Online Courses were delivered between November 2017 and October 2018 with a total of 3110 participants from more than 115 countries. The courses overall have seen representation of women at approximately 30%.

Monitoring progress throughout the review period
The review process was conducted by Seb Mhatre (Lead Adviser, Data for Development team) and was informed through regular communication with Steering Committee members, the GODAN secretariat and feedback from partners and other organisations.
Rachael Beaven (Senior Responsible Owner, DFID Senior Statistician)
This Annual Review was also informed by:
Meetings conducted between DFID and the GODAN Secretariat and GODAN Action during the year and the GODAN Secretariat and GODAN Action summary reports.

Learning
Through the GODAN programme we have learned more about the challenges of moving from knowledge to impact in the area of open data for agriculture and nutrition. However, the main thing that has been a need for further work to better understand how to translate awareness of open data, knowledge about available standards and how to measure impact and open data skills into large scale impact for agriculture and nutrition.