Business Case

Summary Sheet

Title: Business Partnerships for the Global Goals (BP4GG)
Programme Summary: / A programme working with and through multinational companies (MNCs) to support and de-risk core inclusive business initiatives (profitable activities in developing countries which benefit the poor).
Programme Value: £4,850,000		Country/ Region: DFID Priority Countries
Programme Code: 300805	Start Date: / 8 April 2019	End Date: / 31 March 2022
Overall programme risk rating:	Moderate
Vault Number:	47834065

Intervention Summary

Narrative summary of why UK support needed, what the funds will be spent on, where, over what period of time, via whom and what they will deliver

The UK will provide up to £4.85million over three years from April 2019 to March 2022 for the Business Partnerships for the Global Goals (BP4GG) programme. This programme will invest in partnerships with multinational companies (MNCs) to test and scale inclusive ‘shared-value’ business initiatives that support the achievement of the Global Goals.

What are the main programme activities?

The programme will have two components.

Component A will focus on building a network of responsible and inclusive businesses (20-50) and supporting up to 8 MNCs to test and scale inclusive business approaches that will – as part of DFID’s Great Partnerships approach- deliver results for the Global Goals. This component will be managed by an external supplier, procured through a competitive process.

Component B will provide targeted research and support to the design of a new larger Responsible and Inclusive Business programme. This component will be managed by DFID directly.

Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan?

The Business Partnerships for the Global Goals (BP4GG) programme contributes to the Promoting Global Prosperity and Tackling Extreme Poverty pillars of the 2015 UK Aid strategy and DFID’s Single Departmental Plan. This programme will contribute to the Economic Development Strategy’s ambitions to stimulate investment to spur economic growth in developing countries. It will help build opportunities for companies to enter and invest in markets of the future. Through innovation and new partnerships it can help harness new technologies for growth. It also maintains a focus on the poorest and most marginalised people- to improve their access to jobs and markets.

The Business Partnerships for the Global Goals (BP4GG) programme will collaborate with British and global businesses to build partnerships and innovations that can deliver Great Partnerships to achieve the Global Goals.

What percentage of DFID’s Single Departmental Plan results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?

Given the nature of the programme- the specific initiatives that will be supported under the programme are not yet known. However, we expect that they will help promote economic development and prosperity in the developing world by creating more or better jobs, increasing trading opportunities, and making it easier to channel private sector investment to the world’s poorest countries to help grow economies and eradicate extreme poverty. The programme will seek to link initiatives directly to Global Goal targets.

Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?

The Business Partnerships for the Global Goals (BP4GG) programme is consistent with the approach taken by other development partners. The OECD Donor Committee for Enterprise Development, Private Sector Engagement Working Group has been engaged in the thinking and design of this programme- and is available for collaboration, where appropriate. DFID will engage with country offices where proposed interventions may have local impact- ensuring that the approaches are consistent with country office private sector engagement strategies.

Has the programme considered working with HMG Departments and accessing cross-HMG funds?

Given the size and the timeframe of the programme, it will be managed by DFID only. However, there will be opportunities to share learning and build partnerships across government departments- notably through the Responsible Business Group being led by BEIS, DFID and DCMS to promote responsible and inclusive business.

As set out in the 2105 UK Aid Strategy, the BP4GG feeds into the Prosperity agenda, supporting new cross-government economic relationships with fast growing developing countries that use Official Development Assistance (ODA) to help build markets, create jobs and grow opportunities for trade and investment, including for UK companies.

How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?

This programme is part of a larger set of programmes and initiatives to promote more responsible and inclusive businesses and to encourage more informed investment choices that align investment and values (National Conversation). It is also part of DFID’s Great Partnerships initiative- to create more momentum and collaboration on the Global Goals.

DFID’s two flagship programmes on responsible and inclusive business - Responsible, Accountable, Transparent Enterprise programme (RATE) and the Business Innovation Facility (BIF) - are coming to a close in 2020. BP4GG will build on the lessons learned, to create a smooth transition to the next generation of central programming on responsible and inclusive business and to help build lasting and impactful Great Partnerships within the private sector.

It will have close coordination with the Growth and Resilience Department, notably as they build their ‘Gateway for Growth’ programme that is delivering on the prosperity agenda. It will also link with other programmes that work with companies- like the Work and Opportunities for Women (WOW) programme and the Partnerships for Forests (P4F) programme.

This programme is being managed by the Business Engagement Hub, within DFID’s Private Sector Department.

Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?

As a three-year programme, the programme will be implemented swiftly. It will build on the operational lessons and partnerships established under the Business Partnership Fund (with 10 active partnerships and an active pipeline of partners that were not funded under the BPF) and the Great Partnerships initiative. There is flexibility built into the programme to allow for it to respond to the needs of proposed partnerships and to build lessons into future programming.

Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?

This programme is building on the lessons learned from the Business Partnerships Fund (part of the Business Innovation Facility) and is therefore using tested approaches and operating models to working with the private sector. It is a moderate risked programme and fits well within DFID’s risk appetite.

Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not?

This programme will be an important element of the Great Partnerships campaign and will allow DFID to demonstrate a proactive approach to building collaborative partnerships with business to help increase business impact on the Global Goals. There will be a clear communication strategy, linked wherever possible to this campaign, with appropriate branding and outreach which will be set out in a DFID visibility statement.

Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?

This programme is building on the lessons learned from the Business Partnerships Fund (part of the Business Innovation Facility) – that has partnered with 10 companies across multiple geographies- and is therefore using tested approaches to working with the private sector. There are enough consultancy firms with the skills and the relationships to deliver this programme.

Does the SRO and team have the capability and resources to deliver this programme?

The SRO (Private Sector Advisor) and the Senior Programme Manager have been managing the Business Innovation Facility (BIF) and the Responsible, Accountable, Transparent Enterprise programme (RATE) has had experience designing and managing the Business Partnerships Fund (under the Business Innovation Facility) on which this programme has been modelled. In addition, the ongoing partnerships within the BIF and RATE programme provide access to relevant expertise and networks that will be required for the programme.
Strategic Case

Why we should intervene - Strategic fit

Across UK Government, there is clear recognition of both the contribution business can make in driving societal progress and the benefit of that contribution for business. This commitment is reflected across national and international platforms from the UK’s review of Social Impact Investing to international commitments made at the Addis Ababa Action Agenda. There is also growing interest amongst business in operating in a more inclusive and responsible way- as evidenced by the nearly 10,000 companies that have signed up to the UN Global Compact.
[note] https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/664321/Full_Report_Growing_a_Culture_of_Social_Impact_Investing_in_the_UK.pdf
[note] https://www.un.org/esa/ffd/wp-content/uploads/2015/08/AAAA_Outcome.pdf
The Sustainable Development Goals (SDGs), as a unifying agenda with universal credibility, provide a shared framework for sustainable development aspirations and have helped accelerate business awareness of issues relating to sustainable development and the challenges and opportunities they represent. For businesses, the SDGs can offer value in two key ways. First, as a brand to signal commitment to sustainable development, building reputational benefits and opening opportunities for collaboration. Second, as a strategic framework for future-proofing decisions against society’s expectations and ensuring enduring commercial success that accounts for both the risks and opportunities associated with sustainable development. However, only six percent of private businesses were found in a recent survey to be linking the SDGs to their core business models and 19 percent had no business activity linked to sustainable development.
[note] Deloitte (2018). UK Business and the SDGs. Landscape Report.- Summary. Phase 1.
[note] Deloitte (2018). UK Business and the SDGs. Landscape Report.- Summary. Phase 1.
There is an increased momentum around the Sustainable Development Goals, and the Great Partnerships required to deliver them- and an increased attention to the role of businesses as a key partner and catalyst. The Voluntary National Review of progress toward the SDGs (2019), is providing the UK with an opportunity to use evidence from across the UK (government, civil society and the private sector) together with data on the global indicators to take stock of UK progress on all 17 Goals, ahead of high-level events like the UN SDG summit or dialogue on Financing for Development. It is essential that the UK maintains a strong line of sight- and provides opportunities for direct engagement- with companies that can provide meaningful partnerships to help achieve the Global Goals.

Sustainable development unites aspects of responsible business, social impact, and inclusivity. Within DFID’s portfolio, there are a suite of programmes that are strengthening the impact that business can have on sustainable development. Through the Responsible Accountable and Transparent Enterprise (RATE) programme DFID has sought to drive changes to business behaviour by promoting responsible and sustainable business standards and expertise. The Impact Programme is DFID’s means of catalysing the market for more responsible and inclusive impact investment- rewarding companies that are proactively addressing the Global Goals. Company initiatives under the Business Partnership Fund (BPF), are driving commercially viable inclusive business models within MNCs. The BP4GG programme will build on the learning and relationships fostered by these programmes to increase the scale and impact of business activity and conduct on the SDGs.

The 10 matched grants under the BPF have facilitated partnerships with businesses already prioritising responsible and inclusive operational considerations as part of their DNA. These partnerships reinforce DFID messaging that responsible and inclusive business is more than small or one-off projects that create win-wins for business and society – it is the expansion of firms’ core-business in developing markets, embracing socially and environmentally positive conduct throughout supply chains. However, it is also important to effectively communicate widely to share lessons and incentivise companies that are having an impact on the Global Goals. BP4GG will support external communication to empower customers, investors and other businesses with resources about successful businesses that are having a positive impact on the Global Goals.

The BPF has also facilitated new partnerships with companies who are not prioritising responsible and inclusive operations. This is enabling DFID to push underperformers to improve and invest in business growth that can impact on the SDGs. To encourage scale and timely engagement, BP4GG will focus on building partnerships with companies with demonstrated commitment to responsible and inclusive business- and with clear intentions to have a positive impact on the Global Goals.

Building on the evidence and experience from the RATE and BPF programmes, there is a need for catalytic support to enable and encourage companies to test and scale innovative business models- and for DFID to maintain strong partnerships with the private sector. Through the BPF, DFID has supported focused research by leading advisory firms on the constraints and opportunities to increasing inclusive business models.

Multinational Corporations’ Journey to Inclusive Business: by Hystra and drawn from its experience working directly with MNCs. / Identifies the steps MNCs can take to increase their chances of creating and bringing to scale inclusive businesses with sustainable impact. It is based on the analysis of the ‘first wave’ of activity by MNCs, over the last decade, to set up and scale inclusive business.
Inclusive Business – Make or Buy: Corporate Impact Venturing at the Base of the Pyramid: by Endeva and drawn from insights gathered from interviews conducted with eleven companies, four investees and nine experts / Outlines the reasons why companies should consider buying inclusive businesses externally as an alternative to building them internally.
Improving Inclusive Business Management Practices in Corporations: by Business Call to Action and UNDP and drawn from a decade of experience engaging with companies implementing IB across sizes, sectors and regions. It includes insights from the latest State of IB Survey and interviews with executives from over 20 corporations / Analyses constraints within MNCs that are preventing the uptake and internalisation of inclusive business models and presents what it means to develop and tailor management practices to inclusive business, why it is important for the success of the inclusive business and how companies can improve and become leaders.
The intrapreneurship ecosystem: Creating the conditions for social innovation to flourish in your company: by Business Fights Poverty and League of Intrapreneurs and based on insights and information gathered from global workshops, online learning sprints and interviews with dozens of intrapreneurs, leaders and subject matter experts. / Provides a framework for understanding the “Intrapreneurship Ecosystem” – the complex set of processes, practices, resources and relationships which collectively serve to facilitate or inhibit intrapreneurship and social innovation.
Reimagining Inclusive Business: by Accenture Development Partnership and based on a wide-ranging literature review, interviews with 30+ experts in business, finance, policy-making and academia and on a new evidence base of 300+ inclusive business examples. / Illustrates how the basic “meaning” of inclusive business has been transformed over the past decade – and why an increasingly diverse range of profitable new models and opportunities is opening up for companies in almost every industry as we move into the 2020s.

The evidence demonstrates that for successful inclusive business models to achieve scale, external support can help to overcome a range of obstacles. This may include:
- identifying and understanding inclusive business opportunities (in new and untested markets)
- facilitating networks and linkages between companies and external stakeholders (i.e. NGOs, policy makers, specialist expertise, local companies)
- sharing risk when testing, refining and scaling new business models
- supporting innovation through new technologies and platforms
- fostering leadership and learning amongst inclusive businesses

A key lesson from BPF and from the evidence is the importance of a longer-term time horizon and the ability to provide strategic, targeted support.

Through RATE, DFID has been supporting a range of partners that have been at the forefront of testing approaches that encourage companies to adhere to high standards of responsible business practice and to map their impact on the Global Goals. Through DFID support to initiatives like UN Global Compact, B-Lab, Global Reporting Initiative, World Benchmarking Alliance, Ethical Trading Initiative, Shift, Humanity United, Fairtrade Foundation, British Academy and ISEAL Alliance- DFID has access to a strong network of progressive and impactful businesses. Through these partners, DFID also has access to a wide range of expertise that can help businesses drive change.

Both RATE and BPF are ending in 2019-2020, and a follow-on programme will be developed that will work with businesses, investors and other partners to scale up inclusive and responsible business models that will have a direct impact on achieving the Global Goals. It is important to ensure that follow-on programming is well-grounded in the current context, builds on strong evidence of what works to support inclusive and responsible business and is informed by a diverse set of stakeholders.

The Business Partnerships for the Global Goals will allow DFID to maintain the momentum of the Great Partnerships by providing a direct offer to companies that are committed to delivering the Global Goals, and by preparing to deliver a larger impactful programme that can drive results on responsible and inclusive business.

Objectives

The objectives of the Business Partnerships for the Global Goals programme are to:
- Identify a cohort of at least 20 progressive MNCs, that are committed to investing in products and business models to achieve the Global Goals.
- Leverage the reach and technology of at least 8 MNCs to develop, test and scale inclusive business models that will have a direct impact on achieving the Global Goals.
- Apply the lessons from DFID’s Impact Management Programme and RATE to test and scale tools to measure the impact that inclusive business models can have on the Global Goals.
- Apply the lessons learned from RATE, BPF and the Business Partnerships for the Global Goals programme into the design of a new integrated responsible and inclusive business programme.

Delivery Approach
The programme will be largely implemented through an implementing partner that will identify a potential cohort of MNCs through an objective process- valuing companies’ commitment and investment in the Global Goals. Experience from the ongoing Business Partnerships Fund and RATE will strongly inform the design of the delivery model. The programme will provide technical assistance (TA) and/or grants to selected MNCs to generate and grow shared value and inclusive business initiatives. It will also support independent impact measurement and analysis to build the evidence base on why and how businesses can deliver for the Global Goals.
The programme will be implemented in 3 years, but it is expected that the Great Partnerships developed through this programme will be continued through a larger follow-on programme on responsible and inclusive business (that will be designed through Component B). In this way, the results will be staged so that there will be tangible results and impact within the 3 years of the programme, and potential for continued scale through follow on programming.
Impact
The impact of the programme will be:
- At least 4 business models that are tested through the programme are proven to be viable and taken to scale within the MNCs- reaching at least 20,000 people with improved services, products and opportunities. These direct results will be measured in terms of the Global Goals- but we are unable to identify these yet.
- At least 10 of the MNC partners have made public commitments to improve their performance on the Global Goals- and to measure their results using common methodologies.
Geography
The programme will seek to work with businesses whose supply chains and distribution channels operate within DFID priority countries and regions- with a focus on Asia (Southeast and South) and Africa. DFID’s strategy for working with multinationals is to seek opportunities for scale and for influencing markets with evidence that inclusive and responsible business models are viable and profitable- and improving the lives of poor men and women.
Theory of Change

Responsible Business (Environment and Social Safeguards)
The programme will be working with established companies that adhere to a high standard of environmental and social safeguards. Where possible, partner companies will be encouraged to become B Corp or sign up to the UN Global Compact to demonstrate their commitment to key principles of responsible business. As part of the due diligence for participation, DFID will ensure that companies have high standards for workers’ rights, environmental standards and gender equality. DFID will actively seek to work with companies that have progressive and inclusive policies that include opportunities for people with disabilities.

All companies that work with the programme will be briefed on the DFID safeguarding policy and will demonstrate and report on compliance.

Gender and Inequality and Public Sector Equality Duty

We have considered how Business Partnerships for the Global Goals will contribute to DFID’s strategic vision for girls and women as well as inequality.
To promote gender and address inequality, the programme will include ‘Gender’ and ‘Equity’ selection criteria to assess and incentivise how each proposal will impact on women and how it will address inequality. It will also ensure that results metrics used, measure (to the extent possible) equity of benefit for these groups. The programme will seek to filter out (at an early stage) any activities that might increase or entrench existing inequalities and/or actively discriminate against any groups with protected characteristics.
Aid Diversion
There is a minor risk of UK aid funds being diverted through fraud, bribery, corruption or to terrorist organisations. We will follow DFID rules and procedures to ensure UK aid is used for its intended purpose. However, as we seek to scale-up our work in more fragile and conflict affected regions, this means we are working in areas where monitoring that DFID funds are used for their intended purpose which increases the risk that they could be diverted. Contracts will be designed to allocate risks away from DFID, with Implementing Partner assuming risk and liability for fraud, corruption or misuse of programme funds, with all payments made in arrears once activities have been delivered. The programme Implementer will complete a robust due diligence on downstream partners, and ensure they are aware of their responsibilities in relation to anti-corruption and counter-terrorism legislation. We will ensure that all project partners are aware that they must immediately report any suspicions of fraud, terrorism financing, money laundering, bribery or corruption to the BEH team and through the appropriate DFID channels.

## Appraisal Case

Emerging evidence suggest that companies are aware of the opportunities that emerging markets offer but often lack the understanding of these markets or feel that the associated risks are too high. Experience from DFID’s Business Partnerships Fund has demonstrated that relatively small amounts of development funding can unlock shared value opportunities and help MNCs progress them through the company’s own internal decision-making process, which can be a significant barrier. In designing the programme, it is important to find the right strategic entry point where DFID resources can be catalytic to allow companies to do business in a way that will deliver the Global Goals.
[note] The Business Innovation Facility commissioned five papers to better understand the challenges and opportunities for inclusive business. See page 6 for summary.
[note] In just under 3 years, through 10 partners, the Business Partnerships Fund will aim to reach over 350,000 people with new products and services. The BPF focused largely on proof of concept and pilot projects, so it is expected that more mature models can achieve significant scale with the right support.

Design Options

To achieve the desired results, there are three options that have been considered and reviewed for their effectiveness. These are described below.

Option 1 - Do nothing now and focus on a bigger programme: This option suggests that DFID resources should be focused primarily on developing a new and ambitious long-term programme, with a significantly larger budget, delivering both inclusive business and responsible business objectives. This option is concerned that even a small programme comes with significant transaction costs, and that attention may be diverted from the larger objective.

Option 2 – Invest in existing organisations that are supporting inclusive business: There are a range of organisations and multilateral/donor supported initiatives that promote inclusive and responsible business (i.e. UN Global Compact, Business Partnerships Facility (Luxembourg), Labs of Tomorrow (GIZ), B-Labs). This option would involve investing in an existing initiative, to expand reach and depth of ongoing partnerships. DFID could influence the activities to encourage greater innovation and focus on impact measurement.

Option 3- Invest in a time-bound standalone programme, with an eye towards new programme development: This option would allow DFID to continue to have an active programme engaging directly with MNCs, building relationships and testing inclusive business models. It would also build the evidence and relationships to build a new, large-scale programme.

Options Analysis

To assess these options, we have 3 key criteria to consider.

Direct impact: To demonstrate the proof of concept, it is important that the programme deliver tangible results within the companies.

Relationship Building and support to new programming: the investment should contribute to DFID’s direct relationships with MNC partners with an eye to developing longer term partnerships.

Value for Money and Effective Delivery: It is critical that the selected approach maximizes value for money and utilizes a delivery model that is effective and efficient.

Options Analysis	Option 1 - Do nothing now and focus on a bigger programme	Option 2 – Invest in existing organisations	Option 3: Invest in a time-bound standalone programme, with an eye towards new programme development
Direct impact	Weak	Moderate	Strong
Relationship Building and support to new programming	Weak	Moderate	Strong
Value for Money and Effective Delivery	NA	Moderate	Moderate

Based on the above analysis, the team proposes to select Option 3 to Invest in a time-bound standalone programme, with an eye towards new programme development. This option maximizes the direct impact, and the quality of the relationships and pipeline development. If managed strategically, it can deliver value for money by focusing investment in areas that are most strategic for DFID’s interests.

Delivery Model

The proposed programme provides (i) a short-term strategic investment that will continue the established momentum from the Business Partnerships Fund, while (ii) investing in the design process for a new and ambitious programme on responsible and inclusive business. Therefore, it is critical that the delivery model retain a simple structure and enough flexibility to be able to respond effectively to programme needs.

In the interest in time and to promote value for money, the delivery model proposed takes a Business Partnerships Model rather than a Challenge Fund model. This builds on the experience from the Business Partnerships Fund (in operation since 2016), the Responsible, Accountable Transparent Enterprise (RATE, since 2014) and Work and Opportunities for Women (WOW, since 2014).

From the Business Partnership Fund and RATE- the programme will build on:
- An extensive pipeline of over 80 business partners, plus strong networks of responsible businesses
- A robust Operations Manual for selecting and contracting with private sector partners
- A group of experienced inclusive business advisory partners (including Endeva, Accenture Development Partners, Business Fights Poverty, Hystra, Business Calls to Action)
- Relationships with over 13 BPF partners, actively testing innovations in the responsible business space
- The Impact Management Programme has developed tools on impact measurement that can be tested within this programme

There are four windows to the program:

Business Partnerships for the Global Goals windows	Delivery Model	Scale of programme
Component A has three windows that will support up to 8 multinational companies to test and scale inclusive business approaches that will deliver results for the Global Goals. This component will be managed by an external supplier, procured through a competitive process.
A1: Building a community and support network for 20-30 responsible and inclusive businesses (Great Partnerships)	Technical Assistance to convene and vet potential business partnerships. / Deployed through a supplier with strong relationships with multinational companies.	20%
A2: Supporting 5-8 inclusive business models	Business Partnerships providing technical assistance and matching grants to support inclusive business models to achieve SDG impacts - focusing on achieving scale and/or deploying innovation. / Deployed through a supplier with strong relationships with multinational companies.	50%
A3: Evidence on inclusive business models	Technical Assistance to test and implement tools (in collaboration with the Impact Management Programme) to measure the impact that inclusive business models can have on the Global Goals. External communications about successful business models. / Deployed through a supplier with strong measurement capabilities.	10%
Component B will provide targeted research and support to the design of a new larger Responsible and Inclusive Business programme. This component will be managed by DFID directly.
B1: Design inputs for a new integrated responsible and inclusive business programme.	Research inputs and consultations to provide inputs into the design for a new integrated responsible and inclusive business programme. / Deployed through DFID team.	20%

Structure of providing support to companies
Within DFID’s private sector portfolio, we deploy a range of financial instruments when working with the private sector. When working with multinationals- it is particularly important to ensure that support is structured in such a way as to adhere to ODA eligibility rules, to be targeted at a lasting market failure, to maximise systemic and transformational impact on the market, to be additional and to leverage resources from the partner company.
Eligibility Criteria
To receive support under the Inclusive Business window, proposals would need to meet the following eligibility criteria:
Demonstrate impact on the Global Goals: Provides feasible theory of change that links proposed inclusive business models to a specific (or multiple) Global Goal. Includes a method for measuring impact.

Poverty reduction impact: Supports poor people with: raised incomes; more/ better/ safer jobs; gender equality – empowering women and girls; welfare enhancing goods or services; positive environmental impact; climate change mitigation and adaptation; benefits for the very poor, excluded or marginal populations; or improving access to basic goods and services in very difficult/most challenging markets.

Commercial viability, commitment and “scalability”: Activity has potential for growth as part of MNC’s core business. An activity is considered to be core business if it is self-financing i.e. that it does not require external subsidy to continue operating or expanding. The MNC will need to provide at least 50% of the cost of the initiative to demonstrate corporate buy in.

Additionality: Activity would not occur without DFID support - at all, as fast, or with as much benefit for the poor.

Time-frame: Given the limited timeframe of the programme, it is expected that initiatives will be able to demonstrate a clear path to scale- and to demonstrate how 18 months of support can help build an initiative, test it or scale it effectively. The programme will accept initiatives at varying stages of development but will need to have a clear measurable path to scale.

Value for Money
A supplier (commercial consultancy) with strong relationships with MNCs is the most suitable to delivering the objectives of this business case. A consultancy company is more likely to have the necessary skills in-house to understand the business environment in DFID priority countries, a set of existing corporate contacts likely to be actively developing inclusive business projects and an internal structure which has experience of negotiating the necessary third-party arrangements with partners. DFID will use a competitive process to find an organisation with suitable expertise and drive value for money.

Commercial Case

Component A of the programme will be delivered through one contract, with a lead Implementing Partner to bring together a team that can undertake all the interventions identified under that window of the programme (Building a support network for Inclusive and Responsible Business, Managing the Grant Fund for Inclusive Business models and Evidence and Programme Learning. Combining these functions offers the advantages of maximising synergies between the Components and lowering the management costs to DFID. Component B (Design support for a new DFID programme) will be delivered mainly by the Business Engagement Hub (BEH) team. This option is slightly more complex operationally; however it gives more flexibility to identify what support is needed for the development of the new programme, the tasks to be undertaken/information gaps which must be filled and the specialist partners able to deliver them.

The Component A contract will be tendered through an OJEU competition to a third-party supplier. We will use the new Specialist Economic Development Framework using Method 2: Mini Competition applicable to the appropriate specialist Lots [1 - 10 under the Framework]. The SEDF is expected to be operational in April 2019, and we will work with PCD to take the programme through the tendering process as soon as it is in place.

Commercial Advisors and Procurement and Commercial Department (PCD) have been consulted. Terms of reference will be written and an invitation to tender process initiated.

As part of the tender proposal we would expect the Implementing Partner will identify:
- a Monitoring, Evaluation and Learning provider
- an advisory group (made up of experts and thought leaders in the inclusive business field)
(See the management case for more information on the purpose and approach for these tasks.)

Due diligence on the implementing partner should have been undertaken by PCD as part of the SEDF procurement process. Due diligence, based on DFID’s standard due diligence guidance, will be conducted by the implementing partner on each project collaborator receiving DFID funds.

As the value of this supplier contract is likely to be approximately £4million, Ministerial approval will be required (mandatory for all contracts over £1million). We will consult with the relevant Ministerial Private Office to give advance notice of the detail of the contract. The BEH team and PCD will draft the Ministerial submission in the appropriate format.

Component B activities to assist PSD in the development in the design of a new programme will be arranged via framework contracts, mini-tenders, small value contracts or, if appropriate, Accountable Grants with not for profit organisation. These low value arrangements will either be sourced directly by the DFID Inclusive Business Team or, if more appropriate, through the Implementing Partners for Component A. For all these activities, separate Terms of Reference/project proposals will be developed, negotiated (to achieve value for money) and mobilised as appropriate.

Key features of procurement process

For Component A, we will explore to what extent the service provider’s contract can include performance-based milestones. These will be negotiated and agreed with the supplier during post-tender clarifications or inception phase. We expect that payments made to MNCs via match-funded Grants, under Component A.2, would be performance based, with payments being made, in arrears, once delivery milestones had been completed.

All procurements under direct procurement will include DFID standard terms and conditions and bespoke conditions to safeguard key risks and assumptions, including:
- Political and context risks: suppliers will be required to demonstrate ability to adapt programme plans to rapidly changing events in countries
- Duty of care for suppliers in country
- Fiduciary risks: contracts will be designed to allocate risks away from DFID, with suppliers assuming risk and liability for fraud, corruption or misuse of programme funds. Due Diligence Assessments on the suppliers selected for the programme will be carried out by PCD as part of the OJEU process
- Termination clauses, ensuring flexibility to close the programme in case of a change in priorities, changes in country context where the programme is operating and underperformance issues.

Proposed Timeline for Procurement Process

The procurement process is planned to start at the beginning of June 2019 and ideally have the contract signed by September 2019.

Financial Case

How much the Business Partnerships for the Global Goals programme will cost?

We are seeking approval for a budget of up to £4.85m, of which £4.05m is for Component A (to test and scale inclusive business approaches) and £0.8m is for Component B (Design inputs). We anticipate some flexibility on the exact breakdown, e.g. it would be beneficial if unallocated budget under Component B could be used to support additional opportunities within Component A. The overall cost and timing of the programme will depend on the commercial bids we receive from the Implementing Partner, however, a tentative budget breakdown might be as follows:

Programme Budget (£m)	Total	2019/20	2020/21	2021/22
Component A
A.1 Building a support network for IB/RB	0.80	0.30	0.40	0.10
A.2 Programme TA and Grant Fund	2.10	0.00	0.75	1.35
A.3 Programme Learning and Evidence	0.40	0.00	0.20	0.20
A.4 Managements Costs	0.75	0.25	0.25	0.25
Component B
B.1 Design support for a new IB/RB prog	0.80	0.10	0.30	0.40
Total Programme Costs	4.85	0.65	1.90	2.30

Experience from the BIF pilot, BPF and TRANSFORM programme has shown that co-creation of projects is a very effective method of designing company initiatives. The A.1 spending line under this programme we will seek to build a community of practice of responsible and inclusive businesses through which we could co-design initiatives. The BEH team working jointly with the MNC partner, with support from the Implementing partner, would develop and agree the objectives of the initiatives, the means of achieving them and how to measure results. A majority of the costs for the co-design of initiatives will take place during the early stages of the programme.

The Implementing partner will engage a small advisory group - firstly to assess the merit of company concepts and their contribution towards poverty reduction and relevant SDGs, and secondly to assist the co-creation of initiatives. Costs for this group will be covered under the support network budget line.

The A.2 spending line, technical assistance and matching grants funding, will be used to provide support for the inclusive business models and initiatives developed through A.1 activities. The balance of technical assistance and grant finance will need to be decided on a case by case basis depending on the requirements of the individual MNC initiative.

Assuming a funding level of between £250,00 and £400,000 for each project, a Grant Fund of £2.1 million would be enough to support between 5 and 8 MNC company initiatives. We would expect at least 50% match funding from the corporate partners which would generate a project portfolio value of over £4.2 million. Payments under these grants will be made in arrears on a milestone basis, with the delivery of agreed time bound activities triggering a payment. All grant payments are likely to be made during years two and three of the programme.

The following is an example of the delivery chain map for an initiative under Component A.2.

The Implementing partner will recruit a team of monitoring and evaluation specialists to capture and disseminate the learning from across the programme (spending line A.3). This would include activities to test and implement tools to measure the impact that inclusive business models deliver under A2.

Based on similar grant funding mechanisms (WOW and BPF) we have estimated a programme administration fee of 18.5%. The level of effort of the Implementing Partner is likely to be greater in the early stages of the programme as delivery processes are established and initial outreach to partners to scope opportunities takes place. However, we expect the cost expenditures under spending line A.4 to be equally spread across the lifetime of the programme.

As mentioned above, in Component B we will seek to use a series of small value arrangements to assess the development landscape as it relates to Inclusive Business, Responsible Business and Impact Investing which will assist PSD in the design of new programming in this space. These interventions will take place over the lifetime of the programme.

For Component A, an annual budget will be agreed with then Implementing Partner at the outset of the project and thereafter annually at the beginning of each financial year. These annual budgets will be broken down into monthly forecasts. These amounts will form the basis for DFID’s Aries forecasting for this programme. The Implementing Partner will update these forecasts each month. The Programme Manager will track forecasting accuracy over the financial year to help improve financial monitoring over the project lifetime.

Payments to the Implementing Partner will be made monthly in arrears and will include any VAT that is applicable to their invoices.

Component B will follow a similar process, however as activities are likely to be over shorter timescales either with one or more specific deliverables, they might lend themselves more to payment by results against agreed milestones.

Management Case

What are the Management Arrangements for implementing the intervention?

The diagram below illustrates the governance and management arrangements for the programme.

The BEH team within Private Sector Department’s Business Engagement Hub will be responsible for the overall management and day-to-day oversight of the programme, this will include direct management of:

- The Implementing Partner (Component A)
- Organisations that will help support a deeper understanding of a Responsible and Inclusive Business approach by MNCs in order to help design a new programme (Component B)

Given the wide-reaching nature of Component B, a wider team will be established bringing colleagues from DFID’s impact investing, responsible business and mobilisation teams.

Component A: The SRO will be responsible for managing the relationship with the Implementing Partner, project design, logframe changes, etc. The programme manager will be responsible for approvals for staffing, financial management, including updating forecasts, paying invoices and monitoring spending.

The Programme Delivery Plan will capture the main aspects of day to day implementation of the BP4GG (Programme delivery dates and milestones, Roles and responsibilities of Partners, Risks etc.)

The detailed governance arrangements for the BP4GG programme under Component A will be determined as part of the scope of work proposed in the invitation to tender document. These arrangements will be formalised during a 3-month inception phase. This would include the establishment of a Steering Committee (consisting of 3-5 senior representatives of international development, private sector and/or academics organisations) to provide oversight and strategic advice. At least one member of the Steering Committee should represent the impact investment perspective.

A key feature of the programme will be the co-creation of initiatives. Interested MNCs will approach the Implementing Partner with a concept that will be put before the Steering Committee for a prompt approve/decline decision based on the eligibility criteria (see page 11) and a recommendation as to whether to advance the project proposal to the design phase. For successful concepts, the BEH team (bringing in DFID Country Offices as necessary) would work with the MNC partner, with support from the Implementing partner and members of the Steering Committee, to develop the initiative and agree the objectives, the means of achieving them and how to measure results.

This should generate initiatives which deliver stronger developmental results as well fostering a closer relationship between DFID and MNCs. MNCs may wish to bring a trusted facilitator or delivery agent (who are familiar with the intersection of business and development) into these discussions.

Component B: The SRO will identify the research inputs and consultations needed to provide inputs into the design for a new integrated responsible and inclusive business programme. Each of these will be tasks will managed directly by the BEH team, with strong engagement from across DFID and other government departments- where relevant.

Project timeline

The key design, mobilisation and implementation milestones of the programme are detailed in the table below.

Monitoring and evaluation

Monitoring, evaluation and learning is important to help build the evidence base for this and future programming. The Implementing Partner will ensure that the programme has sufficient monitoring, evaluation and learning capabilities.

M&E activities include:
1. understanding what type of results each individual project will deliver and what metrics could be used to collect them, possibly using MNCs own management information systems and other reporting processes;
2. setting baselines, developing milestones and targets;
3. ensuring that the aggregated results match expectations and the programme delivers evidence outlined in its objectives;
4. assessing the effectiveness of partners and their interventions; and
5. producing and disseminating learning to improve the performance of future programmes.

Annual reviews for the programme will be carried out by DFID. We will aim to commission these from Advisors external to the programme to provide an independent view.

Risk Management Plan

The overall residual risk of not achieving the outcome is assessed as Moderate. Fiduciary risk is assessed as minor, while reputational risk is moderate due to the way that the programme will engage with progressive and pioneering MNCs. We will ensure that the BP4GG maintains a strong value for money rationale by ensuring that all activities receive match funding from the MNC and their partners.

We have identified 9 potential risks. These gross risks (before mitigation measures are put in place) have been plotted below in a standard 5x5 risk map.

Almost certain
Likely			E1: MNC caution about moving into FCAS
Possible			D2: Substitution - business activities would take place anyway / D5: Programme benefits do not reach the poorest	D1: Insufficient suitable MNC inclusive business proposals / D3: Sustainability - pilots do not lead to uptake or roll out by corporate partners	O1: PSD lacks the staff resource to deliver
Unlikely			D4: Results cannot be delivered within the project timeline / S1: Safeguarding issues	R1: Reputational risks involved in partnering with private sector partners
Rare
	Insignificant	Minor	Moderate	Major	Severe

We will design and put in place mitigating actions to be taken by DFID and the Implementing Partner to reduce the probability and/or impact of each risk. Mitigating actions will be implemented as part of the project Delivery Plan and will be updated and reported on quarterly. Initial consideration of these risks and suggested mitigating actions are summarised at Annex 1.

Annex 1	Business Partnerships for the Global Goals - Initial Risk register

Risk	Gross Risk	Mitigating Action	Residual Risk	Owner
Category: External Context
E.1 MNCs caution (lack of senior buy-in) about moving into BP4GG focus countries (particularly FCAS)	Likely/Moderate	Build strong relationships at beginning of interventions. DFID sharing the risk in the early stages to help make the business case. / Build political analysis into project proposals. Select an Implementing Partner that has local representation and can work with the local politics. Spread portfolio risk and use an adaptive approach	Possible/Moderate	SRO
Category: Delivery
D.1 Insufficient suitable MNC inclusive business proposals	Possible/Major	Early market engagement / Engage an Implementing Partner with existing strong relationships with MNCs likely to submit proposals Build on existing DFID relationships / Regular monitoring of the proposal pipeline.	Unlikely/Moderate	SRO
D.2 Substitution - Programme interventions are not additional. BP4GG supports activities that corporate partners would have undertaken anyway	Possible/Moderate	Criteria for selecting programme interventions developed and refined to avoid duplication and to ensure additionality. Select interventions that have clear learning and demonstration effects that corporates by themselves would not be incentivised to undertake.	Unlikely/Minor	SRO
D.3 Sustainability - initiatives do not lead to uptake or roll out by corporate partners	Possible/Major	MNCs must present a clear route to scale in their initial proposals to meet eligibility criteria / Co-design process to emphasise the importance of sustainability / DFID to maintain close dialogue with MNC partners throughout the delivery phase	Unlikely/Moderate	SRO
D.4 Results cannot be delivered within the project timeline	Unlikely/Moderate	Early market engagement / DFID/Implementing Partner should be clear with MNC partners about timing constraints at the outset / Maintain close dialogue with partners to ensure initiatives move through the pipeline swiftly / swiftly	Unlikely/Moderate	SRO
D.5 Working through MNC initiatives does not reach the poorest people	Possible /Moderate	Careful scoping to identify best opportunities / Work with business partners to identify beneficiaries in lower paid and vulnerable roles, and opportunities for others to join supply chains who are not already engaged	Unlikely/Moderate	Implementing Partner
Category: Safeguarding
S.1 Risk of inappropriate behaviour by programme partners or unintended negative consequences of initiatives on programme beneficiaries e.g. harassment, gender-based violence	Unlikely/Moderate	Thorough due diligence and delivery chain mapping of programme partners. / Design of interventions to identify potential negative consequences for people who share a protected characteristic (under the 2010 Equality Act) and mitigate against them. / Monitor to identify and mitigate negative consequences of programme activities on employees. Work with MNCs and local partners to engage with all employees, suppliers or stakeholders to ensure understanding of programme objectives and wider economic benefits.	Rare/Moderate	Lead Supplier
Category: Operational
O.1 DFID lacks admin and FLD resources to manage the programme effectively	Possible/Severe	Team SRO and programme management resources currently dedicated to BP4GG operations. / Maintain flexibility in view of competing demands and external pressures on staff time. / Prepare for a smooth re-introduction of staff resources / Streamlined/prioritise contracting and operational arrangements with Implementing Partner to ensure minimal demand on DFID staff time.	Possible/Moderate	BEH Team Leader
Category: Reputational
R.1 Programme works with businesses that are not compliant with environmental, social or human rights standards, including Modern Slavery Act	Unlikely/Major	Draw on existing DFID corporate partnerships. / Thorough due diligence on MNC partners to identify potential reputational risks prior to starting work together. / Ensure Implementing Partner and MNCs are aware of DFID’s requirements for partners to adhere to an accepted level of ESG standards. / Prepare defensive lines on common areas of concern questioning	Unlikely/Moderate	SRO