Programme Completion Report - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	02/06/2015

Title: The Global Legal Empowerment Initiative
Programme Code: 202186	Start Date: June 2011	End Date: March 2015

Summary of Programme Performance

Year	2011	2012	2013	2014
Programme Score	A	A	A	A+
Risk Rating	Medium	Medium	Medium	Medium

Financial Position

Original Programme Value	£500,000
Extensions/ amendments	The business case was amended to reflect a funding uplift of £1,500,000 over two years. The overall programme budget is £2,000,000 over three years June 2011-March 2015.
Log-frame revisions (with dates)	November 2012 / August 2014
Total programme spend	£2,000,000

Follow up actions required following closure

The Conflict Humanitarian And Security Emergency (CHASE) has ceased funding Namati due to pressure on CHASE programme funds and subsequent portfolio reorganisation. Based on Namati’s strong performance against DFID’s strategic objectives, DFID will continue nonetheless to support Namati over the next two years through a joint accountable grant from GOSAC and GRD. The funding will go towards building the evidence base for legal empowerment mechanisms and securing land and natural resource rights (for vulnerable groups, whether male or female) and how legal empowerment mechanisms make a difference for women and girls.

Going forward, it is vital that the Security and Justice team in CHASE retains strong linkages with Namati’s learning and advocacy efforts, to inform DFID’s policy and programmes on legal empowerment and access to justice. The intention is to build on the successes of programming achieved through GOSAC and GRD joint funding (see ICAI S&J review), to strengthen the evidence base and to coordinate with other donors, potentially as part of the post-2015 framework. The impact on the ground and knowledge generated by Namati will be central to this workstream. It is envisaged that some limited advisory time will be dedicated to a cross-DFID steering group led by GRD and GOSAC as the future institutional leads for Namati relationship.

 As follow up actions after closure of this programme, it is crucial that the S&J team continue to draw on Namati’s work. For example:

As an ally in promoting access to justice in the implementation of a future Sustainable Development Goal (SDG) framework
- To inform learning on community justice approaches and mechanisms as part of the S&J learning and evidence strategy.
- Through funding from other parts of DFID (such as GOSAC or GRD) there could be potential scope to work with Namati to implement legal empowerment approaches in DFID coutry programmes.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202186/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202186/documents/

Outline of programme and what it has achieved

The original DFID business case[1] for the Global Legal Empowerment Initiative (GLEI) stated that the impact of GLEI would be “greater and more effective legal empowerment programming worldwide, on the part of donors, national governments and civil society. This will help determine whether legal empowerment should become part of the toolkit for development”. Delivered in partnership with the Open Society Foundatons, a key achievement of GLEI has been the establishment of Namati, www.namati.org, a global organisation dedicated to putting the law in people’s hands, with a particular focus on paralegals. This review focuses on the performance of GLEI over the lifetime of the programme from 2011-2015
[1] The original Business Case committed to an initial review after Year 1 in terms of progress with establishing an independent organisation. The Business Case was revised in 2012 to recommend shifting funding from Open Society Foundations to a direct Accountable Grant to Namati, which had been assessed as a fully independent and functioning entity.
Namati has completed ground-breaking research, built a network of over 400 organizations and developed its own innovative projects in eight countries, aimed at improving access to justice, healthcare, land rights and citizenship rights. Namati works with local partners on the design, technical support and evaluation of projects which are implemented primarily by partners themselves, with varying levels of input by Namati. As well as helping resolve thousands of cases, either directly or through partners, Namati has used the data collected on cases to advocate for systemic reforms.
GLEI first received funding in 2012, in 2013 Namati was set up as an independent entity and received DFID funding through an accountable grant.  Since 2012 through to 31 March 2015 Namati has received $9,653,051.03 in funding.  Of this amount $2,398,771.00 was from DFID, which represents 24.8% of funding over the life of the programme (unril March 2015). The rest of funds were provided by a number of other organisations[2].
[2] American Jewish World Service, Humanity United, Open Society Foundation, Oxfam, Tetratech, UNDP, Echo Street, and additional funding from private individuals.

During the course of the programme Namati has achieved substantial results, often exceeding their targets and milestones within a short space of time. After the first year of GLEI, Namati became independent from OSF, and quickly set up and operationalised a number of innovative demonstration projects in eight developing countries. Namati has used the evidence from the demonstration projects to extrapolate and aggregate results at the global level, providing a rich evidence base to scale up large scale national legal reforms and promote legal empowerment. Namati has also developed a worldwide grass roots network of paralegals and justice organisations, creating the biggest global movement to foster dialogue and promote best practice around legal empowerment. Using evidence of impact, Namati has contributed to policy changes and generated strong demand for legal empowerment approaches at the local and central government levels in a variety of country contexts.
Over the past three years, Namati’s programming has made a positive impact on poor people’s lives through direct provision of advice and systemic changes in the implementation of the law, as demonstrated through progress on Outputs 1 and 2, and towards Outcome Indicators 1 and 2. Advocacy (Output 3, Outcome Indicator 3) has also been effective at national and international level in creating new policy frameworks and legal changes which promote access to justice for the poor. Namati has succeeded in demonstrating the value of legal empowerment for the post-2015 development framework through campaigns, grassroots partner participation and concrete evidence. The evidence in the 2014 Annual Review and feedback from external stakeholders[3] confirm Namati’s status as a leading and unique global organisation making a significant contribution to establishing legal empowerment as an integral component of the development landscape. This PCR draws significantly from the Annual Review completed in January 2015, with additional reporting from the Quarterly report January-March 2015.
[3] A list of organisations and individuals who provided feedback can be found in annex 1.

In summary;
With the help of DFID’s grant, Namati can demonstrate impacts at numerous levels and for a wide range of stakeholders:
- Citizens have directly benefited from legal advice and basic legal services to resolve numerous justice problems, whether related to human rights, land rights or social service accountability.
- Robust evidence of how paralegals can address failures in the rule of law and achieve positive outcomes for poor and marginalized groups has been developed and shared across the globe.
- Legal empowerment practitioners have become more effective through the use of evidence and data and international exchange of best practice.
- National policy changes have steered the law and its implementation towards the poor.
- Access to justice and legal empowerment have been recognised as key to delivering the development results intended in the MDGs and in the future post-2015 development framework.

Outline of the programme

Legal empowerment approaches use the law to benefit the poor. They involve community-based justice services, such as paralegals, alternative dispute mechanisms and street and mobile courts. These efforts tend to be accessible and accepted in communities and respond to the needs of the poor and vulnerable. They can assist people in protecting their rights, pursuing their economic interests and demanding accountable and responsive governance from public institutions.

In recognition that more could be done to know whether, when and how legal empowerment approaches work for the poor, the Global Legal Empowerment Initiative (GLEI) was established in 2011 bringing together a number of agencies, including Open Society Foundation (OSF), DFID, AusAid, World Bank and UNDP, to take forward the movement on legal empowerment by building evidence of what works, a community of practice, and a body of interested donors. OSF and DFID have been the principal partners and funders of GLEI. The International Advisory Council of the Global Legal Empowerment Initiative is also influential, with Amartya Sen, George Soros, James Wolfensohn, Fazle Abed sitting as advisers on the board. Key achievements of the GLEI overall are:

- the establishment of Namati, the first global organisation on legal empowerment;
- effective advocacy for the inclusion of access to justice and legal empowerment in the post-2015 development framework;
- a stronger evidence base, including the first-ever global review on the impact of legal empowerment;
- an informal policy collaborative of interested donors and foundations, to promote coordination and information sharing on legal empowerment.[4]
  [4] The collaborative has met five times since the start of GLEI.

DFID’s support to GLEI has actively promoted DFID’s wider work on the rule of law and security and justice and fits with several commitments set out in DFID Business Plan 2011-15. DFID’s growing programme experience in countries such as Malawi, Nepal and Bangladesh suggests that legal empowerment initiatives can produce significant development benefits, which were highlighted and lauded in the recent ICAI review. GLEI was endorsed by the previous Secretary of State in several meetings with George Soros. It has led to a strong institutional relationship with OSF on justice and legal empowerment, helping to advocate for their inclusion in the post 2015 development framework, a crucial part of the UK Prime Minister’s vision on the golden thread. OSF-DFID collaboration on justice is an integral part of a broader strategic partnership between OSF and DFID.
This PCR focuses on both the initial funding arrangement set up between DFID and OSF in 2011 and the Accountable Grant awarded directly to Namati since 2012, as part of the Global Legal Empowerment Initiative. Namati is an independent organisation established in the first year of GLEI and initially housed in Open Society Justice Initiative (OSJI). DFID funding for Year 1 (2011-2012, £500,000) of GLEI was granted to OSJI, alongside their own contribution ($1m per annum) and smaller grants from AusAid, UNDP and World Bank. Once Namati gained its status as an independent not-for-profit organisation, the remaining grant (£1.5m, 2012-2015) was granted directly to Namati. GLEI continues to exist as it includes the wider international policy work lead by OSJI and DFID (e.g. the policy collaborative).
Namati is the first and only global organisation dedicated to putting the law in people’s hands. Namati aims to build the field of legal empowerment, and in particular paralegals, into an evidence-based, well-financed sector, with the reach and scope to solve critical justice problems, thereby helping communities to fight poverty and achieve sustainable development outcomes. Their approach to legal empowerment is a people-centred, problem driven iterative approach, working with local partners and communities to understand how to adapt solutions according to local context. Namati works in three primary ways, which are reflected in the Outcomes and Outputs for the programme:

Outcome: Greater and more effective legal empowerment programming and policies worldwide.

Output 1: Innovation: Design, testing, and demonstration of what is possible in the field of legal empowerment through programming activities.

Output 2: Network: Developing a robust, networked, growing community of legal practitioners activelyengaged in sharing best practices and advocating for justice.

Output 3: Policy change: High-impact policy successes at the national and global level.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

Throughout the life of the programme Namati has significantly contributed to the aim of fostering greater and more effective legal empowerment programming and policies worldwide.
Namati’s success has been galvanized through the following channels:
Innovation: Design, testing, and demonstration of what is possible in the field of legal empowerment through programming activities.

Namati works with local partner grassroots organizations to demonstrate how paralegals (or grassroots legal advocates) can provide broad reaching access to justice and generate results on pressing justice issues: protecting natural resource rights, ensuring that healthcare services are accountable to local communities, and securing citizenship rights. Namati evaluates and documents all of its grassroots efforts, publishing both impact studies and practical guidance for practitioners, so that these demonstration projects inform development and legal empowerment practice worldwide.

For example, in Sierra Leone, Namati has successfully demonstrated the impact that a fully scaled-up generalist paralegal program (surpassing 40% coverage of the entire population) can have within an ineffective justice system. Namati has resolved over 13,000 disputes and grievances. At a higher level Namati participated in discussions with the leadership of the Legislative Committee of the Sierra Leonean Parliament to discuss a new strategy for amending the Criminal Procedure Bill.

To broaden the scope for paralegal application to a diverse range of development related settings, Namati has also tested the potential for paralegals to make a substantial impact through sector-specific focus. For example:

Developing a health advocate program that has proven successful at resolving critical service delivery failures within the health system in Mozambique which has led to 574 grievances of which 84% have been resolved

A unique community land protection methodology, which has achieved substantial impact in Uganda, Mozambique, and Liberia. It demonstrates the importance of community governance to sustainable and gender-balanced stewardship of land.
More recent tangible evidence of Namati’s impact at the community level and on the lives of the poor includes:
A letter written to the Timis Mining Company on behalf of the Manonjoh Village threatening legal action in response to the recent flooding of the village. As of February 2015, Timis has removed the water and is now discussing compensation for the community.

"Focusing on front line legal assistance and recognizing that there are billion[s of] people in the world who do not have access to the law, [Namati’s] approach struck the board as hugely important and also new and very likely to spread broadly.” [One board member called it] “the “best law-for-all program I’ve seen”; [another called it] “brilliant.” The Board of Ashoka[5], Innovators for the Public.
[5] Ashoka is a foundation promoting social entrepreneurship worldwide.

Outcome Indicator 1: No. of justice problems for which a legal empowerment solution is shown to be effective. Target 2014 – 35. Actual 2015– 60 (cumulative).

Network: Developing a robust, networked, growing community of legal practitioners actively engaged in sharing best practices and advocating for justice.
Namati hosts a network of over 559 legal empowerment organizations (415 are officially registered and 144 in the directory backlog) and towards the end of the grant has amassed the support of 2000 individuals spanning every region of the globe. Since the latest Annual review in January, 200 new people have registered online to the Namati website. Network members both shape and have access to tools, resources, guidelines, innovations, and best practices. Namati also produces research on legal empowerment approaches, other than paralegals.
Namati has worked with the network to create an identity and vision for legal empowerment. The network is a key source of ideas for the innovations Namati and its partners undertake. It is also a vehicle for taking those innovations to scale, and will feature substantially in Namati’s work going forward.
Through the incorporation of paralegal methodologies and programming guidance based on best practice, Namati is helping organizations to have a greater impact on resolving justice problems worldwide. Examples include:

Informal fishermen’s associations in India, whose livelihoods are threatened by industrial development that violates environmental regulations. After working and learning from Namati’s paralegals, these groups are now writing letters, leveraging right to information laws, and sending applications to government departments in search of remedies.

“When I was just another fisherman, I tried approaching the local authorities for an official allocation of land for boat mooring, but got nowhere. The difference Namati’s paralegal model has made is that it has shown me a way through Indian bureaucracy. I have learned that multiple administrative routes can be tried while a result is awaited from one particular body. It creates pressure on an institution to respond if it knows that other institutions are aware of the case. The paralegal’s dogged approach also keeps the case alive.” - Shakir Bhai, Paralegal, Okha Port, Jamnagar District, Gujarat, India.

- In Myanmar, Namati has worked with Civil and Political Rights Campaign Group to add a paralegal component to CPRCG’s land and environment work, which now includes a paralegal training program as well as supervision and data collection systems. This addition has greatly improved the efficacy of the group’s efforts to help small-hold farmers protect their lands.
- In Mozambique, upon request from Médecins Sans Frontières (MSF), Namati has begun to integrate health-oriented paralegals into MSF clinics in Maputo, and is developing a new paralegal supervision tool for MSF clinics across the country.

Outcome Indicator 2: No. of documented examples of organizations in the network improving their work based on learning from Namati and/or other network members. Target 2014 – 40. Actual 2015 – 38 (cumulative). Note:In the first quarter of 2015, Namati completed an evaluation involving semi-structured interviews with members of the Global Legal Empowerment Network from 10 countries in Asia, Africa and the Middle East. Respondents were asked about the impact of the Network's capacity-building initiatives and their potential future needs. Overall, Network members were positive about their experiences, citing numerous benefits and actions arising from network membership. These include: expansion of regional networks and useful continued connections with practitioners in other countries; specific resources downloaded and shared with their colleagues and partners; drafting of national documents based on collaboration at regional meetings; and sustained interest in new learning exchanges, resources, and opportunities.

Policy change: High-impact policy successes at the national and global level.

Aggregating data from expansive grassroots efforts has allowed Namati to advocate for systemic, large-scale reforms both nationally and globally. This work has demonstrated that not only can paralegals help bring the law to life, their work can also lead to positive changes in the law itself, and in the institutions through which the law is implemented. Namati also collaborates with network members to advocate for global policies that advance legal empowerment. In total, 82 of Namati’s 114 policy recommendations have been adopted: 31 have been formally adopted into policy and 51 have been adopted into the draft policy awaiting formal passage.  Key country-level successes include a national land policy in Liberia that embraces the community land protection model developed by Namati and partners, and a legal aid law in Sierra Leone that recognizes the role of community paralegals.

On the international policy front, Namati’s targeted engagement with key actors - from leading grassroots groups such as Kituo Cha Sheria (Kenya) and the Alternative Law Groups (Philippines) to an array of high level leaders, including UN delegates and the President of the General Assembly - has been instrumental in ensuring that access to justice appears in the current proposals for the post-2015 development agenda, including the High Level Panel report , the UN Open Working Group’s final Outcome Document, and the Secretary General’s synthesis report.

Outcome Indicator 3: No. of policy changes that are adopted based on advocacy by Namati and network members. Target 2014 - 40. Actual 2015 – 80 (cumulative)

Output Score and Description

A+, Namati’s performance on the outputs has exceeded expectations.

Lessons and how these have been shared

Data: Rigorous data collection is crucial for translating grassroots experience into large-scale policy change. In Mozambique, the Annual Review monitoring trip verified Namati’s robust approach to data collection. They have collaborated with paralegals to simplify and standardise the capture of key data collection such as demographic data, institutions involved in case work and positive resolutions. Namati is sharing these lessons across the global network, and discussing with donors about exploring how the use of technology can help with data collection and analysis at a large scale.

Specialist paralegals: Namati began its work with holistic paralegals. Over time, Namati has recognised the value of paralegals with specialised expertise in key justice challenges – for instance, citizenship rights, health rights, and land or natural resource rights. In developing and testing the specialised paralegal approach, Namati has learned that:

1. Paralegals who have specialist knowledge are likely to generate faster results on difficult issues and be able to better educate beneficiaries of specific issues. This was verified during the monitoring visit, when Namati held a workshop in Maputo with health paralegals to learn about common challenges and solutions. Similarly, in Inhambane, paralegals with technical knowledge on agriculture and land rights were able to manage land related issues and gain the trust of communities quickly; and
2. By demonstrating sector-specific legal empowerment results, Namati can attract financing and recognition from sector-specific funding streams. For example, in Mozambique, Namati is in discussions with major healthcare agencies interested in the potential for paralegals to ensure that health services are accountable to local communities. In Sierra Leone, Namati advocated for a provision, now included in the draft national land law, which requires firms interested in large-scale land acquisitions to contribute to a basket fund to support legal representation via paralegals for land-owning communities.

These lessons will be taken forward through DFID’s new grant to Namati’s land work.

Equal partnership: Namati maximises its local partnerships with grassroots organisations working on legal empowerment, and this was verified by the AR monitoring trip. In Inhambane, Namati partners with Centro Terra Viva (CTV) to deliver the land rights programme. Namati gives organisations such as CTV the space to challenge and propose new ideas, ensuring that legal empowerment approaches are culturally sensitive and aligned to local values.

Legal aspects: It was observed by DFID Mozambique that there are other organisations using similar methods to Namati on empowerment and accountability. Namati will need to demonstrate more effectively in the next phase how legal empowerment is distinct from social accountability methods, and the value it adds in terms of impact and engagement with legal and judicial frameworks and institutions.

Political economy: Namati’s work is by its nature political and comes up against the imbalances of power. These cannot always be changed, and any change takes a long time. Namati recognises that there are bound to be failures and their approach is to constantly test new ways to achieve success in a culturally sensitive and sustainable manner. The most consistent results are then aggregated to the national and international level for policy and advocacy to promote legal empowerment.

Local governance: There is a potential gap between policy making at the local level and implementation at the provincial/district level. Namati are working with local communities and influencing national processes, but should consider whether/how to engage more at the intermediate level with provincial/district level authorities, in countries where they can act as a catalyst to implement legal empowerment approaches.

Staffing: Recruiting, mentoring, and retaining outstanding staff has been critical to Namati’s success in these early years. However, being a small organization without dedicated HR/recruitment personnel has also posed challenges to timely recruitment, leading to some key vacancies persisting (e.g. Director of Impact position). Namati is looking to address this, resources permitting.

Donor interest: Namati has worked hard to attract funding from other donors and foundations, and has been relatively successful, with grants from Wellspring Advisers, IDRC and UNDP amongst others. However, it is still very reliant on the grants from OSF and DFID. Future financing from OSF has been agreed, including a commitment to match-fund further grants. The lack of interest is echoed in the slow progress with the GLEI policy collaborative. Major donors in the legal empowerment field appear to have limited appetite for international cooperation. It may also be because donors have been unable to fund an active secretariat for the collaborative. There are some promising avenues through foundations such as Omidyar and bilaterals such as SIDA. The recent joint funding from GRD and GOSAC in DFID demonstrates a strong appetite across other sectors within DFID such as land rights and governance and the rule of law.

Recommendation 1: GLEI’s original ambition of growing the field of legal empowerment to make it a key approach to development requires the interest and engagement of donors to ensure update of the new evidence and increased programming. This cannot be fulfilled by Namati alone. In order to be successful, the next phase of GLEI will demand continued effort by DFID (GOSAC and GRD) and Open Society Foundation (OSF) to consolidate a group of interested donors, alongside funding for Namati.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Grassroots legal empowerment methods are developed to address major rule of law challenges
Output number per LF		1	Output Score	A++
Risk:		High	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 # of justice problems for which a legal empowerment approach is developed and tested	2012 – 8 / 2013 – 31 / 2014 - 62	Target 2014 – 55 / Actual 2015 – 78
1.2 # of people served by grassroots legal advocates	2012 – 14,529 / 2013 – 27,809 / 2014 – 53,161	Target 2014 – 45,000 / Actual 2015 – 58,892
1.3 # of publications (practitioners’ guides, impact evaluations, web-based tool kits, videos, case studies, audio programmes, legal literacy materials) developed to share methodological lessons that emerge from those programmes.	2012 – 2 / 2013 – 12 / 2014 – 37	Target 2014 – 25 / Actual 2015 - 41

Performance in this output significantly exceeded expectations.

Key Points A core component of Namati’s work is testing and demonstrating the impact that paralegals can have on addressing justice problems in a range of contexts. Namati works with local partner organizations in eight countries to demonstrate how paralegals can provide grassroots justice services at scale, as well as impact three of the most pressing global justice issues: protecting natural resource rights in the context of the global land rush, ensuring that healthcare services are accountable to communities, and securing citizenship rights for stateless people.
Examples under Output Indicator 1.1 ‘Number of justice problems for which a legal empowerment approach is developed and tested’. Target: 55; Actual 2015: 78 and Indicator 1.2. “Number of people served by grassroots legal advocates”. Target: 45,000; Actual 2015: 58,892.
Access to justice: Namati has scaled up its paralegal program in Sierra Leone to reach 40 per cent of the population. To date, 13,206 disputes and grievances have been resolved. Paralegals are having the greatest impact on supporting cases involving women’s and children’s rights, land and natural resources, and access to essential services.
Accountability of health services: Namati is working with communities to empower them to hold health service providers to account for delivery of effective services and resolve service delivery failure. In Mozambique, health advocates handled around 500 cases. After rigorous evaluation Namati is able to show that a legal empowerment approach was effective in addressing the justice problems of bribery and fee charging; staff tardiness and absenteeism; misconduct by providers; inadequate infrastructure and inadequate equipment; limited physical access to essential services. The success of this approach has been recognised by the Ministry of Health. Namati has been invited to participate in a working group that will develop the new 5 year strategy for the Department of Quality and Humanization of Health Services. Namati will use this opportunity to incorporate human rights into the health framework which previously only focussed on clinical quality indicators.
 “The community and hospital relationship greatly improved after the start of this project.  Now the people of this community know how to claim their rights.  Before it was impossible to complain. There was no room for it.” - Traditional authority, Changalane, Mozambique.
Securing land tenure and strengthening local land governance. In Mozambique, Uganda, Burma and Liberia, Namati and partners have developed a model for documenting customary land claims and strengthening local governance over community lands, with a particular focus on gender equality, sustainable natural resource use, and authentic community approval for all transactions with outside investors.
Namati has also been strengthening land rights in Mynamar through testing how frontline paralegals can scale up support farmers to protect their land rights under a new registration process. Paralegals have tested and made progress in addressing the following justice problems: securing farming rights in forest land; return of land grabbed by military and company; resisting land confiscation; fair compensation for land taken; lack of knowledge among farmers how to use land certificates to protect land tenure long term. This has resulted in 6000 cases being handled to date.
In India Namati has been in the early stages of understanding how paralegals can assist communities who are already experiencing industrial investments of their land. Namati is testing how paralegals can handle cases pertaining to regulation of coastal management zones and developing training models to empower communities to monitor compliance. By the end of the reporting period 47 cases are being actively pursued by paralegals in Gujarat and Uttara Kannada, with 12 resolved.
“Namati fills a significant gap in the community empowerment and transparency & accountability area (in land rights). They do so with outstanding expertise and strategic approach. Their paralegal approach is useful and evidence demonstrates strong impact. Their work is particularly important as part of much needed wider land governance reforms in many countries. However,…impact is limited due to the limited nature of funding. Efforts should be scaled up and out significantly.” Iris Krebber, Senior Livelihoods Adviser, DFID
“The mission of the CLASSY Awards is to recognize the greatest champions of social progress.  Namati has deployed community paralegals to help farmers in Burma to understand the land policy, register their lands, and object if others try to register their lands. Collecting data on each case, they use that information to advocate for systemic improvements. In less than a year, Namati trained 30 paralegals, developed the paralegal methodology and defined the data collection system. This small group of paralegals have already assisted 2,000 clients and resolved more than 100 cases." - Namati Top 5 Nomination in the Livelihood Development category of The Classy Awards, March 2014.

Tackling statelessness: Between Jan and Oct 2014, Namati and partners acquired data by assisting 1,028 formerly stateless people and are using this aggregate data to advocate for systemic improvements to national identity registration policies. Namati has shared this model at the global level – at the global statelessness forum, and to practitioners in the MENA region and across South Asia. UNHCR has asked to co-host a meeting gathering stateless groups in Asia to explore potential for scaling up the paralegal approach. Unprecedented successes have been achieved by paralegals in helping de facto stateless populations in Kenya and Bangladesh to gain the documents they need to access basic services under the state.
Of 62 legal empowerment solutions tested during this project period, 42 were demonstrably shown to be effective (see previous section on Outcome Indicator 1). The remaining 20 solutions tested reflect instances where a particular approach was not effective, as well as instances where it is too early to assess success. For example, in Mozambique, health advocates have thus far been successful in resolving the short supply of medicine resulting from poor supply chain management to the health facility level. However, they have yet to resolve a case involving drugs that are out of inventory at the district or provincial level.
In Bangladesh Namati received notification of a 2009 government order confirming that Urdu-speaking camp dwellers with a valid national ID are eligible to receive passports. Namati paralegals are now able to assist past clients in reapplying for passports, leading to confirmation that some passports may be issued, Namati has used the success as an opportunity to advocate within the Dhaka Special Branch Office for the equal and consistent treatment of passport applicants.
Examples under Output Indicator 1.3: ‘Number of publications (practitioners’ guides, impact evaluations, web-based tool kits, videos, case studies, audio programmes, legal literacy materials) developed to share methodological lessons that emerge from those programmes’. Target 2014: 25, Actual 2015: 41

Namati has authored a wealth of publications developed to share lessons from programming. Highlights include:
- 6-country paralegal study: Namati coordinated, with partners, a six-country empirical study on the impact of community paralegals, covering Indonesia, the Philippines, South Africa, Liberia, Sierra Leone, and Kenya. Papers have been published on Indonesia, South Africa, Liberia, and the Philippines. The team is pursuing publishing all six studies plus a comparative chapter as a book.
- Namati and its partners published the findings of a randomized controlled trial across Mozambique, Liberia, and Uganda that showed how the model leads to improvements in protections for women’s land rights and in sustainable natural resource management.

- Evidence Review: Namati was commissioned by the GLEI policy collaborative to prepare a Legal Empowerment Evidence Review – a paper on the state of the evidence of legal empowerment, analysing a wide-range of existing documentation on the impact of legal empowerment. This publication – lauded as a “huge contribution to the evidence base” for legal empowerment in a review by Maurits Barendrecht of Innovating Justice -- has made a substantial impact in building the field. Namati has presented this research at DFID and ODI, and the document has been a powerful basis for post-2015 advocacy.
- 40 other publications (37 published in 2014) across the full range of sectoral and general legal aid programs. These publications were downloaded over 1300 times from the Namati website in 2014. Namati designs its publications to serve as practical resources for practitioners and policymakers. In Liberia, for example, the publication with Sustainable Development Institute, “Community Guide to Protecting Community Lands and Resources” has been endorsed by the Liberian Land Commission, and brochures developed from the guide are being used and distributed by civil society groups throughout the region.
- From January-October 2014, 27,500 visitors made 43,000 visits to the Namati website. In the same period network members made 1,732 downloads from the tools database. The most downloaded publication -- What do we Know about Legal Empowerment: Mapping the Evidence – was downloaded 383 times between May and November 2014.

Namati has consolidated its international profile throughout 2014, featuring in numerous media outlets, such as the Guardian, the New York Times, the blogs of the Council on Foreign Relations and the World Bank, and participated in events such as the Donor Land Policy Group and the Trust Women conference on Rule of Law.
 ‘FAO is well aware of the work of Namati generally and the Community Land Programme specifically. I deem their work to be highly relevant and of outstanding quality.’ Margret Vidar, FAO.
Summary of responses to issues raised in previous annual reviews (where relevant)
The last Annual review recommended revising the logframe to ensure that Output 1 and the relevant indicators effectively measure the success and innovation of the country projects. The logframe was fully revised and agreed with DFID in spring 2014. See previous section on logframe revision for more detail.

Recommendations
Recommendation 2: Namati has devoted significant resources to establishing country projects aimed at testing paralegal methods, now in eight countries and bearing fruit across a range of justice problems. It will be important going forward to consolidate these innovations, and to shift the focus to learning and scale-up, instead of initiating new test cases.

Output Title	A network of civil society organizations dedicated to greater collaboration and learning.
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 # of legal empowerment organizations represented in the network	2012 – 150 / 2013 – 300 / 2014 – 510	Target 2014 – 450 / Actual 2015 – 559
2.2 # of legal empowerment practitioners actively participating in learning exchanges or collaborative action	2014 – 727	Target 2014 – 50 / Actual 2015 – 736 / Note: The original milestone value focused on international activity, and did not fully account for learning exchanges and collaborative action at the national level. The reported figure reflects both national and international activity.

Performance under this output exceeded expectations

Key Points
Namati’s aim in operating paralegal programs across several countries and spanning several themes is to demonstrate the relevance of the legal empowerment approach on a global scale, showing how legal empowerment is applicable to multiple contexts and sectors. To this end, Namati convenes a global network to foster dialogue, collaboration, and ultimately a stronger international movement.

Since 2012, 559 organizations and 2,000 individuals have joined the global network, and Namati continues to actively grow the membership. An online platform, containing the world’s largest database of tools and evidence on legal empowerment, allows network members to share resources, including research, training materials, monitoring and evaluation tools, case management systems, and advocacy strategies. Examples of learning and collaboration through the network are:
Examples under Output indicator 2.1: ‘Number of legal empowerment organisations represented in the network’ Target: 450, Actual 2015: 559 and Output indicator 2.2 ‘Number of legal empowerment practitioners actively participating in learning exchanges and collaborative action’. Target: 50, Actual 2015: 736

- Namati’s Sierra Leone program provided training on its methodology to over 110 practitioners, both locally and internationally. In January a picture gallery ran in The Guardian documenting the work of scaling up paralegals in Sierra Leone. This accompanied a travelling photo exhibition.
- In January 2015 Namati launched a new learning exchange programme. Network members and practitioners from all over the world will spend a couple of weeks learning and working alongside legal empowerment veterans in the field. The National Alliance for the Development for Advice Offices in South Africa and the Alternative Law Groups in the Philippines will play host to the first round of participants in April and May.
“[The network] has exposed me to a number of things that I didn’t think could happen in Zambia.  I didn’t know that other countries have legislation that recognizes paralegals. Now that we know which countries do, we would actually like to collaborate with them so we can see how we come up with such legislation in Zambia.  It’s really helped us and it’s opened our minds to think further.” - Namuchana Mushabati, from the Legal, Sexual and Reproductive Rights Project with Women and Law in Southern Africa (WLSA), Zambia.

Accountability of Health Services
- 42 practitioners attended workshops and training in Mozambique hosted by Namati. Namati also produced a Right to Health manual to share with local NGOs and created a mobile library of resources for health advocates.
- Namati collaborated with the OSF Law and Health Initiative to conduct a meeting exploring the intersection of legal empowerment and health. The meeting brought 16 organizations from Africa and Eastern Europe together with a number of donors to discuss the state of the field and priorities for action. Over 60 participants shared their experiences developing legal empowerment methods to serve the needs of people affected with HIV, including sex workers and drug users; palliative care patients; the Roma community, and others.
Community Land Protection:
- During 2014 Namati and its network partners began publishing a Lessons from the Field report from Namati’s CLPP. This report describes challenges – and solutions – arising from Namati’s land protection work and has launched a series of four animated videos that describe Namati’s community land protection approach.
- The community land protection model was presented to a group of 11 NGOs in Thailand and a policy paper developed for paralegals in Thailand based on the Namati model.
- The model was also shared at conferences of the International Land Coalition, The World Bank, UNITAR-Yale and with 15 practitioners at the African Symposium on Community Land Protection.
- In Kenya, Uganda, and Nepal, 70 local, national and international practitioners, including from FAO and Oxfam, attended workshops conducted by Namati on the land protection model.
- The CLPP team has convened the third Partner Summit in Naivasha, Kenya, (in 2015) thirteen members of Namati’s partner organisations participated. The summit was filled with practical discussion on how to undertake community land protection activities
- Namati facilitated a week long training on CLPP and monitoring and evaluation and project management, attended by Oxfam, Kenya Land Alliance and a number of other partners.
- In January 2015 Namati co-organised and co-hosted a workhop with Partners Asia called ‘Land and Law: Legal Remedy, Paralegals, and Documentation for Advocacy’. The workshop is targeted at public interest lawyers who are focusing on land rights cases but also served as professional development for junior lawyers and paralegals assisting the public in claiming their rights.
Citizenship:
In September, Namati and partners made featured presentations at the first Global Forum on Statelessness, on adapting the community paralegal model to claim citizenship rights. To coincide with the forum, Namati placed in the Guardian a photo essay on its citizenship work in Bangladesh.

Recommendations
Recommendation 3: Namati should continue to demonstrate the impact of their knowledge and tools on the effectiveness of network members. There are plenty of examples showing the development of the products and uptake by network members. However it is not always clear how network members’ use of the tools and products has enhanced their success as paralegals. It is recommended Namati considers how to grow the field, what tactics are paying off to attract membership and how practitioners’ understanding of the paralegal approach is enhanced via membership. The current evaluation of the global network’s capacity-building initiatives should go some way to addressing this.

Output Title	Advocacy for policy reforms that advance legal empowerment
Output number per LF		3	Output Score	A+
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 # of national, regional, and international policy reform proposals based on grassroots experience (e.g. in policy briefs, op/eds, presentations with government or agency officials, campaign documents).	2012 – 28 / 2013 – 44 / 2014 – 114	Target 2014 – 80 / Actual 2015 - 120
3.2 # of civil society organizations who advocate for legal empowerment in the post-2015 agenda		Target 2014 – 150 / Actual 2015 – 257 / Note: The original milestone was an ambitious target given the limited information Namati had on hand; this marks Namati’s first global campaign, and the first ever campaign of its kind. Namati invested significant energy in the campaign and was able to build momentum, leading to the engagement of a higher number of organizations than anticipated.

Key Points
Namati’s unique position both as an implementer of paralegal programs as well as a convenor of the paralegal movement allows Namati to build a compelling narrative and evidence base for national and global policy/advocacy. Namati collects data on every case arising from its grassroots work in the eight countries it operates in, and aggregates grass roots data to advocate for systemic, large-scale reforms.

Examples under output indicator 3.1: ‘Number of national, regional, and international policy reform proposals based on grassroots experience (e.g. in policy briefs, op/eds, presentations with government or agency officials, campaign documents)’. Target 2014: 80, Actual 2015:120

Examples of advocacy, and ensuing policy change, are as follows:

- In Liberia, the first national land policy has been heavily influenced by Namati’s community land protection model, prioritising inclusive and equitable community governance processes. Namati and partner (SDI) signed an MoU with the Land Commission to deploy paralegals to engage in community land protection nationwide.
- In Kenya, the majority of Namati’s recommendations on the draft Community Lands Bill were adopted.
- In Sierra Leone, Namati and partners successfully advocated for a legal aid law that recognizes the role of community paralegals. It is now advising on implementation of the law. "Namati played a key role in the development of Legal Aid in Sierra Leone from drafting to enactment and development of key documents to support of implementation of the Legal Aid Act. With their unflinching support they helped move a process that seemed impossible". - Olayinka Laggah, Justice Sector Coordinating Office, Ministry of Justice, Sierra Leone.
- Namati and network members raised the profile of legal empowerment through the Kampala Declaration on Community Paralegals, which was endorsed by 60 groups across Africa and cited in legislative debate regarding legal aid in Zambia, South Africa, Tanzania and Rwanda.
- In Sierra Leone, Namati made eight policy proposals, and delivered substantive changes to Sierra Leone’s Draft National Land Policy. One key provision requires firms interested in large-scale land acquisitions to contribute to a basket fund which will in turn support legal representation via paralegals for land-owning communities.
- In Mozambique, Namati is using data from its health accountability efforts to advocate for systemic improvements to healthcare delivery systems. The health program won the Humanization Award from the Ministry of Health and Namati is advising the Ministry by helping to write a new five-year national strategy for the Humanization and Quality of Health Services.
- In Kenya, Namati and local partner Nubian Rights Forum made recommendations during the passage of a Registration of Persons Bill based on the work of paralegals. Namati requested, among other things, limits on the discretion of registrar officials.
- In Bangladesh, Namati and partner the Council of Minorities are working to ensure the Bangladesh Law Commission’s anti-discrimination legislation addresses language-based discrimination.
- In India, Namati worked with communities to campaign for the creation of District Level Coastal Committees (DLCCs), which by law should include community representatives. It also made representations with the Fisheries Departments, the expert Committee on Environmental Laws and to six other regional and national-level bodies.
- In Mynamar, in response to a Legal Aid Bill which will be discussed at the Parliamentary Assembly, Namati submitted three key suggestions to the Union Parliament Chair, Legislative Committee-public Parliament and the Office of National Parliament. Namati is in continued discussions with the Land Core Group Secretariat for collaboration on paralegal expansion to new parts of the country.

Examples of achieving output indicator 3.2: ‘Number of civil society organizations who advocate for legal empowerment in the post-2015 agenda’. Target 2014: 150, Actual 2015: 257
At the global level, Namati harnesses the legal empowerment network as a vehicle for international advocacy; and has been collaborating with OSF and network members to advocate for the inclusion of legal empowerment and justice targets in the post-2015 agenda. Highlights under this output include:

- Namati and Open Society jointly published an Open Letter to the UN General Assembly, drawing on issues related to legal empowerment and access to justice. Around 260 organizations representing 60 countries and 16 world leaders -- including Archbishop Desmond Tutu, Mary Robinson, Jimmy Carter and Mo Ibrahim amongst others, endorsed the letter. Throughout the sessions of the Open Working Group on Sustainable Development Goals (OWG), Namati supported signatories of the letter to lobby their governments through a number of awareness raising mechanisms and intellectual inputs. As a result, Namati’s network members’ recommendations were included in the OWG zero draft.
- The inclusion of a number of the networks recommendations on goal 16 in the OWG’s final report.
- Namati and network members were able to generate buy-in by influential decision makers (such as senior officials in UN agencies and country missions) by convening a high-level Namati/OSF-sponsored Greentree retreat in October 2014. A standout success of the retreat was Namati’s ability to bring together high level decision makers and grassroots activists from the network, to ensure discussions and recommendations were anchored in on-the-ground experiences of legal empowerment in their countries.
- Namati initiated advocacy activities related to post-2015 with network members in Jordan, Kenya, India, South Africa, Indonesia, Nepal and Nigeria. In total, 308 organizations had taken part in post-2015 advocacy at either the international or national level.

Recommendations
Recommendation 4: Namati is effective at using grassroots solutions and data to influence legal empowerment policies at the national level, and then at the international level. It is worth Namati continuing to explore campaigns targeted at strengthening regional level coordination, beyond the post-2015 campaign, in order to secure as much global momentum as possible.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Primary costs supported by the DFID grant include core costs, grants provided to Namati’s in-country partners, and personnel and travel costs for Namati staff. Namati performs well on relatively limited human resources – a core staff of 57, with 6 offices and work spread across eight different countries, working with numerous partner organisations. Namati maintains contractual relationships with several outside consultants for technical assistance in areas such as website development and monitoring and evaluation.

VfM performance compared to the original VfM proposition in the business case

Performance matches with the original proposition in the Business Case of building better evidence and stronger practice in legal empowerment, as a high-impact low-cost approach to delivering justice, leading to greater and more effective use of funds and interventions in this field. It was expected that the indirect benefits would include greater provision of grassroots justice services with associated welfare and development impacts. Namati have begun to show that this is the case.

Assessment of whether the programme continues to represent value for money

The programme represents excellent value for money. Namati is delivering against its aims and targets and has exceeded all the logframe indicators.

The impressive achievements of the overall three year period show that Namati has significantly contributed to the field of legal empowerment. With the help of DFID’s grant (£750,000 per annum), Namati can demonstrate impacts at numerous levels and for a wide range of stakeholders, e.g.:
- Citizens have directly benefited from legal advice and basic legal services to resolve numerous justice problems, whether related to human rights, land rights or social service accountability.
- Robust evidence of how paralegals can address failures in the rule of law and achieve positive outcomes for poor and marginalized groups has been developed and shared across the globe.
- Legal empowerment practitioners have become more effective through the use of evidence and data and international exchange of best practice.
- National policy changes have steered the law and its implementation towards the poor.
- Access to justice and legal empowerment have been recognised as key to delivering the development results intended in the MDGs and in the future post-2015 development framework.

These impacts represent very good value for money, and are complemented by the role the grant has played in consolidating DFID’s strategic relationship with OSF, a foundation with significant resources and an influential partner on post-2015. GLEI’s International Advisory Council, as well as Mr Soros’ commitment to GLEI, has provided intellectual direction and political leverage during the post-2015 UN negotiations. Namati have also been effective in using the global network and diverse media outlets to demonstrate legal empowerment in action.

As part of the new funding arrangement with GOSAC and GRD, DFID could benefit further from Namati’s work by building stronger links between Namati and DFID country offices. The S&J team will also work with Namati to ensure best practice and evidence informs our learning and evidence strategy. DFID will work with Namati, whether it be through direct advice or through uptake of best practice, in order to improve DFID’s own programming on legal empowerment. This has already happened:
- In Sierra Leone, DFID provides funding to Namati through the bilateral S&J programme. Most recently, DFID’s land rights design team teamed up with Namati to carry out their assessment.
- In Burma, Namati advised and collaborated with Pyoe Pin, DFID’s civil society strengthening program.
- In Bangladesh, the DFID-funded Community Legal Services Project drew on Namati’s data collection tools for paralegals in developing similar tools for Bangladesh paralegal organizations. The project also invited Namati to speak at a national meeting on access to justice in Dhaka in February 2014.

Recommendation 5: As all of the targets for these indicators have surpassed the target level, it is recommended GOSAC and GRD ensure future indicators and targets at output and outcome level measure impact and are sufficiently challenging and stretching, including qualitative indicators at output level where appropriate.

Quality of financial management

Namati has maintained all requests for funds within the parameters set by the Accountable Grant agreement and accounts for both actual expenditure and forecasted expenditure in the statements of accounts each quarter. In 2014, Namati had an independent financial audit of all institutional activities completed for 2014.

Namati is aware of value for money principles, incorporates the concept as part of the institutional accounting and finance procedures, and continues to keep cost effectiveness at the forefront in all implementation.   Namati is on target to achieve all indicators set out over the programme.

Date of last narrative financial report	31.03.2015
Date of last audited annual statement	19.05.2015

E: RISK (½ page)

Overall risk rating: Medium

See below for rationale

Overview of programme risk

Risks that Namati has successfully addressed:
- The programme has been running for four years and Namati has firmly established itself as an entity independent of OSF.
- Despite being a nascent organization, Namati has consistently achieved outputs against an ambitious logframe.
- As outlined in the previous section, Namati has continued to demonstrate value for money. These benefits have helped ensure the longevity and continued relevance and recognition of Namati’s mission.

Risks that require continued attention:
To date, GLEI has had sufficient funding, with both OSF and DFID committing multi-annual funding to Namati. Namati has succeeded in attracting funds from a range of other donors in support of specific projects and OSF has committed to a further $1m per annum and matched funding of up to $2.75m per annum for 2015-2017. Nonetheless, the organisation continues to be dependent on just two donors for core funding, so Namati will need to continue to diversify its funding streams particularly for core funding.[6]
[6] Budget of $4.3m for 2014, and DFID contributed 24% of revenue up until end of 2014.
- The legal empowerment approach can encounter resistance from national governments and donors focused exclusively on state justice provision. In its innovative country-level interventions, Namati has demonstrated a clear capacity to build positive relationships with government actors engaged in state justice provision.
- Namati acknowledges that the paralegals and the communities they work with are regularly exposed to risks of various kinds. Namati’s organisational principles highlight safety as an issue of paramount importance to the organization, and they have a detailed safety and security protocol in place for staff.
- There are inherent human rights risks linked to the legal empowerment work carried out at the community level, and these can be mitigated. This programme predates the requirement for an Overseas Security and Justice Assessment. Nonetheless, Namati has demonstrated appropriate consideration and management of the human rights risks in a number of ways:

- Namati seeks to protect human rights by the nature of its work, which engages with power imbalances and seeks to rectify local level injustices for communities and individuals.
- In order to ensure human rights risks are tracked and mitigated against, Namati assesses each case against human rights principles.
- Namati is committed to ensuring that men and women of all ages are equally served by legal advocates. All negotiations with community chiefs and community members include a mandatory requirement to ensure women are equally represented on a management committee before Namati agree to provide paralegal support – this was verified during the AR monitoring visit.
- Human rights principles are at the core of the social accountability mechanisms carried out by paralegals. In many cases, paralegals are tied to a community level oversight mechanism that ensures they are working effectively, abiding by their code of conduct, and serving the communities responsibly. Paralegals are also tied to supervisors who engage in regular monitoring of the paralegals’ work, providing a safeguard to help ensure sound judgment and ethical practice.

As part of the new funding arrangement between GOSAC and GRD, an OSJA will be conducted.

Outstanding actions from risk assessment
N/A

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Namati has met all of its output targets on time per the logical framework.

Performance of partnership (s)

Namati works closely with local partners to implement all of its country-level interventions, e.g. in Sierra Leone, Uganda, Liberia, Mozambique, Kenya, India, Burma, and Bangladesh. Namati develops locally contextualized models and methods in conjunction with partners, and jointly strategizes, implements, and monitors activities. Namati also undertakes joint fundraising with local partners to support collaborative work.

OSF and Namati work together to fulfil the goals and targets set out for GLEI, as described in the GLEI logframe. This requires constant coordination and information-sharing. A number of initiatives aimed at developing the network or advocating for international policy are also undertaken jointly.

Asset monitoring and control

There are no significant assets under the Accountable Grant.

G: CONDITIONALITY (½ page)

Not applicable

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
Namati was set up to evaluate and document all their programmes, publishing both impact studies and practical guidance for practitioners. The systematic documenting of successes and failures in legal empowerment, using a variety of methods, is intended to strengthen practice worldwide and has already significantly increased the body of evidence in this field.

New evidence which challenges the program design or rationale:

The evidence generally supports the design of the project. Still, the effort to scale-up legal empowerment worldwide has encountered some challenges:
- For many legal empowerment organizations, unstable financing is a rate-limiting factor and makes it difficult for grassroots groups to sustain systems for rigorous supervision and support of frontline paralegals - these systems are crucial for success. Namati will continue to harness post-2015 advocacy to push for increased investment to the field as a whole. Namati is supporting partners to build internal management systems so they can operate independently, with limited technical support – this has been demonstrated with their partner Centro Terra Viva (CVT) and will replicated. Namati is also testing alternative forms of revenue-generation, such as crowd-sourcing, social enterprise, and client contributions.
- Learning and collaboration among legal empowerment practitioners across borders is impeded by differences in language and limited internet access. In-person exchanges are invaluable but costly. Namati is revamping the network’s virtual platform, drawing on the latest evidence on global social networks. Namati is working with direct partners and the network guidance committee, made up of fourteen organizations from fourteen countries, to foster greater collaboration at a regional level. The post-2015 campaign has been an energizing catalyst.

Monitoring
Monitoring throughout the review period has been done through quarterly reporting, regular updates,monthly discussions and Annual Reviews with Namati. We have attended events led by Namati, such as the workshop at ODI in November 2014 on why legal empowerment matters to development. Namati have also provided beneficiary feedback, some of which is reflected in the 2014 Annual Review. One illustrative beneficiary statement is:

“Although I am young and a woman, since becoming a paralegal I have experienced a lot of respect from my community. Everyone says ‘salam’, and they call me Madame. I now want to train as a social worker.” - Nahid Parvin, 20, Paralegal, Geneva Camp, Dhaka, Bangladesh.

The DFID programme manager undertook a monitoring visit to Mozambique in December 2014 to review two of Namati’s projects - health accountability in Maputo and land rights in Inhambane. She accompanied the CEO of Namati, Vivek Maru, and spent time with Namati staff, partners, paralegals and beneficiaries to gain a holistic view of the programme and Namati’s vision looking forward.

Annex 1: List of organisations and individuals that have provided feedback on GLEI/Namati performance

Feedback generated through Namati
1. The Board of Ashoka Innovators for the Public.
2. Allison Moore, Senior Access to Justice Expert, UNDP, Myanmar
3. Namati Top 5 Nomination in the Livelihood Development category of The Classy Awards, March 2014
4. Win Naing Soe, Local Officer, National League for Democracy, Shan State, Myanmar.
5. Nay Dun, Founder Civil & Political Rights Group, Myanmar.
6. Elias, Mucizo Village, Marracuene District, Mozambique.
7. Traditional authority, Changalane, Mozambique.
8. Shakir Bhai, Paralegal, Okha Port, Jamnagar District, Gujarat, India.
9. Olayinka Laggah, Justice Sector Coordinating Office, Ministry of Justice, Sierra Leone.
10. Ahmed Ilias, Executive Director, Al-Falah, Bangladesh
11. Nahid Parvin, 20, Paralegal, Geneva Camp, Dhaka, Bangladesh.
12. Khalid Hussein, Founder Council of Minorities, Bangladesh.
13. -Fatma Bitwataa Talib, Paralegal, Nubian Rights Forum, Kibera.
14. Moufida Guirmani Ep Oueslati, Tunisia.
15. Namuchana Mushabati, from the Legal, Sexual and Reproductive Rights Project with Women and Law in Southern Africa (WLSA), Zambia.

Feedback generated through DFID
1. Margaret Vida, Legal Officer, Food Agricultural Organisation (FAO)
2. Iris Krebber, Senior Livelihoods Adviser, DFID