Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Innovative Vector Control Consortium (IVCC) 2013-18
Programme Value: £12,050,000		Review Date: June 2015
Programme Code: 204076	Start Date: August 2013	End Date: March 2018

Summary of Programme Performance
Year	2014	2015
Programme Score	A	A
Risk Rating	High	High

Summary of progress and lessons learnt since last review

The Innovative Vector Control Consortium (IVCC) continues to make good progress in its mission to eliminate transmission of mosquito-borne pathogens through improved insect vector control with innovative products. During the reporting period IVCC has advanced their portfolio of novel active ingredients. In addition, they have advanced their development work on long lasting insecticide treated nets (LLINs) and long lasting indoor residual spraying (IRS) that are not wholly reliant on pyrethroids. IVCC expect to submit these insecticides to the WHO Pesticide Evaluation Scheme (WHOPES) in the second half of 2015 for regulatory approval. The programme has also made progress towards its aim of improving the quality assurance and monitoring and evaluation systems of vector-borne disease control.

A key lesson relates to the importance of unblocking regulatory pathways for any products produced. Pyrethroid resistance continues to increase dramatically both in frequency and level particularly in Sub-Saharan Africa. The rate of resistance selection means that new product introduction is likely to be needed well before the standard regulatory route could be completed. To this end, IVCC are working with its partners to evaluate various regulatory pathways and reduce time to market for novel interventions.

Another lesson relates to getting industrial commitment to support projects as they transition from research to development phases. This transition requires significant stakeholder alliance to optimise product development, release and in-country management to prevent resistance outbreak.

Summary of recommendations for the next year

1. IVCC should continue to keep DFID updated on progress on the active ingredient programme and alert DFID if projects are closed early, throughout the year.
2. IVCC should continue to synthesise the lessons learned and share these with funding agencies and in-country stakeholders in a more proactive way and report progress in next year’s annual report.
3. Future annual reports should include more details on progress of the Disease Data Management Systems as the systems are rolled out to countries

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-204076/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-204076/

Outline of the programme

The mission of IVCC is to eliminate transmission of mosquito-borne pathogens through improved insect vector control with innovative products. IVCC facilitates the development of improved public health pesticides and formulations, provides information tools to enable the more effective use of existing and new disease control measures, and works with the disease endemic country stakeholders and industry to establish target product profiles for new vector control products and tools.

DFID’s investment in IVCC will contribute to the development of new vector control tools which will mitigate the threat posed by insecticide resistance to existing tools and help to reduce the global burden of malaria. Specifically our support will help to address the immediate problems of pyrethroid resistance by stimulating the development of new public health insecticide classes. The main 5 year outputs associated with DFID funding and contributing towards the achievement of this outcome will be:

- New vector control products developed that will impact on malaria transmission
- Enhanced R&D and technology transfer capacity in disease endemic countries
- Effective dissemination leading to adoption of new vector control products for malaria and neglected tropical diseases

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment: A – outcomes met expectations

The intended outcome of the IVCC programme is to generate new knowledge and new tools to address the immediate problems of pyrethroid resistance. The programme is continuing to make steady progress towards this aim and the novel active ingredient projects are gradually switching from a research phase to development phase. The portfolio remains on schedule to deliver three new active ingredients to the market by 2022. The repurposing projects are now going through the required regulatory review processes with the expectation that they will be ready for release by 2017. IVCC is also working with funders to evaluate various regulatory pathways and reduce time to market for novel interventions. This activity is critical to ensuring that the PDP achieves its intended outcome.
Overall output score and description: A – outputs met expectation

Key lessons

Key lessons in this reporting period relate to unblocking the registration pathway and managing resistance:

Registration pathway: IVCC’s portfolio is making good progress toward the creation of the data package for registration of new products. Within a few years it is very likely that their partners companies will submit 3 to 5 registration dossiers for public health product without a prior registration for crop protection, a first in vector control. IVCC will therefore need a coordinated approach between stakeholders to map and optimize regulatory pathways. To this end IVCC is working with the Innovation to Impact Initiative under the leadership of the Bill and Melinda Gates Foundation (BMGF). This will enable products to be efficiently brought to market while maintaining product quality throughout the system.

Resistance management: The products under development will especially be useful in situations where mosquitoes have developed resistance to insecticides currently available. The mechanisms of resistance build up are well identified. A number of recommendations to manage resistance spread are known but difficult to implement. IVCC is collaborating to the creation of a stakeholder alliance which will help coordinating activities between industry, programs and funder community to implement best in class insecticide resistance management strategy.

Key actions

DFID will discuss IVCC’s plans for obtaining further funder support within the current programme. The current BMGF programme grant ends in 2015, although IVCC are in discussions with BMGF on renewal. The progress to date has been very positive and DFID will liaise closely with IVCC, and IVCC will update DFID on progress and will alert DFID if any delays occur. DFID should also continue to follow up on BMGF PDP funding plans.

Has the logframe been updated since the last review?
Yes. During the year IVCC has made amendments to the log frame in response to suggestions from DFID.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Pipeline of innovative new chemical entities advanced to the Development Phase
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	80%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes – increased from 70%

Indicator(s)	Milestones by Sep 2015	Progress May 2015
Completion of Stage Gate reviews showing achievement of staged Target product Profiles.	ESAC* recommendation, prioritisation and comment on portfolio balance	On track - 75% Completed (3 companies out of 4)
Number of new chemical entities in late stage development	Selection of 3 compounds from new and different chemical classes for progression with back-ups (both within the selected class and from alternative classes of chemistry)	On track – 75% completed (3 projects out of 4 competed)

Key Points

IVCC are performing well and the portfolio remains on schedule to deliver three new active ingredients to the market by 2022. Since their inception IVCC has screened 100,000 compounds from chemical libraries containing more than 4.5 million compounds. They are now working on 9 classes of chemistry with a high potential for vector control. Three out of four projects with industrial partners have completed and IVCC are now progressing with the selection of lead compounds which will be put in pre-development and development. This selection is done based on a multidisciplinary approach supported by their Expert Scientific Advisory Committee (ESAC*) and is expected to be complete by September 2015.

In addition to identifying new active ingredients, IVCC has continued to scan the agrochemical development pipelines of all the major companies. Unfortunately one potential line of enquiry with an industrial partner did not allow the identification of chemistry with potential for vector control and this project was discontinued. However, IVCC is in dialogue with another company which is well advanced in developing one compound for crop protection which also has potential for vector control.

The IVCC continues to monitor changes in the insecticide resistance profile of the major African malaria vectors that could have a negative impact on its Product Development Portfolio. Major adverse changes in resistance are logged and attempts made to secure colony material to test new active ingredients against through IVCCs testing facility.

Summary of responses to issues raised in previous annual reviews (where relevant)

Last year’s annual review suggested that IVCC should keep funding agencies informed about negotiations with regulatory agencies (notably WHOPES) to identify ways to overcome some of the blockages in bringing products to market. To this end IVCC has been working with BMGF and others to identify bottlenecks in the regulatory process and improve time to market. A regulatory expert has now been employed to lead on this activity. The objective is to reduce the time from a development decision to market availability from the current ten to seven years.

Recommendations

IVCC should continue to keep DFID updated on progress on the active ingredient programme and alert DFID if projects are closed early, reporting details in the next annual report.

Output Title	Completed development and Adoption of new Resistance breaking LLIN / IRS formulations
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		Yes – this is a new output	Impact weighting % revised since last AR?	Yes – this is a new output

Indicator(s)	Milestones	Progress
No of IVCC supported products recommended by WHOPES / Vector Control Advisory Group (VCAG)	Portfolio of IVCC sponsored products entering WHOPES, VCAG or regulatory pathways	On track: Completed for 2 LLIN projects
No of IVCC supported products adopted by national control campaigns.	At least 2 IVCC sponsored products available to control programmes by 2016	On track to meet milestone in 2016
At least 3 products distributed in disease endemic countries	Vector control products available by 2017	On track to meet milestone in 2017

Key points

Activities under this output are in line with expected milestones. IVCC has successfully completed the development of two indoor residual spraying (IRS) products formulations including appropriate regulatory pathways and both are now commercially available.

The formulation for treating insecticide nets with two different insecticides (bi-treated) continues to pass all its development hurdles. This product has entered community trials, supported by EU funding, to demonstrate the epidemiological effect of the bi-treated net formulation in an area of pyrethroid resistance. Net distribution began in October 2013 and the field trial started in Q1 2014.

Work to test activity of LLIN treated with the new formulation have shown much improved activity against pyrethroid resistant mosquitoes both in tunnel tests and hut trials. The development of the methodology caused some delays, but IVCC partners have submitted a dossier to WHOPES and are waiting to hear the outcome of the review. The IRS project is a prototype development stage and once a suitable prototype is available it will be taken into hut trials for full evaluation. In addition several proof of principle projects are either in development or evaluation.

One issue emerging is the consequences of Pyrethroid resistance continuing to increase dramatically, both in frequency and level particularly in Sub-Saharan Africa. The rate of resistance selection means that new product introduction is likely to be needed well before the standard regulatory route for new agrochemicals can be completed. IVCC are in discussions with other stakeholders to map out these processes, document the roadblocks and look for potential routines to unlock these problems.

Summary of responses to issues raised in previous annual reviews (where relevant)

None. This is a new output.

Recommendations

This work is progressing well, as it develops IVCC should continue to synthesise the lessons learned and share these with funding agencies and in-country stakeholders in a more proactive way, including through the annual report.

Output Title	Improved quality assurance and monitoring and evaluation systems for vector-borne disease control
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	5
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes – reduced from 10%

Indicator(s)	Milestones	Progress
Insecticide quantification kit diagnostic into commercial production	Standard Operating Procedures in place in all trial sites with WHO endorsement of procedures by 2016	On track to meet milestone in 2016
Decision support system established and in use in one malaria endemic country by control programme	Demonstration programme of resistance management planning in one African country by 2015	Achieved: System implemented in Equatorial Guinea.
No of Partners in low and middle income countries adopting IRS QA tools and information systems.	QA tools and methods available and endorsed by WHO by 2016	On track to meet milestone in 2016

Key Points

Progress for this output is on track. IVCC has undertaken further testing of their Insecticide quantification kit (IQK) to define the test accuracy better and to improve the quality assurance and monitoring of vector control interventions. They plan to initiate discussions with PMI later this year on how incorporating the IQK into operational IRS programmes.

IVCC together with its partners are implementing their Malaria Decision Support System (MDSS) in Equatorial Guinea. The MDSS aims to be a best practice, continuous surveillance system that integrates monitoring and evaluation data from a malaria control programme and presents it in a web-based, real time geographic format to assist with intervention planning. IVCC has consolidated 22 databases in the system and are planning to roll out the system to 19 countries during 2015/16.

IVCC has installed their Decision Support System in Ethiopia and Zambia for monitoring entomological and IRS activities and have reported that countries are gaining confidence in using the system.
IVCC are also working on other monitoring and evaluation systems and analytical tools, including an Insecticide Quantification Kit - a simple to use kit which can quickly determine how much insecticide remains on a bednet or indoor surface. Experience with implementing the system in a number of malaria endemic countries over the last 5 years has demonstrated that uptake and use by the national programme is greatly improved by a step wise introduction of the different modules of the programme.

Summary of responses to issues raised in previous annual reviews (where relevant)

None.

Recommendations

Future annual reports should include more details on progress and lessons learnt as the systems are rolled out to countries.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers are research salaries and the cost of doing research in developing countries. The costs of doing research are escalating in developing countries, especially as fuel, travel and food prices continue to rise sharply. IVCC and partners are working together to identify opportunities for cost savings.

Product development is a high risk, long term and costly process, particularly during the early development stages. The PDP model explicitly aims to manage resources to ensure that there are funds available to test the most promising products as they are developed. This includes widening partnership with the private sector in low, middle and high income countries and leveraging of resources, in-kind contributions and expertise; working with other not-for-profit organisations to share costs wherever possible.

VfM performance compared to the original VfM proposition in the business case
The original business case emphasises the added value of funding product development through a PDP such as IVCC. IVCC demonstrates good VfM performance through:
- The use of a portfolio approach which allows funding to be redistributed if individual projects are stopped if they do not meet their milestones
- Support for the continued development of the most promising candidates: facilitating opportunities to explore innovative partnerships with private and public sector organisations (in many different countries including low and middle income) to reduce costs
- Leveraging contributions from the private sector and/or in-country funds, by fostering country ownership and encouraging emerging economies to invest in insecticide development.
- The work on identifying bottlenecks in the regulatory process has the potential to reduce the time from a development decision to market availability from the current ten down to seven years. This will save significant costs as well as save lives if successful
- IVCC has been streamlining its insect rearing and testing unit to reduce the number of colonies and maximize the throughput of compounds for testing

Assessment of whether the programme continues to represent value for money
IVCC continues to represent value for money and a good investment for continued DFID funding. The PDP is well on track to produce a range of new products to tackle the threat posed by increasing resistance to insecticides.

Quality of financial management
IVCC is core funded by DFID. Spend continues to be on-track and is disbursed in accordance with the agreed Memorandum of Understanding (MoU). IVCC is routinely audited; annual audited statements have been submitted and have been assessed as satisfactorily.

IVCC operates under the Liverpool School of Tropical Medicine (LSTM) code of practice on corruption and transparency with zero tolerance of corruption and full transparency on reporting. Any breaches to this policy are reported, fully investigated and appropriate action taken.

LSTM's core activities and costs are subject to stringent audit and financial reporting requirements. All projects are subject to the same requirements with additional local and US or UK based ethical review where appropriate. All projects have the potential to be subject to external and/or internal activity and financial audit. These audits are randomly assigned, linked to donor requirements or commissioned if unusual activity is suspected.

Date of last narrative financial report	19/12/2014
Date of last audited annual statement	19/12/2014

E: RISK (½ page)

Overall risk rating: High

Overview of programme risk
Product development is long term and high risk. The development of insecticides for the purpose of protecting human health is novel, previously insecticides have received agrichemical approval and then been used to protect human health. The PDP model represents a mechanism to mitigate the risks associated with the development of new products for diseases where there is little likelihood of private sector companies recovering the costs of development due to perceived risks and profit potential. IVCC manages these risks on an ongoing basis, through monitoring its portfolio and prioritising or stopping research as appropriate, when data indicates a change in the probability of success of an insecticide candidate.

IVCC has a well-developed risk assessment matrix which covers all aspects of their work, including technical, regulatory, managerial and financial risks. IVCC is working on long-term projects (over 10 years) with significant stage gates such as: product efficacy, cost of goods, safety assessment, manufacturing, registration etc. This is especially true for the development of novel active ingredients which have high failure risks. In this area IVCC is undertaking a strategy to mitigate these risks. This is done through early screening to identify any significant issues and by maintaining a portfolio of backup chemistry which could be used in case lead compounds would fail. This is done in collaboration with their innovation partners and their external advisory board.

A key risk relates to the ability of IVCC to continue to attract funding, particularly from the BMGF. IVCC is supported by key funders: BMGF, DFID, USAID and the Swiss Development Corporation. The current grant from the BMGF will end in 2015 and IVCC will work with its funders to ensure the continued support of its projects.

Outstanding actions from risk assessment
DFID and IVCC staff continue to review risks and discuss mitigating actions. To mitigate against the current high risk areas, ensuring key people are in place and poor product acceptance. IVCC has made good progress in recruiting staff to key roles and is undertaking extensive market research on future product use/acceptability and ensuring these are built into future plans. DFID and IVCC will monitor progress in future reports

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
IVCC has its own strategic plan, used by many funders (including DFID) and has been the basis for the development of a DFID logframe. There were 6 organisational objectives in 2014 and a further 8 for 2015. The majority of these objectives are on-track. One project, to establish whether two agro- chemicals currently in development by IVCC partners could be used in public health, was closed due to lack of potential leads. However there is ongoing discussion with another company to monitor the development of a new product and its potential use in vector control.

Performance of partnership (s)
The DFID-IVCC relationship is good and there is satisfactory communication on issues affecting the programme. With appointment of a new Project and Business Resource Manager, IVCC has strengthened their ability to manage projects including accurate forecasting of project advancement and forecasting of the funds needed to enable the IVCC mission.

Asset monitoring and control
IVCC does not own any physical assets. Monetary asset are invested in regulated financial institutions and IVCC follows LSTM’s investment policy which is monitored by the Finance and Investment Committee of the IVCC Board.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

DFID provides core funds to IVCC. This programme does not involve direct bilateral assistance to a priority country. The partnership principles are not applicable in this case.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

During 2014, the IVCC Board commissioned an independent review of its governance structure and operations. Analysis by Quantum Governance (a Washington DC-based non-profit focused on optimizing Board performance) showed there that there had been good progress in the Board’s performance, in terms of its governance structure, fund raising and development, practices and culture.

Monitoring progress throughout the review period

This review was carried out by members of the Human Development Team in DFID’s Research and Evidence Division, with input from other funding agencies and staff from IVCC. Members of the team met with IVCC staff at the DFID offices in Whitehall in October 2014, at LSTM in December 2014 and at the PDP funders Forum in Seattle in May 2015. In addition there have been a number of teleconferences during the year, during which progress and challenges have been discussed.