Annual Review – post April 2018

Title: Land Investment for Transformation (LIFT) Programme, Ethiopia
Programme Value £ (full life): £72.7 million		Review Date: December 2019
Programme Code: 202900	Start Date: Feb 2014	End Date: August 2020

Summary of Programme Performance
Year	2014/15	2015/16	2016/17	2017 (MTR)	2017/18	2018/19
Programme Score	A	B	A	A+	A+	A++
Risk Rating	High	High	High	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.DfID.gov.uk/projects/GB-1-202900/documents
DevTracker Link to Log frame:	https://devtracker.DfID.gov.uk/projects/GB-1-202900/documents

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)
The objective of the Land Investment for Transformation (LIFT) programme is to improve the incomes of the rural poor and to enhance economic growth. It does this through a focus upon and activities related to improving Second Level Land Certification (SLLC), improved Rural Land Administration Systems (RLAS), cross-cutting policy reviews, and development of the rural land sector to enhance productivity and investment. Complementary market systems interventions through LIFT’s Economic Empowerment Unit (EEU) seek to maximise the benefits of improvements to the SLLC and RLAS. A further component of the programme supports the Government of Ethiopia (GoE) in reviewing existing proclamations and regulations to improve security of tenure. This component focuses on communal land holdings, pastoralists and customary land use and the transparency of land allocation, in line with international good practice and human rights obligations.
Specifically, LIFT aims to:
- Enable provision of map-based land certificates to farmers in four regions through support for the production of aerial imagery; development of a digital cadastre; engaging farmers to identify their land parcels on the resulting photographic map and resolve any disputes; and issuance of certificates of ownership;
- Strengthen capacity in the rural land administration system to register, update and enforce rights through developing land administration systems backed by IT; training land administrators; refining and documenting administrative processes;
- Facilitate increased investment and productivity through support to the development of the land market, based on detailed analysis and research; and
- Strengthen the existing land policies and procedures, with the aim of enhancing security of tenure for communal land holdings, pastoralists and customary land use and improving the transparency of land allocation.
Overall output score and description
The programme has scored an ‘A++’ for this annual review.

Output description	Score	Weighting	Indicator scoring
Output 1. 2nd level certificates issued recognising rights of joint, polygamous and Female-headed Household (FHH) land holders	A++	30%	All 3 indicators A++
Output 2. Land administration system implemented and operational in targeted woredas	A+	25%	2 indicators A+
Output 3. Improved supporting functions for the rural land market for poor male and female farmers	A++	25%	2 Indicators A++ and one A
Output 4. Improved policies and institutions for the rural land sector	A++	20%	One indicator A++

Summary supporting narrative for the overall score in this review (1/2 page)

LIFT continues to be a high performing programme, at the output level, justifying the score of A++. LIFT has navigated a series of challenges (including profound political reforms, an unpredictable security situation, and procurement delays) to continue to push the boundaries of what is possible in terms of economical and effective certification and administration of land, and reform of some of the supporting functions which govern how people are able to use their land, and on track to surpass a number of the end of the programme targets well ahead of schedule.
Same of the main achievements this year include: -
- Trendsetter. LIFT has continued to demonstrate the pace and cost of land certification that can be achieved at scale surpassing end programme target on demarcation and cost per certificate;
- Crowding in. The Government of Ethiopia (GoE) and other donors have increased their commitments to investment in both SLLC and RLAS following LIFT’s proven practices, adopting LIFT manuals and guidelines;
- Innovation. LIFT continues to employ new approaches for sustainable results such as the commencement of the model office and satellite office approach to ensure sustainability of Rural Land Administration System (RLAS);
- Economic empowerment – Focused on bolstering existing interventions and gathering evidence on their impact, ensuring sustainability, and piloting some new interventions;
- Policy reform – helped identify and plug key policy gaps acknowledged by stakeholders including Government. Notable this year is the ratification of a proclamation allowing the ‘land use rights’ of farmers to be used as collateral to access loans by the National Bank of Ethiopia; and
Since the pilot and scale up of Social Development Officers (SDOs) in May 2018, 2,248 parcels have been returned to 1,265 women and Vulnerable Group (VGs) in 67 woredas alone.

Still a lot to do. Despite the huge achievement brought by LIFT programme, the work is far from finished. With 14 million certified through the LIFT programme, 1.9 million through World Bank, 200,000 through USAID and 359,162 through Finland programmes, more than 38 million parcels remain without land certification. Land policy is still missing with continued disconnected between rural and urban land institutions and policies governing the sector. Current dispute resolution mechanisms do not adequately address issues facing women and vulnerable groups’ land rights. As such, DFID Ethiopia has designed and submitted the second phase of the LIFT programme for approval by January 2020.

Main recommendations for the year ahead (1/2 page)

Second Level Land Certification (SLLC)
- Follow-up on the recommendations and implementation of proposed actions to support Internally Displaced People (IDP) and their land rights in SLLC process to ensure their rights are upheld. Timing – March 2020; Implementing Technical Service Provider (ITSP) and DFID
- Investigate why women’s involvement in Land Administration Committees (LAC) is so low and what needs to be done to increase participation. Timing – March 2020; ITSP

Rural Land Administration System (RLAS)
- Develop action plan and closely monitor implementation to address the underperforming woredas on RLAS implementation. Timing – February 2020; ITSP
- Review the impact of regional and woreda restructuring on RLAS implementation. Timing – February 2020; ITSP
- Track the political commitment of the regional government and woreda by assessing allocation of resource (manpower and budget) as well as streamlining RLAS operations into mandates of Regional Land Administration Offices (LAOs) and Woreda LAOs. Timing – February 2020; ITSP

Economic Empowerment Unit (EEU)
- Conduct an assessment to better understand the existing financial products targeting women and VGs and identify opportunities for additional products and services. Re-examine sharia compliant assessments to ensure the financial products also meet the Muslim community’s needs. Timing – April 2020; ITSP
- Monitor the liquidity of MFIs to ensure the supply continues to meet the demand for loans including assessing opportunities that would enable MFIs increase their liquidity. Timing – Ongoing; ITSP
- Undertake a comprehensive study on sharecropping rental transactions to better understand the incentives or disincentives arising from knowledge, capacity, legal and social views with recommendation made for policy makers. Timing – March 2020; ITSP
- Establish a clear exit strategy for all EEU interventions with clear ownership of activities by the relevant partners in the sectors EEU is working in. Timing – May 2020; ITSP
- Advocate for ratification of relevant policies and legal framework to support existing interventions and ensure their sustainability, particularly in SNNPR, Oromia and Tigray. Lobby the Government for speedy execution of the legal framework as outlined in the home-grown economic reform. Timing – ongoing; ITSP and DFID
Policy work
Systematically tracking and contributing LIFT’s policy influence. Timing – ongoing; ITSP and DFID

Logframe
Log frame targets need to be reviewed to ensure stretching and ambitious results are set and definitions are clear. Timing – January 2020. ITSP, EETSP and DFID.

A Comprehensive review. The programme will undertake a detailed assessment of all the lessons generated from the programme as part of the Project Completion Report process in 2020 that will be used to inform future DFID programming in Ethiopia and to inform global approaches.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	2nd level certificates issued recognising rights of joint, polygamous and FHH land holders
Output number per LF		1	Output Score	A++
Impact weighting (%):		30%	Impact weighting % revised since last AR?	No

*Revised log frame targets approved July 2019. Vault no 50587856.
Indicator(s)	Original Milestone(s) for this review	Revised Milestone(s) for this review*	Result	%
1.1A. Cumulative number of parcels supported by LIFT for demarcation	13,690,000	13,690,000	13,846,992	101
1.1B. Cumulative number of parcels supported by LIFT for certificates approved	12,660,000	11,810,000	12,501,915	106
1.1C. Cumulative number of parcels supported by LIFT for certificates made available for collection at woreda land offices	12,200,000	11,300,000	12,224,561	108
1.2A. Percentage of second-level land certificates that are held in joint ownership by a male and female at the point of distribution	N/A	50%	71.77%	144
1.2B. Percentage of second-level land certificates that are held in the sole name of a woman at the point of distribution	N/A	15%	19.27%	128
1.2.C. Percentage of second-level certificates that are held in the sole name of a man at the point of distribution	N/A	5%	8.96%	179
1.3. Cost per certificate issued with LIFT support (£)	£3.54	£3.79	£3.44	110

Key points

LIFT has continued to make impressive progress in SLLC to deliver at pace. Due to external factors such as political instabilities (security issues, organisational reform and political reform) and procurement delays the programme had to reduce targets for output 1.1B, 1.1C and 1.3 (see approval note for logframe revision on vault no 50587856). Yet LIFT managed to exceed:
All revised targets. LIFT’s has managed to demarcate 13,846,992 (target of 13,690,000), approve 12,501,915 (target of 11,810,000) and printed and made available for collection 12,224,561 (target of 11,300,000). This means in this year alone, LIFT has managed to demarcate 4,013,887 parcels, 4,317,015 certificates have been approved and 4,543,576 certificates have been printed and made available for collection setting a world record for demarcation in one year.
SLLC Output	Original Targets	Status Oct 31 2019
Demarcation	13,690,000	14,079,531
Approval	12,660,000	12,662,128
Printing	12,200,000	12,341,806
Distribution	9,028,000	10,094,904

- Original targets for 2019. LIFT has also managed to deliver an additional 24,561 certificates available for collection at woreda land offices beyond the original target. Cost per SLLC has also been reduced considerably over the past 12 months from the original targets of £3.54 to £3.44. Furthermore, the original approval and printing targets set for this year were surpassed by October 2019 eliminating the backlogs created by external factors and bringing the programme back on its fast track.
- Original target for end of year programme. The LIFT programme has not only outstripped the end of year target for cost per parcel at £3.44 (from £3.54) but has now surpassed the demarcation target achieving 14,079,531 parcels demarcated by October 2019 and in doing so setting a world record for cost and scale of land certification operations.

LIFT has also made great progress in working with the Government of Ethiopia to ensure the distribution of certificates to landholders. While in September 2018 the backlog was still at 20.6% of the certificates available for distribution, this has reduced to 18.3% in September 2019, showing a continuous improvement in reducing the distribution backlog. The Regional Government allocated budgets to organise regional level workshops (including zonal office, zonal administration, regional administration) to be more engaged in certificate distribution. This is mirrored in the high distribution figures between October 2018 and September 2019, where overall 3,639,120 certificates were distributed to landholders, breaking the annual distribution record for the programme. This also meant that LIFT managed to exceed the September 2019 distribution target by 706,379 certificates as of 31st September 2019. The Government of Ethiopia has clearly exceeded its targets and needs to be commended for their efforts.
[note] As of 19th September 2019. The end-of-programme Logframe targets for number of certificates printed and number of certificates distributed is estimated at 26%.

	No of individuals	No of parcels
VGs	1,265	2,348
Of which are women	814	1,580

Gender equality and social inclusion (GESI) work continues to improve land rights of women and Vulnerable Groups’ (VGs’). The scale up to full capacity of the Social Development Officers (SDOs) has also improved the related monitoring and evaluation procedures. As of September, a total of 2,348 parcels have been restored to 1,265 VG landholders of which 1,580 parcels have been restored to 814 female landholders. In addition, the programme has placed greater focus on undertaking research in order to a) highlight the positive impact that the SDOs have made in ensuring women and VGs are included in the SLLC process and b) ensure that the land rights of women and VGs are maintained post-SLLC with close engagement with Government on recommendations. With the additional GESI team recruited, the programme was also able to enhance its M&E process by compiling monthly reports on the impact of SDOs as well as making the report compatible with the Management Information System (MIS).

Gender equality for all. LIFT programme not only protects the rights of women and vulnerable groups but also men and the landless youth as well. This year, not only women (joint or as single) were registered more but also men.

Political instability and reform are now the biggest risk to the programme. There have been multiple cases of civil unrest and political rallies across Amhara, Oromia and SNNPR since September 2018 that have impacted programme delivery. In Oromia, almost half of SLLC active woredas were affected by security issues (some starting as far back as the end of 2018). Although the State of Emergency that impacted LIFT in the previous year was lifted in June 2018, new State of Emergencies were imposed in Amhara (due to the assassination of Amhara’s President and Chief Justice Officer) in June 2019 and in SNNPR (due to ethnic conflict and demonstration) in March 2019. The resulting civil unrest and demonstrations have had a severe impact on back-office and public display events. Furthermore, Ethiopia is currently going through unprecedented political reform that has induced changes of mid-level officials at the zonal and woreda levels as can be seen in the table below. This has contributed to significant backlogs in the SLLC process until the staff were replaced and oriented to the LIFT programme. This was further compounded by woreda administrations restructuring, resulting in the subdivision of several SLLC operational woredas. This year alone, 13 woredas in Amhara, Oromia and SNNP regions were split into 29 woredas. This has had significant resource implications.
Region	#SLLC operational woredas*	#woreda staffs changed	% woredas with staff changes	#Staffs left RLAO	#woreda Head changes	#zonal head changes	Total staffs left
Amhara	22	4	18%	3	4	3	10
Oromia	30	3	10%	0	3	0	3
SNNP	15	6	40%	2	6	0	8
Tigray	6	1	17%	0	1	0	1
Total	73	14	19%	5	14	3	22

        *Oct 18 - Sept 19

Internally Displaced People (IDP) and land rights improvement – LIFT has also completed a study into the way that IDPs are managed within the SLLC process with several useful recommendations. This is currently with DFID for review and if accepted, the recommendations will be added to the SLLC Manual.

Lessons identified this year,
- Importance of political intelligence. As the country continues to go through political reform, its critical that the programme remains in a position to get accurate and timely information on the situation to ensure the programme can adjust accordingly.
- GoE capacity and planning. This is a continuing challenge for the Government of Ethiopia, particularly with staff turnover and change due to political reforms that will require closer management and support to ensure timely delivery of results.

Recommendations for the year ahead linked to this output
- Asset disposal exit strategy to be finalised as the programme starts to unwind. Timing – Feb 2020; ITSP and DFID
- Follow-up on the recommendations and implementation of proposed actions to support Internally Displaced People (IDP) and their land rights in SLLC process to ensure their rights are upheld. Timing – March 2020; Implementing Technical Service Provider (ITSP) and DFID
- Investigate why women’s involvement in Land Administration Committees (LACs) are so low and identify what needs to be done to increase their participation. Timing – March 2020; ITSP
- Log frame targets need to be reviewed to ensure stretching and ambitious results are set and definitions are clear (particularly for indicator 1.2). Timing – January 2020. ITSP, EETSP and DFID.

Output Title	Rural Land administration system (RLAS) implemented and operational in targeted woredas
Output number per LF		2	Output Score	A+
Impact weighting (%):		25%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	%
2.1 Number of woreda offices in which RLAS is being implemented and at least 10 transactions have been processed	105	110	105%
2.2. Number of woreda offices in which RLAS has been operational for 12 months or more that pass the RLAS implementation assessment	67	69	103%

LIFT has continued to roll out and operationalise RLAS. Effective operationalisation of RLAS to sustain the long-terms benefits of land reform is a key responsibility of the regional and woreda governments. LIFT supports the capacity building of the regional and woreda governments through the provision of materials/equipment, training of the regional and woreda staff, RLAS processes and system updates and carrying out regular implementation monitoring assessments. Despite the external challenges explained above, LIFT has been a) installing RLAS and providing the necessary training and back-up support and b) implementing the RLAS action plan to ensure the sustainability of RLAS. Major achievements include:
- Exceeded targets. LIFT has installed RLAS in 33 woredas bringing the cumulative total of woreda offices with RLAS to 110 and has therefore surpassed the target of 105.
- 30,416 transactions were registered from 1st September 2018 to 31st October 2019 which is a massive increase from 12,939 transactions that were recorded in the previous year. 31.6% of all land transactions were formally registered by landholders, with credit being the most likely to be formally registered at 100% of transactions registered (excluding sharecropping) followed by inheritance at 39% registered.
- Focused on sustainability. To ensure the sustainability of RLAS, the programme launched innovative interventions such as the model office and satellite office initiatives.
- Better coordination with Economic Empowerment Unit work. By working closely with the EEU team, the system is being developed to accommodate economic activities such as RLAS/NRLAIS prerequisite templates for credit transactions. A significant effort was also made in advocating for the registration of all land rental transactions in Tigray through lobbying the regional land bureau to issue a directive to the WLAUOs. This was confirmed by the RLAS Transaction Survey that found that rental transactions, but also other land transactions, are significantly more likely to be formalised in EEU locations when compared to non-EEU locations.
- Crowding in. The RLAS business case was presented to the G7 Land Partnership group and this resulted in the World Bank establishing the USD 165 million Climate Action Through Landscape Management (CALM) programme to support land administration activities. In addition, by providing resource to develop the Project Implementation Manual (PIM) for the Rural Land Administration deliverables for CALM, LIFT ensured that new programme/CALM activities will complement LIFT’s priorities to achieve a sustainable and well-resourced RLAS (NRLAIS).
National Rural Land Administration System (NRLAIS) now operational in 23 woredas. Developed by the Finnish funded Responsible and Innovative Land Administration in Ethiopia (REILA) programme, the system is now being rolled out. By the end of last year, only eight woredas were piloting NRLAIS but now, with the support from LIFT programme, 23 woredas in Amhara with 6 woredas in Oromia have commenced implementation after received training and material support. There has been a delay in developing the credit module on NRLAIS that impacted the pace and quality of roll-out, but this is now on track to be implemented by the end of December 2019.

69 woredas passed the implementation assessment process. The assessments to September 2019 have covered 69 woredas where RLAS has now been in operation for 12, 18 or 24 months. 69 woredas passed this new implementation assessment process. 18 are underperforming and require several improvements such as organisational capacity via recruitment and training of new staff, allocation of service delivery time by woreda staff to register transactions and back-up support and monitoring of KLAC members in filling transaction application forms.

The RLAS transaction survey confirms land rental (particularly share cropping) and credit as the main transactions. The survey confirmed sharecropping (30.4%) followed by rent and gifting (each 6.8%) and credit (2.1%) as the main transactions engaged in by households either formally or informally. Although all Regions require that all land rental agreements be registered, not all require woreda level registration. Additionally, sharecropping transactions are almost entirely informal, which should be further explored. If the woreda level registration was required in all regions, then the number of transactions would be much higher than the current 31%.
Region	#RLAS operational woredas	#woreda staff changed	% woredas with staff changes	#Staff left RLAO	#Staff left WLAO	Total staff left
Amhara	23	11	48%	3	13	16
Oromia	36	8	22%	0	12	12
SNNP	32	24	75%	2	38	40
Tigray	19	13	68%	1	33	34
Total	110	56	51%	6	96	102

Policy limitations still hamper the pace and trajectory of the programme. Over the past 12 months limited progress was made on reversing policies to improve the enabling environment such as the recommendation to reverse the policy decision to downgrade land administration positions and pay scales. DFID formally raised this with the State Minister of the Ministry of Agriculture and Natural Resources and further raised this at the Programme Steering Committee. The same approach was taken with the still pending federal land proclamation yet to be approved by the Parliament. Although no response was received, the GoE has now harmonised salary scales across different Ministries and Departments and therefore this action was considered as closed in June. Due to the current political reform and competing priorities, the other pending policies could not be pushed through to completion.

Political reform also presents the biggest risk for RLAS. The new wave of political reform in the whole country has also induced changes of mid-level officials at the zonal and woreda levels that have impacted the RLAS process as many trained experts have left as can be seen in the table below. Woreda restructuring has also created 29 new woredas by splitting 13 woredas in Amhara, SNNPR and Oromia region. The highest number is recorded in the SNNP regional state, where the former 11 woreda administrations are split into 25 new woredas. From these woredas, 12 new woredas are eligible for RLAS operations and therefore created a need for additional new RLAS/IWORLAIS materials/equipment. There are instances where RLAS woredas have been subdivided, with kebeles allocated to existing woredas without RLAS (and vice-versa). Same with the creation of a new region with the creation of Sidama Region where four LIFT woredas exists. These reforms in administrative structures have a strong bearing on RLAS operations. These include:
- Supply of RLAS/iWoRLAIS equipment/materials: New RLAS/IWoRLAIS equipment/materials are required for newly created woredas located in Amhara, Oromia and SNNP regional states. In Amhara and Oromia regional states, the RLAOs supplied the required RLAS equipment’s/materials to the newly created woredas. While for the 12 newly created woredas in the SNNPR, which are eligible for RLAS operation, new RLAS equipment /material must be supplied considering multiple factors including: whether SLLC is complete throughout the whole woreda, availability of staffing, stability/security and other factors. LIFT is currently undertaking an assessment of these factors prior to installing RLAS.
- Training of woreda staff for the newly created RLAS woredas: Most of the newly created woredas are in the establishment phase, and in the process of hiring new staff, arranging office facilities etc.
Lessons identified this year
Capacity of the Government to deliver. Its vital to have a strengthened training and awareness raising work on RLAS to ensure the new staff within Government are up-to-speed on how the land administration system works and that they can maintain it.

Recommendations for the year ahead linked to this output
- Develop action plan and closely monitor implementation to address the underperforming woredas on RLAS implementation. Timing – February 2020; ITSP
- Assess the progress of RLAS action plan including its impact on uptake and sustainability. Timing – February 2020; ITSP
- Review the impact of regional and woreda restructuring on RLAS implementation. Timing – February 2020; ITSP
- Track the Political commitment of the regional government and woreda by assessing allocation of resource (manpower and budget) as well as streamlining RLAS operations into RLAOs and WLAOs mandate. Timing – February 2020; ITSP
- Explore option to use Land Rental Service Providers (LRSPs) for RLAS work by identifying the services that could be included in the LRSPs’s service offer. Timing – January 2020; ITSP
- Completion of NRLAIS – LIFT to engage with REILA II on the credit module with the module developed and made available. Timing – January 2020; ITSP and REILA
- Follow-up on CALM programme to ensure synergy with LIFT. Timing – ongoing; ITSP

Output Title	Improved supporting functions for the rural land market for poor male and female farmers
Output number per LF		3	Output Score	A++
Impact weighting (%):		25%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	%
3.1. Number of new innovations introduced by LIFT in the A2F, LR and Agr. input sectors, disaggregated by innovations that encourage env. sustainable practices	8 / 2	10 / 2	125% / 100%
3.2. Cumulative number of market actors that have adopted and continue to promote LIFT innovations, disaggregated by: / MFIs / MFI branches / LRSPs / woreda offices that enact the Standard Land Rental Contract (SLRC) / Input retailers / Input suppliers	MFIs: 7 / MFI branches: 103 / WLAOs: 35 / LRSPs: 430 / Input Retailers: 65 / Input Suppliers: 13 / Total: 653	MFIs: 7 / MFI branches: 120 / WLAOs: 41 / LRSPs: 525 / Input Retailers: 116 / Input Suppliers: 12 / Total: 821	126%

Key points
LIFT focused on bolstering existing interventions and gathering evidence on their impact, testing different approaches to ensure sustainability. As LIFT has less than 12 months left, the programme has prioritised the soundness of existing interventions by providing technical assistance to the MFIs on the SLLC-linked loan, facilitated cascading of the LRSP model to remaining kebeles in intervention woredas and supported input suppliers to improve the linkages with partner retailers. Additionally, LIFT has undertaken work to ensure the sustainability of the interventions such as testing a LRSP payment scheme in SNNPR and Tigray. LIFT has also piloted a new micro-insurance product and identified interventions to improve the dispute resolution system. Ethiopia’s recent home-grown economic reform launched September 2019 clearly emphasises the need for a legal framework which would allow farmers to lease their land use rights. Furthermore, the strategy has identified the gap in legal framework for agriculture-specific financial services such as micro-lending, crop insurance, and forward contracts where LIFT is already piloting innovative products.

LIFT has not only exceeded its targets for the year but has also exceeded its end of programme logframe targets with 821 (target for 2019 was 653 and 2020 was 711) market actors having adopted and continuing to promote 10 innovations (target of 10). Furthermore, qualitative and quantitative assessments undertaken by the EEU have shown that in general LIFT’s theory of change and existing assumptions hold true i.e. there are significant improvements in investments, productivity and income due to the EEU interventions.
[note] Nathan Associates London Ltd 2019. EEU Impact Survey Report 2019. Land Investment for Transformation (LIFT) Programme. DFID Ethiopia. May

Access To Finance (A2F):
The loan product has expanded to 120 branches of the seven partner MFIs with 13,328 loans worth £11 million disbursed to 10,699 beneficiaries (35% to women). In addition, 11 branches in seven non-LIFT woredas have issued 279 loans worth around £300,000. More than £1 million savings were mobilised. The multi-peril crop insurance product was also developed and piloted in two woredas in Amhara. LIFT successfully lobbied the National Bank of Ethiopia (NBE) to include SLLC as a movable property security for accessing credit in its draft proclamation that was ratified allowing the ‘land use rights’ of farmers to be used as collateral to access loans. A default census was conducted to better assess the status of defaults among partner MFIs. Currently the overall portfolio at risk (PAR) above 1 days and 90 days are 2.37% and 0.47%, respectively. This is well below the industry average and the NBE requirement. Default management technical assistance including training, guidelines, templates and an implementation plan were developed and shared with partner MFIs. Liquidity will become an issue if the product is going to meet the current demand.
[note] Percentage of female loan clients per MFI: ACSI – 51.12%, AGGAR 6% –OCSSCO 19. % –OMFI 14.7%, PEACE – 46.5%, WASASA - 17.4%, Harbu 22.2.5% and per region: Amhara – 51%, Oromia – 18.5%, SNNPR – 10%

Economic Empowerment Unit (EEU) impact survey highlighted that overall satisfaction with the loan is high with 75% for males and 85% for females. The requirement of having a spouse’s signature on the loan agreement has increased women’s awareness and decision making when it comes to household finances. Out of the respondents, 81% stated joint-decision making increased due to the joint signature requirement for accessing the loan and 88% stated that they are more actively participating in household finance decisions due to the SLLC loan.

LIFT has launched a multi-peril area yield index insurance product following lessons learnt from a previous pilot undertaken with ATA/Kifya on micro insurance. Currently, this is being piloted in partnership with ACSI and Abay Insurance, with ACSI being the distribution channel for the product. So far, two pilot woredas have issued a total of 46 policies. The low number is due to substantive delays created by getting the partners and NBE on board but is expected to increase in outreach once the lessons from the pilot have been incorporated.

Formalising Land Rental (LR):
In total 19,278 rental transactions have been formalised with over 700 LRSPs trained and 525 are operational in 32 woredas. 1,393 land office staff have been trained on the use of the rental contract and the need for LRSP services in non-LRSP kebeles. Formalising the sector was boosted through woreda land offices cascading Land Rental Service Providers (LRSPs) training to all the kebeles with LIFT’s support and a total of 536 kebeles have now been reached. LRSPs need to strengthen their efforts to ensure sharecropping transactions are formally registered as it is currently the highest transaction made by rural households. There is room to further explore the possibility of formally registering sharecropping and this requires multiple studies to understand the different perspectives and practices of sharecropping in the nation. This may include the magnitude, reasons, social views and understanding of the parties practicing it, the capacity of the local land institutions, legal gaps and possibilities, etc.

To address the lack of incentives and ensure the sustainability of LRSPs, LIFT supported four woredas in SNNPR and Tigray to pilot an LRSP payment modality. A key factor identified during the different assessments were the high costs incurred by LRSPs in facilitating the formalisation of land rental contracts. These included, for example, hiring daily labour to cover their farming tasks, making copies of contracts, making telephones calls and transport. The pilot has received support from clients, kebele and woreda officials who have asked for its scale up. Assessment of the payment pilot showed i) community members are very willing and able to pay LRSPs for their services; ii) LRSPs are interested in becoming licensed entities; iii) woreda land offices are very much in support of this effort and believe further formalisation will help bolster the LRSP and iv) other relevant government stakeholders such as the trade and tax offices are able and willing to incorporate LRSPs within the relevant structures for licensing and tax. Close monitoring of the roll-out is necessary. The other added benefit is that LRSPs are well positioned to offer other land related services to the community such as providing information on other land transactions such as inheritance and gift that would contribute to the sustainability of RLAS.
Regions	Structure	Initial pilot fee	Suggested fee identified during pilot assessment	Key costs incurred	Profit	Proposed (rentee and renters)
Tigray	Proportional to size of land	25 ETB / 0.25 HA per renter and rentee i.e. 50ETB total for 0.25 HA	75 – 200ETB /0.25 HA with renter ¼ and rentee paying ¾.	220	25% (i.e. 54.88)	275 ETB per 0.25 HA. / Renter – 69 ETB / Rentee – 206 ETB*
SNNPR	Flat rate	50 ETB / Contract from both renter and rentee i.e. 100ETB per contract	200 - 300 per contract i.e. with renter paying ¼ and rentee paying ¾.	220	25% (i.e. 54.88)	275 ETB total per contract / Renter – 69 ETB / Rentee – 206 ETB

*For a transaction which is above 0.25 HA, an additional 25% will be charged.

Environment and Conservation Agriculture (ECA):
106 input retailers are operational and actively promoting and selling agricultural inputs. LIFT has focused on reinforcing the direct linkages created between suppliers and retailers and ensuring that relevant woreda level stakeholders ensure proper demonstrations and trainings on inputs. Over £0.3 million in sales have been recorded by LIFT’s ten partner input suppliers so far.

LIFT re-assessed the logic of its supplier-retailer direct linkage model following last year’s annual review, two qualitative assessments and an impact survey were carried out to ensure LIFT was achieving its goals. The findings were i) suppliers are adopting and adapting the model by expanding to non-target woredas, employing incentive mechanisms with retailers such as commissioning and assigning full-time staff for regional promotion; ii) retailers are increasing their sales significantly because of the supplier linkages. They are also increasing the offering of training/advisory services and passing on the price advantage gained from suppliers to farmers; and iii) farmers now have enhanced knowledge on inputs and their application. The survey was able to attest a substantial gain in productivity as a result of the intervention. The programme will continue to monitor and support implementation of the interventions as per the agreed action plan.

Recommendations for the year ahead linked to this output
- Conduct an assessment to better understand the existing financial products targeting women and VGs and identify opportunities for additional products and services. Re-examine sharia compliant assessments to ensure the financial products also meet the Muslim community’s needs. Timing – April 2020; ITSP
- Evaluate how the default management guide has been mainstreamed in MFI’s operational manuals and/or as a stand-alone manual. Pilot implementation of the default management guide in select branches and evaluate the results. Timing – May 2020; ITSP
- Monitor the liquidity of MFIs to ensure the supply continues to meet the demand for loans including assessing opportunities that would enable MFIs increase their liquidity. Timing – Ongoing; ITSP
- Undertake a comprehensive study on sharecropping rental transactions to better understand the incentives or disincentives arising from knowledge, capacity, legal and social views with recommendation made for policy makers. Timing – March 2020; ITSP
- Assess the feasibility of different payment modalities for rental payment system as well as roll-out to ensure the product meets the beneficiaries’ needs. Timing – May 2020; ITSP as well as assessment on licensing and tax appropriate for the LRSPS. Pilot the recommended payment modality, licensing, and relevant taxation in select woredas in Tigray and SNNPR alongside regional land offices. Timing – May 2020; ITSP
- Establish a clear exit strategy for all EEU interventions with clear ownership of activities by the relevant partners in the sectors EEU is working in. Timing – May 2020; ITSP
- Advocate for ratification of relevant policies and legal framework to support existing interventions and ensure their sustainability, particularly in SNNPR, Oromia and Tigray. Lobby the Government for speedy execution of the legal framework as outlined in the home-grown economic reform. Timing – ongoing; ITSP and DFID
Output Title	Improved policies and institutions for the rural land sector
Output number per LF		4	Output Score	A++
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress (as at 30 September 2018)	%
4 – Number of research-based land policy reports, regulations, procedures, strategies and plans produced and delivered to the Government of Ethiopia and other key stakeholders that strengthen structures and processes for improved land certification and administration in Ethiopia or knowledge products which make new data or understanding available to a broad range of stakeholders (cumulative target)	65	79	122

Key points
LIFT continued to focus on advancing policy change related to the programme’s work. As the programme will come to its completion date on August 2020, LIFT’s main areas of focus under Output 4 have been; 1) disseminating LIFT’s accumulated knowledge within the Ethiopian land sector 2) producing result-based research showing LIFT’s impact. By the end of September 2019, LIFT had completed the following additional research papers under Output Indicator 4, bringing the cumulative total to 79. Outputs for this year include:
- EEU: Assessment of land dispute resolution systems in Ethiopia in the context of SLLC and an improved RLAS
- GESI: Land Certification: Ensuring no one is left behind (Policy Brief)
- GESI: Impact of the SDO on women and VG’s inclusion in SLLC and Administrative Constraints to Ensure Women and VGs Land Right Security (Research Paper) and Strategy to address issues in three non-SDO woredas (pilot)
- GESI: Addressing Legal Constraints to Enhance Land Right Security of land holders post-SLLC (Research Paper)
- GESI: Protecting Land Tenure Security of Women in Ethiopia: Evidence form the Land Investment for Transformation Programme
- RLAS: Formal Registration of Land Transactions in Ethiopia
- RLAS: LIFT’s Economic Empowerment Unit (EEU) incentivises landholders to keep their SLLC up-to-date
- RLAS: Model woreda MoU (establishes responsibilities of LIFT, LAUTT and REILA II and budget contributions)
- RLAS: Framework on Land Administration Best Practices for the Model woredas
- RLAS: Model woreda Office MoU (one between Zonal Land Administration Office & Regional Land Office and one between Zonal Land Administration Office and woreda Land Administration Office)
- RLAS: CALM P & R Project Implementation Manual
- EEU (LR): Impact of LRSPs on formal rental transactions taking place and use of rental contract
- EEU (A2F): To what extent does access to credit (SLLC loan) increase incomes and benefits the poor, women and VGs? (DFID Lesson Learning)
- EEU (ECA): Impact of purchasing high quality inputs from woreda level retailers because of supplier-retailer network
- EEU (ECA): Policy on need for private retailers to have separate licenses and amending this (results on impact from above feeds in)
These outputs were selected to meet programmatic needs, produce strategies or procedures for GoE stakeholders, inform future initiatives by GoE or development partners, or advance learning about the land sector in Ethiopia. Additional outputs are due to be completed by October/November 2019 as follows:
- SLLC: Examine the challenges of ensuring land tenure rights of IDPs through SLLC and potential means to ensure this.
- GESI: Examining Women’s Economic Empowerment Impacts of the SLLC-linked loan and potential unintended negative impacts (strategy will be developed to mitigate any negative impacts identified)
For effective access and dissemination of LIFT’s products, the programme has
1. Completed development of a website. The website will assist in disseminating LIFT’s knowledge through:
  1. Publishing news stories and case studies that will be distributed to stakeholders through an electronic newsletter. It is planned that the newsletter will provide brief summaries with a link to LIFT’s website where the news story can be read, and a PDF downloaded (as LIFT is aware that stakeholders have a preference to print materials).
  2. Creation of an online knowledge hub where all of LIFT’s relevant Output 4 research will be uploaded for public consumption. To ensure that this information can be easily digested by viewers 4-sider summaries are currently being developed and will be uploaded (as well as the full reports). Currently LIFT has had the following research papers/reports summarised:
    1. EEA Transaction Study (Graphics Completed)
    2. Assessment of Constraints in the Land Regulatory Frameworks in Tigray and SNNPR
    3. Assessment of Rural Land Rental Determinants
    4. What are the Challenges for Decentralising Large-scale Land Registration?
    5. Can land registration LIFT farmers out of poverty in Ethiopia?
    6. How can Second Level Land Certification protect women and vulnerable groups in Ethiopia?
    7. Is second level land certification (SLLC) being implemented in a conflict-sensitive and dispute-resolving way?

1. International and national conferences. Three LIFT papers were presented as posters at the 2019 World Bank Annual Land Conference in Washington and included 1) Understanding the use and management of communal land in the highland regions of Ethiopia, 2) Formalisation of Rural Land Rights Transactions; the Search for an Innovative Approach in Ethiopia and 3) Innovative private sector initiatives to incentivise public buy-in to Land Administration Services – examples from Ethiopia. Additionally, LIFT’s study on Protecting Land Tenure Security of Women in Ethiopia was presented at the 4th Annual Land Conference in Bahir Dar University which occurred on 24/25th May 2019 to other land programmes and research institutes.
2. Media Engagement: The programme explored the use of media outlets to disseminate knowledge and increase LIFT’s profile. LIFT has engaged with the Ethiopian News Agency (ENA) on news items which included an introductory piece on LIFT and LIFT’s work on protecting women and VG’s land rights. The article was published on ENA’s website in June https://www.ena.et/?p=53535. LIFT did examine the option of contracting TV channels to host TV debates and specific programs for LIFT. The costs however could not be accommodated under LIFT’s budget. This will be reassessed next year, however a recent opportunity with the MoA to host a joint land conference with other donors and utilise a media company to promote this as well as the conference topics has arisen, and LIFT will pursue this option in the coming months.

Recommendations for the year ahead linked to this output
- A greater focus on delivering genuine policy influence. Timing – ongoing; ITSP and DFID
- Systematically tracking and contributing LIFT’s policy influence. Timing – ongoing; ITSP and DFID
- Re-assess the possible options of engaging with the media if any efficiencies or savings are identified based on other component’s needs. Timing – Feb 2020; ITSP

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

No changes were made to the programme’s theory of change (ToC). The core logic underpinning ToC of most land programmes is well-established: namely, that if landholders feel secure in their land tenure, then they are more likely to invest in and improve their land. Incomes will rise as a result. To ensure that security of tenure is sustainable, rather than being a one-off resulting from the registration and certification of land, a land administration system is introduced to record any changes and ultimately ensure that the land certification is kept up to date.
What makes LIFT unique and innovative is the scale and speed at which the programme is working as well as the use of Making Markets Work for the Poor (M4P) approach for the Economic Empowerment Unit (EEU). The purpose of the EEU is essentially to catalyse and enhance land tenure security impact by addressing any market constraints that might prevent landholders from investing in their land, whether due to a lack of capital (addressed through the EEU’s Access to Finance interventions), concerns over the security of renting land in or out (the land rental interventions), or a lack of access to agricultural inputs and how to use them appropriately (the Environment & Conservation Agriculture interventions). The ToC shows how SLLC, RLAS and the EEU are interrelated. Please see last year’s Annual Review for further details on the ToC that was revised last year.
EEU Impact survey, RLAS transaction survey, and desk-based research have provided rich evidence on existing theory of change assumptions, including on:
- SLLC process leads to high certificate collection rates
- Women’s rights are maintained over time through subsequent transactions
- EEU creates demand for SLLC and formal registration
- EEU leads to increased investment, productivity and incomes
- Women and poor households benefit from EEU
- Proximity to roads has a strong impact on registering land transactions in RLAS

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

LIFT has undertaken several large-scale surveys and studies, which has provided clear evidence that the programme is on track to achieve its intended outcomes. The programme focused on designing and conducting high-quality quantitative and qualitative research that follows rigorous methodologies as listed below:
- EEU Impact Survey (Outcome 2B) conducted in February/March 2019 to provide evidence on whether the EEU’s land rental and access to finance interventions lead to increased investment, productivity and incomes.
- RLAS Transaction Survey (Outcome 1A and Outcome 3) conducted in June/July 2019 to provide quantitative and qualitative evidence on the percentage of subsequent land transactions that are formally registered, considering social and economic factors, and proximity to WLAO.
- ECA Impact Survey (Outcome 2A and 2B) was conducted in August 2019 to provide quantitative evidence on the number of beneficiaries from the EEU’s ECA input supplier intervention, as well as the percentage of ECA beneficiaries that increased investment in improved inputs leading to an increase in productivity.
- Study on subsequent transactions to identify whether the rights of women are maintained over time (Outcome 1B) (desk-based research using data sourced from IMASSREG and IWORLAIS) to report on Outcome Indicator 1B.

Another large-scale survey is planned for October/November 2019 to provide evidence on whether SLLC leads to an increase in perceived security of tenure, which in turn would lead to investment and productivity increases (one of LIFT’s key theory of change assumptions). Findings from this survey will be available in December.

The above surveys and studies provided rich evidence to show how LIFT’s outputs have led to the anticipated outcomes and, in the case of EEU, contributed to anticipated impact-level results. This allows the programme to confirm key theory of change links, including on:
- How the SLLC process leads to high certificate collection rates;
- How the EEU’s market systems-based approach magnifies and accelerates the impacts of land certification, leading to increased investment, productivity and incomes for farmers;
- How rental formalisation and the SLLC-linked loan specifically lead to increased investment, productivity and incomes for farmers;
- How rental formalisation, land rental service providers (LRSPs), and the SLLC-linked loan benefit poor farmers and women;
- How the EEU’s market systems innovations creates a demand for SLLC and provides incentives for landholders to formally register land transactions more frequently; and
- How women’s rights are maintained over time through RLAS.

Outcomes

SLLC – Outcome 3
- LIFT has overachieved against this indicator by 706,379 certificates, equivalent to 107.8% of the target, by distributing 9,734,379 certificates against a logframe target of 9,028,000 certificates.
- While there have been initial difficulties in securing commitment from the regional governments, LIFT organised workshops at the beginning of August to agree ambitious targets to reduce the existing backlog. This effort was very successful, with regions having invested the required resources to distribute a large number of certificates throughout August and September.
- Additional verification of high collection rates was provided by the RLAS transaction survey. It was found that for 92.1% of all certified parcels, the landholder collected and held their certificate, providing verification of the effectiveness of certificate distribution events. These findings are deemed to be robust, considering the survey was designed to be representative of the population, with 9,600 households sampled across the four programme regions.
- Evidence of LIFT’s EEU innovations creating demand for certificate collection was found through the EEU Impact Survey. 72% of all SLLC-linked loan (A2F) beneficiaries stated that the prospect of taking-up the loan had initially motivated them to collect their certificate and keep it up-to-date.

RLAS – Outcome Indicators 1A and 1B
- LIFT has overachieved with 31.6% of all land transactions being formally registered in RLAS, against a target of 30% on Outcome Indicator 1A. 17.3% of all rental, 100% of all credit transactions and 28.2% of all other transactions were formally registered.
  [note] This figure excludes sharecropping as registering this transaction type is not required
- 100% of access to finance linked to SLLC registered. The high percentage of formalised credit transactions is explained by a) no alternative in using SLLC for loan and b) there is high compliance of MFIs and landholders with formal procedures required to obtain the SLLC-linked loan. The SLLC-linked loan is a formal transaction since the loan will not be issued without the landholder presenting an official blocking letter.
- A strong effect of the EEU component on formally registering land transactions in RLAS was found, both for rental transactions and other non-EEU transactions such as inheritance. This provides proof for the programme’s theory of change assumption that the EEU component creates demand to keep SLLC up-to-date and sets incentives for formal registration.
- This is the first time that it was measured through a statistically representative survey covering all operational RLAS woredas across all four programme regions. The percentages indicated have high statistical validity, and a follow-up survey will be conducted in April 2020 to report on progress against this indicator again.
- Outcome 1B measures whether the rights of women are maintained after subsequent transactions are registered over time in RLAS. This is done by comparing the percentage of certificates that are held in joint, sole female or sole male ownership at the point of certification (iMASSREG) with the latest status reported in RLAS this year (through iWORLAIS data back-ups). It was found, that the percentage of parcels that are held in joint ownership was maintained at 71.75% compared to a target of 50% - with a slight decrease of 0.02 percentage points when compared to the initial registration reported under Output 1.2. Similarly, the percentage of parcels held by a sole female and a sole male were maintained at 19.33% and 8.92% respectively – surpassing the targets of 15% (sole female) and 5% (sole male). Compared to Output 1.2 parcels held by sole males reduced very slightly by 0.04 percentage points, while parcels held by sole females increased slightly by 0.06 percentage points. Note that changes noted in the percentages are very small because of the total number of transactions being small compared to the total number of parcels held.

EEU – Outcome Indicators 2A and 2B
- Overall 87,859 farmers have directly accessed an innovation introduced by EEU. LIFT has overachieved on Outcome 2A by making great progress last year on reaching farmers with market systems innovations across the four programme areas. Compared to a target of 76,554, this indicates that 114.8% of the target was achieved. 11,414 of EEU beneficiaries are SLLC-linked loan clients, 30,321 are land rental beneficiaries, 33,480 are clients of ECA retailer shops, and 12,644 are farmers benefitting from best-fit practice training.
- An average of 71% of farmers that had accessed an EEU innovation, change their behaviour and investment more in improved inputs and other/new income-generating activities. LIFT has also overachieved on Outcome 2B as per the findings from both the EEU Impact Survey and the ECA impact survey. This implies both an improvement compared to when this indicator was measured last in 2017, and, against a target of 65% demonstrating that 109.23% of this year’s target was hit.
- EEU innovations benefit women: 23% of farmers that have increased investment are women, showing how EEU innovations offer new opportunities for both males and females to benefit, considering beneficiaries across the Access to Finance, Rural Land Rental, and ECA components. Compared to a Logframe target of 20% of farmers with increased investment to be females, LIFT is overachieving the target at 115%. This is further supported through findings from the EEU Impact survey, where 83% of women stated that they invested the SLLC-linked loan in income-generating activities, and 88% stated that they could not have placed the investment without the SLLC linked-loan. Also 85% of women showed high satisfaction with the SLLC-linked loan. Overall, there is strong evidence to show progress towards LIFT’s outcomes, with rental formalisation, SLLC-linked loan and availability of improved inputs through EEU’s input supplier model leading to increased investment of farmers.
- Crowding in. Findings are further supported through the EEU’s semi-annual qualitative assessments, which found that in the access to finance have also begun disbursing the SLLC-linked loan without support from LIFT. Regarding rural land rental, both SNNPR and Tigray regional land bureaus have signed MoUs to test out the payment of LRSPs for their service. The payment pilot has gone well with community members accepting the fee and even requesting an increase to support the LRSPs. Furthermore, the regional land bureaus and other relevant offices are engaged in supporting the licensing and certification of LRSPs. For the ECA intervention, the EEU has observed that suppliers are reaching out to retailers outside of their target woredas. Their business relationships are also lasting beyond the contract periods as they are adapting the linkage by offering incentives such as purchase on credit and sales commission.

Policy reform – Outcome 4
LIFT’s Outcome 4 result increased from 29 to 37 thus overachieving LIFT’s AR target of 30 as well as its overall programme target of 30. During the year, based on the various researches undertaken under output 4, the following have been adopted or otherwise implemented by the Government of Ethiopia (whether at federal, regional, woreda or kebele level) or development partners to strengthen land certification and administration structures and processes
- NBE Proclamation: Through LIFT’s efforts the NBE now allows for the use of the land use right as a form of collateral.
- Tigray Registering Rental Transactions in EEU woredas on iWORLAIS regardless of duration: Through engagement with the Tigray Regional Land Bureau, a formal letter was distributed to all EEU woreda Land Administration Offices in July stating that all rental agreements regardless of duration should be registered on iWORLAIS.
- Business case for rural land administration information services: This was presented at the G7 Land committee as per LIFT’s RLAS Action Plan. As a result, the World Bank committed USD 165 million and has designed the CALM programme.
- SDO guidelines – Procedure to build capacity of field teams on social issues: This was annexed to the SLLC manual so has been adopted by GoE as the SLLC manual is a GoE document
- Model woreda Office MoU: This details the responsibilities of LIFT, LAUTT and REILA II in delivering the Model woreda Office as well as budget contributions.
- Framework on Land Administration Best Practices for the Model woredas: was presented to the Model Office task force which comprises of the Director of RLAUD, GIZ, REILA II and SLMP and was approved by RLAUD in JUNE. The guideline was then presented at the launching workshop for the model woreda initiative to the regional bureaus and staff of selected model woredas in JULY and the guideline has been adopted by the Regions
- Regional Model woreda MoU: Includes one MoU between the Regional Land Administration Offices and Zonal Land Administration Offices and one MoU between the Zonal Land Administration Offices and woreda Land Administration Offices. The MoUs set out the responsibilities of each actor in each Region in delivering the model woreda office approach
- CALM Project Implementation Manual: the manual has been provided to RLAUD of the MoA and been adopted for the CALM programme

Impact:

The programme is on track to achieve its impact targets. Strong indications were found that both the SLLC-linked loan and rental formalisation lead to productivity and income increases of farmers. This supports the theory of change assumption that the EEU’s market systems-based approach magnifies and accelerates the impacts of land certification on investment, productivity and incomes.

For SLLC-linked loan beneficiaries it was found that the additional investment in agricultural inputs resulting from the loan led to an average yield increase of 33.6%. The EEU Impact Survey provides evidence on how the SLLC-linked loan and land rental formalisation has led to increased productivity and incomes. It is further estimated that taking out a single loan leads to a net additional income increase of 16.6% in the first year after taking out the loan. This implies that farmers make a net profit from the loan after repaying interest, and this happens in the short term. Note that the effect is only estimated for the first year after taking-out the loan. These positive income effects are expected to further cumulate over the years, leading to an overall higher percentage increase in incomes.

Overall the effect of land rental formalisation is estimated to have increased the productivity of rented land by 36% on average. For land rental formalisation it was found that land is used more productively due to less resource-constrained rentees using the land. The EEU impact survey found that rentees are on average 44% more productive than renters and therefore put the land to better use. When looking at land that was rented-out for the first time due to the additional tenure security provided by the LRSPs and the standard land rental contract, yield productivity is estimated to have increased by 94%.

Furthermore, land rental formalisation specifically benefits more vulnerable renters, whose bargaining position is strengthened through LRSPs and the security provided through the standard land rental contract. It was found that renters who formalise an existing informal agreement with an existing rentee would benefit from a 11% rental price increase, while renters who make a formal rental agreement with a new rentee benefit from a 68% increase in rental price.

Explain major changes to the logframe in the past year (1/2 page)

LIFT’s logframe was revised in response to last year’s AR recommendations. DFID worked closely with the Annual Review team and implementing team to ensure that all changes addressed the Annual Review recommendations and were agreed. The final Logframe V16.1 was approved on July 2019 by DFID Head of Office. All changes to LIFT’s Logframe are listed in the Logframe’s change log.

While some minor changes where introduced to indicators relating to SLLC and RLAS, more substantial changes were introduced to EEU indicators. Output 3 indicators were re-defined to capture innovations in a more consolidated way, and a new Outcome Indicator 2A was introduced to count the number of EEU beneficiaries. As a result, the Logframe now capture how outputs translate into outcomes and into the impact-level in a better way.

All the changes made to the Logframe are explained in more detail in a separate note (see Vault No 50587856). The key changes made are as follows:
- Gender disaggregation was removed from Outcome Indicator 1 and targets were revised in response to latest findings from the qualitative study on formal transactions by the EEA;
- Outcome Indicator 1B (new) was added to measure how the rights of women are sustained through subsequent transactions in RLAS;
- Outcome Indicator 2A (new) was added to count the number of farmers that have accessed an EEU intervention (number of EEU beneficiaries). This was in response to a specific request by the AR team to better show how outcomes translate into impact;
- Previous Outcome Indicator 2 (now Outcome 2B) was slightly revised to clarify that only farmers who have directly accessed an EEU intervention will be considered;
- Output indicator 1.2 was slightly reworded;
- Targets for output 1.1B, 1.1C were reduced (due to external factors such as political instabilities and procurement delays that impacted delivery) while target for 1.3 was increased (as the cost per parcel increased with the reduction in certificates approved and made available);
- The definition for Output 2.2 was updated. Only RLAS woredas that have registered at least 10 transactions over the last 12 months will be considered “operational”;
- Reporting for Output 3.2 (old Output 3.1) will be disaggregated by different market actors going forwards. Further the definition for counting LRSPs as “active” was further tightened;
- Output Indicator 3.1 was considerably revised to qualify how innovations are counted. Under the new definition, fewer activities will be counted as innovations, which justified a reduction in targets. For example, while previously six innovations were counted under the SLLC-linked loan (one for each MFI), this is now only counted once. This change also needs to be considered for the respective VfM indicator for number of innovations introduced, since with a fewer amount of innovations counted the cost per innovation will increase; and
- Output Indicator 3.2B was dropped with new Output Indicator 3.1 included that will capture ECA innovations through disaggregation.

Describe any planned changes to the logframe as a result of this review (1/2 page)

As the programme has started to exceed the end of programme targets, the logframe targets need to be reviewed to ensure stretching and ambitious results are set. DFID will work very closely with the ITSP and EETSP.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The VfM performance of LIFT has continued to improve in the last year, as has the process for monitoring it. The following table provides the programme’s assessment against these indicators.

VfM Domain	Indicator	2017	2018	2019
Economy	Average Daily Fee Rate for Int. Consultants	£578	£576	£385
Economy	Average Daily Fee for National Staff	£35	£31	£26
Economy	Fees Share in Overall Spend	66%	64%	63%
Efficiency	Burn Rate (variance)	12%	9%	10%
Efficiency	Cost per Parcel Registered	£5.46	£4.00	£3.39
Efficiency	Cost per Innovation by EEU	£222,481	£163,517	£588,540
Efficiency	Cost of EEU outreach (beneficiary)	n/a	n/a	£67
Efficiency	Cost of RLAS Functioning woreda office	n/a	£20,290	£18,220
Effectiv.	Cost per transaction Formally Registered	n/a	£90.80	£46.61
Effectiv.	Cost per Household with Tenure that is Legally Recognised and Documented	£32.54	£21.65	£18.36
Effectiv.	Benefit of Increased Income per Household or Beneficiary	n/a	£40.43	£46.09
Effectiv.	Cost of Sustainable Change from EEU Interventions	n/a	£185,814	£980,900
Equity	Changes in LIFT level of spend (year on year) on reaching the Vulnerable Groups	£230,664 / (2.9%)	£58,792 / (1.9%)	£246k / (11.5%)
Equity	Cost of SLLC holder female beneficiary accessing finance or using land rental services	£661	£380	£322
Cost Efficiency Savings (actual, tracked and documented)		Over £300k	Over £2 M	£1,651,790

Main VfM Highlights from 2019 are:

- On a majority of VfM indicators, the trends are positive, indicating good value for money, often with reduced costs and/ or increased result units.
- On a couple of EEU indicators, there were higher cost trends due to sense checking and re-counting of results. We expect improvements on those next year.
- The programme CBA was updated with programmatic evidence which still represents value for UKAid’s investment.
- VfM examples outside of periodic metrices were collected. These were achieved not only through applying cost-conscious behaviour, but also through better resource allocation across the components and working with others to maximise value. Those savings amounted to £1.65m in value over the reporting year (not cumulative since the outset).
- LIFT learnings contributed to the design of a $200m World Bank programme in the land sector which is expected to work on sustainability of RLAS in hundreds of woredas across the country.

Minor changes were made on VfM reporting this year. New information was added to present a more comprehensive narrative for all indicators. Furthermore, the technical implementing team was consulted for sense-checking and revision process to ensure that VfM stays relevant and live to the changes that occur during programme implementation. In addition, the cost effectiveness narrative was strengthened by using the results from the updated Cost Benefit Analysis (CBA). CBA headline results, as well as results pertaining to year 2019, now show that LIFT interventions have a positive return for UKAid investment (vault no 52509602 and 52511393). The revision was done considering accurate costs break down over the programme years as well as results from impact surveys, among others. This is to ensure that the CBA derives more from programmatic evidence, and not only from the founding assumptions, as per VfM best practice.

Financial aid also represent value for money for DFID. The total approved budget as of the end of the 8th set of Woredas to be covered is £13,363,106 (the equivalent in Birr 423,246,335) with a target of 15,182,846 parcels to be demarcated. This gives a cumulative average of ETB 27.88 per parcel demarcated. To date the average cost is ETB 25.09 per parcel vs target of ETB 31 per parcel. Savings due to exchange rate have also resulted in an additional four woredas being budgeted for SLLC at no additional cost to DFID getting more result. However, this price will increase slightly as final disbursements are planned to be made to finalise outstanding SLLC activities in beneficiary woredas.
Set	Budget			Actual					Diff. (ETB)
	FA budget (ETB)	Parcels	Cost per parcel (ETB)	FA spent (ETB)	Reg. and Zonal supervision (ETB)	Total (ETB)	Parcels demarcated	Cost per parcel (ETB)
1st	15,157,810	1,040,439	33	25,984,415	552,008.00	33,568,910	942,115	35.63	2.63
2nd	57,389,032	1,293,717	31	42,217,664	800,722.87	43,018,387	1,366,598	31.48	0.48
3rd	65,831,385	2,192,839	30	48,927,671	1,185,328.21	50,112,999	2,023,006	24.77	-5.23
4th	58,488,940	2,381,887	26	60,929,362	1,576,435.56	62,505,798	2,690,511	23.23	-2.77
5th	67,479,180	2,506,460	26	58,602,872	1,658,010.86	60,260,883	2,829,736	21.30	-4.70
6th	71,369,531	2,337,963	31	66,555,932	1,440,072.25	67,996,004	2,457,779	27.67	-3.33
7th	56,181,900	1,794,135	31	26,489,072	652,835.60	27,141,907	1,114,198	24.36	-6.64
[note] This is a proportional amount of the ETB 8,113,288 assigned for Regional and Zonal supervision of SLLC and has been apportioned based on the number of parcels demarcated for each completed set (the remaining value is assigned to the 8th set and additional 4 woredas undergoing SLLC due to savings from exchange rates)
[note] Of this value ETB 7 million was contributed by LIFT
[note] This budget includes additional funds for the 1st set

Main risk to VfM for the coming year will be financial aid shortage, budget pressure from woreda split and limited budget restricting flexibility of the programme to address unforeseen challenges.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The programme scores well across the vfm indicators. There are some improvements that could be made particularly those related to EEU. As those were caused by recalculation of the assumptions, the programme expects to see improvement next year. The programme’s intentional focus on empowering women and vulnerable groups is delivering positive results. Effectiveness is a challenging metric for LIFT. When compared with the value for money projection from the business case, which was based entirely on economic returns to poor people, the limited evidence is undermining the projected impact and therefore the effectiveness of the programme. Additional data collection around the impact of LIFT’s work on incomes and productivity will be a priority for 2020.

Given the multiple benefits of LIFT, the stage in the programme’s lifecycle, and its innovative nature giving great learning potential, the review strongly recommends that the programme continue.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation
LIFT maintains a comprehensive risk matrix covering policy, programmatic, fiduciary and political risks. It is reviewed in detail by the Senior Response Officer (SRO), Deputy Programme Manager and M&E Manager every quarter and reflected in quarterly reports. In between, it is reviewed as part of the monthly update meetings between LIFT and DFID-E.
Throughout the past year, the main risks to the successful implementation of the LIFT programme continues to be:
- Procurement delays – to address the continued procurement of goods delay, the office had decided for the implementing team/DAI to take over the procurement of goods with an amended contract submitted in October 2018. Yet the contract amendment was formally approved in May 2019. During this time the programme couldn’t undertake any procurement (even funded from within the programme’s expenses budget for urgent items) and the depleted stock had a major impact on and, in some cases, ceased SLLC activities. However, once the CA was approved in May, LIFT prioritised the procurement of key equipment needs and since then materials have been procured on an ongoing basis as per LIFT’s procurement plan.
- Security situation – Although the State of Emergency that impacted LIFT in the previous year was lifted in June 2018 new State of Emergencies were imposed in Amhara (due to the assassination of Amhara’s President and Chief Justice Officer) in June 2019 and in SNNPR (due to ethnic conflict and demonstration) in March 2019. There have been multiple cases of civil unrest and political rallies across Amhara, Oromia and SNNP since September 2018. The programme strives to minimise the impact on delivery, but more recently, issues relating specifically to the organisation of public display events, have become more severe;
- GoE commitment and diversion of attention - Although CALM is a major achievement and will contribute to the sustainability of RLAS, it does present some potential risks to the programme. There have already been a few instances where workshops have been delayed due to Government staff being engaged on CALM. This is being closely monitored and LIFT will ensure it maintains engagement with GoE. This included financing the development of the Project Implementation Manual to ensure the work complements and supports LIFT work.
- New region and woreda creation – following the political reform, a new region (Sidama) is created with more coming up. Same with Woreda administration splitting. This has substantive resource implication as well as capacity to implement. The programme is working closely with the Government to ensure the necessary resource are allocated from Government to install and maintain RLAS.
All of these issues are captured and addressed (including proposed mitigation actions) in LIFT’s risk matrix, and each of them has the potential to have a significant impact on LIFT’s performance. However, as noted above, a combination of factors including procurement delays, the political situation and the security situation contributed to the SLLC targets for September 2019 being reduced in agreement with DFID-E.
The following are the risks that are currently deemed to be ‘red’ (severe/certain/now) prior to mitigation:
- Risk 2 – Political instability or widespread civil unrest undermines government capacity, markets and the certification process;
- Risk 3 – Political commitment to land certification and administration processes is not maintained;
- Risk 7 – Government fails to maintain the land register, resulting in the register becoming obsolete;
Following mitigating actions, no risks are still estimated to be red.
Update on partnership principles (1/2 page)
The implementers of LIFT have an effective and transparent process for monitoring the performance of partners which, by and large, are contracted service providers. There are clear due diligence procedures and a process for the escalation of concerns through the contractor’s head office and through DFID, with all parties remaining informed at all points.

The 2019 Partnership Principles Assessment noted the political transition underway in Ethiopia and the increased commitment to respect and protect civil and political rights. It highlighted the Government’s continued commitment to reducing poverty. We therefore judge that it remains appropriate to use targeted financial aid (alongside other forms of aid) to improve the life chances of poor people in Ethiopia.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)
Date of last narrative financial report(s)	Interim Financial Report Q4 September 2019 (Vault No 52442892) / DAI Annual Report February 2019 (Vault No 47390296)
Date of last audited annual statement (s)	Independent Auditors’ Report. Tesfaye Teferi Anbesse, Certified Audit Firm Nov 1019 (Vault No 52503135) / Annual Financial Audit Report 03 Jan 2019 (Vault No 52509891) / Internal Audit Report – DAI vault no 52554550

LIFT continues to operate in a changing political environment fraught with unrests, change in senior and junior staff. Delay in procurement of goods exacerbated the challenges faced by the programme. Despite those challenges in the operating environment, the programme has not only achieved all of its targets for the year but is on track to surpass a number of the end of the programme targets well ahead of schedule.
The Implementing Technical Service Provider (ITSP) worked closely with the External Evaluation Technical Service Provider (EETSP) to plan and agree a joint research plan for the remainder of the programme, so that all important research areas are covered. LIFT also collaborated closely with the EETSP and DFID in agreeing the approach and methodology for each survey by sharing detailed methodological notes in advance of carrying out the work.

DAI is a Strategic Partner of DFID and as such, their full portfolio is monitored under the Strategic Relationship Management (SRM) Process. The performance scores indicate DAI contracts are generally being delivered at expected standards. Apparent from central SRM processes, DFID E has adopted a local process of bi-annual review. This process has helped with timely feedback for effective delivery at pace.

Financial performance
The financial management for each component continues to be reported effectively on spend. DFID’s financial planning and spend controls are getting stricter and the partners are responding to the changes positively. Quality of forecast of spend remains key limitation for the programme.

Component	Value	Proportion of Total Spend	Oct. 2018 to Sep. 2019	Total Spent since programme starts	Total Spent since Programme Start
Procurement of services to undertake land certification, administration, facilitation and cross cutting policy work (Milestone based fees and expenses DAI)	£42,455,268.69	58.4%	£8,200,097	£33,863,499.18	80%
Procurement of goods to undertake land certification, administration facilitation and cross cutting work (CDEL-DAI)	£297,772.13	0.4%	£0	£185,472.13	62%
Land certification and administration support to the Government: (Financial Aid)	£13,324,301.00	18.3%	£2,610,000	£13,324,301.00	100%
Independent Evaluation and external audit:	£1,982,367.00	2.7%	£137,151	£1,017,578.89	51%
Procurement of goods to undertake land certification and administration (Capital and non-capital items)	£14,644,692	20.1%	£1,922,198	£9,993,577.08	68%
Total	£72,704,400.82		£12,869,446	£58,384,428.28	80%

Spot checks were undertaken regularly (latest one during AR field visit and head office visit. See vault no 52532819) that found no major issues. But asset control and tracking systems need further improvement.
The auditors of the financial aid have issued unqualified (clean) audit opinion on the financial statement and the designated accounts. Furthermore, it is noted that no significant issues were reported in the four woredas. Interim Financial Reports (IFRs) on the financial aid confirmed that the money has been used for the intended purpose in line with DFID regulations. The latest IFR confirmed all ineligible expenditures for the cumulative reporting period ending 7th July 2019 has been reimbursed fully. However, both the management letter of the audit and the IFRs continue to raise internal control weaknesses which are recurring. DFID and DAI are following up on the necessary actions, which need to be taken by all concerned finance and land offices at woreda level, to ensure the findings have been addressed.

The independent audit commissioned by DFID on the implementing service provider/DAI for the period 1st November 2017 to 31st March 2019 came with some issues for the first time. Even though the report is still in draft, the following points were raised as qualifying issues:
- SIAPAC, sub-contracter, charged a margin to the Fees charged by ABCON and therefore there is GBP 26,604 excess over the actual expenses incurred by SIAPAC;
- Reimbursable expenditures of GPB 132,894 under survey cost, incurred by the sub-subcontractor ABCON were not supported by a contractual agreement, of which GBP 49,329 was adequately supported;
- In connection with “Sustainable value creation for title holders – SELECTOR” project, expenses related to an invoice from Wageningen Environmental Research for a total GBP 59,068.35 were not adequately supported; and
- Payments for procurements of goods and services by LIFT office in Ethiopia have been inclusive of Value Added Tax (VAT) at 15%.

The ITSP has until the end of December to produce the necessary documents to substantiate those expenses or will be required to reimburse DFID fully. Except these financial findings mentioned above, the independent auditors’ opinion is that the Statement of Income and Expenditures of ITSP presents fairly, in all material respects, the expenses of GBP 11,692,180.20 incurred by Land Investment for Transformation (LIFT) for the period from 1st November 2017 to 31st March 2019 in accordance with agreed upon accounting policies were: i) in conformity with the approved project budget; ii) for the approved purposes of the project; iii) in compliance with the relevant policies and procedures; and iv) supported by properly approved vouchers and other supporting documents. This was confirmed by their internal audit report as well.

There were three fraud cases reported this year, one in SNNP and two in Oromia Region. Two cases involved Kebele Land Administration Committee member and Kebele office manager extorting fees for LIFT related activities while one fraudulently stole ETB 700,000 birr from LIFT regional account. No DFID funds were involved in the first two cases and money taken fraudulently has not been invoiced to DFID. But ITSP and DFID are closely following up on the open cases as well as further tightening LIFT procedures to protect from such incidences.

Performance of partnership(s)
The DAI-led consortium that implements LIFT has maintained strong relationships with the relevant agencies of the Government of Ethiopia, particularly the Land Administration and Use Directorate (LAUD) in the Ministry of Agriculture. Relationships with the governments of the four programme regions, particularly their respective land bureau, are of importance to the successful implementation of LIFT. LIFT has also developed strong partnerships with relevant private sector actors such as MFIs, agricultural input suppliers and other businesses through its EEU, which has been crucial to the significant progress made under Output 3 over the course of the year.

DFID Ethiopia has an excellent partnership model with the implementing team, and with the federal and regional governments. The governance structures of the programme are functioning well at all levels. DFID and DAI have regular meetings whereby progress is reviewed. Such platforms are also used to discuss challenges and risks escalated for timely action by all concerned. For example, the Federal Programme Steering Committee chaired/co-chaired by Minister for Agriculture and Natural Resources (MoANR) and DFID representative respectively have played a key role for the improved performance on SLLC and RLAS. This has been made possible through proper risk analysis and pushing the performance bar higher for the four regional governments. The commitment of regional governments was further proved through increasing allocation of resources for RLAS implementation. This needs to continue for sustained impact of the programme.

DFID’s relationship and traction with the External Evaluation Technical Service Provider (EETSP)/Palladium has been weak. The primary cause of this has been substantial staff turnover within Palladium which has delayed evaluation and research work. Palladium has confirmed that it will submit a revised approach to bring the work back on track. This will be closely monitored.
 MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

There has been good progress on M&E across the programme with the recruitment of a dedicated M&E manager and replacement of the previous SLLC/RLAS M&E coordinator in late 2018. New processes have also been introduced to reform the existing monitoring system, especially across SLLC and RLAS as outlined below.

New functions introduced to MIS automate aggregation and analysis of weekly SLLC reports and monthly PAC reports

A major reform to aggregate and analyse weekly SLLC reports was introduced in February 2019, introducing large efficiency gains to the monitoring process. A new weekly reporting format that is compatible with MIS was introduced to all woreda coordinators. This allows for all woreda reports to be uploaded and automatically aggregated by LIFT’s MIS. This also allows for more in-depth, Kebele-level analysis of weekly SLLC reports through the MIS such as identifying specific Kebeles that are late for completing certain SLLC activities. Low performing woredas and kebeles can be identified with specific problems.

To communicate progress to LIFT’s management, automated dashboards to visualise progress against targets for key indicators were developed to allow for more effective adaptable management. A similar process was followed for the monthly SLLC PAC reports collected through SDOs and aggregated by the GESI team. These are now also uploaded and aggregated in MIS, introducing efficiency gains and more in-depth analysis of the number of parcels recovered by vulnerability type and process. Furthermore, the MIS now also functions as a database for all weekly woreda and federal-level SLLC reports and SLLC PAC reports, as previous reports can be accessed and downloaded through a search function. See separate AR note on new MIS functions for more detail.

New M&E processes introduced to RLAS component
Several new monitoring procedures have been introduced to the RLAS component to allow for more comprehensive and timely monitoring of activities:

- New SMS reporting system for RLAS transaction reports: One of the major constraints to aggregating monthly transaction reports from RLAS operational woredas is internet connectivity. This often makes it difficult for woreda Land offices to share transaction reports with the central RLAUD and LIFT offices. In many cases, collection of monthly transaction reports still required physical visits to the respective woreda Land Office. To make this process more efficient, LIFT, in collaboration with RLAUD, is working on introducing an SMS-based system, where woreda Land Office staff can share transaction reports through coded SMS. An automated system at the central RLAUD office then translates these SMS into a database that can be downloaded and analysed.
- RLAS results chain: A results chain was developed to capture all activities under RLAS and visualise how this work together to contribute to a sustainable system.
- RLAS indicator plans and monthly monitoring tools: A system of performance indicators (indicator plans) and monitoring tools were developed to measure each box depicted in the RLAS results chain. A monthly monitoring tool was developed to pick-up on essential issues and raise these with GoE in a timely manner. Monthly monitoring will focus on staff capacity, availability and functionality of equipment and materials, awareness raising activities, and the functionality of the front-office (KLAC/ Kebele Land Administration). The new monthly monitoring system was rolled-out in September 2019 and is expected to allow for more effective monitoring from October 2019 onwards.
- Streamlined RLAS implementation assessment tool: With the substantial increase in the number of RLAS woredas that are due for a 12-monthly implementation assessment (69 woredas in 2019), the existing monitoring framework was reviewed in early 2019. The assessment tool was streamlined by consolidating the analysis from 7 to 5 thematic areas. Care was given to protect crucial indicators that define whether a woreda in operational or not.
- Model woreda Monitoring Framework: A comprehensive monitoring framework was developed to provide frequent and robust monitoring of the Model woreda pilot complete with regional monitors for each model woreda. Furthermore, two senior monitoring consultants were hired to carry out an extensive baseline survey, as well as to support the data collection for and report write-up of quarterly reports. Findings will be presented at both quarterly regional and federal-level workshops to share learnings and give feedback to GoE on the performance of the eight model woredas.
- RLAS Public Awareness Campaign (PAC) M&E: A detailed M&E framework was developed to complement the new RLAS PAC strategy, which will be rolled out through the satellite woreda and the model woreda interventions. Monthly monitoring will allow to identify which PAC activities are carried out across woredas and Kebeles and evaluate which ones are most effective in raising landholders’ awareness to register transactions.

EEU monitoring of instances of systemic change: The EEU component has continued to measure instances of systemic change and captured these in the previously established systemic change log, which is structured along the Adopt, Adapt, Expand, Respond framework. To capture evidence of systemic change, the qualitative semi-annual assessments from previous years were continued. Monthly monitoring data was also collected as per the previously established monitoring system, allowing to pick up on how EEU innovations expand in the market through different market actors.

Evidence (1/2 page)

LIFT carried out several large-scale surveys and in-depth studies in 2019 to provide evidence on the programme’s key theory of change links. According to this joint research plan, the ITSP (in collaboration with EETSP) carried out the following large-scale surveys and studies:

EEU Impact Survey (February/March 2019): This survey sampled 1,382 households across 4 regions to provide evidence on whether the EEU’s land rental and access to finance interventions increase investment on land, leading to increased productivity and incomes. It reports on Outcome Indicator 2B - Percentage of farmers with SLLC that have directly accessed EEU interventions and as a result have invested/increased investment in improved inputs and other/new income-generating activities. The programme’s Theory of change assumptions around the two interventions were confirmed as outlined below.
- The SLLC-linked loan provides access to finance, both in terms of higher loan amounts and in terms of offering loans to farmers who did not access formal credit before. Due to the unique nature of the SLLC-linked loan, a lot of new clients are engaging with the MFIs, many of which are accessing formal credit for the first time. Additionally, the average amount available through the SLLC-linked loan is 2.6 times higher (11,800 vs 30,000) on average than the amounts accessed by those who attained formal credit in the past through group lending. Out of these loan clients only 2% of the respondents reported having ever missed a payment. Most of these rural farmers are smallholders making up 64% of male clients and 73% of female clients. Therefore, the SLLC-linked loan is successfully targeting smallholder farmers and increasing their access to large, more transformational credit amounts when compared to group lending or informal lending.
- The demand for the SLLC-linked loan is strong, with high satisfaction and a sense of empowerment (especially felt by women). Clients are very satisfied with the loan and its features. 69% of clients stated that the loan amount meets their investment demand and 85% of those who had already completed their loan term applied for a second loan. Overall, 75% of male clients expressed their satisfaction while it was 85% for female clients. Women were specifically asked questions regarding their engagement with the loan as both spouses are required to sign the loan agreement. 81% stated that joint-decision making had increased due to the joint signature requirement. Additionally, 88% stated that they are more actively participating in household finance decisions because of the SLLC loan, indicating an empowerment effect for women in male-headed households.
- The SLLC-linked loan increases investments to enhance agricultural productivity, leading to increased yields and incomes. The primary purpose of this loan is to increase investments in agricultural, making land more productive. We found that 88% of loan clients invest the loan to increase agricultural productivity. Especially for the clients who invested the loan into inputs to enhance crop production, the access to additional finance resulted in a 26% increase in their input investments. As a result of the increased investments in inputs, farmers experienced a 33.6% rise in yields, when comparing yields before and after the SLLC-linked loan was taken out. Overall the SLLC-loan clients had an average return of investment rate of 42%, which is significantly higher than the average interest rate of loans taken (17.4%). Due to this high return of investments, loan clients are able to attain an average additional income increase of 16.6% because of taking out one loan. This evidence depicts a clear picture of how the SLLC-linked loan is catalysing investment and resulting in significant income gains for SLLC farmers.
- Renters are on average more marginalised and benefit strongly from the security the Standard Land Rental Contract (SLRC) offers as shown in a decrease in disputes and increase in rental prices. A higher proportion of renters are smallholder farmers when compared to rentees. Renters are on average significantly older than rentees, and more likely to be female-headed households. Furthermore, renters are more likely to be in the lowest wealth group when compared to rentees and the average farmer as measured through non-beneficiaries. The land rental intervention ensures access to a secure and more lucrative opportunity for renters, while providing affordable and secured access to land for rentees. We found that the SLRC has resulted in increased security with 80% of SLRC clients reporting that it reduces the risk of disputes. While across the intervention areas the use of the contract has reduced land rental disputes by 30% on average.
- Security of tenure offered through the SLRC incentivises new farmers to rent-in or out for the first time, as well as to increase the land size rented for existing agreements. This leads to an overall expansion of the rural land rental market.
- Renters benefit from an increase in rental prices as a result of the SLRC and LRSP support, leading to an increase in available income for household consumption. LRSPs aim to prevent exploitation of the typically more marginalised renters, leading to fairer and higher rental. Renters who rent out to the same rentee as in the past were indeed found to have experienced a 11% price increase. Renters who switched rentees as a result of formalisation and LRSP facilitation however experienced a much higher average price increase of 68%. This is an indication that some renters used to agree to prices that are below the market price, but through the support of the LRSP have a strengthened negotiating position.
- Rentees use land more productively than renters, leading to a more productive use of land overall. Rentees benefit from an income increase by increasing overall investment in land. Furthermore, rentee use the rented-in land more productive when compared to renters: on average rentees are 44% more productive than renters and achieve an average return on investment rate of 71%. Thus, the land now under rentee cultivation, approximately 2400 ha, experiences a 36% yield increase. These results show how the formalisation of the land rental market, with LRSPs playing an integral role, boosts productivity and facilitates a more efficient allocation of land, while ensuring tenure security.

RLAS transaction survey (June/July 2019): The RLAS transaction survey is a large-scale quantitative study to estimate the percentage of subsequent transactions that are being formally registered in RLAS by landholders. 9,600 households were sampled across LIFT’s 4 programme areas to generate a representative sample across all RLAS operational woredas. The study also allows to compare demographic and socio-economic characteristics of landholders that do or do not formally register land transactions. The study provides evidence on Outcome Indicator 1A - Percentage of land transactions which are formally registered in RLAS in programme woredas in which RLAS is operational, disaggregated as follows: Rental, Loan, All other transactions. Main findings were:
- It was found that overall 31.6% of all land transactions are formally registered (17.3% of rental transactions, 100% of credit transactions, 28.2% of all other transactions).
- Rental transactions but also other land transactions are significantly more often formalised in EEU locations when compared to non-EEU locations. A direct, positive effect on formalising rental transaction can be found. In EEU areas, formalisation of rental transactions is nearly twice as likely as in non-EEU locations (21.7% in EEU locations vs. 11.9% in non-EEU locations).
- Further, strong evidence for an EEU demonstration effect was found, where the prospect of accessing EEU products, such as the SLLC-linked loan or the formal land rental contract, sets positive incentives for landholders to formally register land transactions more often in general (including for other, non-EEU transaction types such as inheritance or gifting). Overall the differences are strongly pronounced, with landholders in EEU locations being roughly 50% more likely to formalise any land transaction.
- Landholders are also much more likely to formally register transactions in locations closer to the woreda centre or an all-weather road as compared to landholders living in remote locations. A clear difference between remote and non-remote locations can be found. This was further confirmed by LIFT’s study on the frequency of formal land transactions in remote versus non-remote areas (see below).
- It was also found that SLLC collection rates are high with 92.1% of landholder households where the SLLC process was conducted having collected their certificates (average across all four regions). This provides additional verification of Outcome 3, meaning that once a certificate was issued by the authorities, it makes its way to the landholder.
- It was further found that if landholders heard about the need to formally register transactions during the SLLC process, they were much more likely to do so afterwards.

SLLC Outcome Survey (October/November 2019): Currently underway, this large-scale household survey will provide evidence on one of LIFT’s key theory of change assumptions: Does SLLC lead to increased perceptions of security of tenure, which in turn leads to higher investment rates, and increased productivity and income. The survey will follow up on baseline locations to allow for a before/after comparison by sampling 2,800 households. A detailed methodological note to carry out this survey has been shared and signed off by both the EETSP and DFID. The report is due end of December.

In addition, the programme has also conducted the following studies:

- Household survey on the impact of EEU’s input supplier intervention on investment and productivity
- Study on the frequency of formal land transactions in remote versus non-remote areas (desk-based research using data sourced from IWORLAIS)
- Study on subsequent transactions to identify whether the rights of women are maintained over time (desk-based research using data sourced from IMASSREG and IWORLAIS)

Overall, these studies are intended to assess the key assumptions underlying LIFT’s theory of change and were selected in part in response to the last Annual Review. Findings will be incorporated into communication products for further dissemination with key stakeholders.

Learning (1/2 page)
LIFT’s M&E procedures have fed into learning and adapting as follows:

- Introduction of Mobile Back-Office Centres to reduce barriers to formally register transactions in more remote locations: Findings from the RLAS transaction survey and the programme’s desk-based research on the frequency of formal transactions in remote vs non-remote areas showed that landholders are much less likely to formally register a transaction in more remote areas, especially in areas that are far away from major roads. These findings fed into the development of the Mobile Back-Office Centres, which aim at reducing transaction costs of landholders by setting up temporary transaction registration centres in remote locations.
- Intensifying RLAS Public Awareness Campaign (PAC) activities during SLLC process: Findings from the RLAS transaction survey have shown that landholders who heard about the need to formally register land transactions during the SLLC process are much more likely to do so afterwards. The programme has addressed this by intensifying PAC activities during the SLLC process through SDOs.
- Detailed SLLC monitoring allows for better planning of activities: The detailed, Kebele-level performance analysis of weekly SLLC data introduced through the new automated MIS functions highlighted above has allowed the programme to quickly identify low-performing woredas. Reasons for possible performance gaps can then be evaluated and addressed in discussion with regional coordinators and woreda coordinators, allowing to manage the SLLC process more efficiently.
- Awareness Raising: Assessment on Knowledge Attitude and Practices towards land registration indicated that as many transactions occur between family or within social circles, levels of trust are very high which is a contributing factor to them not formally registering them. As a result, LIFT has developed new awareness raising poster concepts that highlight the positive impact of formally registering land transactions for both parties.
- The EEU component continues to adapt its interventions based on evidence gathered:
  - The LRSP payment pilot was designed to address the reduced activity identified amongst LRSPs due to lack of incentives as part of an in-depth analysis of land rental monitoring data.
  - The licensing and certification of LRSPs has now been explored with the supportive evidence of the LRSP payment pilot and activities are underway to enact it.
  - The area yield index crop insurance currently being piloted in Amhara region was designed and developed with full consideration of lessons learned from the previous ATA/Kifya partnership. One of the key lessons learned was the need to include a multi-peril option for insurance, which not only covers drought but also pests and diseases.
  - There was clear evidence that many partner retailers lacked adequate capacity and faced licensing constraints to expand their services. As a result, the programme assessed the various capacity and licensing constraints of retailers. The findings from this assessment were validated in a workshop with relevant stakeholders and a policy brief was prepared to be used as an advocacy tool with the relevant regulatory bodies. Next year consultative sessions with both government stakehoders and development partners active in this space will be carried out to remedy the constraints identified.

Progress on recommendations from previous reviews (1/2 page)

#	Action from Dec 2018 AR	Status
1	Qualitative assessment of the impact of SLLC on the broader rights of women and VGs	Completed. EETSP’s qualitative GESI deep dive and findings are submitted in October (see vault no 52509494)
2	Continue to minimise any backlogs in distribution of certificates	Ongoing. LIFT continues its work on minimising the backlog in certificate distribution by working with regional offices and holds regular performance meeting. In September 2018 the backlog was still at 20.6%, but this has now reduced to 17.4% in September 2019 (see vault no 52510007 on assessment and 52510008 on strategy to minimise backlogs).
3	Assess the benefits (and possible costs) to women in different cultural/social contexts	Completed. Field work was completed in August and the report was finalised in September and the findings submitted to DFID for the AR.
4	Lessons on conducting SLLC in more challenging woredas where adjudication of rights is more complex	Almost completed. A draft report is submitted to DFID on the way that IDPs are managed within the SLLC process. This research was severely delayed due to external factors (the first contractor had to withdraw due health issue and then the field work by the replacing contractor further delayed due to lack of permission from Oromia Regional Government). This will be completed by end of this year for recommendation to be actioned next year.
5	Explore options to make SDO’s role sustainable	Completed. Studies on ‘Strategy to Address Administrative Constrains’ and ‘Strategy on Legal Constraints’ were undertaken providing recommendations on how the GoE institutionalise the SDO intervention by the government as well as establishing a position at the kebele level to provide legal support to women and VGs to legally support them in maintaining their tenure rights post-SLLC. woredas assigning dedicated staff to work with SDOs and learn safeguarding procedures is also being explored.
6	Permanent solution to address the delay in procurement	All remaining procurement of goods have been transferred to the implementing team contract with contract amendment finalised.
7	Uptake and sustainability of RLAS	Compete. RLAS action plan was developed with regular report on progress submitted to DFID. See latest action plan report on vault no 52509897.
8	Quantitative studies to evaluate the percentage of subsequent land transactions that are formally registered	Complete. Three studies were undertaken. 1) Study on impact of household proximity/accessibility to WLAO on registering land transactions (vault no 52509503). 2) Study the extent to which the rights of women and VGs may be maintained through subsequent land transactions, by analysing RLAS data (vault no 52509502); and 3) Constraints for women to formalise transactions in RLAS (vault no 52509493)
9	Compare RLAS data on registered rental and credit transactions with data on transactions in LIFT woredas	This is an ongoing work. Since Jan 2019, LIFT compiles data and undertake a monthly analysis. For credit transactions by end of March 2019 there were 24% of all loan transactions in the relevant RLAS woredas recorded in iWORLAIS, however by August 2019 this had increased to 35%. This is a great improvement with an increased recording of 46% between March and August of 2019. The case is similar for land rental when considering transactions over 2 years. The proportion in iWORLAIS in March was 15% while the August data accounts for 24%. Again, this is evidence of boosted performance by 60%.
10	Monitor characteristics of low transaction woredas and Kebeles	Ongoing work. Through LIFT’s RLAS M&E, regular monitoring assessments and studies the programme has developed several action points to increase formal transactions. This includes the MBOC approach, Model woreda Office, Satellite woreda Approach and revisions to LIFT’s PAC approaches. Further details of these activities are detailed in the RLAS Action Plan Update Report (vault no 52509897)
11	To achieve priority policy reforms	Ongoing. The programme held several workshops to improve regional governments knowledge and awareness of LIFT’s work and the need for key policy reforms. Currently the revised federal proclamation is under review by the Council of Ministers. In addition, through advocacy and consultative meetings, the National Bank of Ethiopia (NBE) have now passed their proclamation in parliament which allows land use rights and the produce of land as valid forms of collateral.
12	Facilitation of further crowding in should be a priority	Although the Federal Land Proclamation is awaiting approval, new MFIs are already using the SLLC-linked loan such as Harbu (started distributing the loan product in Amhara, Oromia, SNNPR) and Metamen (has signed MoU with Oromia Regional Office). / RuSaccos have also begun disbursing the SLLC-linked loan to their members. LIFT has helped facilitate experience sharing discussions on what the best practices are for disbursement and the legal ramifications.
13	Monitor a) SLLC loan portfolio performance and MFI portfolio management capacity; b) inclusivity of the loan programme; and c) the ultimate impact (positive and negative) of the loan on farmer yields and incomes	a) Portfolio performance: LIFT conducted a Default Census among its partner MFIs during June/July 2019. The census showed that the loan product is performing better when compared against other portfolios (less than 2% even with rise of incidences of defaults due to drought and security issues). / b) Loan Inclusivity: The EEU Impact Survey examined the inclusivity of the loan and found that 2/3 of beneficiaries are smallholder farmers. 34% of loan beneficiaries are women (of which 85% of which said that they were highly satisfied with the product from the EEU survey) / c) Ultimate impact: The EEU Impact Survey examined the impact of the loan and found that 88% invest in productive agricultural activities leading to an average yield increase of 34%.
14	Performance of registration of land rental agreement	Ongoing. Following the recommendation of the RLAS Transaction survey and EEU Impact Survey, action plan has been developed and progress closely monitored. See vault no 52510788
15	The market system impacting farmer productivity and use this analysis to adapt the input distribution model	The EEU impact assessment, validated the model showing through the market systems work the farmers are experiencing boost in productivity as a result. The only major constraint identified was the need for retailers to have separate licenses for different agri-products. LIFT undertook further research and presented policy recommendations to relevant stakeholders in September.
16	Option to make extension support sustainable	Complete with actions recommended. The programme conducted a review of the SELECTOR project (see vault no 52509405), which identified some strengths, but also some key weaknesses. The findings have been shared with the SELECTOR team and they have developed an action plan (SELECTOR Action Plan see vault no 52510813) to address these constraints. LIFT will continue to monitor their progress, especially the results of the Mid-Line Survey to test the assumptions in their theory of change.
17	2nd Impact Assessment survey	Complete. Field work for the 2nd Impact Assessment was completed at beginning of March and the report was finalised and submitted to DFID at the end of May (vault no 52510001)
18	Logframe indicator on which rules LIFT is trying to influence	Complete. The logframe indicators and definitions were revised and submitted to DFID E on 19th April. DFID approved the logframe revisions on 3rd July. (vault no 50587856)

Safeguarding

There is a strong level of awareness and capacity to manage safeguarding issues under LIFT programme. There is a clear Gender Equality and Social inclusion (GESI) strategy that is regularly updated based on feedback and lessons from the ground (see vault no 52510091 for the latest version). Regular risk matrix reviews and field visits have also taken place.

Due to the SDO intervention, 2348 parcels were restored to 1265 VGs as of September 2019. Of these 1580 parcels, 814 belong to female VGs. The parcels were taken by powerful disputants illegally and have now been returned to their legitimate holders.

The programme has also launched the following studies to assess and strengthen mechanism supporting safeguarding issues:

- A study to develop a strategy for women and VGs access to SLLC linked loans was launched in collaboration with the A2F Intervention manager. The consultants are now conducting field work;
- An evaluation of the SDO performance was undertaken to strengthen their role after it was scaled up from eight SDOs to 24 SDOs and now ready to be rolled out to non SLLC woredas;
- Interim SDOs (ISDO) were identified from among good performing Field Teams and trained for two days at the beginning of 2018. The purpose was to support non SDO woredas until the SDO position is officially filled. However, this was not as effective as it might have been as there was no monitoring from the LIFT Addis office. This is now being piloted in 3 Oromia woredas by one SDO where SLLC is implemented without a SDO to identify an effective approach.
- Further actions in the programme pipeline include lobbying to establish legal aid for women and VGs including:
  - Strategy developed to provide effective legal service for women and vulnerable groups
  - Strategy developed to address legal constraints of Women and vulnerable groups to secure their land rights
  - Impact of Social Development Officers (SDOs) in protecting land rights of women and vulnerable groups conducted
- SLLC Implementation Guideline Note (SIGN) to be further refined to include orphan children registration;
- Continued lobbying to include women in polygamous households in the land proclamation

Staff in LIFT’s head office, as well as Regional Coordinators and Woreda Coordinators, continue to receive DAI’s ethics and anti-harassment training during the last year. The learnings from these are fed into reassessment of programme approach to ensure GESI issues are always considered.

Smart Guide

The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided