Business Case Summary Sheet
Department CDD/ Portfolio/ Business Plan Summary: Developing countries face significant shortfalls in their private (and sovereign or public) sector financing needs. Taken together, financing needs are estimated at about $2.5 trillion a year. Development finance is a core part of DFID’s Economic Development and Building Markets strategies, helping unlock private sector capital to finance the SDGs. Working with institutional investors such as pension funds, insurers, asset and fund managers there is opportunity to unlock new sources of capital and at a greater scale. This new capital is needed to help bridge the SDG financing gap. Doing so will support UK and global development objectives on jobs, stability and low carbon sustainable growth.
Mobilising institutional capital, in partnership with the City of London, through listed product structures - “MOBILIST”
Programme summary: / To address the financing gap for the UN Sustainable Development Goals (SDGs) DFID will catalyse the listing on major exchanges in public markets of up to 5 Emerging and Frontier market focused investment products. / A condition of DFID’s support - and a significant market innovation - will be asset exposure to ODA-eligible countries only, with a strong preference for low-income (LIC) and low middle-income country (LMIC) assets. We seek a step change in the method and scale of private capital mobilisation for development finance by demonstrating that new models for intermediating capital can through ‘price discovery,’ begin to crowd in new investors and new capital to help bridge the financing gap. / Fig 1: IFC highlights the scale offered (and demand for) public market or ‘listed’ vehicles. / DFID research indicates that it is financial products listed on public capital markets that offer the surest route to attracting the large-scale volumes of high-quality and cost-effective institutional capital needed to bridge the financing gap, and that presently, these intermediation mechanisms are almost wholly absent. / Alongside a series of policy and technical interventions that will help address some of the associated factors inhibiting more Emerging and Frontier market assets reaching deep and liquid secondary markets, MOBILIST will help catalyse a series of relatively modest listed products that are possessed of the twin properties of replicability and scalability. As the portfolio of new products focused on developing markets begins to address a key constraint - the absence of transparent price and risk signals, or ‘asymmetry of information’ holding back effective investment appraisal - the portfolio of investment products will begin to build the ‘financial architecture’ that is essential to the intermediation between large pools of institutional capital in international financial centres, like London, and those developing countries where the gap is largest and the needs greatest. / Hence, the listed products we expect to catalyse will be subject to the same legal and regulatory frameworks as existing mainstream investment products that today comprise the vast bulk of institutional and retail portfolios in the UK and other leading financial centres. / Where DFID expects these new products to differ is in their (uniquely) broad-based exposure to geographies where currently the bulk of institutional capital has at best extremely limited exposure and/ or cannot reach because suitable mechanisms to intermediate large-scale institutional capital, matching buyers and sellers through open, transparent and tradable instruments – the ‘financial architecture’ - does not exist. / More than this, the programme commits to ensuring that its support for any specific listed product is conditional on demonstrating to investors a clear line of sight between their investment and efforts to close the SDG financing gap in critical sectors like health and education infrastructure, transportation, clean energy generation and distribution, and low-cost housing. This qualification will inform the partners we choose to work with, the product design process, the investment mandate, (including the geographies we want to see covered), as well as the measurement and reporting standards to be implemented. / By deploying a portfolio of interventions, catalysing these products will, it is expected, create increased opportunities for investors and savers to access the sectors and geographies most associated with poverty reduction and sustainable growth. This helps to create a route for savers and individuals to have choices over their investment portfolios: demand for which is clearly identified in DFID’s September 2019 ‘Investing in a Better World’ report.’ / This effort compliments and supports our longer-term strategy on mobilisation, with ambition to systemise DFID’s collaboration with investors across a range of products and risk mitigation tools.
What is the rationale for UK Aid spending? / Private investors must be part of solving the SDG financing gap (US$2.5 trillion across public and private sectors) because the supply of private finance dwarfs the public funds available to be deployed. Global ODA flows are estimated to remain between US$140-150bn/ annum, equating (at best) to some 10% of the investment needs. UK-based institutional capital (like UK public capital) could play a leading role in addressing this financing shortfall, without sacrificing fiduciary responsibilities, including financial returns. / MOBILIST is most concerned with how to upscale investment flows - specifically in demonstrating the opportunity to mobilise capital that resides within the mainstream, public market portfolio asset allocation of institutional investors. MOBILIST approaches this problem with two principles in mind: / scale must be underpinned by sound commercial investment logic for investors and; / scale must demonstrably help bridge the financing gap for developing countries, including DFID priority countries. / MOBILIST recognises the need to collaborate with asset and fund managers to ensure these principles shape the investment opportunities that the programme seeks. These are the institutions who best understand what are the product characteristics that will be most appealing to institutional investors when thinking about emerging and frontier markets. / The programme recognises the aspiration to find opportunities, through public markets, to appeal to UK retail investors. In principle, a determined retail investor can purchase any asset listed on for example the London Stock Exchange, including potentially any fund that MOBILIST helps acquire a stock market listing. In practice however, all but the most capable retail investors will rely upon the fund platform offerings of retail brokers because for retail investors, trading directly on an exchange is a difficult and costly business. Instead, and for a fee, a broker fund platform will screen the universe of funds available, thereby providing retail clients access to a select range of funds listed on an exchange. Through this discrimination, these platforms offer their clients a level of assurance about a sub-set of listed funds. It is unlikely that any product that MOBILIST initially seeks to bring to listing would sit comfortably in a retail portfolio and on a broker’s fund platform unless the retail client is a High Net Worth client, with a portfolio sufficiently large (and sophisticated) to possess the kind of a high level of portfolio diversification enjoyed by institutional investors. Therefore, whilst MOBILIST will prioritise institutional investors in the first instance (because of their scale, investment expertise and because the assets we seek to bring to market are most likely to appeal to them as investors), it is entirely possible that High Net Worth, and potentially even some more sophisticated retail investors will be able to participate in a listed product brought to market by MOBILIST, but most likely through a wealth manager or intermediating broker. / Longer-term, and once MOBILIST has demonstrated that these products can attract institutional investors, we have ambition to help catalyse products that can appeal to the mass market of individual retail investors. / The primary benefit of the product development approach set out is at a systemic market level: the intention is to lay the foundations for a wide-range of investment vehicles that combined, successfully intermediate large-scale institutional capital towards SDG financing opportunities, with transparent pricing, robust governance and sufficient return to make investing in Africa, the Middle East, South and South East Asia (and on a case by case basis, specific countries from other emerging regions, like Latin America) – a normal part of the consideration for investors seeking portfolio diversification, quantifiable and bench-marked risk-adjusted, and development impact. / Fig 1: SDG’s global investment gap: / The 2015 Addis Conference on Financing for Development was a call to action for donors to step up its collaboration with the financial markets and the big international financial centres. As a consequence, development partners like the European Union, France, Germany, Canada and Japan are pressing ahead with their own responses to the Addis Agenda. / For the UK, MOBILIST builds on the strong competitive advantage the UK has in helping solve the financing gap. The City of London’s is one of the leading international financial centres, with approximately £8 trillion in investor assets under management. The breadth and depth of DFID and HMG’s relationships with the City in particular, presents a huge opportunity for the UK to play a leading role in donor responses to Addis. / Investors too are changing. Increasingly investors want to know where their money is invested and what is its social as well as financial impact. The Investing in a Better World project’s nationally representative survey of 6,000 people reported that 56% of people are interested in making responsible and impactful investments, 25% of respondents indicated that they would be open to some of their money being invested in Africa. / MOBILIST helps further align DFID’s own ambitions with those of increasing numbers of investors – to achieve development impact through investing. Potentially, this approach creates the opportunity to help investors (who are by and large also UK tax-payers) choose the development impact they want, in the places they want, and thereby creating new sources of legitimacy for the SDGs and new avenues by which to help fund their delivery. / The advantages of listed products: / Listed products are the preferred investment structure for both institutional and retail investors, in part because of the investor protections afforded by public markets. Listed products (comprising equities, fixed income products such as bonds which may themselves be listed) comprise more than 90% of most large-scale institutional portfolios (which represent at least $80 trillion of assets under management) and listed products dominate the product universe for institutional and retail clients. / To unlock pools of scalable capital, proof of concept listed products would make an important contribution to price discovery and awareness building for the market at large. Building the track record of both these products and of the fund managers responsible for them would make an important contribution to the financial architecture needed to facilitate sustainable and scalable flows of capital.
Programme Value: / Up to £90 million - we will size our investment across up to 5 individual products according to market appetite and necessary scale to play the required role either as an investor (on commercial or concessional terms) or provider of risk mitigation instruments. / £10m of this £90m is allocated to technical assistance. With the expectation that this funding will support DFID’s role as an investor and/ or be sufficient to catalyse products without development capital as investment.		Country/ Region or Sector: / Strong focus on Low Income Countries (LICs) and Lower Middle-Income Countries (LMICs) but may also include some Upper Middle-Income Countries (UMICs) where there is a clear case for additionality, for example into higher risk sectors or new green sectors
Department/Country Office confirmation / Contact name / Before submission Department procedures for review of papers should be followed. Contact for CN may be author or other who leads on follow-up / Ross Ferguson, Senior Adviser, PSD		HoO/HoD / Rachel Turner / Phil Stevens
Threshold for Approval of Business Case: / Deputy Directors <£40m / Director £40m-£100m / Minister >£100m. List of Ministerial Portfolios for CNs available from Private Offices or BDD		DFID Secretary of State
Date of Approval of Concept Note:	24 October 2019 (52454477)	Name of Approver: DFID Minister of State Stephenson
Date of Approval of Business Case	14 November 2019	Name of Approver: DFID Secretary of State (52454475) / CHX (19 December 2019) (54052269)
Programme Code:	Start Date: / 2019-2020	End Date: / 2024-2025
Overall programme risk rating:	Major
Vault Number:	48640916
[note] “Fostering new international development partnerships, and capacity to mobilize more private sector investments for sustainable development, with particular attention to inclusive Growth" G7 Charlevoix Commitment on Innovative Financing for Development.
[note] Public Markets refer to investment markets in tradable, listed investment products that can offer exposure to both private or public assets (both debt and equity) in emerging and frontier markets. A key feature of public markets is as mechanisms for publication and transparency of prices at which these products are bought and sold i.e. prices are set by the market.
[note] There is no single definition of emerging market and frontier market countries. Emerging markets are generally defined as those new markets that international investors consider relatively high risk but are beginning to increase their exposure (e.g. Brazil, Mexico, South Africa and Turkey). Frontier markets are those just outside the fringe of most international investors’ risk appetite (e.g. Indonesia, Nigeria, Philippines, Vietnam, Ghana, Kenya and Tanzania). A Frontier market is a type of developing country which is more developed than the least developing countries, but too small to be generally considered an emerging market There are about 24 to 40 different frontier markets globally. Frontier Markets represent 1% of total global market cap and 4% of global GDP.
[note] A particularly high bar on additionality will be set for any product exposure to UMICs in any programme funding decision. Nevertheless, more than 59% of the world’s poorest people live-in Middle-Income Countries and continuing progress in those countries is essential to achieving the SDGs and presents sound argument for portfolio diversification, within the context of a preference for LICs and LMIC exposure.
[note] IFC report on potential of Impact Investing 2019
[note] Sept 2018 DFID research “Frontier Markets Mobilisation: Facility Structure and Assets Study.”
[note] In terms of the volume of capital each product will mobilise and the leverage ratio of private capital to DFID’s investment
[note] The UK’s private pension fund sector (AUM) is 50x larger than all SSA (excluding SA) combined (source FSDA).
[note] MOBILIST balances DFID support between convening, enabling support and technical support, and capital participation in investment instruments, the combination of which is determined by deep analysis of specific product concepts and recommended ‘route to market’ plans developed by market experts.
[note] “Aid currently only fills one-sixth of the financing gap of the 48 most under-resourced countries,” Financing the end of extreme poverty, ODI Briefing Note, Sept 2018
[note] 32 bilateral programmes as a result of the 2016 Bilateral Aid review https://www.gov.uk/guidance/where-we-work
[note] There is increasing demand among UK retail investors for impact and yield products which some of these products could meet as regulated, listed vehicles. For a variety of reputational and regulatory reasons, active promotion to retail investors should wait until the products are seasoned and have a stable track record over a period of some years. But this future opportunity should be reflected in the inclusion of retail friendly investment vehicles now, so that they become retail-ready products overtime.
[note] Source: Initial analysis based on assessment of needs identification conducted by Sustainable Development Solutions Network (SDSN) https://www.unsdsn.org/
[note] The guiding policy agenda, to which DFID is committed was the 3rd International Conference on Financing for Development Addis Ababa from 13-16 July 2015.
[note] Including transparency, liquidity, asset and corporate governance requirements, etc.
[note] OECD Global Pension Statistics, Global Insurance Statistics and Institutional investors databases
[note] Currently, there are very few credible listed product opportunities for investors. For example, if an investor approached Blackrock (the world’s largest asset manager), then Blackrock would struggle to be able to offer any mainstream Africa-related product to their client and would be unable to propose a product that showed clear line of sight to (and impact on) the SDGs.
[note] Signifies end date for spend: the investments will initially stay on DFID’s balance sheet, but as the DFID’s mobilisation strategy develops and an off-balance sheet option comes on line (either through CDC, PIDG or a new entity), investments will either be exited or may be transferred to the new platform.

## Strategic Case

Context and need for DFID intervention
1. There is a US$2.5 trillion annual financing gap for the Global Goals (US$1.4 trillion of unmet need) through to 2030. The UN Stocktake of SDG progress in September 2019 concluded that the international community is significantly off-track., In response, the World Bank Group together with the IMF and other multilateral development banks coined the phrase “Billions to Trillions” to illustrate the scale of the global development challenge.
  [note] UNCTAD: Investing in Sustainable Development Goals – “Action Plan for Private Investments In SDGs” (2015), p. 7, available at: http://unctad.org/en/PublicationsLibrary/osg2015d3_en.pdf
  [note] LDC share of investment in SDG sectors, based on the current size of their economies and on the specific needs related to vulnerable communities, amounts to nearly $120 billion a year and a total for the 2015 - 2030 period of $1.8 trillion. Current investments in LDCs in SDG sectors are around $40 billion. https://unctad.org/en/PublicationChapters/wir2014ch4_en.pdf p.147 The guiding policy agenda, to which DFID is committed was the 3rd International Conference on Financing for Development Addis Ababa from 13-16 July 2015
  [note] UN General Assembly commitment to the ‘2030 Agenda for Sustainable Development.’ Emerging from this agenda, the final SDG (17) was qualitatively different. Rather than expound on what needed to be achieved, it addressed how to achieve the goals: “An important use of international public finance, including ODA, is to catalyse additional resource mobilization from other sources, public and private” https://sustainabledevelopment.un.org/post2015/transformingourworld.
  [note] “Marshalling other types of financing at the levels needed will demand greater efforts to unlock, leverage, and catalyse more public and private flows. Financing from private sources, including capital markets, institutional investors and businesses, will become particularly important” IMF: https://www.imf.org/en/News/Articles/2015/09/14/01/49/pr15170
  [note] April 2015 – “From Billions to Trillions: Transforming Development Finance, Post-2015 Financing for Development: Multilateral Development Finance:” African Development Bank, Asian Development Bank, European Bank for Reconstruction and Development, European Investment Bank, Inter-American Development Bank, International Monetary Fund, World Bank Group
2. International private investment (foreign direct investment and portfolio equity) in Africa and South Asia has remained persistently low, especially compared with ODA and remittances. This reflects high actual and perceived risks and high costs in those markets. DFID is acutely aware of the recent, cyclical withdrawal of investment flows from emerging markets and particularly how the poorest countries are failing to retain capital and attract new inflows.
Fig 2: OECD DAC members aid allocation to the poorest countries fell from a third in 2011 to a quarter in 2017.
[note] https://www.odi.org/publications/11433-financing-end-extreme-poverty-2019-update

Emerging and Frontier markets in Africa, the Middle East, South and South East Asia need capital across a broad range of sectors associated with the financing gap and SDG associated investment and spending needs. In broad terms, these markets need a combination of:
[note] The financing needs of these markets have been well-documented, for example, in the World Bank’s Billions to Trillions Report
- Large amounts of capital to fund infrastructure projects targeting the supply of basic needs such as electricity, water and sanitation, roads, ports, hospitals, etc, but also more broadly, to ensure and finance specific low carbon sustainable pathways to development.
- Smaller ticket size pools of capital to fund local businesses and priority sectors that create good jobs and drive inclusive economic development.
- Very small ticket sizes to fund the large number of micro-enterprises and individuals who have little or no access to funding, which in aggregate become sizeable.
Meeting these financing needs requires both greater local capital mobilisation, including public and private finance, as well as mobilising international capital flows. Whilst MOBILIST is focused specifically on international flows, or “foreign portfolio investment,” we do not exclude local capital and local listings as a desirable outcome for the programme.
Fig 3: Estimated SDG Financing Gap:
[note] ‘Investment Needs to Achieve the Sustainable Development Goals’ Guido Schmidt-Traub* UN SDSN Working Paper 2015

Geographical scope for MOBILIST
1. MOBILIST seeks broad geographic coverage in mobilising institutional capital. All ODA-eligible countries are in scope. However, the focus will be on Low Income (LIC) and Lower Middle-Income countries (LMIC) in Africa, South and South East Asia. We expect every product to have a significant profile in those markets. The precise weighting will be determined in consultation with selected fund managers and the identification of appropriate benchmarks, and subsequently codified in any resulting investment mandate. Performance, and geographical allocation would be assessed against these selected benchmarks, and tolerance for the fund to deviate from agreed benchmarks would include a recognition of both tracking errors and the fund manager’s discretion in actively managing the fund. From time to time there may be a case for Upper Middle-Income countries (UMICs) to be part of portfolios but only on the grounds of wider portfolio diversification and benchmarking purposes or for very high developmental impact and alignment with DFID policies – for example in North Africa and the Middle East.
  [note] Benchmarks relate to the availability of relevant indices, for example MSCI Emerging markets index https://www.msci.com/emerging-markets
  [note] The investment mandate is included in the Fund Prospectus, the marketing document for investors.
  [note] DFID will be able to monitor adherence to the investment mandate quarterly and ad-hoc portfolio reporting.
  [note] We would not expect the products to include China or other countries with their own strong capital markets.
2. DFID’s ambition is to increase the degree of portfolio exposure that institutional investors will commit to the poorest regions and countries. We seek to achieve that within the fiduciary, legal and commercial constraints that apply across legal jurisdictions, including the UK. Many of these countries represent the toughest markets in terms of investment opportunity but offer concentrated SDG impact in markets we are determined to help develop.
  [note] Typically, these offer less opportunity for scale because market activity is often the most constrained, through liquidity issues, tight capital markets and levels of risk perception. LICs and LMICs are investment destinations have limited appeal to institutional investors, and there is case, based upon strong additionality for portfolio diversification i.e. including wider markets where CDC operates, and more broadly still, to ODA-eligible countries where capital markets are sufficiently developed and where investor appetite is greater is the first step for any intervention seeking the close the financing gap
Key market failures addressed by the MOBILIST programme
1. Real and perceived risks explain why investment flows remain low in Low Income and Lower Middle-Income country assets. For investors to act at the scale required for the SDGs, they require evidence of the track record of the firm, sector and country they are investing in. According to Global Impact Investing Network 2017, the lack of high-quality investment opportunities with a track record of risk-adjusted returns is one of the top challenges reported by impact investors, together with (among others) the challenge of the availability of appropriate capital across the risk/reward spectrum.
  [note] An available performance track record (which is a function of already listed products) can be considered a high-quality proxy for investor due diligence, acquired at no cost to the prospective investor.
  [note] Annual impact Investor Survey 2017, the Global Impact Investing Network, 17 May 2017
2. Despite instances and periods of successful investments in Africa and South Asia, scale and continuity of track record is still absent. Lack of track record together with scarcity and unreliability of information means investors increase their view of the risk associated with an investment. Consequently, the required return and therefore the cost of capital for businesses is inflated.
  [note] Paul Collier notes how investors remember and over-compensate for negative information such as news of unrest or conflicts and are slow to adjust their investment decisions as a situation improves. This means that even if political and regulatory environments improve, this will not enable sufficient private investment to flow. Instead investment markets will find an equilibrium based on a lower level of investment because of the perception of risk - The Bottom Billion Paul Collier, Oxford University Press 2008
Table 1: Assessment of some of the key barriers is based on extensive investor consultations:
Lack of investable assets:	The core challenge is the lack of investment-ready opportunities. Our review of the investable assets across listed equities, bonds, as well as private equity and listed funds highlights how shallow these markets are when looked at from the perspective of a global asset or fund manager. Listed stocks and tradable bonds markets in frontier countries tend to be shallow and illiquid.
Fragmented markets:	Private debt and private equity markets in Emerging and Frontier markets are fragmented, which makes it difficult to access investments at scale. Yet investment products that can operate at scale, and with sufficient liquidity and yield, are needed if mainstream institutional investors are to allocate capital to frontier markets.
Lack of liquidity:	A substantial proportion of the assets in these countries are private with no developed secondary markets, and there are very few listed securities that offer enough traded volume negatively impacting the entry and exit strategy of investors. / MOBILIST’s strategy examines ways of aggregating private assets and bringing them into the regulated, publicly traded markets through a range of structures that are known to the market. This is key to expanding secondary market depth and could with time provide an exit route for private equity investors (such as CDC, DFIs and MDBs) to sell and recycle their capital.
Lack of transparency:	Emerging and particularly Frontier markets are opaque markets where governance levels tend to be low compared to more developed markets. There is very limited availability of information, there are no efficient data gathering mechanisms and there is very limited public information of key data. Without access to information, the perception of risk of investing in these markets increases and investors demand a higher risk premium. Most investments in these regions take place through private markets led by DFIs and private equity funds. These private investments, however, are by their very nature opaque. Increasing transparency and information flow of investable assets will be key to enhancing confidence in frontier markets and encouraging investment from the private sector. / MOBILIST’s strategy is based on developing structures that enable more transparency and market pricing because this is a pre-condition for inclusion of these markets into asset allocation models. Transparency includes strengthening governance and Economic Social & Governance (ESG) adherence.
Information asymmetry (and consequently misperception of risk)	The costs of capital (finance) is higher in markets characterised by capital market dysfunctionality i.e. there is a risk premium that comes from opacity. The yield premium demanded when track record is missing is a characteristic of asset pricing across emerging and frontier markets.
Lack of suitable exit options:	Investors need not only confidence that they find the right type of companies to invest in, but also that they can exit at an appropriate time and generate a return. However, in many developing countries, exits can be challenging due to a mix of regulatory/legal constraints, shallow capital markets (lack of public exchanges and secondary markets) and issues with major currency and other macroeconomic fluctuations.
Regulatory environment and regulatory constraints for investors	In most developing countries, regulatory frameworks have improved but the pace of reform is slow and further progress is needed to create a predictable, safe enabling framework for firms while protecting consumers. / Institutional investors face regulatory constraints in their own jurisdictions which inhibit scaling up investment in developing countries (e.g. higher capital requirements).
High political and macroeconomic risks:	The economic environment remains challenging with low domestic saving rates, dependencies on commodity prices and increasing private debt burdens. Political risks arising from pockets of conflicts and instability and lack of trust and accountability in public institutions due to corruption and weak rule of law add to actual and perceived risks. / This influence is mostly captured by movements in foreign exchange, which can at times erode all or part of the financial return generated in local currency.
[note] Private debt is comprised of mezzanine and other forms of debt financing that comes mainly from institutional investors such as funds and insurance companies and banks, which are generally illiquid, opaque and not regularly traded on organised markets. They are not publicly traded on a stock exchange and cannot easily be bought and sold on a secondary market.
[note] Political risk is made up of the following factors as measured by the Worldwide Governance Indicators (WGI): i) Voice and accountability; ii) Political stability and absence of violence; iii) Government effectiveness; iv) Regulatory quality; v) Rule of law; vi) Control of corruption

Making good on our ambition to support London as the ‘development finance hub for the world’:
Ensuring that the UK is well equipped to navigate, influence and lead the investment landscape, which is rapidly changing, requires acting today in order to develop first-hand knowledge and expertise in the pursuit of dual financial and impact mandates at scale in the medium term. The MOBILIST strategy (which alongside its product objectives, has a strong policy agenda focus) has the potential to contribute to the UK maintaining its leadership position as the financial service capital of the world, as a leader in sustainable development, with the City as the development finance intermediary of choice for Emerging and Frontier Markets and regional investment flows.
Investment landscape – state of the market:
1. Underpinning this agenda, pension funds, insurance firms and sovereign wealth funds, which together hold about $84 trillion in assets, will have to play a leading role if the financing gap is to be bridged. This institutional capital comprises roughly $54 trillion held by OECD asset owners, including pension funds and insurance firms. The balance is held by sovereign wealth funds, and in the form of excessive central bank reserves. These stakeholders are far from homogenous and they represent a wide range of investor types, with different interests and different investment appetites across many different jurisdictions.
  [note] OECD institutional investors manage up to US$84 trillion in assets, and OECD-based asset owners alone manage around US$54 trillion, including OECD asset owners (pension funds, insurance companies, and global public pension reserve funds), and excluding investment funds, as of December 2016. Source: OECD Global Pension Statistics, Global Insurance Statistics and Institutional investors databases and OECD staff estimates.
2. Current levels of invested international capital in Emerging and Frontier markets remain relatively low and offer tremendous growth potential. In 2018, only $1.6 trillion out of an estimated $44.1 trillion in global pension assets were invested in non-OECD markets. Foreign direct investment (FDI) flows to Africa slumped to a total of $42bn in 2017, a 21% decline from 2016. From this low base, there are non-cyclical long-term structural trends that should be favourable to increasing levels of interest. These include demographic trends, country growth rates that exceed OECD countries, and reports of an increasing interest, particularly among millennials, in the wider impact of their investments. There are plentiful supplies of institutional capital on OECD countries looking for good investment opportunities, and relatively low or negative yields for investors across their portfolios are deeply problematic, particularly for pension schemes that are unfunded or under-capitalised. For example, the simple weighted average for OECD pension funds returns in 2018 was negative 3.2 per cent. With investors focused on short term cyclicality, capital flows to Emerging and Frontier markets seem to some as detached from the longer-term structural drivers, particularly in some of the countries where the need for greater development impetus is most acute.
  [note] https://www.oecd.org/finance/private-pensions/globalpensionstatistics.htm Fig 1.5 “Total amount of assets in funded and private pension plans in the OECD and in other jurisdictions, 2008-2018”
  [note] UNCTAD, World Investment Report, 2018
  [note] https://www.oecd.org/finance/private-pensions/globalpensionstatistics.htm Figure 1.13. “Annual real investment rates of return of funded and private pension plans, net of investment expenses, 2018”
  [note] Monthly average available open source at: https://www.quandl.com/data/MULTPL/SP500_DIV_YIELD_MONTH-S-P-500-Dividend-Yield-by-Month
Fig 4: Trends of investment products: global and frontier markets:

1. Arguably pre-eminent amongst the world’s leading financial centres, the City of London provides more international lending than any other financial centre, is home to over 250 foreign banks, has over 500 foreign companies listed on its exchanges, and hosts over 200 foreign law firms in part due to its legal code being the most widely used legal system in the world. The UK is, as a result, well positioned to expand its role as a financing hub for the developing world.
2. As much as 96% of the assets of OECD institutional investors are invested in developed economies, mostly in listed bonds and stocks. This exposes them to low returns, record low interest rates and inflated asset valuations, making generating returns harder than at any time in recent history.
3. The lack of investment opportunities in Emerging and Frontier Markets is striking: only 0.5% of assets under management in the UK relate to Africa. Of the 341 UK domiciled, closed ended funds, only 10% have an emerging market focus. These funds direct about 10% of the market capitalisation attributable to UK domiciled closed ended funds to emerging and frontier markets. Of these funds, the largest number are backed by real estate. Total equity market capitalisation in frontier markets (often heavily weighted towards telecoms and extractives) is US$368 billion (excluding India and South Africa). This is a tiny amount when compared to over US$5 trillion for the primary developed markets represented on the London Stock Exchange.
  [note] ASSET MANAGEMENT IN THE UK 2017-2018, The Investment Association Annual Survey, September 2018
  [note] Sept 2018 DFID research “Frontier Markets Mobilisation: Facility Structure and Assets Study
4. In Frontier markets, the bond universe is highly concentrated in a few countries: South Africa with 441 bonds worth USD 2.1bn, and 38 bonds in India worth USD 24m and 3 bonds in Namibia worth USD 11m. Only India has municipal bonds in Asia (390 in total) and Nigeria and South Africa are the only African countries with tradeable local currency municipal bonds (22 and 18 respectively).
  [note] Universe comprises only 16,476 bonds, of which only 482 securities are tradable at three-month liquidity or better. This number does not rise for six-month liquidity.
5. Consequently, UK and OECD pension funds will have to work their developed markets assets harder to compensate for the reduction in returns, raising new interest in emerging markets. To some limited extent this search for new types of asset and new markets is already happening through the ’alternative’ – ‘private markets’ and MOBILIST seeks to capitalise on this following wind. MOBILIST is predicated on an increasing appetite to allocate a portion of money managers’ mainstream portfolio asset allocation to emerging market and frontier countries - if opportunities with an appropriate risk/ return profile coupled with an appropriate structure were available.
  [note] despite the growing allocation of alternative asset classes by pension funds to their portfolios, pension funds still primarily invest in traditional asset classes (bills and bonds, equities, and cash and deposits). For example, analysis conducted by the OECD in 2015, showed that in 2014, pension funds in the OECD invested 84.7% of their assets in traditional asset classes with on average 23.8% of their portfolio in equities, 51.3% in bills and bonds, and 9.6% in cash and deposits (OECD, 2015). This is a similar trend in non-OECD countries, who in 2014, had invested 89.6% of their portfolios in traditional asset classes.
  [note] In the US, Canada, Brazil, UK and Israel, pension funds’ assets in ‘alternative investments increased by close to or more than 5 percentage points’ (OECD Pension Markets in Focus 2015).
The emergence of a new type of investor and industry responses:
1. Other structural factors also support the approach of MOBILIST and likely demand for new investment products. Emerging evidence suggests that younger investors, sometimes referred to as “Millennials” are increasingly willing to invest in a way to ‘achieve both their personal objectives and to generate positive social and environmental outcomes.’ Whilst recognising the need to engage with older generations as well, Millennials will be the beneficiaries of ‘a significant intergenerational wealth transfer from Baby Boomers.’
  [note] Barclays Bank, Investor motivations for impact – A behavioural examination (2017), p. 3, available at: https://www.barclays.co.uk/content/dam/documents/wealth-management/investments/impact-investing-product/investor-motivations-for-impact.pdf.
  [note] Ibid., p. 9. According to Accenture, in North America alone ‘over the next 30 to 40 years, an estimated $30 trillion will change hands’ as assets are transferred from aging ‘baby boomers’ to millennials who are becoming the largest generation. See Accenture, Future of Wealth Management (2016), available at: https://www.accenture.com/t00010101T000000Z__w__/gb-en/_acnmedia/Accenture/Conversion-Assets/DotCom/Documents/Global/PDF/Consulting/Accenture-Future-Wealth-Management.pdf#zoom=50
2. The increasing demand for positive social and environmental impact is another factor that could entice investors to invest in frontier markets, where the positive impact from investment can be greatest. As a result, a number of investors, some mainstream and others niche, have made commitments to help fund the SDGs, help tackle climate change or invest for impact, especially in the form of development and poverty reduction. This group sees investing in Emerging and Frontier economies as a way of achieving these goals.
3. As a sub-set of this group on interested investors, ‘Impact’ investing too is on the rise. According to the GIIN’s 2018 Annual Impact Investor Survey, impact investing assets under management (AUM) have increased from USD 114bn reported by 208 investors in 2016 to USD 228bn reported by 229 investors in 2017.17 In 2017, Sub-Saharan Africa accounted for 36% of total deployed capital, and South Asia for 22%.
  [note] Nevertheless, the majority of impact investment funds are close-ended private fund structures only suitable for qualified private investors, typically high net worth individuals and foundations. Mainstream listed impact investment funds that are available typically focus on investments in European and US stocks.
  [note] Annual Impact Investor Survey 2018, GIIN
4. The programme’s assessment of which products to support to a listing, and how to then measure the development impact these interventions will draw upon the work of IMP. Helping investors to steadily progress across the chart below from left to right and where appropriate from top to bottom critical to the programme’s ability to quantify the primary and secondary impacts outlined in the Appraisal Case. The tools available to MOBILIST through IMP, including the IMP matrix (that helpfully categorises asset classes for impact) will be tailored and utilised in our own Monitoring & Evaluation framework (and in relation to the first two products identified in a competitive process, deployed immediately).
  [note] The Impact Management Project (IMP) has collaborated with over 2,000 investors and enterprises to develop “impact classes”, which group investments with similar impact characteristics based on their impact performance data (or, in the case of new investments, their impact goals). In short, an impact class combines the impact of an investment’s underlying asset(s) with the contribution the investor makes to this impact https://impactmanagementproject.com/wp-content/uploads/A-Guide-to-Classifying-the-Impact-of-an-Investment-3.pdf
  [note] N.B. Monitoring & Evaluation is covered in more depth in the Management Case.
Fig 5: The Impact Classes Available

1. Building on these identified supporting trends DFID’s Investing in a Better World initiative held a national conversation to find out more about the UK public’s views on and interest in ethical, responsible and impactful investment practices that helps achieve the SDGs. Amongst a range of findings, the results appear to indicate that, when presented with a choice, most people in the UK would prefer their investments to consider the impact on people and the planet, alongside financial considerations.
  [note] Investing for a Better World” survey report, Sept 2019:” The results show that, when presented with a choice, most people in the UK would prefer their investments to consider the impact on people and the planet, alongside financial considerations.”
2. According to the Business and Sustainable Development Commission (created to make the business case for the SDGs): “There is a major business opportunity for the private sector to invest in the SDGs (at least US$12 trillion in investible opportunities and 380 million new jobs by 2030), and there are big pools of long-term capital currently on the side-lines which could be invested. But mobilising an extra US$1 trillion of private capital a year (about 10% of annual net inflows into global savings pools) will require better deployment of blended finance…”
  [note] The Business and Sustainable Development Commission, Blended Finance Taskforce for the Global Goals, Private Capital and the SDGs: The Urgent Need for Scale, available at: http://businesscommission.org/our-work/blended-finance-taskforce-for-the-global-goals, accessed 03 September 2018.
3. It is clear that in order to avoid what could be unrealistic demands on many developing countries sovereign capacity to fund new infrastructure and social services through debt raising instruments, as well as funding existing contingent liabilities in public sector service provision, the SDGs (as a policy agenda) must be accompanied by strategic initiatives to increase private sector participation. Public listed markets are a critical element to this response and efforts to increase fund manager capacity to provide evidence of the nature and magnitude of development impacts achieved will be needed. This will be a critical aspect of the ‘learning’ component of MOBILIST which will support this capacity building.
The international response:
1. There is a strong interest from donors and private investors alike. Some European and North American Pension Funds are well advanced in identifying ways to gain exposure to developing economy assets. For example, ABP, the Dutch pension fund, invests 8% in emerging market equities and has 5% in private equity. Two of America’s largest pension funds, CalPERS and CalSTRS, are sophisticated investors with large holdings of emerging market equities, as well as a close to 9% allocation to private equity.
2. Amongst donors, the UK and Germany have been amongst the most proactive, and fora, like the ‘Nordic Plus,’ are proving to be effective showcases for new initiatives. For example, the Swedish SIDA, Dutch FMO and the Danish IFU have forged ahead with partnering institutional investors, especially pension funds and insurers, through models such as the Danish SDG Investment Fund. These partnerships illustrate a view, amongst development agencies and recipient countries alike, that the traditional DFI model alone will not mobilise capital at scale required. We need to develop new financial instruments able to mobilise institutional investment for developing countries.
  [note] In June 2018, the Danish Prime Minister launched the Danish SDG Investment Fund as a Public-Private Partnership with a 60/40 allocation between private and public investors. The Fund will contribute to the SDGs through commercial investments in developing countries. The Fund is established by six Danish pension funds, and IFU, Denmark’s official Development Finance Institution, which will also act as fund manager. Private investors, mainly Danish pension funds, will contribute 60 per cent of the Fund’s capital. IFC’s Managed Co-Lending Portfolio Platform for infrastructure has a guarantee element provided by Swedish SIDA
3. These institutional responses recognise that the financing gap across a wider set of ODA-eligible countries cannot be bridged by existing development finance approaches alone, nor should the UK nor OECD donors expect existing DFI and MDB instruments to catalyse private capital at the scale and in the time required. MOBILIST, like DFID, will continue to share information about the programme with development and private sector partners and to identify opportunities for collaboration, recognising that the programme’s ambition is to catalyse investment products on international and/ or local exchanges, and mobilising sources of both UK-based, international and local capital. That breadth of scope naturally leads MOBILIST into productive discussions with a wide range of UK and non-UK based partners.
  [note] Whilst MOBILIST welcomes partnerships with other development agencies where it makes sense, we also recognise that DFID’s relationship with and proximity to the City of London presents DFID with an almost unparalleled opportunity to lead and break new ground too.

How MOBILIST delivers DFID’s strategic portfolio
Alignment with DFID’s wider strategic goals:
1. There is a strong argument to use public finance to catalyse multiples of private investment, given market failures that restrain investment in developing country markets.
2. MOBILIST delivers DFID’s strategy by (a) mobilising high-quality private finance towards development outcomes as the core strategic objective and (b) demonstrating that ‘normal’ risk-adjusted financial returns are achievable for institutional investors who want to invest specifically in markets and sectors with a high impact on the SDGs. This includes delivery towards the following:
- Increasing private sector investment from the managers of the largest pools of global capital, including those located in the UK, into the world’s developing economies, specifically for SDG financing; including a strong focus on the lowest income countries (LICs and LMICs will have a significant profile in product portfolios);
- Creating additional pathways to mobilising private finance for development at scale through proof of concept, demonstration effect and an insistence on product ‘replicability;’
- Increasing access to finance, by creating new incentives for firms to list locally and internationally and for local institutions and development finance institutions to sell-on assets sub-optimal to the balance sheet, thereby enabling scare public capital to be recycled for new lending, and encouraging new investing and lending further down the value chain to businesses which are most capital constrained;
- Inclusive job creation through investments made into underlying investee companies across a range of economic sectors whose growth is critical to development objectives such as energy, infrastructure, manufacturing, agriculture, financial services and social sectors; the programme will establish ex ante and ex post methods to measure impact in these specific sectors.
  [note] According to DFID’s 2018 ’Best Buys’ analysis” energy provision and pricing are issues in virtually all of DFID’s partner countries. Interventions are best suited to those places where there is potential to undertake pricing reform alongside generation investments.” Illustratively, these are issues which will feature in DFID’s ’additionality’ considerations when reviewing product proposals.
MOBILIST seeks to showcase a type of intervention more aligned with the ‘financing’ as opposed to ‘funding’ model - a shift of emphasis in ODA spend that is proving interesting for a range of donors when thinking about the future of aid approaches.
Moreover, MOBILIST should be seen as one component of a portfolio of DFID programmes seeking to mobilise public investment into developing countries for development impact, but one uniquely focused on public market interventions.
Aligning with DFID’s current and future programming:
1. As part of the DFID’s wider mobilisation work, DFID is developing three other programmes – an early-stage SME financing programme, a planned investment into an IFC-managed private equity fund and a balance sheet optimisation transaction with the African Development Bank.
2. MOBILIST will inform the development of DFID’s long-term approach to mobilisation with a strong commitment to learning by doing, and through the close engagement with institutional investors upon which delivery is predicated. Moreover, the technical assistance component will include a strong monitoring, evaluation and learning workstream, implemented through the proposed Technical Assistance Facility, that will generate broader lessons on the effectiveness and impact that can be applied across other DFID programmes, and has a specific role to play in the development of the longer-term approach and programming that are now under consideration. Anchoring listed products now will help DFID learn what is possible and how strategically, new mobilisation work should be positioned relative to CDC, Private Infrastructure Development Group and DFID’s own balance sheet mobilisation efforts.
Fig 6: Private Sector Development Finance Spectrum:

1. To date DFID’s focus has been on private markets. CDC makes investment into private equity and debt opportunities, and DFID acts through multilateral or regional institutions who have built products (MCPP/ AfDB’s synthetic securitisation) or platforms (AMC/ PIDG’s EAIF and GuarantCo) to mobilise institutional wealth. MOBILIST would represent a first focus for DFID directly on accelerating the commercial ‘listed investment’ end of the development finance continuum.
2. Building investment in traded instruments should be seen as complementary to DFID’s existing mobilisation strategy of catalysing private capital through direct investment and through DFI-led bespoke structures. These DFI-led structures provide opportunities for a group of investors to invest in specific investment amounts, through their private market allocations and under specific timeframes. However, these structures are proving difficult and slow to replicate, information on performance is not disclosed to the market, and they can take a few years to be investment ready. Relying solely on orchestrated transactions to deploy capital may not be enough to enable the amount of fund flows that the capital markets could provide if the appropriate investment vehicles are available to them.
  [note] Typically, these structures tend to mirror or in some way leverage DFI activity and are usually supported by a first loss facility of some kind. DFI-led bespoke structures have the advantage of being able to mobilize larger pools of capital for deployment in emerging and frontier countries in one transaction
3. Another important role of MOBILIST will be in using listed products to help evolve how the investment community uses capital to directly target ESG, impact and other risk management frameworks, thereby demonstrably contributing to bridging the SDG financing gap. This will be an important way of influencing behaviour and raising standards in markets where there are already concerns of impact, green and SDG washing.
  [note] That is to say, identify ways in which all or most SDGs can be supported as opposed to focusing on one with no regard for the others, and same with ESG factors, which are increasingly viewed in tandem. At present, we can see an environmental fund that invests in renewable energy companies that have a very poor human rights track record. Going forward, we should be able to integrate the need for all these factors to be considered in order to meet the stewardship and SDG guidelines.
4. MOBILIST complements the work of other DFID programmes, seeking to promote prosperity, enable capital market reform, to grow new sectors, and to improve the skills in developing countries and critical cross government agendas including climate finance. For example, the Prosperity Fund and new ‘Building Markets’ DFID geographies align well to the geographies of MOBILIST. DFID has a strong proposition at the stages of business development. Through its innovation funding DFID offers challenge fund opportunities for businesses looking to prove their concept and supports sector investment vehicles such as Financial Sector Deepening Africa and AgDevCo.
  [note] The SoS-PM letter in Summer said we would extend our “building markets” offer in up to 10 new geographies including Indonesia, Philippines, Vietnam, Côte d'Ivoire, Senegal and South Africa. DFID is currently exploring which additional countries to expand into, alongside what this would like in practice, country by country.
5. The governance of MOBILIST, through the establishment and targeted membership of a dedicated programme governance body, the MOBILIST Investment Committee or ‘MIC,’ affords DFID the opportunity to consider the work of MOBILIST in the context of this wider HMG strategic portfolio, and there is opportunity to consider the programme’s product selection in relation to wider programming and policy objectives. For example, an HMG portfolio of interventions that is weighted towards one sector and not another would afford the MIC the opportunity (in the context of the programmes listing objectives) to place more emphasis on underweight sectors. Once convened, we propose to test appetite for broadening the MIC’s remit to include a portfolio approach.
  [note] This Committee is separate from DFID’s Investment Committee with ExCo members in attendance
Fig 7: Role of development capital in attracting private capital: DFID’s existing instruments and gaps

Programme Narrative
1. MOBILIST seeks to support up to 5 investment products to list on the London Stock Exchange (LSEG), and/ or dual or domestic exchanges, that meet the requirements of institutional investors (to allocate the bulk of their portfolios to exchange listed products). By doing so, the programme will help accelerate investment flows from developed public markets to Emerging and Frontier markets to help bridge the SDG financing gap.
  [note] [Former] Secretary of State FT interview, 11 April 2018: “DFID’s aim is to facilitate pension funds’ investment in emerging countries...”
2. These products may be unlisted private market products to begin with, but DFID’s support is conditional on the intention for listing. Nevertheless, all the products envisaged will be in the form of standardised legal structures that are familiar to UK investors, but with mandate to deploy capital in ways that achieve positive development impact.
3. The focus will be on Low Income and Lower Middle-Income countries in Africa, South and South East Asia. We expect every product to have a significant profile in those markets.
4. MOBILIST balances DFID support between convening, technical assistance, and capital participation in investment instruments. Once the programme is operational, the combination of which will be determined by deep analysis of specific product concepts, existing and future ‘route to market’ plans developed by market experts during earlier design work.
5. The focus is on those vehicles that would be scalable, replicable and contribute to price discovery for particular geographies, sectors, or asset class. The selection of structures presented is based on four factors:
  [note] ...and will be cognisant of other programming approach, including an HMG portfolio approach and in relation to international partners.
- the potential demand for underlying assets from institutional investors in relation to their risk-adjusted returns;
- the relative simplicity of familiar structures that would potentially not require regulatory changes or prolonged negotiations between DFID, investment managers and investors;
- availability and capability of fund managers, and specialist brokers, underwriters, lead investment banks to execute on preferred structures and investment mandates;
- cost and commercial competitiveness.
1. The programme complements DFID’s current and future efforts to mobilise capital. DFID will continue its strong offer in private markets including through CDC and DFID shareholdings in the MDBs as well as the any future collaboration with IFC’s Asset Management Company. MOBILIST therefore marks a further step forward in the evolution of the UK Aid Strategy: expanding DFID’s intermediation role to enable new channels for mobilisation to emerge. The business case seeks to expand DFID’s role from a provider of capital for development focused on private markets, to encompass the ability to play a catalytic role for mainstream institutional capital.
  [note] The work on mobilisation is aimed to complement DFID’s existing private market interventions, including new proposed collaborations with IFC, by addressing the public-market failures that constrain the mainstream investment allocations of the principle categories of institutional investors (pension funds, insurance companies, commercial banks and other asset managers).
  [note] https://www.gov.uk/government/publications/uk-aid-tackling-global-challenges-in-the-national-interest
2. Over the longer term, MOBILIST builds a platform for developing more complex, long term listed product strategies which may take 3 to 5 years or more to be ready to catalyse capital. These types of product will require a lot of market building, including adoption of a common language, common metrics (including for development impact) and reporting, standardised bundling processes and standardised ratings processes.
  [note] The most probable instruments to reach this scale would include SDG bonds and synthetic CLOs.
  [note] We refer in this case to instruments that are extremely complex largely due to the amount of information that needs to be processed, shared and priced. These vehicles could become the products of choice for market participants to enter frontier markets given their attainable scale and impact potential. They are expected to achieve a high level of standardisation over the long term, after a number of other products have tried out alternative ways of aggregating assets in lower scale in specific sectors or markets. They would also be able to reach further down the value chain into the small loans that are needed to reach the low- and middle-income populations in these countries, offering some of the highest levels of impact.
Fig 8: MOBILIST’s strategy to anchor more complex listed products, increase the ability for SDG targeting and catalysing greater volumes of capital:

Key development impact metrics to be tracked:
1. Mobilising private investment that has direct line of sight to the SDGs is the basis for the international community’s commitment to close the financing gap. Our research has determined that the sophistication of development measurement tools that target SDG related financing - be they in relation to ’green’ finance, impact, or ESG, is developing rapidly. Through MOBILIST, DFID has the opportunity to help catalyse products that are differentiated not just in their exposure to the places that matter developmentally, but to demonstrate that viable listed products can have a verifiable line of sight to impact and the developmental issues that people care about.
  [note] In food security and agriculture, total investment needs are around $480bn per year, implying an annual gap of some $260bn over and above the current level; in climate change mitigation, only a minority share is contributed by the private sector – estimates up to 40% in developing countries.
2. MOBILIST will work with Fund Managers to design and tailor appropriate development impact measurement methodologies, through the TA component, or through the stages of a competition, to determine which approaches best balance the need to appeal to institutional investment capital in public markets, and at the same time deliver a market proposition that meets DFID’s requirements in delivering against the SDGs. DFID will work with leaders across the impact measurement field (including the Impact Management Project) to propose and integrate effective development impact measurement across the products. This is a challenge due in part to the complexity of attributing impact in publicly owned investment structures. All products will apply IFC performance standards (as part of the risk management framework) and as both the product and programme evolve, we will actively seek to build on standards that assess ESG primarily as a financial risk, towards broader development impact measurement as the body of evidence grows and new thinking emerges.
  [note] https://www.ifc.org/wps/wcm/connect/Topics_Ext_Content/IFC_External_Corporate_Site/Sustainability-At-IFC/Policies-Standards/Performance-Standards
  [note] The M&E and L&D components of MOBILIST have the potential to lead some of this work.
3. Each product line will have its own log frame, which complements the programme’s overall log frame. Independent monitoring and evaluation support will be developed for each product to check progress against expected outcomes.
4. At a product ‘Outcome’ level, impact metrics will include three essential components: i) metrics relating to the investment vehicle itself, including outputs on leverage (volume of capital raised); ii) time and milestones to market (including listing and Initial Public Offering (IPO)); iii) developmental impact, including for example, the poverty reducing effect of infrastructure financed; iv) jobs created or capital recycled for onward lending in priority sectors – these metrics will be expressed through a strong ESG and/ or impact investment mandate and tracked through measurement tools; v) systemic effect, including the effect of price signals on the market’s ability to obtain price discovery and to reduce an asymmetry of information; risk/ return profile; product replicability and demonstration effect (including coverage of harder to reach frontier market assets) etc.
5. The overall programme log frame will be concerned with outcome metrics in relation to market building. For example, its concerns relate to the ability (through proof of concept), to catalyse increasingly complex and scalable listed products; the ability to change the narrative on listed products, emerging and frontier markets and the opportunities these markets present in terms of both yield and developmental impact.
6. The policy element of MOBILIST, which will be supported by products, the TA Facility and through DFID’s ‘convening’ role will support the systemic market building element of MOBILIST’s work. Moreover, policy work will also support wider portfolio and policy work streams within DFID, for example on impact, or on capital market reform either through centrally managed programmes or through country office interventions.
7. Finally, the log frame will consider opportunities to assess the impact the programme may have on policy debates around how the development community funds – or finances – poverty reduction and climate objectives and the role of securitisation and balance sheet optimisation for DFIs’ and IFIs as well as banks and other financial service providers.
Stakeholder considerations:
1. That the programme’s product outputs are market-led solutions is of critical importance because these must be – and be seen to be – commercially-grounded investment products. These must be products that the market stands behind and that reputable financial institutions are committed to, either in terms of their capital and/ or their professional reputation, before DFID agrees to participate. The willingness of institutional investors to work with MOBILIST – and through formal bids - to articulate their requirements is critical.
2. We are working in close collaboration with our existing investment vehicles, CDC and PIDG. Whilst we do not expect DFIs or the World Bank (through IFC) to invest, with neither currently invested in ‘listed’ products, both our own CDC and PIDG, DFIs and selected IFIs possess relevant insight into investor behaviour. We are also engaging with development partners, who recognise the potential, but with the exception of the MDBs (who supplement their own capital through listed market activity – bond issuances), have limited activity in this area.
3. A supportive regulatory environment is also a critical factor in a country’s ability to attract capital, and in-country regulators, together with the UK’s own regulatory authorities are critical stakeholders. These are issues that our Financial Sector Deepening Africa programme for example, is seeking to address. With a differentiated approach, MOBILIST seeks to identify where regulatory barriers need to be addressed at a country level by demonstrating how capital can flow through listed product structures in comparable countries, with similar levels of capital market development, but where crucially, the principle ingredients for inclusion in a listed product portfolio are already in place. By demonstrating proof of concept, specific jurisdictional barriers can be better highlighted in policy discussions with partner countries.
4. HMT, DIT and the City of London are amongst the key HMG and external stakeholders. MOBILIST links across the UK financial services sector, including leading asset and fund managers, asset owners, including pension funds and insurers; including the Sustainable Development Capital Initiative (the City’s response to the ambition that London is “the worlds’ development finance hub”), Insurance Development Forum, Investment Association and Pensions & Life Savings Association.
  [note] https://news.cityoflondon.gov.uk/london-set-to-help-meet-un-sustainable-development-goals/
5. This business case has been developed in close collaboration with DFID Financial Accounting and ODA teams and HMT to ensure that DFID’s investment can be (a) fully classified as ODA and (b) the impact on the DFID balance sheet aligns to DFID’s financial accounting controls. Our clear priority is to avoid any risk to ODA eligibility or boundary conditions, due to the complex nature of the products that could emerge from the competitive processes. A zero tolerance for non-ODA-eligibility, or balance sheet consolidation or an adverse classification of the preferred entity as a Non-Departmental Public Body (NDPB) is a stated assessment red-line (evaluation criteria) in any consideration of support to list products, including a clear articulation of these issues in competition documentation. As an additional control, the programme will continue to track these issues and through the programme’s governance mechanisms (including the MIC) ensure that approvals for intervention include consideration of these risks.
Impact and Outcomes to Achieve:
1. The primary benefit of the interventions outlined is at a systemic level: building a portfolio of listed products is intended to lay (at least an element of) the foundations for the medium to long-term development of open and transparent capital markets at scale. This will not be achieved by creating markets with a long-term reliance on subsidy, which is has already proved not to be scalable in relation to the needs nor can subsidy-based model be considered sustainable over the long-term. For these reasons, MOBILIST seeks to be both catalytic and facilitative.
2. The specific impact and outcomes that each listed product seeks to deliver will be specific to that particular investment structure.
  [note] Once the products are determined and the sectors impacted are clear. DFID will work with the fund managers to develop appropriate tools to track development impact, drawing on existing best practice and the latest approaches for public markets. For example DFID will use our specific infrastructure impact tracking approaches from our experience at PIDG, adapting as required for the public market context.
3. The expected impacts of these interventions are i) contribute to the closing of the financing gap; ii) an expanded and more engaged investor base (including more opportunity to partner with DFIs and development agencies) for developing country assets; iii) a lessening of market information asymmetry and iv) more accurate risk/ return assessment and profiling of emerging and frontier markets through listings as a mechanism for price discovery; v) reduced cost of and increased access to capital in LICs and LMICs; vi) higher portfolio returns (yield) for UK-based customers of institutional asset managers.
4. The key outcomes of the programme are the expansion of finance to underpin sustainable growth, including infrastructure and services that deliver social benefits direct to households, such as electricity and clean water, and the delivery of economic benefits to businesses such as roads that give access to markets and electricity that help run storage or manufacturing facilities, and finally the development of productive assets upon which a government’s tax base and long term revenue stream depends.
How MOBILIST fits with UK Strategic Priorities
1. Providing the global public good of financial stability and efficiency is not just in the interest of developing countries and the poor. Stable growth in developing countries provides growing markets for UK exporters and increasing profitable opportunities for UK-based investors. Greater prosperity in these countries also reduces potential political instability, helps populations finance mitigation and adaption to climate and environmental risks, and reduces pressure for migration to developed economies like the UK.
2. In terms of MOBILIST’s geographical coverage, we will focus on Low-Income Countries (LICs) and Lower Middle-Income Countries (LMICs) but may also include some Upper Middle-Income Countries (UMICs) where there is a clear case for additionality, for example into higher risk sectors or new green sectors. The investment mandate will specify an approach to countries likely to graduate from ODA-eligibility during the investment period. Where possible we will weight towards DFID’s priority geographies, which may evolve based on a range of factors including fit with the National Security Strategy, HMG foreign policy and trade objectives, alongside the wider geo-political context.
  [note] it is worth noting that in addition to Africa being an obvious development priority, the NSC has also recognised that Africa’s strategic importance to the UK will increase considerably over the coming decades, driven by economic, demographic, climate and other trends. Coupled with the view that the UK’s offer to Africa is being overtaken by our international partners, who are increasing their engagement with and presence on the continent, MOBILIST has a clear relevance to wider HMG objectives for the continent.
The Evidence Base:
1. The financing gap is real and growing. ODI estimates that between the 46 poorest countries in the world, there is an additional aid financing need of $131 billion a year – six times the $22 billion a year of aid that is currently given for human development in these countries.
  [note] Nearly half (41%) of the $222 billion a year funding gap in the 46 countries could be filled by the countries themselves. They could, on average, increase their tax revenues by a quarter. And they could increase the share they allocate to human development from 28% to 50% (some have already been allocating over 40%, including Ethiopia and Tanzania). If they maximised their tax revenues and allocated half of their revenues to human development, they could fill half the gap. https://www.odi.org/sites/odi.org.uk/files/resource-documents/12907.pdf
2. MOBILIST recognises that cyclicality presents particular challenges to an investment approach that is predicated on broad long-term trends for developing countries, when short-term market conditions are a key driver of FDI and foreign portfolio flows (FPI). Evidence on cyclicality illustrates the challenge: according to data quoted in the CDC business case, in sub-Saharan Africa, financial flows are characterised by significant volatility (due to strong dependencies on commodities) and concentration (in individual countries). From a period of significant increase between 2004 and 2008, FDI flows to Africa have flat lined and have fallen since 2013. Reflecting deteriorated overall growth in 2016 (mainly from lower commodity prices), FDI inflows to Africa accounted for 3.4% ($59bn) of global FDI flows. Within Africa, there is a significant annual variation in FDI inflows driven by large one-off infrastructure or mining investments in specific countries. Countries such as the DRC have suffered significant falls in FDI in 2016 as a result of low commodity prices.
  [note] Data from UNCTAD (2017), World Investment Report - Investment and the Digital Economy, UN, New York http://unctad.org/en/PublicationsLibrary/wir2017_en.pdf and World Development Indicators http://data.worldbank.org/products/wdi – unless otherwise indicated
  [note] The sum of equity capital, reinvestment of earnings, and other capital. The criterion for direct investment is ownership of 10 percent or more of ordinary shares.
  [note] African Economic Outlook 2017 http://www.africaneconomicoutlook.org/sites/default/files/2017-05/African_Economic_Outlook_2017.pdf
  [note] Much of the most recent growth in FDI flows to Africa in 2016 can be attributed to investments related to natural gas discoveries in Egypt; much FDI in past decades has also been associated with oil and gas.
  [note] Ibid.
3. Similarly, portfolio equity investments to Africa have more than halved since 2010 and are lower than in 1998, standing at $7.2bn in 2015. This trend is not set to reverse, with the African Economic Outlook 2017 predicting further falls over coming years. Domestic credit is an important source of capital with 46% of GDP being lent to the private sector in Africa, but well below the global average of 129%. However, there are substantial inter-regional variations with most of Africa’s figure driven by South Africa’s 150% ratio, compared with 5% in South Sudan or 7% in the Democratic Republic of the Congo. Since 2009, average domestic credit to the private sector in Africa has been falling as a share of GDP.
  [note] Portfolio equity includes net inflows from equity securities other than those recorded as direct investment and including shares, stocks, depository receipts (American or global), and direct purchases of shares in local stock markets by foreign investors. Data are in current U.S. dollars.
  [note] African Economic Outlook 2017 http://www.africaneconomicoutlook.org/sites/default/files/2017-05/African_Economic_Outlook_2017.pdf
  [note] Financial resources provided to the private sector by financial corporations, such as through loans, purchases of non-equity securities and trade credits that establish a claim for repayment.
  [note] World Bank database
4. In South Asia, financial flows are characterised by trend reversals (due to more integration with world markets) and inter-regional variations (given the diversity of the region). Similar to Africa, South Asia experienced a period of significant increase of FDI from 2000 until 2008. Since then FDI flows have mostly fallen and only since 2012 have grown again. Nevertheless, South Asia still accounted for only 3.8% ($66bn) of global FDI flows in 2016. South Asia's FDI inflows remain among the lowest relative to GDP among developing country regions, for example in 2015, the UK’s FDI per capita was US$897, whereas Pakistan’s was just $5.
  [note] Definition of South Asia as per CDC’s Investment Policy
  [note] Data from UNCTAD (2017), World Investment Report - Investment and the Digital Economy, UN, New York http://unctad.org/en/PublicationsLibrary/wir2017_en.pdf and World Development Indicators http://data.worldbank.org/products/wdi – unless otherwise indicated
  [note] UNCTAD World Investment Report 2017 http://unctad.org/en/PublicationsLibrary/wir2017_en.pdf
  [note] 2015 FDI new inflows data based on World Bank data https://data.worldbank.org/ divided by population numbers for the UK and Pakistan
5. Portfolio equity inflows to South Asia have also fallen dramatically since 2012, down from $23.4 billion to $2.3 billion in 2015. Domestic credit to the private sector is 48% of GDP, only slightly higher than in Africa. There are also substantial inter-regional variations with Nepal’s emerging capital markets (65%) standing against Pakistan’s (15%) or Afghanistan’s (4%) constraints. Even though average domestic credit has been consistently increasing in South Asia since the 2000s, it has done so from a low basis of 20%.
6. There is strong global consensus across governments and businesses about the vital role institutional capital plays in underpinning economic growth, dispersing risks and reducing the cost of capital. Institutional capital is a central plank of the UK’s economic model and it has a substantial profile in Frontier and Emerging as a primary modality for financing sustainable growth opportunities. Institutional capital is a major theme of G20 discussions on the global economic crisis and featured prominently during the last G20 summit. It also featured heavily during the Addis Conference.
  [note] Building on the G20’s Action Plan on the 2030 Agenda for Sustainable Development and 2013 G20/OECD High-Level Principles of Long-Term Investment Financing by Institutional Investors, the Osaka Update underscored the G20’s collective and concrete actions contributing to the implementation of the Agenda and helping to ensure that ’no one is left behind.’
  [note] Third International Conference on Financing for Development, Addis Ababa, Ethiopia, from 13 to 16 July 2015
7. The economic literature on the importance of institutional capital in creating an enabling environment for economic growth and income generation in developing country contexts is well established and its role as a key constraint in growth has been identified in numerous studies and surveys. While access to institutional capital is viewed as a constraint by businesses in growth and job creation, it is also seen as an integral part of the Frontier and Emerging Markets growth story, as well as more cautionary tales about the fickleness of international capital and the effect its volatility has on a country’s capital account.
  [note] “Institutional capital development in Frontier and Emerging Markets has a significant positive contribution toward growth…causality analysis shows that there is unidirectional causality from institutional capital development to output growth. From a policy perspective, there should be greater emphasis on institutional capital development to sustain the high economic growth which the Frontier and Emerging Markets economy has been experiencing for the last few years.” Pravakar Sahoo & Ranjan Kumar Dash (2009): Infrastructure development and economic growth in India, Journal of the Asia Pacific Economy, 14:4, 351-365
8. The impact of institutional capital development on economic growth, productivity and trade has been extensively studied, and most studies conclude that improvements in a broad range of institutional capital is supportive sustainable growth and development. There is a significant positive causal link between institutional capital and a positive and significant output contribution.
  [note] IMF Working Paper on Financing Institutional capital in Frontier and Emerging Markets (2011)
  [note] Roller and Waverman (2001), using data for 21 OECD countries for over 20 years
  [note] Calderon and Serven (2003)
9. In the Frontier and Emerging Markets context, some studies show that institutional capital development has a significant positive contribution toward growth. DFID’s own ’Best Buys’ analysis notes that it is “difficult to estimate a causal relationship, though correlation between finance and growth is strong.”
  [note] Sahoo and Dash (2009) looks at the role of institutional capital in economic growth over the period 1970–2006
10. Imbalances in regional infrastructure availability have been a major reason behind lopsided development in Frontier and Emerging Markets. There are substantial positive association between levels of development and levels of institutional capital, with the association weakening over time.
  [note] Rajarshi Majumder (2004) assesses the role of institutional capital investments in regional development
11. A recent IMF working paper concluded that financial sector development helps reduce poverty. Specifically, the study estimated the quantitative impact of financial sector development on poverty in 65 developing countries and found that (i) financial sector development raises economic growth and reduces poverty; (ii) financial sector development directly reduces poverty by raising the investment and interest incomes of the 20% poorest households and; (iii) financial sector instability directly reduces incomes of the poor thereby raising poverty.
  [note] G. Jeannwney, S. and K Kpodar (2008), Financial Development and Poverty Reduction: Can there be a benefit without a cost? IMF Working Paper #62. Washington DC
  [note] The authors estimated quite large coefficients on the financial sector development variable – a 10% increase in the broad money (M3) to GDP ratio raises the incomes of the 20% poorest households by between 3 and 5%
12. Some studies have established a clear, positive linkage between financial development – and more specifically growth in bank credit relative to GDP, and stock market liquidity relative to GDP – and the overall rate of economic growth.
  [note] Bagehot (1873); Schumpeter (1912); Gurley and Shaw (1955); Goldsmith (1969); and McKinnon (1973); R. Levine and S. Zervos. 1998. Stock Markets, Banks, and Economic Growth. The American Economic Review; M. Arena. 2008. Does Insurance Market Activity Promote Economic Growth? A Cross-Country Study for Industrialized and Developing Countries. The Journal of Risk and Insurance. 75 (4). pp. 921–946.
13. Specifically, growth in bank credit and the traded value of the stock market positively predict growth, capital accumulation and productivity improvements even after controlling for economic and political factors. In effect, stock markets support pooling of funds, risk diversification, and liquidity management, which improves the efficiency of capital allocation and increases productivity in economic sectors relevant to the SDGs (like for example, the fast growing, high labour absorbing serve sector). This observation was confirmed by a study by Robert G. King and Levine (1993) that showed the level of financial intermediation is a good predictor of long-run rates of economic growth.
  [note] This observation was confirmed by a study by Robert G. King and Levine (1993) that showed the level of financial intermediation is a good predictor of long-run rates of economic growth, capital accumulation, and productivity improvement. Countries such as Indonesia which experience lagging, or below average levels of bank credit and stock market liquidity also report below average levels of GDP growth
  [note] Ross Levine and Zervos (1998) also demonstrated that stock market liquidity and banking development both positively predict growth. Although the two analyses confirm financial sector development does impact growth, the impact on growth from stock markets and bank credit varies from one country to another country.
14. Another study provided the first multi-country time series analysis of the connection between bond markets and economic growth. When applied to most of the EU member states, the United States, Japan, Switzerland and Norway, the analysis mirrors existing research in that development of bond markets leads to increases in real economic activity.
  [note] Gerhard Fink, Peter Haiss, and Sirma Hristoforova. 2003. Bond markets and Economic growth. Vienna
15. Nevertheless, the 2008 financial crisis and the experiences of emerging economies as previously beneficiaries of institutional capital flows are cautionary. Countries like Indonesia, which began to rely for development financing on debt securities and private sector financing after the 1997-1998 crisis, were highly vulnerable to external shocks that result in disruption of foreign capital flows. Financial contagion occurred when negative market sentiment and changed perception of risks set in: the 2008 financial crisis, and subsequent crises across South East Asia is a case study on how easy it can be for foreign investments flows to be reversed, causing severe macro shocks to the economy, destroying growth and eventually lower standards of living.
  [note] https://www.odi.org/sites/odi.org.uk/files/odi-assets/publications-opinion-files/4327.pdf
  [note] For the full year 2008, the Indonesian, the stock exchange index fell 51.17%, with 26.04% in the last three months of the year. Market capitalisation for equity at the end of the year fell by 46.42%.
16. Central to the financial crisis was the role of international capital markets. The key element in relation to capital flows was their volatility. Subsequently, policy makers have sought both the encourage capital flows and at the same time identify ways to mitigate or reduce their volatility.
  [note] ”Consequently, the study recommends the need for the prudent management of these determinants (with particular reference to indigenous variables) to ensure reduced volatilities in these capital flows which are essential for the growth of the domestic economy, particularly at this time when the Nigerian economy is in great need of foreign investment” Determinants of FDI and FPI Volatility: An E-GARCH Approach, CBN Journal of Applied Statistics Vol. 8 No. 2 (Dec 2017) https://www.cbn.gov.ng/Out/2018/SD/Determinants%20of%20FDI%20and%20FPI%20Volatility_An%20E_GARCH%20Approach.pdf
17. The poverty reducing impacts of institutional capital depend heavily on the characteristics of the institutional capital sub-sector being considered (accessibility, quality and affordability In Uganda, roads and in particular rural feeder roads, were second only to agricultural R&D in reducing poverty. In China, roads and particularly low-grade roads contributed to poverty reduction for both rural and urban poor through improved transport of food and raw materials, reduced food prices and growth of industry.” Institutional capital that enables low-skilled and semi-skilled income earning opportunities are likely to be the most poverty reducing. Rural, district and state roads; rural electrification etc. and are more likely to be poverty reducing than many other kinds of transport institutional capital (national roads; airports etc.).
18. DFID believes that investment and job creation are fundamental to poverty reduction and leaving no one behind. The work of the Office of the Chief Economist and the Research and Evidence Division of DFID on ‘best buys’ in economic development has rated debt and equity investments in firms in LICs and MICs as ‘high potential’ pending further study on macroeconomic effects of DFI investments but notes that there is a ‘range of evidence showing firms benefit from participating in global markets.’ It is estimated by the World Bank that the doubling of investment rates is associated with a 2% increase in the rate of GDP growth. Research shows that a 10 percentage-point increase in the ratio of private credit to GDP could lead to a 2.5–3.0 percentage-point reduction in poverty incidence.
  [note] Research and Evidence Division’s ‘Best Buy’ note on Economic Development, 25 January 2019.
19. The DFID Best Buys report also considers “modest amounts” of technical assistance (or partial guarantees) as having “high potential” to “unlock substantial amounts of finance.”
20. The programme has to be underpinned by the commercial logic of institutional investors welcoming an expanded investment choice. The benefits of an expanded investment universe for institutional investors is perhaps the most well-researched body of evidence available. Historically, a balanced portfolio of rich country stocks and bonds has generated good returns. For example, SocGen finds that the medium-term real returns on such portfolios in the mid-80s were around 8% but have fallen precipitously since to 3% in the mid-2000s to just 1% now. The S&P 500 now yields about 1.9%, with the DAX only marginally higher.
  [note] https://www.societegenerale.com/sites/default/files/documents/Econote/N29%20Econote%202015-09_MHD_Low%20interest%20rates.pdf
  [note] The largest outliers are energy exporters, because wealth in these countries is not reliant on the social and governance progress that goes hand in hand with rising wealth in other countries - Thoughts from a Renaissance man, Economics & Strategy, 17 October 2018
21. The importance of public listed markets is also extensively addressed in the literature: Banerjee (1992) and Bikhchandani, Hirshleifer and Welch (1992) both addressed information aggregation in market contexts. An early reference is the paper by Grossman and Stiglitz (1976) that showed that uninformed traders in a market context can become informed through the price in such a way that private information is aggregated correctly and efficiently.
22. In relation to investor behaviour, we note the behavioural work of philosophers Søren Kierkegaard and Friedrich Nietzsche who were among the first to criticise what they referred to as "the crowd" (Kierkegaard) and "herd morality" and the "herd instinct" (Nietzsche) in human society.
23. The technical analysis school of investing have long recognised the phenomenon of herding behaviour amongst investors and its impact market sentiment. The academic study of behavioural finance has identified herding in the collective irrationality of investors, particularly the work of Nobel laureates Vernon L. Smith, Amos Tversky, Daniel Kahneman, and Robert Shiller. The 2016 Law Commission report on pension funds investing cited ““Herding” is a fear of first-mover disadvantage” as a key barrier preventing greater innovation in investment.
24. Greater availability of investment products that make a difference to the things that people care about would enable more sustainable investments. According to the recent “Investing in a Better World” survey, 55% of people say that greater availability of sustainable products would make them more likely to make a sustainable investment. Of all the factors that would make people more likely to make a sustainable investment, this was the most frequently stated factor among the 56% of people who say they are interested in making a sustainable investment.
  [note] The ‘Sustainable Finance Study Group’ (SFSG) defines ‘sustainable assets’, as “sustainable loans, sustainable debt and sustainable bonds as specific financial products or debt linked to assets or investments that target environmental and social sustainability; however, the more general consideration of financial sustainability is also contemplated” (G20, 2018).
25. Finally, given the innovative nature of the programme, evidence specific to the role that listed products can play in bridging the financing gap, and evidence in relation to the approach DFID proposes to take, remains scarce. As a DFID programme MOBILIST proposes to learn by doing and is both experimental and adaptive enough to learn from what is likely to be a series of intensive market consultations across a range of product concepts. Capturing these learnings as MOBILIST proceeds will be critical, both to help the programme evolve, but also to help other programmes in the mobilisation and PSD portfolio learn too. The technical assistance component, together with the monitoring and evaluation for each specific investment product and TA intervention, will be the method through which we intend to capture this learning. The learning component of MOBILIST’s work is further addressed in the Management Case.
How we engage with other HMG Departments and accessing cross-HMG funds:
MOBILIST will work with other government departments where there is opportunity, recognising that efforts to increase investment, including in overseas markets is a common concern across a range of HMG teams. The level of that collaboration will be dependent on the products and technical assistance and the stakeholder context. For example, our work is related to HMT’s interests in emerging markets and the UK’s financial sector offer; DCMS’s lead on impact investing could have insights for the key regulatory agencies. DFID will work with these and other key stakeholders, including making appropriate links to the Prosperity Fund.
How MOBILIST relates to other UK aid programmes within the specific sector, including multilateral, bilateral and centrally managed programmes:
1. MOBILIST will position DFID to drive this agenda and to take this conversation to a new level. The work of MOBILIST provides a key building block by firstly creating an investable landscape of products with a particular focus on sectors with demonstrable development impact.
2. Concurrently, DFID also has a role to play in developing a pipeline of underlying assets. In particular, there is a need for market standardisation of particular products to enable securitisation and collateralisation to occur, establishing new liquid assets at scale. DFID already plays an important role in supporting a variety of work on ESG, green or impact measurement methodologies, including for example support to create a unified reporting framework. These efforts are helping evolve the approach from development practitioners and the financial sector. MOBILIST will help broaden these considerations into mainstream portfolio asset allocations through its focus on public listed market instruments. This will allow global institutional and retail investors to better understand the outcomes of investing in a product with both commercial and development outcomes.
3. MOBILIST compliments DFID’s capital market reform work in Africa through the Financial Sector Deepening programme (FSD Africa) which focuses specifically on governance issues and investment regulatory reform. There is also complementarity with aspects of DFID’s SME/ microfinance financing approaches, and investment into local businesses through CDC and PIDG facilities including GuarantCo. DFID funding through the multilateral financing institutions incorporates significant funding to address pipeline issues, and this work is critical for broader take up of listed products which are reliant on the ability to source high quality assets.
  [note] Public debt creating instruments will remain an important source of concessional finance for developing countries, ensuring that governments have access to affordable financing (both lower interest rates and longer loan maturities). There are risks that overly limiting the use of these instruments (which this programme does not seek to do) may force countries to seek more unsustainable finance [at higher interest rates and shorter maturities] https://eur-lex.europa.eu/legal-content/EN/TXT/?uri=CELEX%3A32011L0061n
Ensuring sufficient flexibility to learn and adjust to changes in the context: the flexibility to shift this and future commitments:
MOBILIST’s objective is to catalyse a portfolio of investment products over a six-year period, with each successful launch providing the springboard and lesson-learning exercise for the next. Exactly how much capital we chose to deploy into investment vehicles over the course of the programmes’ life will depend upon decisions taken by the MOBILIST Investment Committee and based upon milestones and success in the early stages of programming.
Key risks to the success of MOBILIST:
- Failure to identify a suitable Fund Managers, with the right team or consortium in support;
  [note] We would also expect that the Fund Manager will invest some of their own capital in the fund. This will provide strong alignment and incentive for performance management, and the absence of that alignment presents a risk.
- Failure to negotiate and agree investment terms with a preferred bidder undermines sentiment and/ or reputational risk to DFID;
- Failure to attract private capital into the investment products at, or before, the point of listing, delaying or ending plans for IPO;
  [note] IPO and subsequent rounds of fund raising are critical tests for any product: we would expect blue-chip institutional investors will come on board in the first (i.e. at IPO) and subsequent rounds of fundraising, but investor appetite is uncertain until tested.
- Failure of the investment model to deploy or recycle capital because of absence of origination/ pipeline, poor sourcing strategy;
  [note] DFID research points to strong interrelationships between the unlisted markets and the various listing vehicles discussed in the business case. There is a ready pool of unlisted assets, in PE funds, with banks, and on DFI balance sheets in frontier markets.
- Investments underperform their benchmark over a sustained period, creating negative sentiment about the product or wider market opportunity;
- Risk of sudden reversals in portfolio flows as market sentiment shifts rapidly and investors withdraw from emerging and frontier market products as volatility and uncertainty is elevated;
- Currency risk affecting sterling value of DFID and investor capital;
- Exogenous risks damage investor sentiment for target geographies reducing institutional appetite and demand for the product;
- Environment, social and governance risks are improperly quantified and development impact underperforms selected benchmarks;
- Corruption at the investment project or firm level (i.e. at the level of the underlying asset) with resulting reputational risk;
- Change in UK political commitment to provide investment capital to products managed by City firms;
- Failure to understand nature of the investment leads to poor headlines and/ or retail sentiment (e.g. fund trades at a significant discount i.e. below Net Asset Value)
- Other donors help launch or support similar products attracting more institutional capital and/ or outperforming MOBILIST products.
The proposed level of risk to be taken fits with DFID’s risk appetite for this portfolio (see risk register for more detail):
1. The overall Risk rating is ‘Major’ post mitigation. It is envisaged as a high risk, high return programme, and falls within DFID’s risk appetite for such an approach. MOBILIST is pioneering in developing a new range of investment products. This approach has no precedent within DFID or within the development community. Some headline risks are captured above, and key risks are detailed and addressed in the Management Case. Given that our interventions seek to catalyse market-led solutions, the role of UK branding should be considered carefully.
2. Despite the risks associated with portfolio flows (as witnessed in the global and Asian financial crisis), we believe the risks are within appetite and the programme encourages counter-cyclical behaviour, seeking where possible to link portfolio flows with longer term assets and to build products that offer good return potential over time. By definition, speculative capital flows are considered by the programme to be ‘low quality’ investment capital: MOBILIST seeks to attract high quality capital only.
3. Specific to MOBILIST, DFID has three intervention tools available to deploy: i) to run a competitive process with DFID as potential investor; ii) as a provider of technical assistance; and/ or iii) as a “convenor.” All interventions will involve advertising widely to market participants.
4. As product concepts are developed, through structuring, investor engagement, pre-listing (pre-IPO) and launch (IPO) there is no intention to brand with the ‘UK aid’ logo. Moreover, because the programme is intended to attract and mobilise private sector institutional investment, the logo would not be consistent with the nature of the planned interventions. However, in communications by the Fund Manager, the UK’s participation as an anchor investor (in that case) will be recognised and highlighting the role the UK would be playing in the development and strengthening the role that public listed markets can perform in intermediating high-quality capital between OECD investors and emerging and frontier markets is desirable. What branding cannot do is serve to endorse an investment product or validate specific investment advice.
5. Moreover, we will work with DFID communications to showcase the UK’s support, link this effort with the wider effort to support a growing a culture of impact investing in the UK, as reported by the Advisory Group appointed by HM Government: Growing a Culture of Social Impact Investing in the UK, and to highlight DFID’s work towards meeting the SDGs.
  [note] Growing a Culture of Social Impact Investing in the UK, 14 November 2017, https://www.gov.uk/government/publications/growing-a-culture-of-social-impact-investing-in-the-uk
Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver MOBILIST?
- Yes, as the proposed investment by DFID exceeds £40m, the business case has been submitted to DFID’s Quality Assurance Unit (QAU) for review and has received approval. The business case has been revised on the basis of QAU’s recommendations.
- MOBILIST is based on the experience and learnings from DFID’s commissioning of earlier listed product mobilisation research phases.
- Competitive processes envisage onboarding of market experts, and the programme will work with a range of sector, asset class and geographical expert partners, such as CDC’s trade finance team.
Do the SRO and team have the capability and resources to deliver MOBILIST?
- Yes, based on its experience with a range of development finance instruments and collaborations and additions to the team since its establishment with private sector, financial and investment experience. The team is also drawing on external expertise where necessary through the design, procurement and evaluation stages to ensure that the technical qualities of any investment meet DFID strict criteria.
- The team will be drawn from within PSD. The skills and capabilities required to deliver the project from a DFID perspective are available. PSD has significantly increased the number of private sector advisers who have investment and financial experience. This issue is covered further in the Management Case.

## Appraisal Case

Introduction
MOBILIST’s overarching strategic objective is to help catalyse new vehicles for financial intermediation (through a public market approach) that begin to accelerate investment flows needed to bridge the financing gap. MOBILIST interventions seek to work with fund and asset managers to bring forward their ideas and expertise to launch (potentially incubate as private market investment products) and eventually list (IPO) these products on a London exchange and/ or locally or dual listing, demonstrating the ability to attract institutional investment capital in the process.
Fig 9: Overarching Theory of Change:
[note] Given that MOBILIST seeks to catalyse a range of different listed products, there would naturally be variations in how change is given effect for each different product concept. The business case does not set out to describe each of these, partly because until the programme is empowered to examine each in detail these theories are unavailable, and where theories of change have been developed for the three road map products, as a matter of brevity for the business case. However, the business case does seek to provide an overarching theory of change for the concept of listed products itself and provides an illustrative product theory of change (for the infrastructure product) – see Annex D.

MOBILIST will adhere to the three guiding principles of DFID’s use of programme funds:
a.	Additionality – the programme will only support products that clearly target the geographies, sectors and assets that are critical to the financing gap and meeting the SDGs, and where the private sector, through the medium of public listed instruments has, little or no access to investible assets i.e. where there is an identifiable market failure/ barrier that DFID support can help overcome. This issue is addressed in more detail later in the Appraisal Case.
b.	Minimum Subsidy – for each investment supported through the listed products programme, the issue of concessionality requires careful evaluation. MOBILIST has a preference not to deploy capital in a concessional form, but rather to offer investment capital where the need is demonstrated, on commercial terms. This is better value for money for the DFID’s limited resources. The principle that product development is led by the market is the key assurance that MOBILIST has no appetite to facilitate transfer of investment risk from private to public sector without careful assessment of the VfM metrics. Nevertheless, we recognise that concessionality can be an important tool, deployed tactically, that can even be used to demonstrate a commercially viable opportunity. We do not exclude the possibility of deploying concessional capital to help bring a product to IPO, but we will only do so if the systemic case for change can be made. This issue is addressed in more detail later in the Appraisal Case.
c.	Development Impact – any investment through the programme would be carefully tracked through a tailored impact measurement process, which builds on IFC Fund Standards for ESG. We will work with organisations like the Impact Management Project, Harvard Business School to deliver this. This issue is addressed in more detail later in the Appraisal Case.

Additionality - the case for additionality is based upon MOBILIST’s unique focus on public markets (rather than increasing existing work in private markets)
Public markets have a pivotal importance in the development of successful economies. It is the mainstream (and usually liquid) public markets where trillions of dollars flow, intermediating between investors and investees across sectors that are helping to drive broad based and efficient economic growth.
[note] “As a first step, we decided on something that works for biggest sets of clients: liquid assets” - Damian Payiatakis (Director), Barclays Wealth and Investment Management.
Table 2: Public markets have the following attributes:
Transparent market pricing:	Transparent market prices are critically important to mainstream investors and provide the basis for cost-effective investment decision-making. Transparency can also reduce the risk premium, the cost of due diligence for investors and cost of capital for underlying enterprises. Public markets provide a trail of detailed publicly available time series on market pricing by individual security.
International best practice governance standards:	Public markets set rule-driven standards for business conduct and governance, which firms are motivated to comply with in order to access capital. While enforcement of standards may be relatively weak on some local stock markets, those firms wishing to attract investment from international investors will generally recognise a higher bar. Strong public markets also tend to set a “gold standard” in local private markets creating a wider influence on standards.
Exit opportunities and lower cost of capital with no illiquidity premium:	Public markets create an important ‘destination market’ for private market and earlier stage investments; growth in listed equity markets will improve the exit opportunities for the very significant private equity market, including exit opportunities for DFIs. This will help complete the funding continuum for businesses, and open up new sources of low-cost capital, while having a positive knock on effect on the attractiveness of earlier stage investment products.
Multiplier effect of publicly listed companies:	Listed companies have distinctive qualities that make them important economic development assets. A listed company is generally seen to be more prestigious, stable and financially viable than a private company, having passed the scrutiny of regulators in its listing attempt. Listed companies also increase economic resilience, attract and retain talent and have large multiplier effects, through their supply chains, that boost local job creation and SME development.

1. Like Europe during (and ever since) the industrial revolution and more recently in East and South East Asia, public capital markets investment must play a catalytic role in the development of Africa, the Middle East, South and South East Asia and other developing parts of the world, both in providing critical capital flows for financing the ambitions set out in the SDGs, and in creating positive forces for transparency, the diversification of risks (and rewards) and plurality of ownership as that development takes place.
2. Transparent market prices are critically important to mainstream investors, facilitating price discovery and overcoming information asymmetry, and consequently provide the forum for the bulk of institutional investment decision-making. Over time, freely available price signals that are a feature of public markets, help to reduce the risk premium and cost of capital for underlying enterprises. Greater transparency and listings lead to higher quality capital and accountability, cheaper financing and increased flows and speed of financing.
  [note] “Retail, including wealth managers, need regulated products, while institutional investors such as pension funds can do (invest) unregulated products…To move capital at scale, look at what structures are they (large investors) using. Wealth managers prefer regulated products such as investment trusts, mutual funds, UCITs. You can put VC and PE into Investment Trusts.” - Jamie Broderick Former CEO UBS Wealth Management – Now Advisor UK Taskforce on Impact Investing
Fig 10: Transparency helps mobilise more capital:

1. Public markets set rule-driven standards for business conduct and governance as critical elements of the due diligence process, making listed products both attractive and prudent for institutional investors as custodians of client monies. Over time, as these vehicles benefit from elevated standards of governance and an established track record, they attract more capital and will increase in scale, making these markets deeper and more liquid.
2. The business case is timely for reasons other than responding to the limitations and opportunities of the private mobilisation model. There are changes affecting institutional investors that can be seen to bring public policy objectives and private commercial objectives together. For example, international financial markets are facing two major negatives in the traditional investment approach: i) low and falling yields (returns) on their investment portfolio; ii) the increasing correlation of asset performance across the investible universe (increasing portfolio risk). Both these factors are driving increasing investor interest in emerging and frontier economies (notwithstanding current cyclical trends which are broadly negative towards emerging markets). New and emerging asset classes such as clean energy or climate-smart infrastructure have the potential to offer higher yields, reflecting the market’s perception of their greater risk but also the diversification benefits they bring at the portfolio level (reducing portfolio risk).
  [note] According to data from the S&P 500, current dividend yields stand at only 1.88%, as of 16th October 2018. In the UK the income generated by bonds has fallen steadily over the last 30 years, with yields of 1.5% for a 10-year gilt (Vanguard, 2018, Investing for income: The risks of chasing yield). Data from PIMCO showed, that at the end of September 2016, a staggering US$12 Tn in global investment grade bonds were trading with negative yields (Pimco, 2016, Negative Interest Rates).
3. Moreover, there is a strong interrelationship between the unlisted markets and the kind of product structures referenced throughout the business case. There is a ready pool of unlisted assets, in PE funds, with banks, and on DFI balance sheets in Emerging and Frontier markets. The possibility that these assets could be pooled and packaged to construct a ready-made diversified, critically sized investible structure, allowing institutional investors to gain exposure to asset classes and geographies that would previously have been inaccessible is one example of how MOBILIST presents a mechanism to intermediate hitherto untapped assets and new investors between private and public markets.
4. The City of London, with its ambition to be the development finance hub for the world, has a unique opportunity to develop the products needed, in the markets that offer those investors the risk-adjusted yield and the diversification that investing in developed markets increasingly cannot offer. London offers the kind of high-quality capital (in terms of governance, transparency, price etc.) that helps raise standards and can remain invested (i.e. non-speculative) within the assets in country providing vital finance to businesses.
Why DFID should be involved:
1. While many of the proposed listed investment products have already attracted credible interest in the City of London, few real examples exist and those that do have broad based coverage with relatively small exposure to LICs and LMICs. Institutions have many competing priorities, and internal sponsors can have difficulty cutting through to their leadership with new ideas about what are still today regarded (to varying degrees) as ‘exotic’ and perceived as poor investment opportunities.
2. Early movers in new markets have been put off by the financial and reputational risks of promoting funds that comprise high levels of innovation, and there are examples of products failing to attract a critical mass of support for a launch. Finding new ways to unlock this capital is a priority agenda for the international community, as it is for DFID, and HMG. Leadership from the UK government on this issue in partnership with UK and global financial stakeholders, including the City, can secure the attention of large-scale institutional capital. By doing so, this collaboration can help overcome the barriers that have so far prevented these listed products from being developed.
3. Any support that DFID provides comes with strict criteria to be reviewed and approved through the MOBILIST Investment Committee:
- MOBILIST will only provide support because demonstrably the private sector will not;
- By providing support we are sure that a barrier to a long-term sustainable market can be tackled (i.e. without the need for further support)
- MOBILIST seeks to invest on the same terms as other investors i.e. on commercial terms. However, we recognise the role of concessionality to overcome specific product and/ or market barriers, and therefore limited and minimum subsidy (to build rather than distort markets and ensure value for money) is available;
- Development impact (making sure the line of sight to economic transformation through a closing of the SDG financing gap (and poverty reduction) is clear;
- Other elements of additionality include the counter-cyclicality of portfolios - i.e. investment in long-term assets that are attractive to long-term investors, as opposed to speculative foreign portfolio flows, and thereby seeking to minimise market distortions and pro-cyclicality.
1. Whilst the programme prioritises pools of UK institutional capital, and not local capital pools, the market building opportunity goes beyond the MOBILIST’s focus on UK-based pools of institutional capital. A public market focus is also relevant for pension fund assets in the African and Asian regions. It follows therefore that meeting the SDGs will require a step change in the scale of capital investment, both international and local in nature, and whilst focusing on how we can work with the City of London specifically, that step change, across international markets, is the bold ambition for the programme.
  [note] Estimated to be c. USD 70bn equivalent and growing at around 15% per annum
2. Given the scale of capital needed, the scale of fund flows that the DFI system can support (combined with the private capital allocations this model attracts) are insufficient to meet the development needs of Africa, the Middle East, South and South Asia., Through the modality of listed products, MOBILIST does not seek to measure success specifically in terms of the amount of private capital DFID’s own investment leverages. Neither does the business case argue that investors will immediately crowd into the emerging and frontier market space as soon as these listed vehicles are made available. Instead, we argue that private capital at scale will not flow into these countries unless a critical mass of these or similar instruments are available, and the systemic market-building effect of beginning to build a portfolio of listed products will require replication and momentum within the wider market to truly build the financial architecture or ‘plumbing’ that defines a functioning market for finance.
  [note] “the best estimates of private finance mobilised by MDBs, DFIs and donors in LICs appear to be in the range of $725 million to $1.6 billion annually” World Bank, 2018a
  [note] “The upper end of the range rises to $5.3 billion if we take the total direct and indirect mobilisation most recently reported by MDBs” https://www.odi.org/sites/odi.org.uk/files/resource-documents/12666.pdf
  [note] “Each $1 of MDB and DFI invested mobilises on average $0.75 of private finance for developing countries, but this falls to $0.37 for LICs” ODI Report https://www.odi.org/sites/odi.org.uk/files/resource-documents/12666.pdf i.e.

Minimum subsidy - the case for “minimum subsidy” is based upon MOBILIST’s approach to using programme funding to help the market create new listed investment products that are replicable and scalable
1. An important component of MOBILIST is the recognition that over the medium term, efficient financial intermediation between institutional capital and emerging and frontier market assets cannot be a subsidy-based model, because of the shortage of public capital and the reputation risks of using (UK) taxpayers to subsidise private capital at the scale needed. Simplicity, clarity and substantially lower transaction costs (including due diligence) will provide a compelling offer to investors. Efforts to ‘create’ markets with a long-term reliance on subsidy are unlikely to prove scalable or indeed sustainable, and the use of subsidy itself arguably harms efficient financial intermediation because of the effect it has on price signals, performance track record and the ability of markets to properly price risk and return. For these reasons a programme that sought to mobilise capital on the basis of subsidy alone would be difficult to justify in policy or value for money terms. Moreover, we assess that DFID’s political support is more important than concessional capital and it is with that context in mind that MOBILIST will consider which products and product partners to support.
2. Nevertheless, the programme does allow for the consideration of subsidy (including ‘concessional’ capital) where the alternatives are undesirable, and its deployment can be demonstrated to further MOBILIST’s core objectives. For example, MOBILIST recognises that the tactical, short-term use of concessional capital during the pre-listing phase could be deployed to secure co-investors during the pre-listing phase (given DFID’s lack of appetite to fully fund the pre-IPO phase of the product’s life), thereby diffusing control and ownership of the vehicle during pre-listing.
  [note] As an alternative, using a waterfall structure, DFID could take a first loss position coupled with a share class attracting a higher return on its investment. Through not strictly ’concessional,’ neither is it pari-passu
3. As well as concessional capital, ‘subsidy’ can take a range of forms, including in relation to grants and technical assistance. Until we test the market, initially through the proposed competitive process, it would be unwise to rule out the tactical deployment of grants or TA if a sufficiently compelling case could be made that a specific cost is outwith the normal cost structure of a new fund set-up and is a key impediment to set-up and/ or listing. For example, with a focus on LIC and LMIC countries assets, there is likely no single or composite benchmark that a fund manager can adopt to construct a portfolio strategy, and which would later form the basis of the prospectus’s investment strategy to be marketed to institutional investors. In this scenario, support by MOBILIST to help create a benchmark or composite would have a clear systemic market building benefit and create a public good that would support both the products launch and enable replicability.
4. To ensure we have the right investment skills to make this judgement, DFID will work with CDC and investment experts deployed to support MIC decision-making during the competitive process to define if and how any concessional support develops and exits over the lifetime of the investments. The MIC governance structure ensures that issues of concessionality are considered and endorsed by the MIC as the investment decision-making body. Furthermore, we can confirm that concessionality is not an explicit offer by DFID to the market, and no reference is made to its possibility in any competition documentation now, or in the future.
5. In cases where subsidy is deemed necessary e.g. through lower than commercial returns, the products will seek to ensure only the minimum required is deployed, for a limited period of time, to mitigate the risk of market distortion, or in the case of grants and technical assistance intended to create public goods that further market building objectives, that these interventions are monitored and evaluated as part of the important learning function that the programme seeks to implement.
What MOBILIST will do:
MOBILIST will ‘catalyse’ up to 5 investment vehicles with the intention to take those vehicles to IPO – listing – on the London or local market exchanges. These vehicles will possess distinct qualities:
- A listing, through an Initial Public Offering, will be central to the investment product’s purpose;
- Will appeal to and have market demand from the mainstream portfolio asset allocation of institutional investors;
- Will be replicable, and in that replicability, have the potential for attracting capital at a scale that is relevant to bridging the financing gap;
- Will be commercially viable, and whose sustainability will be independent of any initial support DFID might provide to bring the vehicle to market;
- Will allow UK institutional investors to gain exposure to countries and regions where development priorities are greatest, including Africa, the Middle East and Asia and other ODA eligible countries, where strong additionality can be demonstrated.
- Will provide investors will a clear line of sight to how their investment is helping bridge the financing gap for SDG investment and spending priorities in emerging and frontier economies.
  [note] As a condition of DFID support, the products supported through MOBILIST will have rigorous controls in place to ensure adherence to the highest ESG standards (such as IFC’s performance standards). This is a critical aspect of the programme’s ambition: DFID will work with leaders across the impact measurement field (including Harvard Business School and the Impact Management Project) to propose and integrate effective development impact measurement across the products. This is a challenge due in part to the complexity of attributing impact in publicly owned investment structures.
1. Product concepts favoured in the near term are those which would take the least amount of time to develop (potentially within a year) and may be able to respond to investor’s demand for liquidity and yield. As we progress in time, more complex products may be able to come to market based on improved quality and availability of local assets and increased investor knowledge of frontier markets. Standardisation of products through agreement on the characteristics of particular assets resulting in consistent quality and comparability will also enable the aggregation of currently illiquid assets into new tradeable products.
2. Until we test the market through a procurement process, we cannot be sure that we will find a suitable consortium, with a suitable product, ready for DFID to support, because all of these elements involve costs that at the outset, we are asking the market to bear. MOBILIST is prepared, in case the ‘market’ proves unwilling to cover all of the design and set up costs to provide some limited grant funding, supporting the incentive of DFID capital to anchor, part fund, or risk mitigate the product before and possibly after listing. However, grant funding in addition to the possibility of development capital as an investment is sub-optimal as a way forward. DFID is prepared to cancel the competition or decline to nominate a ‘winning bid’ if we cannot be assured that the institutions involved are making a tangible contribution to systemic change and genuinely believe in the commercial opportunity they are proposing to create. This will be a required aspect of the flexibility required when approaching the market with a number of uncertainties. This could have an impact on expected spend forecasts.
  [note] We recognise that the proposed ‘market led’ approach may cost more, for example where a fund manager with large working capital reserves proposes to fund product development and ‘reclaim’ this funding through management fees. Our capacity to negotiate must reflect the complexity of negotiating a financial transaction that may never have been done before. A function of this work is that there will be no past examples to strictly compare with. As a result will have limited mechanisms to assess whether costs/ concessionality/ fees are commensurate with risk being taken.
3. Maintaining competitive tension during the process reduces that risk, but this will be offset by the costs related to securing the expert technical advice (under the competition management team) to help us best quantify our contribution in relation to the structures proposed risk profile.
4. Moreover, the technical assistance component of the business case is explicit about the need for DFID to provide some level of funding to support product development, where the market already appears unwilling to bear these development costs. This is the reality of seeking to innovate where the market considers there to be substantial barriers that it deems cost-ineffective to overcome.
  [note] It is difficult to make a reasonable assumption about whether we could expect entities to fund this, but the Phase II research did directly address this and determined that there were well-resourced market participants who see these products as a commercial opportunity and DFID’s investment contribution or risk mitigation as the primary driver of their future participation. Similar to the challenge of benchmarking and controlling costs through the RFP process, ensuring a high degree of competitive tension will be important with the TA component.
5. Over the longer term, six years and over, we could see a variety of high scale, high impact products that reach further into frontier market’s SME funding needs as intermediation improves, and which are likely to have the highest developmental impact. Each product will have an explicit theory of change and where subsidy is considered will be subject to DFID’s use of concessionality principles to ensure it is minimised and time bound.
6. Careful consideration has been given to the balance in any DFID support between convening, technical support, and capital participation in investment products with the ability to list. We recognise that investments on DFID’s balance sheet will need to be monitored particularly closely. By proposing different modalities of intervention (invest/ risk mitigate/ TA and convene) the design of MOBILIST allows for flexibility in the scale of investment activities over time based both on the lessons from early experience, wider investment market developments and on the evolution of the public discourse on DFID’s participation in this area.
7. The product development process will need to be market-led. However, DFID will have the opportunity to influence the developmental context and potential for impact of any investment vehicle it chooses to support beyond ‘business as usual’ through the use of investment terms and conditions e.g. country or sector focus and ESG/ impact measurement and management requirements.
Approach to learning
1. The evidence base for MOBILIST is set out in the Strategic Case, and given the innovative nature of the programme, the business case is clear that there is a real opportunity through learning for MOBILIST to make a significant contribution to examining the programme hypothesis (articulated in the strategic case) and for each product concept supported, their individual product theory of change.
  [note] The first detailed product theories of change are captured in the annexed route to market plans.
2. Demonstration effect is key and in determining which products to support. We must have confidence that the investment structure is easily replicable – with future iterations able to stand without or with reduced need for concessional support. Other critical factors in this market building approach include the importance of building experience/ track record, establishing price signals and benchmarks for investors to quantify risk and return in developing markets. These and other metrics are intended on building market confidence and upon which the market can then build. Institutional investors are by and large, highly conservative, and are wary of “first mover disadvantage.’ We think there is opportunity for DFID to be that first mover or to support investors who are considering new products.
3. The TA Facility has, across a range of functions, this learning capability as a core objective. The ability to test product ideas and adjust the Theory of Change as new evidence is generated across an expanding range of activities is codified in the Monitoring & Evaluation framework.
  [note] The emphasis will be on gathering evidence on causal links in the theory of change with limited or no evidence.
4. With a commitment to tender for the Technical Assistance Facility manager in Q2 2020, this will also include an outline of the learning function that the Facility, as a component of the wider programme, should encompass.

Development Impact
The programme will contribute to two main impacts:
1. Higher rates of economic growth leading to poverty reduction
2. Financial efficiency (e.g. via growth of financial assets or reduction of financial intermediation costs): the key criterion for measuring financial efficiency is its contribution to growth and development; in that context, measures to deepen markets through more investment options for investors play an important role. A second criterion for financial efficiency that MOBILIST will adopt is the ability to intermediate investors values and desire for social impact through investment choices: i.e. the availability of product options which meet an investors financial and social needs
1. At one level, additionality and development impact will be assured through focus on the under invested economies and the intermediation of capital at a macro-level, helping to bridge the SDG financing gap. The intention is to lay the foundations for the medium to long-term development of open and transparent capital markets at scale that intermediate between large pools of institutional capital in international financial centres like London, and emerging and frontier market assets. This is a ‘systemic’ impact. The challenge will be to develop effective measurement frameworks, and for this we propose to both collaborate with and build upon the work CDC in undertaking to quantify and measure changes in investor sentiment in CDC-focus countries.
2. At a product level, MOBILIST will need to consider both how specific products supported contribute both to systemic market building (at the macro-level) but also on their own merits as vehicles intermediating small amounts of capital into specific geographies and sectors (including the specific investment assets themselves).
  [note] CDC’s own work to understand how to more effectively articulate and assess the market building elements of their own investments is proving to be extremely valuable in helping MOBILIST develop its own Monitoring & Evaluation framework, for example, with plans under way to integrate institutional investors into CDC’s work on a long-term survey of investor sentiment in CDC’s target markets.
3. The specific impact and outcomes that each listed product seeks to deliver will be specific to that particular product and are not possible to assess at this stage in the programme. However, to take an infrastructure fund as an example: at the systemic level, we seek to i) replicate the evolution of the infrastructure financing model in the European market (the UK played a leading role in pioneering this finance modality) for listed infrastructure funds and; ii) assess the contribution that priced emerging market infrastructure assets (that have possess a performance track record) have made in attracting volumes of institutional capital. At the product level, we would seek to i) measure the impact of specific assets through for example, their contribution to sustainable low carbon paths for growth in a particular country economy and; ii) the investment contribution in terms of yield and diversification benefits to the institutional investor etc.
  [note] Monitoring & Evaluation approaches are described in more detail in the Management Case.
  [note] that today provide the bulk of non-sovereign infrastructure re-financing in developed markets
Outcomes:
The purpose of these interventions is to boost investment and promote economic development and poverty reduction. MOBILIST will deliver the following outcomes:
- Increased high-quality foreign portfolio inflows in priority sectors for financing SDG related investment and spending priorities
  [note] The ‘leverage’ ratio (i.e. how much private sector funding is crowded-in as a result of DFID’s investment or risk mitigation) is a metric more appropriate to private market interventions, where the ambition of our own involvement is to seek at best, matching funding from the private sector (where we seek to catalyse products through a DFID investment and/ or through risk mitigation). We cannot finance the gap through the existing leverage model. The programme objective is not ultimately to attract an equivalent amount of GBP90 million to ‘match’ the size of DFID’s contribution. Welcome as is any private investment contribution, if a matched contribution was the only result, MOBILIST would be a failure.
- An improving enabling environment for sustainable low carbon economic growth, capital market reform, and income generation
- A raised level of financial intermediation positively impacting long-run rates of economic growth, capital accumulation, and productivity improvement
- Systemic market change in the volume of type of opportunities available to OECD investors in Africa, the Middle East, South and South East Asia.
Critical is the ability to reconcile a focus on Impact and/ or ESG principles with investments in Emerging and Frontier Markets that are (almost by definition) less well governed, more corrupt and increasingly polluted than OECD markets.
Outcome risks:
1. We are cognisant of the risks around the short-term nature of foreign portfolio flows, particularly in relation to the speculative nature of some flows and increased volatility in the event of global financial stresses. For this reason, we consider our requirements for ‘additionality’ to include an element of counter-cyclicality, and by ensuring that the need to link long-term assets to portfolio flows in incorporated into product design, we can demonstrate that our work on financial intermediation is building systemic resilience.
2. Through the process of investment and the re-financing of existing assets, capital is not recycled as per Theory of Change: i.e. capital not recycled in same sectors e.g. renewables etc or, in the case of private equity with a limited fund life, capital is returned to investors.
3. Lack of replication: other investors and Fund Managers do not replicate the structure. An obvious contributing risk factor in this case is likely to be investment performance against the benchmark, although underperformance (largely in efforts to generate Alpha) is itself is a constant risk that every investor faces and is not in itself problematic. More problematic would be a successful product that through its public listing transmits price signals to the market that are not in line with our theory of change.
4. To note that the learning component of the programme is expected to play a key role in how MOBILIST mitigates risks, as product complexity increases, and as the theory of change is tested and modified in response to each successive product catalysation.

Secondary Benefits
Developing economies are keen to attract private capital funding from the OECD capital markets without which the scale of the financing gap in the infrastructure may not be addressed. High-performing listed products would be expected to raise global and UK based investor confidence leading to deeper and broader engagement with the large and fast-growing economies, especially across infrastructure sectors. In summary the secondary benefits may involve:
- Increased access to finance for asset owners in emerging and frontier markets, enabling them to expand and grow, or improve their capital management. This ‘category’ of international finance will also improve governance and ESG standards as compliance will be required to participate in the investment product.
- Gaining access and credibility with key decision makers;
- Strengthening the position of collaborating international financial centres as partners of choice for raising finance for SDG financing;
- Commercial returns to UK and/ or OECD institutional investors through the listed products;
- Encouraging UK investors to enter or expand their portfolio, diversify in emerging economies which holds the potential for steady long-term returns;
- UK companies may win contracts for the construction or consultancy associated with the projects that are financed and win projects through expansion of the infrastructure sectors.
In summary, whilst not all of the above secondary benefits may be realised, DFID, through MOBILIST does have the influence to convene actors from the City of London and other financial centres, the London Stock Exchange and the DFI community and help set a new agenda for action on mobilisation.

Options for alternative approaches:
1. The alternative to the public market intervention is a continued focus of our efforts and the deployment of public resources in private market investment solutions. This focus is important for DFID’s private sector portfolio and will continue, but the ability of private market solutions (measured in terms of leverage ratios and predicated on the deployment of concessional forms of capital) to close the financing gap is constrained by ODA flows, which are both insufficient in scale, and are currently falling rather than rising in volume.
2. The alternative to MOBILIST’s approach to catalysing specific products would be for DFID to instead establish a TA facility with a broader ‘investment climate’ mandate, with a single contracted provider (i.e. not grant funding given the absence of NGO’s/ CSOs/ not-for-profit agencies working in this space). The facility could then address a range of systemic barriers to investment flowing through public markets to frontier countries, but without using a product-led approach for demonstration effect. There is no shortage of barriers, and no shortage of initiatives ready to absorb any given amount of ODA to overcome them. Examples could include work to tackle the domestic regulatory environment in target countries, addressing capital market reform across countries and regions, work to address the lack of information about risk/return of asset managers (e.g. transparency of GEMS data) and ‘soft’ advocacy work to overcome perceptions of risk.
3. Within DFID’s Private Sector Department portfolio and like other development partners, DFID already has programmes seeking to address some of these issues, though without an explicit focus on public markets and institutional investors based in the City and elsewhere. Taking care to avoid duplication, additionality with respect to existing programming would include the following:
- Continue essential market building activities at country and global levels, including investment readiness and pipeline development, improving corporate governance and supporting improvement in the standards of impact measurement and management.
- Examine regulatory barriers that conflict with this overall agenda and prevent investment at scale and seek to eliminate or reduce these barriers wherever possible, including a focus on anti-corruption and building local stock exchanges and supporting IPOs.
- Keep the focus on impact through specifically impact related programming. DFID’s focus on closing the financing gap for the SDGs means that there is a particular role for DFID in ensuring that the demonstration and measurement of impact on SDG investment and spending priorities is maintained.
- Convene, and encourage participation from a range of institutions. Specifically, DFID has influence to convene actors from the City of London and other financial centres, the London Stock Exchange and the DFI community and help set a new agenda for action.
1. These are important issues and DFID is already supporting initiatives in this area – for example through the FSDA programme. MOBILIST recognises the imperative to work in collaboration with partners across these critical agendas: the TA component of the programme can also address some of these important issues but will focus on those developing countries where the investment climate is sufficiently enabled.
  [note] https://www.fsdafrica.org/
2. Whilst an alternative investment climate approach is perfectly valid, it is likely to be difficult, politically complex country focused work and incremental over a long period. It is unlikely to leverage the City’s talents, or to raise the profile and visibility of the policy agenda in the same way that a product launch, partnering blue-chip firms in the City presents.

Implementing partners:
1. A range of capabilities and experience is needed to successfully manage a listed product, and these vary from product to product. These potential partners were identified (and many consulted with) in earlier phases of research to inform business case design:
2. DFID are in consultation with a wide range of institutions that make up a complex financial architecture in the City of London and more widely across UK financial services sector, including leading asset and fund managers, asset owners, including pension funds and insurers; representative bodies, including the Sustainable Development Capital Initiative, Insurance Development Forum, Investment Association and Pensions & Life Savings Association, as well as CDC, PIDG and related development partners, including via Convergence’s network of development partners. We do not rule out any stakeholder collaborating with DFID during the programme’s life.
  [note] https://www.markflorman.com/the-un-launches-the-sustainable-development-capital-initiative/
Fig 11: the financial ecosystem:

Alternative implementing partners for MOBILIST:
CDC:
1. CDC is the UK’s development finance institution. It is 100% owned by the UK government and is the main vehicle through which the UK provides patient capital in the areas where CDC operates. CDC is knowledgeable about markets, fund managers and has the ability to originate direct transactions. To date, CDC has not been active in listed products or managing third-party capital. CDC makes direct private equity and private debt investments and invests in private equity funds alongside other investors (intermediated equity business). CDC does not have an asset management business that is set up to mobilise and manage third party institutional investments.
  [note] For DFIs more broadly, the opportunity to interact with the MOBILIST agenda relates to two key factors: i) can DFIs contribute to enabling product listing by performing the role of capital intermediaries and originators (in addition to their role as providers of capital); ii) can DFIs contribute by providing more open source and transparent data on risk-return and by releasing data on price signals (GEMS data) into the public markets (The GEMS database is one such data set but a collective pooling and compiling of all data sets by the MDBs and DFIs is a public good that would significantly reduce the risk premium demanded for investing in frontier economies).
2. CDC is a key part of DFID’s strategy to mobilise investment. In 2018, private capital mobilised represented US$41 private capital mobilised for every US$100 committed by CDC.
Fig 12: Private capital mobilised by CDC for the years 2014-2018.
[note] Source: CDC Annual Review 2018, available at: https://assets.cdcgroup.com/wp-content/uploads/2019/07/29142246/22218_CDC_Annual-Review_2018_190723.pdf.

For the following reasons, CDC is not an appropriate implementing partner for MOBILIST:
1. CDC has begun increasing its engagement with investors and the City of London generally; however, under its current mandate, this is with a view to crowding in private sector capital alongside CDC’s private direct or indirect deals rather than public listed interventions.
  [note] Although CDC has hired a senior executive reporting to CDC’s chief executive officer to lead CDC’s mobilisation work, this is a recent development and developing CDC’s mobilisation strategy and ramping up its mobilisation work is CDC’s immediate priority, rather than actively fundraising and managing third party capital which it cannot do at present.
2. There are other operational issues which might prove problematic for CDC. For example, CDC’s investment mandate is limited geographically to Africa and South Asia. For purposes of mobilising private investment into public listed investments in emerging and frontier markets, the geographic footprint of the programme will need to be more global in order to achieve a level of diversification that is attractive to investors and to achieve the minimum size needed for the intervention to make economic and financial sense.
3. Major shifts in CDC’s current structure would be needed if CDC were to list products and manage third party funds, including addressing regulatory implications and requirements (such as the Alternative Investment Fund Managers Directive, or AIFMD), recruiting experienced portfolio managers, aligning incentives for asset management staff and developing appropriate governance and reporting structures for its investors.
  [note] Directive 2011/61/EU of the European Parliament and of the Council of 8 June 2011 on Alternative Investment Fund Managers and amending Directives 2003/41/EC and 2009/65/EC and Regulations (EC) No 1060/2009 and (EU) No 1095/2010, available at: https://eur-lex.europa.eu/legal-content/EN/TXT/?uri=CELEX%3A32011L0061
4. Accordingly, using CDC as the platform to mobilise and deploy third party institutional investment by listed products into Emerging and Frontier markets is not a practical option in the short-term. That said, CDC have engaged with the listed products development through their trade finance team, who have been instrumental in helping us map out a route to market for a listed trade finance product, with CDC ‘incubating’ the trade finance portfolio prior to listing.
PIDG:
1. PIDG is a multilateral institution, funded by several donors focused on providing ‘affordable and sustainable infrastructure services in low-income countries and fragile states to combat poverty and help economies grow’ and on ‘building capacity and resilience in frontier markets.’
  [note] DFID is the lead donor in PIDG. It has, together with the UK Department for Business, Energy and Industrial Strategy (BEIS), provided US$1,000.1m of the US$1,377.5m cumulative donor disbursements to PIDG from 2002-2017. In August 2018, DFID approved a further tranche of funding of up to £500m for the four-year period from 2018 to 2021: PIDG website, https://www.pidg.org/about-us/.
  [note] Among the other investors are Australia, Germany (via KfW), Switzerland, Norway, Sweden via its international development cooperation agency (SIDA), The Netherlands via FMO and the International Finance Corporation (IFC, part of the World Bank group): Nederlandse Financierings-Maatschappij voor Ontwikkelingslanden N.V
2. Mobilisation is a key part of the mission of PIDG. ‘For every US$1 of PIDG member funding, projects PIDG has supported have mobilised $23, of which $17 comes from private sector financing.’
  [note] Ibid. See Investment Mobilised, https://www.pidg.org/ar2017/measure/investment-mobilised/
For the following reasons, PIDG is not an appropriate implementing partner for MOBILIST:
1. PIDG’s geographic focus is sub-Saharan Africa and South and South-East Asia. For purposes of mobilising private investment into public listed investments in emerging and frontier markets, the geographic footprint of the programme will need to be more global in order to achieve a level of diversification that is attractive to investors and to achieve the minimum size needed for the intervention to make economic and financial sense.
2. PIDG mandate is to focus exclusively in financing infrastructure in private markets. The proposed Infrastructure Fund would be a publicly listed fund.
3. The focus of the various PIDG companies is on providing debt financing or debt guarantees for infrastructure, rather than on equity investments.
  [note] InfraCo Africa and InfraCo Asia, can hold equity stakes during construction and operation of projects; however, their focus is on providing risk capital and expertise in the early development stage of infrastructure projects. PIDG Annual Review 2018, p. 19.
4. PIDG has formulated its new governance structure and strategy over the last two years (‘One PIDG’), and donors would likely resist exceptions to this agreed strategy to accommodate listed products as proposed by MOBILIST.
FSD Africa:
DFID also supports FSD Africa. Although FSD Africa do provide finance in the form of grants, loans and equity and their focus is on frontier markets, their mandate is financial sector and financial markets development and they operate only in Africa. Their work does not focus on the scale of mobilisation needed to impact the SDG financing gap. This platform is therefore not well-suited for the purpose sought by working with institutional capital designated for public listed market instruments.
Regional Development Banks:
Working with one or more of the regional development banks (RDBs) would be appealing, but in the absence of suitable investor mobilisation vehicles and a meaningful mobilisation track record in public markets, this is an avenue of partnerships that needs to be developed over the longer term.

Summary Value for Money Statement
1. As outlined above, the value for money of the programme broadly hinges on three key aspects of its design and theory of change – namely (a) the focus on mobilising investment capital specifically through public markets; (b) the way it does this by supporting the creation of a set of new listed investment products that are replicable and scalable and; (c) how the new listed products that will be developed are selected and their respective theories of change, leading ultimately to more sustainable investment in developing countries.
2. It is also important to recognise that for the majority of programme funding, DFID is an investor, expecting a commercial return and capital preservation of its investments.

Compliance with Gender Equality Act
1. International Development (Gender Equality) Act 2014 amending the International Development Act 2002, requires that regard be given ‘to the desirability of providing development assistance that is likely to contribute to reducing poverty in a way which is likely to contribute to reducing inequity between persons of different gender.’
2. We have considered the three aims of the Public Sector Equality Duty (PSED) set out in Section 149 of the Equality Act 2010, namely, to eliminate unlawful discrimination, advance equality of opportunity and foster good relations when making policy decisions and delivering services and have allocated a gender marker ‘2’ (gender considered but not targeted). A more detailed discussion of these considerations will be set forth in the full business case.
3. As part of its investment policies, the products will adhere to DFID’s policies on gender equality and promoting economic opportunities for women as well as any additional policies that participating financial institutions may have in place, where they strengthen the gender focus. MOBILIST will expect the products to consider the impact on gender equality of the investment policies of the underlying fund managers and make decisions that would be inclusive on this criterion as well as considering potential gender-specific metrics that against which data might be able to be collected form the portfolio companies in which the sub-funds invest.
4. Note on distributional and gender impacts - left to itself the market would not take explicit account of the extent to which investments benefit specifically women, low income households and other disadvantaged groups. DFID participation will help to ensure that these objectives are given due consideration and that technical assistance resources are available where necessary to ensure that they are incorporated into project design and monitoring. At a minimum, the programme will seek to evaluate differentiated poverty impacts by gender to provide reassurances of doing no harm.
Terrorism, Bribery and financing
1. This programme (like all other interventions) must comply with relevant legislation, including the Terrorism Acts 2000 & 2006, Proceeds of Crime Act 2002 (Part 7) Money Laundering Regulations 2007, Terrorist (Asset Freezing etc.) Act 2010, the Bribery Act 2010, and the Al-Qaida (Asset Freezing) Regulations 2011. This will require DFID, and its delivery partners to (a) identify our partners (including robust due diligence) and ensure they are aware of their responsibilities in relation to the legislation; (b) keep appropriate records; (c) establish internal procedures and controls to mitigate risks; (d) prepare guidance and training sessions to increase staff awareness; and (e) report any contra indicators to the relevant authorities.
2. As an investor in the product vehicles, DFID will stipulate as a condition of participation the Fund Manager’s adherence to DFID policies on both money laundering and counter-terrorist financing. The product will also be subject to the participating institution’s policies on money laundering and counter-terrorist financing. In the UK, is some of the strictest legislative and regulatory framework in the world. Moreover, DFID ensures that these policies will be consistent with the requirements set out in Part III of the Terrorism Act 2000. These policies also address the selection and oversight of fund managers for the sub-funds in which the Fund Manager may seek to invest. As such, we consider these risks to be low in the context of investing the respective products, but they will be reviewed by the MOBILIST Investment Committee as part of the investment decision-making process.
  [note] Part III of the Terrorism Act 2000 (Sections 14-31) contains provisions on fund-raising and funding arrangements, money laundering, information disclosure, among other matters.
3. The risk of funds being misappropriated for terrorist purposes is assessed to be very low given the nature of the programme. At the same time, the programme must be alive to potential unintended consequences of more robust enforcement, which can create a compliance burden so great that it deters compliant behaviour and leads to “shortcuts” or bribery. A risk-based approach will be important. Requirements over and above the standard investment practices will be met through the DFID-funded technical assistance.
Sustainability
DFID may provide development capital and catalytic grant funding to help launch the product, but on the basis that this support has systemic effect i.e. that it overcomes a market barrier preventing a functioning, commercially based intermediation mechanism that is a normal feature of functioning markets. In effect, DFID support is to replicate - or extend - an existing sustainable market function to new geographies.
Climate
1. There is forecast to be a significant component of the listed products asset exposure that can and will target climate related investment opportunities, e.g. concepts such as a Green Covered Bond intervention identified during earlier phases of supporting research advocate for support in the form of technical assistance.
2. More broadly, a likely thematic area for impact measurement will be the concept of ‘low carbon sustainable growth.’ It will be for Fund Manager’s working with existing impact measurement frameworks (and in collaboration with new framework design) to respond to DFID’s investment criteria. As part of an iterative process, DFID will be able to determine market appetite and opportunity to reflect climate ambition in each listed product. DFID has flexibility to respond accordingly and ICF targets for the programme will be set by the MOBILIST Investment Committee in line with DFID’s strategic guidance.
3. ESG requirements will comprise a high element of climate related impact, and this will be reflected in any agreed investment mandate.
  [note] ESG investors can argue that despite higher carbon emissions, investing even in countries where carbon emissions are going up, is still consistent with an ESG focus, because the S and G and parts of the E will improve.

## Commercial Case
DFID plans to catalyse investment in listed products that demonstrably channel new sources of capital to bridge the gap in SDG investment and spending needs. Early market engagement and the appraisal case sets out three routes that DFID will use to catalyse listed products under the Business Case (financial allocation to each is described in the financial case):
1. DFID will provide technical assistance services to facilitate the launch of listed investment products where a cornerstone de-risking investment is not required e.g. into facilitating a Green Covered Bond. Whilst recognising that product development is best done by market players with experience of such products and with product marketing and distribution capabilities, for some product concepts, the involvement of a dedicated entity that can participate in and manage the strategic partnerships between DFID and the mainstream financial sector and development actors, including DFIs, and sector specialists is required.
  [note] It is not thought that one single TA provider would be responsible for more than a single product, given the specialist nature of the services required in relation to product options, although we keep this option open in the business case. TA for products like the green covered bond, which already have a well-worked through route to market plan will be procured in the first year, whilst a broader TA contract, supporting the convene option would be considered in year 2 of the programme.
2. DFID will make direct investments or provide risk mitigation into up to 5 first of their kind listed investment products where a cornerstone investment or investment for risk-mitigation by DFID is needed in order to prepare a product for listing (and subsequent investment by institutional investors) or ensure its successful listing. These first mover funds would act as proof of concept products. Areas of specific interest include a product that is focused on Infrastructure, Trade and Small-Medium Enterprise Bank Finance and Green Covered Bonds. DFID investment may be accompanied by the provision of technical assistance grant funding (possibly matching grants) to partially cover the costs for the set-up of a proposed financial vehicle.
3. DFID will ‘convene:’ this option is supported by DFID’s internal resources and refers largely to DFID’s ongoing engagement with the City and institutional investors with regards to listed products. Depending on the type of listed product concept, this intervention may be something a TA provider would support, noting that it could (where appropriate) be included in the scope of that facility.

Technical Assistance Services
1. DFID plans to procure a supplier(s) to manage a Technical Assistance (TA) Facility or facilities in relation to identified product concepts where specific technical assistance interventions are deemed the critical barrier to listing. These interventions might include supporting the design and structuring of new product concepts; addressing regulatory barriers; acting as a convenor of relevant stakeholders, and in taking forward DFID’s policy agenda on listed products. The TA will need to be product specific.
2. MOBILIST seeks to procure a TA Facility supplier that would be responsible for helping scope the TA support that is needed for products (where discreet TA is not procured directly by DFID for a particular product), and most likely then sourcing and managing suitable experts to deliver each piece of TA.
  [note] For example, in relation to the Green Covered Bond Road Map, a TA facility would be concerned solely with bringing a green bond to public listing. The facility could also provide a learning function to help inform DFID’s broader mobilisation work (and specifically the design of the mobilisation facility) – evaluating and disseminating lessons on what is needed and what is working or not to catalyse this market. This illustrative example is described in the indicative “Route to Market” plan for the Green Covered Bond – Annex C.
3. To ensure the efficient allocation of TA support, the TA Facility supplier will be expected to consult with managers of listed products on ways to address investment policy and regulatory barriers. This will ensure that the TA Facility fulfils its function of addressing market failure that would hinder the effectiveness of the listed product in question.
4. The TA Facility manager is expected to be procured through an OJEU Procurement Process, given the likely size of the support needed. The tender process will be led by Procurement and Commercial Team who will work closely with the DFID programme team to set out the service requirements, and the sourcing strategy during the first six months of MOBILIST.
5. To get the best value for money, results and impact, the contract for managing TA will be output focussed (to the extent possible) with payments linked to achievement of agreed outputs and milestones. The Terms of Reference will set out what the supplier is expected to achieve with sufficient flexibility to address new priorities or address risks that may arise in the future.
6. The Supplier will be asked to provide a detailed methodology in their bid to demonstrate what they intend to achieve, how and by when. A work plan will be developed to drive and monitor the agreed activities and outputs. A break clause will be built into the contracts to enable DFID to review priorities, incentivise the supplier and mitigate risks. The contracts will clearly lay out the processes to cover the management of off-track performance and how the supplier will share and manage investigations of fraud and corruption.
7. As mentioned above, our research has identified the most promising listed product to commence TA support (Green Covered Bond), and that there is a window of opportunity to support the launch of this product within 6 months. To achieve this, the team expect to procure the TA required to achieve this separately from the main facility using a combination of low value tender and crown commercial frameworks. This first product will provide lessons that will help inform the sourcing strategy for the OJEU tender for the main facility.

B.	Catalysing new products from the market by providing cornerstone investment or by deploying risk mitigation tools like guarantees
1. The scoping work demonstrated the need for DFID to provide catalytic investment, like cornerstone capital, if a sub-set of the product concepts identified are ever to come to market through an IPO. DFID commissioned design work from experts in listed products who engaged with a broad spectrum of asset and fund managers to test their interest and willingness to develop new funds, and what type of investment would be needed by DFID.
2. The intention is for MOBILIST to have the flexibility to invest or risk mitigate in different listed product areas – some of the first areas prioritised in the supporting research are Infrastructure and SME Bank Finance. These are research recommendations, not instructions, and MOBILIST will have opportunity through the Investment Committee to consider these and other product ideas before proceeding. MOBILIST also has scope to expand into other sectors based on the funds available and additional market scoping work, up to a maximum of 5 listed products launched into the London and/ or dual or domestic exchanges of target countries.
3. When deciding which sectors and listed products to support with DFID support, the following overarching evaluation criteria for a DFID investment is provided indicatively (each individual intervention will have their own criteria through their competitive processes), and once MOBILIST is operational these criteria will be tested and refined. The governance around the investment decision-making is covered in detail in the Management Case, which describes the MOBILIST Investment Committee.
  [note] During the proposed 2-window competition in Q2, we anticipate procuring technical expertise and evaluation support to examine the relevant criteria and help the MIC assess proposals against these criteria.
Table 3: Overarching evaluation criteria:
Nature, size and tenure of Investment	DFID will provide an equity only investment or a risk mitigation instrument (that is not classified as debt). This intervention would be recorded on the DFID balance sheet. Unlike debt, equity investment and guarantees can qualify as ODA provided that the primary purpose of the investment is the promotion of economic development and welfare of developing countries and must comply with various further requirements of the Reporting Directives. Note that DFID’s Finance Department will be a member of the governance committee and which will sign-off on every investment.
	The investment will be made in GBP, unless otherwise agreed with DFID Finance (currency exposure on DFID’s balance sheet is normally not permitted). The investment vehicle itself may be denominated in another currency and may make non-GBP investments.
	Support for any particular investment product must be predicated on the reasonable expectation that the product can be listed on the London Stock Exchange and/ or on a local market exchange, within an aspirational time limit of 18 months. Should there by delays in listing, or an assessment that a listing is not possible, DFID will look to the investment agreement to manage its exit from the investment or risk mitigation tool, in line with normal market practice. The detail of this is product dependent and will be the subject of commercial negotiation.
	The structure of the investment will count as ODA. DFID expects its entire investment or risk mitigation to count as Official Development Assistance. To be scored as ODA each DFID’s investment will need to meet both structural requirements (developmental impact), and broader tests on primary purpose and additionality.
	DFID’s investment may be concessional or pari passu. Scoping has suggested that DFID may be required to take a junior capital investment tranche, though the level of concessionality will depend on what proposals are received through the RFP process and on the precise focus of each product and markets perception of risk associated with the underlying investment class.
	DFID is willing to act as an anchor investor (this includes DFID acting as a first investor to enable a private launch of the fund, which may be necessary for the fund to build an initial portfolio from which to raise institutional co-investment and enable the public offering). The appropriate level of concessionality will be the subject of commercial negotiation predicated on the principle that agreement ensures that there is a realistic prospect that this delivers the required market demonstration and not disproportionate market subsidy i.e. unlikely without concessions it would be a viable product.
	Investment is between £10m and £50m based on investor consultations in relation to a long list of product concepts and the 2 route to market plans annexed.
	The rate of return for the intervention is expected to be in line with the risk adjusted return expectations for similarly risk profiled investments that are currently held in institutional portfolios. Indicatively this is likely to be between 200 and 500 bps above the benchmark T-Bill rate.
	The duration of DFID’s investment is expected to be less than 5 years, based on the premise that DFID’s involvement is to help take the product to a listing (which by definition implies the crowding in of private investors) and thereafter to seek a managed exit.
	DFID’s investment will not create a non-departmental public body.
	DFID has capacity to divest once the DFID investment is no longer required or if intervention objectives cannot be delivered or (should the political will emerge) ability to transfer ownership of the asset to another government owned entity e.g. CDC if there was appetite and ability.
	The investment mandate of the fund will be fully aligned with DFID objectives and we expect clear additionality of investment or risk mitigation.
Relevance, Impact and additionality	DFID will work with leaders across the impact measurement field (including the Impact Management Project) to propose and integrate effective development impact measurement across the products. This is a challenge due in part to the complexity of attributing impact in publicly owned investment structures. All products will apply IFC performance standards and as both the product and programme evolves, we will actively seek to build on these standards for wider development impact measurement in line with wider industry work.
	Fund’s mandate ensures that at least 100% of the products’ investments are in DFID priorities - broadly ODA eligible countries (there will be strong preference toward higher % in LICs and LMICs, while recognising need to de-risk, and a high bar of additionality for UMICs).
	The level of investment requested is appropriate to need.
	The investment will be compliant with State Aid Rules (legal advisors will engage throughout the process to ensure this is the case).
	Manager of the vehicle demonstrates relevant product and sector experience and track record.
Ability to deliver	Strong evidence that the fund is feasible to establish and listable on LSE or another major exchange in an international financial centre and/ or local exchange.
Governance	The investment structure will not result in the creation of a non-departmental public body. [Should teams identify that this may be a risk for a particular investment asset class, the team would check this with DFID Treasury Spending Team before progressing with the RFP or investment process] / DFID does not want or expect to exert a controlling role in the new vehicle and is not intending to create a controlling stake.
Fund Management costs are VfM	Fund management fees must be demonstrated to be comparable to benchmark and appropriate to the nature of the investment and/or risk mitigation. It is likely that we will receive proposals whereby management fees will be netted of the Net Asset Value and not paid separately. / Choice of partners: the track record and reputation of the fund manager matters to the markets: “the track record of the fund manager is key.” This means products launched by or in partnership with established players are likely to take off more quickly than those launched by newcomers or niche players, and a key decision metric will be the quality and market reputation of the partnering financial institutions.
Compliance and safeguarding	The investment or risk mitigation tool is untied, and contracts will be let out on transparent and competitive processes. / Vehicle demonstrates capacity to comply with industry relevant compliance requirements as well as sanctions list, anti-terrorism financing, anti-money laundering, and anti-bribery and corruption legislation and regulations.
[note] The interim directives (General Principles ii) specify that [Donor] “effort may be measured either at the point of transfer of funds to a vehicle providing PSI to developing countries or for each PSI transaction between the vehicle and the private enterprise or institution in the partner country. These two methods of calculation are referred to as institutional and instrument-specific approaches retrospectively” http://www.oecd.org/officialdocuments/publicdisplaydocumentpdf/?cote=DCD/DAC/STAT(2019)1&docLanguage=En
[note] We use the instrument approach for our investment portfolio in DFID India, which includes our investment in the Green Growth Equity fund under India’s National Infrastructure Investment Fund (NIIF). DFID India’s investments are equity investments, which are 100% ODA-eligible.
[note] https://www.ifc.org/wps/wcm/connect/Topics_Ext_Content/IFC_External_Corporate_Site/Sustainability-At-IFC/Policies-Standards/Performance-Standards

1. The scoping work identified that there is a broad market of financial entities with relevant experience, capability and interest to design and structure a new investment vehicle able to deliver the objectives set out in this business case, provided there was a relevant anchor investment along the lines described above.
2. DFID therefore proposes to use an open Request for Proposals (RFP) process, separate for each product, to elicit proposals for listed products from this experienced market and to select the Fund Manager, related consortium and product proposition that is best able to achieve DFID’s objectives and into which DFID would be willing to make an investment and/ or risk mitigation once the investment vehicle has been legally established by the Issuer (in collaboration with the Fund Manager).
3. The investment assessment process will be clearly articulated in competition documents so that prospective applicants are fully cognisant of governance arrangements for investment decisions by DFID, and also for the criteria by which DFID will assess the investment potential of product proposals. Key elements include an assessment criteria and scoring methodology to be used, as well as the governance/ assurance function that will manage and approve any investment or risk mitigation instrument (i.e. the MOBILIST Investment Committee).
4. Legal advice is that as DFID is not procuring any services but instead considering making an investment or providing a grant to enable such products to launch, the process to identify which products to support from a market of applicants is not subject to public contract regulations. Notwithstanding this, DFID will still run a transparent and fair competition and ensure that decisions taken are reasonable and proportionate.
5. To ensure that the RFP process compares proposals on a like-for-like basis, DFID expects to run a specific RFP window for each new product area.
  [note] An indicative Route to Market plan, including an RFP approach for infrastructure is included as Annex B.
6. Each Request for Proposals window process will be developed and articulated by the DFID programme team to suit the specific product area. The programme team will draw in specialist advice from the following sources to co-develop the RFP and ensure the process is relevant, effective, and fair:
- DFID commercial advisors to help structure and run the process;
- Government Legal Advisors who will advise on check that the proposed RFP processes is compliant with State Aid rules and protects the principles of fair, open competition, as well as formalising DFID’s investment agreements;
- Supplementary specialist commercial legal advice to support for example the commercial negotiation, and legal due diligence of each investment vehicle and agreement;
- Specialist product relevant Financial Transactions Advisory Services with strong market and product development understanding who will help define the parameters of each investment and/ or risk mitigation and support the due diligence of the bidders and their proposed product;
- Independent valuation services to value the investment and/ or risk mitigation on an on-going basis until the product is listed on the stock exchange.
1. The requirements and parameters for shortlisting bids based on common bid evaluation criteria will be clearly articulated in the bidding process documents. The process will be designed to ensure that the competition stage is well structured, allowing some issues to be aired and clarified at this stage while ensuring competition entrants are not able to reduce the comparative value of their proposal vis a vis other competition participants. Hence, there will be a mechanism for bidders at each stage to submit clarification questions and DFID will ensure all clarifications are shared with all bidders to ensure a level playing field (the exception is that clarifications on a bidders commercial/ technical proposal do not require disclosure).
2. Procurement and Government Legal Advice has already been identified and has already provided substantive advice during the design of MOBILIST. Specialist financial transactions and commercial legal advice expertise are not skills that DFID/government routinely has in house. Therefore, the programme team will work with DFID commercial advisors to select the best route for sourcing this advice. Given the specialism of these skills, preferred sourcing options include using crown commercial frameworks and/or running low value competitive tenders. When sourcing this advice, value for money will be achieved by precisely scoping the work required by each provider for each stage of the RFP process, using frameworks and tender processes that include suppliers with relevant expertise and experience, and using competitive bidding when calling off the frameworks or tendering to enable selection of bidders based on relevant quality and cost criteria. Supplier contracts will include performance indicators, breakpoints and payment structures that drive performance.
3. The DFID SRO and Programme manager will be responsible for bringing these inputs together and for ensuring that the RFP process is delivered as planned.
Fig 13: Anticipated Stages of the RFP process (for each product the RFP process is expected to be run as a three-stage process): / Each RFP from the outset should include full detail on the context and objectives that DFID has, and details on the role DFID is looking to play and the support it is willing to provide. The following description is indicative, and there will be some latitude to amend the format and competition process in consultation with procured specialist advice. / 1. RFP Stage 1 - Expressions of Interest applications (EOI) and shortlisting of applicants / The EOI document will provide sufficient information to enable all fund managers in the market to understand the opportunity – indicating the purpose of the RFP, the type of anchor investment support DFID may be interested to provide (a range is acceptable), the details of the application process and timeline, and how applications will be evaluated and the scoring criteria. / The EOI applications are an important first step, inviting applicants to submit a formal expression of interest and initial product concept. The EOI stage will formally test the level of interest in the market against the requirements put forward by DFID. As part of the EOI (and under advice from specialist support), DFID will issue the criteria it will use to shortlist which applicants will be invited to the second stage of the RFP - Full Proposals. The shortlisting criteria will include ‘Key Eligibility Criteria’ setting out minimum experience applicant fund managers will be expected to possess. Shortlisting is relevant given there is limited funding available and the Fund Managers that progress to second stage of the RFP will need to invest significant resources to develop a robust proposal. / If the volume or quality of responses to the EOI is inadequate, DFID would seek feedback from the market of bidders and consider whether to revise the proposition and reissue. It is important that products are underpinned by a commercial logic and are being taken forward by institutions who are willing to put ‘skin in the game’ be it resources or their own contracting of resources. Should it be clear during the EOI phase that market actors are unwilling to develop products without DFID sharing some of the design costs DFID would consider revising the opportunity to allow some technical assistance grant funding to be available and would then reissue the Stage 1 RFP to the whole market with that revised scope. / 2. RFP Stage 2 – Submission of Full Proposals evaluation and selection / Following selection at RFP Stage 1, shortlisted fund managers will be invited to develop comprehensive proposals in response to the RFP. In order to develop a sufficiently robust proposal, fund managers will be expected to enter into an initial design phase, that will involve market soundings and securing a ‘consortium’ of relevant market participants and the development of a comprehensive proposal that meets the RFP requirements. In preparing the new product concept, fund/ asset managers will need to consult with institutional investors and structure their proposals around the prospect of institutional investors’ appetite to invest at the point of listing. / Submitted proposals will be assessed by the MIC (again, supported by specialist advice) against the evaluation criteria set out in the RFP documents, which will vary depending upon the listed product concept. The purpose of the bid evaluation is to identify proposals that could achieve DFID’s stated aims for the vehicle and also offer the best value for money to DFID. The criteria will be expected to cover key themes, such as: i) firm experience; ii) proposed vehicle; iii) additionality; iv) vehicle structure; v) ‘practical considerations; vi) team and; vii) financial proposal, including requested technical assistance funding (if permitted and requested). Indicative criteria are described in more detail in Annex B (Infrastructure Road Map). / RFP Stage 3 - Product structuring, negotiation diligence, and, if satisfied, invest / In the negotiation phase, due diligence on the fund manager and investment vehicle will be carried out throughout the process to ensure the manager is able to deliver the product and meet DFID and sector wide compliance and ESG expectations. DFID’s investment and/or risk mitigation in each product will be set out in a legally binding investment agreement. The investment agreement is expected to reflect market norms for listed products, while protecting specific DFID requirements e.g. relating to the investment mandate and relevant caps on management fees. Concurrently we would expect the Fund/ Asset Manager to be conducting bilateral discussions with potential investors in the fund to achieve financial close ahead of the fund launch date.
[note] E.g.: ’Deliverability‘- Fund Managers must demonstrate how they will deliver the vehicle from design to IPO including potential issues that could arise and how they intend to mitigate them; Asset Manager operations: Fund Managers should demonstrate that they have appropriate structures and ethical standards that will aid in establishing and operating the vehicle

The RFP process will be structured to fit with the key steps of a typical listed product launch:
Fig 14: Typical Fund Launch Process:

C. Catalysing products through DFID’s ‘Convening’ power:
1. For some identified product concepts, our research indicates that the market should be able to support these without direct DFID capital investment needs. However, these initiatives could benefit from “soft” support from DFID – these activities would fall under MOBILIST’s role in “convening” relevant stakeholders.
2. Convening as an approach has some similarities to the TA approach, where technical assistance can be thought of as akin to an “Active convene” response: where DFID identifies key stakeholders who need to be brought together in order to kick-start a product structuring process e.g. Green Covered Bond. ‘Convene’ in the absence of technical assistance is predicated on the idea that in this scenario DFID will support initiatives by giving them a platform for additional exposure, where these initiatives either already exist and have launched without DFID support but align well with DFID’s goals, or should be able to launch without DFID support.
3. Key commercial risks are summarised in the Risk Matrix in the Management Case.

## Financial Case
DFID/HMG will provide a total budget of £90m over 6 years from December 2019 to March 2026. £76.40m will be provided as non-fiscal CDEL as investments into a sub-set of the 5 products and is expected to be disbursed over 6 years (Nov 2020 - March 2026). A further £13.6m of Technical Assistance and associated services though the DFID Resource budget will be disbursed over the 6 years. The table below gives an indicative spend profile based on the scoping study market assessment and will be reviewed before the implementation phase begins.

Year	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25	2025/26	TOTAL
NON-FISCAL CDEL
Capital Investments		20.0	30.0	26.4	-	-	-	76.40
RDEL
RFP competition advisory services	0.15	0.4	0.4	0.2	0.2	0.2	0.1	1.65
TA Facility		2	3	2	1	1	1	10
Investment valuation		0.0	0.06	0.09	0.09	0.06	0.03	0.33
Programme review and evaluation		0.12	0.3	0.3	0.3	0.3	0.3	1.62
[note] An equivalent service charges £0.06m per year.

Who are the recipients of all the proposed payments?
1. The content and scale of MOBILIST was determined after a scoping study followed by extensive consultation within HMG independent experts and development partners. It is judged that UK investment of £90m (comprised of DevCap, TA and advisory service costs) is the minimum necessary scale to support the needed portfolio of listed product interventions predicated in this approach.
2. MOBILIST includes £76.40m non-fiscal CDEL for Development Capital investments that will be paid into new private investment vehicles and £13.6m for TA Services and supplementary advisory services that will be purchased from private advisory firms. The intervention does not involve financial aid to governments.
3. The financial allocations and management for each workstream are described below:

A. Non-Fiscal CDEL Investment
Investment size and cost drivers:
1. The full £90m programme expects to catalyse a maximum of 5 products. It is estimated that MOBILIST will invest up to £76.4m in equity into approximately 2-3 of these new listed products. The size of each equity investment expected to be between £15-50 million.
2. The RFP process for each investment will help to determine the volume of funding necessary to launch each new product concept. An indicative timeline of the process for one of the products, the listed infrastructure fund is presented below:
Fig 15: Illustrative timeline for the infrastructure product:

1. The fee for management (and other relevant industry standard costs) will be paid to the Fund Manager. Any additional or alternative forms of remuneration (e.g. receiving a share of realised profits above an agreed hurdle level) will like the Fund Management fees be subject to competitive pressure through the RFP process.
  [note] Listing agent fees are normally incorporated into the products Annual Management Charge (AMC)
  [note] Management fees could be netted off against Net Asset Value (NAV), and not paid separately
2. If DFID invests directly in an investment vehicle or transaction, the investment will appear as an individual asset on DFID’s balance sheet and will be accounted for and valued in accordance with the relevant accounting rules. DFID will ensure that the asset is structured as an investment and does not inadvertently create an arms’ length body.
  [note] It would most likely be subsequently accounted for as a ‘private sector asset’, i.e. it will not be treated as a Central Government asset; a public sector or WGA asset; or a ‘rest of the world’ asset. These would each have other undesirable accounting and non-accounting implications.
3. In order to support a private sector asset designation, DFID would likely need to ensure that (i) its own stake in the vehicle is not a controlling stake (for example, not giving rise to an equity share of over 50% or a controlling influence on the Board) and; (ii) that the vehicle operates at arms-length, without DFID’s day-to-day involvement in specific investment decisions. Both of these facets are likely to be desirable in any case from a policy perspective and DFID will ensure that the asset is structured as an investment and does not create an arms’ length body.
  [note] It would most likely be subsequently accounted for as a ‘private sector asset’, i.e. it will not be treated as a Central Government asset; a public sector or WGA asset; or a ‘rest of the world’ asset. These would each have other undesirable accounting and non-accounting implications. In order to support a private sector asset designation, DFID would likely need to ensure that (i) its own stake in the vehicle is not a controlling stake (for example, not giving rise to an equity share of over 50% or a controlling influence on the Board); and (ii) that the vehicle operates at arms-length, without DFID’s day-to-day involvement in specific investment decisions. Both of these facets are likely to be desirable in any case from a policy perspective. This arms-length arrangement would not preclude DFID from insisting that certain investment restrictions are maintained, for example excluding investment into the arms or tobacco trades).
4. DFID expects to take a minority stake in any product identified through a competitive process, and co-investment from other funders will therefore be required. The need for 100% seeding to catalyse the product would be an (unlikely) exception, only to be considered if we were satisfied on issues in relation to financial accounting and/ or ODA-eligibility (a non-negotiable assessment criterion for the competition).
5. The asset would then be valued (a) upon initial investment and (b) subsequently on an annual basis. Annual formal valuations would be likely to take place as at 31st December, and then be updated to give a 31st March year-end position for the Department’s financial statements. It is theoretically possible that the initial valuation could be at a discount to the funds disbursed.
6. Subsequent accounting could follow the Fair Value through Other Comprehensive Income (FVOCI) method, in line with most of DFID’s existing investment assets. This means that increases in value would pass into DFID’s reserves while impairments would impact Annually Managed Expenditure (RAME).
  [note] DFID's RAME budget is non-cash, but still has to be managed appropriately as it is a control total. DFID has two opportunities per year to request RAME budget through the Supply Estimates process. The programme team will monitor the valuation trends and alert DFID Finance if valuations are likely to move significantly through the year to ensure sufficient RAME budget is requested from HMT. It could also be the case that all changes in asset valuation could impact on the Department’s AME budget
7. Dividends received or costs incurred by DFID in respect of the vehicle would be reported under the Resource Departmental Expenditure Limit (ResourceDEL). Any proposed sale or partial sale would need to be conducted with due advance planning to manage the fiscal impact, including the likelihood of this being recorded as negative ODA.
In which jurisdiction will the listed products be registered:
A listing on a major exchange, located within an international financial centre, is the primary objective for MOBILIST. However, the programme will consider the relevance an opportunity to support local listings and/ or dual listings in order to achieve that major exchange listing, if market discussions are persuasive that this is an advised route to market.
How will you work to ensure accurate financial forecasting and avoid paying in advance of need?
1. Investments will be paid into the agreed Product structures in GBP. Disbursements will be made against firm investment commitments approved by the MOBILIST Investment Committee and a draw-down notice from the Fund Manager.
2. At this stage we expect the schedule of disbursements to be within the next spending round (expires March 2024). It is worth highlighting that there are inherent risks attached to the investment portfolio, the external environment, pipeline of projects and rigor of the assessment process. All can lead to delayed disbursements. Disbursement risk will be monitored closely by the team, based on assessment of the active pipeline provided by the Fund Manager.
3. Management fees of the listed product(s) are reasonably predictable, and accurate forecasts are expected. However, predicting the draw-down of the capital investment will be more difficult. The ‘flow of funds’ from DFID to the fund is predicated on the identification by the Fund Manager of assets to purchase and based on need. DFID expects to have a legally binding obligation to disburse capital against a draw-down notice by a Fund Manager, based upon the funds’ asset acquisition policy and commitment from other investors. We will seek to obtain an accurate forecast of the investment draw-down and set out a schedule of payments and requirements on forecasting; this will be reviewed regularly, and the Fund Manager will be required to inform DFID at least 2 months prior to any adjustments to the drawdown profile. The Fund Manager will be expected to submit annual audited statement of accounts to DFID no later than four months after the end of each financial year.
4. The Fund Manager will be responsible for the relevant due diligence, selection, supervision and execution of the activities undertaken, and will report on progress as outlined in DFID’s investment agreement.
Expected investment rates of return:
Return expectations will be dependent on the nature of the asset portfolio: debt vs equity, and the level of risk associated with the underlying assets each product is invested in e.g. in infrastructure the amount of greenfield vs. operational infrastructure etc. can be expected to vary the return profile. Crucially, during the RFP process Fund Managers are being asked to structure a vehicle which they believe institutional investors will be interested in, so the returns offered must be in line with market expectations for that type of asset strategy. There is no incentive for fund managers to offer a vehicle which they don’t believe the market will buy.
[note] Emerging Market valuations are at 12-year lows because of both external and endogenous factors. This cannot be disregarded in impacting sentiment.
Volatility of Investment value and yields:
It is expected that the vehicles’ value will experience in year and year-to-year volatility. Key factors that will cause the value of the vehicle to fluctuate include foreign exchange fluctuations where the product holds equity in assets where the underlying asset value is in local currency; local political risk that causes operations within underlying assets to stop; and once listed on the market – share prices will also be subject to fluctuation owing to “market sentiment”. It is not possible to give a range of volatility values today, however the below fund provides an indicative example:
Fig 16: The UTILICO Emerging Markets Trust Plc is listed on the LSE and invests in listed equities and debt of EM companies in the infrastructure and utilities sectors:

Exit Planning:
1. MOBILIST seeks to catalyse products that can list on a major exchange. It is probable therefore that DFID’s support will be predicated on our participation up to and following the point of listing. How long after listing would DFID remain an equity shareholder will be determined by market conditions and our strategic appetite i.e. the desire to set the product on a sustainable commercial footing for the long term. What will not determine DFID’s decision-making with respect to investment tenure is the investment opportunity (financial return).
2. During the period before listing (i.e. an ‘incubation period’), we expect these products to demonstrate their ability both to originate assets and recycle capital as those assets reach maturity. By doing so, the fund begins to build a track and performance record against a recognised benchmark that allows institutional investors to more confidently appraise the product as an investment opportunity. It is this ‘confidence’ that is the basis for DFID’s support and ultimately will determine the timing and ease by which we can divest.
  [note] An investment’s track record effectively serves as a low-cost due diligence mechanism
3. Only by achieving a successful track record and delivering that confidence to institutional investors will an IPO by feasible. The pre-listing period, where DFID will likely be one of several investors (and hold a minority stake), serves to remove a portion of the risk of investing in these instruments, including what is commonly known in investment circles as “first mover disadvantage.” Listing, and the decision by new investors to become equity holders removes still more risks in relation to liquidity, governance and transparency, and the act of listing itself has a powerful effect on market sentiment, as more cautious investors, driven by heard behaviours, see the opportunity. That is the theory of change that describes how DFID sees its exit strategy on a product level.
4. On a strategic level, MOBILIST is predicated on the notion of catalysing products and then moving on to more scalable but more complex products, so that the programme seeks to support a portfolio of products, with different partners, and different investment profiles that together begin the populate the market with a range of price signals that address a principle barrier to mobilisation – information asymmetry.

B. TA Facility Contract and other Procured Support Services Contracts
Cost Drivers:
The key cost driver for both the TA Facility as well as supplementary financial transactions, legal and valuation services will be the fee rates charged for specialist skills. Earlier scoping work developed road maps for two potential investment products and a first proposed TA intervention (to support the launch of a covered green bond). This scoping provided an outline of type and duration of services that will be required. We have also compared this with similar projects in DFID India to estimate likely overall costs of delivering these outputs. We have also been able to use fee rate price ranges agreed for suppliers on relevant crown commercial services framework contracts to estimate likely costs. The scope of the TA work will evolve over the lifetime of the programme based on the market opportunities available. The budget plans for the TA facility to support between 1-3 transactions to be launched with support from non-DFID investors.
[note] DFID India committed capital to four equity funds (£85m) & two debt funds (£76m) aimed at mobilisation of capital. DFID India has put forward a future strategy with increased scale (£50-150m/year) and an emphasis on earlier stage interventions for market development/systemic change.
Expenditure monitoring, reporting and payments to suppliers:
1. As highlighted in the commercial case for directly procured technical assistance contacts, the DFID programme team will ensure payments to suppliers are paid in arrears, linked to the work delivered, and wherever possible, linking payments to delivery of agreed outputs.
2. In accordance with the contractual provisions, payments will be disbursed on receipt of a valid invoice that is supported by a breakdown of the costs being claimed and the Programme Manager will be responsible for ensuring due diligence in the disbursement of payments. Where appropriate, full details of forecasted future spend by financial years against the annual work plan will be included in an annual report to DFID and agreed/monitored by the DFID team.
Programme additionality:
We will provide capital based on the three principles of additionality (only investing where the private sector is not); minimum subsidy (to build rather than distort markets and ensure value for money); development impact (making sure the line of sight to economic transformation and poverty reduction is clear and defined by an impact measurement framework that will inform design and ongoing product investment decision-making and evaluation).
Is DFID funding classified Overseas Development Assistance (ODA)? How will ODA forecasting be managed?
1. At this stage, DFID’s interpretation of OECD-DAC Guidance leads us to adopt the ‘institutional’ approach to measurement and reporting, as opposed to the ‘instrument’ approach. The basis for our understanding of current OECD Guidance is Annex 21 ‘Reporting methods for private sector instruments.’
  [note] http://www.oecd.org/officialdocuments/publicdisplaydocumentpdf/?cote=DCD/DAC/STAT(2019)1&docLanguage=En
2. The interim directives (General Principles ii) specify that [Donor] “effort may be measured either at the point of transfer of funds to a vehicle providing PSI to developing countries or for each PSI transaction between the vehicle and the private enterprise or institution in the partner country. These two methods of calculation are referred to as institutional and instrument-specific approaches retrospectively.” General Principle ii) explains that under the institutional approach, ODA-classification occurs at the point of transfer of funds to the “PSI vehicle” in extending PSI to developing countries i.e. the vehicle itself is classified as ODA-eligible.
3. We are now of the view that the most appropriate course of action is to seek ODA-eligibility through the institutional approach. In accordance with the Guidance, this would be an ODA-eligibility self-assessment followed by retrospective application and classification by OECD DAC.
4. Accordingly, we propose to integrate ODA-eligibility criteria into DFID’s competition criteria (by including the Annex 2 application). DFID will ensure that the vehicle concerned meets the overarching ODA definition of having for a main objective the economic development and welfare of ODA-eligible countries and ensure compliance with the additionality requirements for PSI.
  [note] DCD/DAC (2018)47/FINAL: “Reporting Methods for Private Sector Instruments” 12 December 2018
5. As set out through the course of this business case, we are confident that interventions will meet i) our own internal assessment for a primary development purpose and additionality and subsequently ii) OECD-DAC guidance criteria. Nevertheless, it is important to acknowledge that ODA rules on ODA classification are in flux. Ensuring that the products are invested only in ODA-eligible countries makes (and with a strong preference for LICs and LMICs, together with a high bar of additionality for UMICs) classification much easier. We are sharing and discussing our approach widely to determine where unforeseen issues might arise. To date we are not aware of any objections that would make ODA classification problematic.
6. The entire investment and associated routine management fees that are charged as part of that investment will score as ODA. ODA will be scored at the time at which DFID disposes funds to the programme. DAC rules with respect to private sector investment are undergoing review but the ODA December 2016 paper notes the changes will not affect equity investments. In the event of exits, any monetary reflows that are received by HMG will be recorded as negative ODA.
  [note] Regardless of whether the proceeds are higher or lower than the invested amounts in accordance with established DevCap principles and ODA guidance. This ODA reflows will be discussed with FCPD well in advance and PSD will ensure it is included within budget forecasts for the relevant fiscal year.
7. The investment and technical assistance from DFID are untied in nature, since there is no requirement for only UK companies to be involved.
  [note] The programme will ensure that interventions are not deemed to fall under state aid rules.
Are there any accounting considerations arising from the project?
1. DevCap requires specialist knowledge and processes in government accounting. MOBILIST will be managed by the team currently managing the DFID PSD DevCap portfolio using accounting and financial procedures approved by FCPD, IAD and NAO. Before committing to each investment, the accounting procedures for each investment will be approved by DFID’s Financial Accounting and Control department.
2. Treatment of assets: The assets will remain on the DFID balance sheet and will be treated in line with the processes followed for the DFID PSD DevCap portfolio including transfer and disposal of assets. There is no expectation (nor appetite) for balance sheet consolidation of the legal entity.
3. The Fund Manager will provide regular valuation of the investment. This asset will also be independently valued by a DFID contracted valuation provider to inform the fair value of the asset on DFID’s balance sheet. If an impairment of the assets value is required Annually Managed Expenditure (AME) budget will be required to cover the cost. AME will be forecast at either the Main or Supplementary Estimates in conjunction with advice from Financial and Accounting Department, and PSD will provide FCPD with relevant information to support accurate AME budgeting.
4. There are no foreseeable contingent liabilities associated with this listed product programme. MOBILIST has no tolerance for fund strategies that involve leverage or borrowings, and this is one (of several) guiding principle that inform MIC decision-making.
What is the assessment of financial risk and fraud?
1. The financial risk and risk of fraud at the level of the listed product investment is Major. The Fund Manager will need to operate procedures to mitigate these risks and to put in place due diligence procedures and checks for financial management and fiduciary risk that meet DFID’s standards and norms. The credibility of the promoter, the governance as well as financial and accounting systems of investee companies will be the subject of close due diligence by the Fund Manager; reviewed by the Investment Committee prior to approving each investment. The Fund Manager may have representation on the Board of the investee companies and where this is the case, all significant transactions will be monitored through this mechanism.
2. All directly procured contractors will be bound by DFID wider government operating procedures, and beholden to regulations on reporting any suspicion of financial misconduct. The TA Facility will be contracted using DFID’s high value tender procedure which includes due diligence on bidders through PCD and sets out DFID’s requirements with regards to downstream delivery and risk management where sub-contractors are involved. Where DFID procures supplementary advisory services via the crown commercial services frameworks, those suppliers will have already been government vetted (though will not have full DFID T&Cs).
3. As in all programmes, a zero-tolerance approach is taken to fraud and corruption. MOBILIST will be subject to regular review as part of DFID’s Annual Review process and where possible may be independently reviewed by the Internal Audit Department. Implementing partners may be subject to a formal DFID audit assessment if deemed appropriate.
Fiduciary and Corruption Risks:
The vehicle and its manager will be obligated under the investment agreement with DFID to ensure the fund carries out relevant integrity and ESG due diligence on all the investments it makes (including both reputational risks and compliance with sanctions lists). The ESG due diligence process that is used will also be expected to comply with anti-corruption guidelines and includes assessment of ESG systems in place within investee assets that make up the vehicle. DFID will also require the manager to make reference calls, and obtain detailed due diligence questionnaires from product sponsors, and review co-investors in investee funds who hold more than 5% of the product. DFID expectations with regard to compliance and due diligence will be set out in the EOI and RFP phases, and the vehicle and its managers procedures for doing this will be assessed during the EOI and RFP phases, and again prior to making the investment.

## Management Case

Key risks and risk mitigation approach
The overall risk rating for the proposed facility is Major. Key risks mentioned and scored below.

Risk	Gross Risk	Mitigation Measure	Net Risk	DFID appetite
Reputational: DFID participation in investment models which have underlying assets features counterparty risk as our other investment vehicles do – counter party risk exists at several levels including: Product Manager; co-investors in product; investee companies/assets that the vehicle invested in and co-investors at the investee level.	P: Possible / I: Major	Mitigate: RFP processes will set out compliance requirements based on best in class investor standards and including vetting of counterparties. DFID will undertake relevant due diligence on each products’ final legal structure, managing agent, systems and procedures prior to making any investments to ensure compliance can be achieved. Once listed products will also be subject to usual market level compliance activities/checks. / Treat: Where DFID invest in products, we will work with lawyers and market practice to build in adequate redress mechanisms based on the legal concept of fiduciary responsibility. Investment risk ultimately lies with the end investor, subject to redress through the regulatory and legal framework in place.	P: Rare / I: Moderate	Programme is in-line with usual DFID appetite.
Reputational: DFID is perceived as providing unjustified subsidies to private sector operations, thus supporting private sector profits through the inappropriate deployment of UK ODA public finance.	P: Possible / I: moderate	Mitigate: DFID will adhere to product selection criteria highlighted in appraisal and commercial cases to ensure only engaging in products with clear development purpose and additionality.	P: Possible / I: Moderate	Given innovative nature - TBC
Delivery: Duplication with existing instruments (CDC and PIDG in particular). Institutional investors, using these listed products may end up competing with CDC capital in emerging markets	P: Unlikely / I: Minor	Mitigate: CDC does not raise third party institutional capital and DFI’s face little competition in emerging markets from mainstream institutional portfolio investment through listed products. DFID team will continue to collaborate with CDC on their mobilisation strategy to ensure synergies and avoid duplication.	P: Rare / I: Minor	Programme is in-line with usual DFID appetite
Delivery: Investment products do not achieve impact targeted.	P: Possible / I: Major	Mitigate: Product selection process, diligence on final agreement, and investment agreement will ensure product is set up to drive impact and performance benchmarks. Impact will be measured for each investment product against agreed benchmarks and tracked across the lifetime. Underperformance against benchmarks can result in corrective action by the Fund Manager. Ultimately the most practicable sanction available to the investor is divestment (exit), or if possible, the replacement of the fund manager or revisions to the investment agreement.	P: Possible / I: Moderate	Programme is in-line with usual DFID appetite
Reputational: ODA-eligibility - ODA rules on development capital are still not settled. DFID confident that ODA eligible under ODA instrument rules, however, there is still a small residual risk that OECD disagrees with UK interpretation or tightens definition in some way that excludes UK approach.	P: Unlikely / I: Major	Mitigate: We worked closely with FCPD and HMT colleagues to check ODA classification rules, and will continue to check how ODA rules apply as we define each new product area/ investment we work in. DFID is also closely engaged in DAC process to modernise ODA rules and will ensure DFID application of ODA rules in these cases is fully socialised and properly considered as the DAC continues with its ODA modernisation work.	P: Unlikely / I: Minor	Given innovative nature of the programme
Context: Capital markets in some emerging and frontier markets do not have the required level of sophistication to attract and properly manage the risk associated to incoming capital flows.	P: Possible / I: Minor	Mitigate: The volume of capital mobilised is expected to be relatively small. The listed products will primarily address investment products which will most likely include mix of assets from different geography and sectors. In addition, the capacity of building a successful track record for products may prove a powerful incentive for DFID to advocate and support capital market reforms in partner countries in Emerging and Frontier markets.	P: Possible / I: Minor	Given innovative nature of the programme - TBC
Context: Frontier markets are highly influenced by macroeconomic, political risks, and climate risks. Such risks erode investor interest to launch new products that DFID has provided TA for, or negatively impact value of a DFID capital investment. Likely that some many of the products will have some geographic diversification to reduce impact if risk materialises.	P: Possible / I: Moderate	Mitigate: Portfolio of TA projects helps diversify risk; selection of investments and TA projects will consider likelihood and impact of contextual risks occurring on new product launching to decide case by case whether to proceed with that product/TA. / DFID has conducted significant research analysing emerging and frontier market risks at a country level. / Accept risk in investments: Purpose of MOBILIST is to demonstrate that difficult markets can present a risk-adjusted return, as part of a portfolio alongside developed market investment opportunities is critical to the success of this initiative.	P: Possible / I: Moderate	Given innovative nature of the programme - TBC
Financial risk: there is an investment risk that the returns are below (or above) expectations, and over the medium term, could translate into capital erosion through currency fluctuations, underperformance, default or systemic market effects, such as a sharp negative turn in investor sentiment towards emerging markets.	P: Possible / I: Major	Investment and risk mitigation framework and policies as per best in class investors. Financial risks include macro-economic and market conditions worsen; demand for investment products is lower than expected; risks of fraud and money-laundering. These are similar risks faced by all DFID’s development capital programmes.	P: Possible / I: Moderate	Given innovative nature of the programme - TBC
Delivery: Minimum subsidy - for each investment supported through MOBILIST, the need for concessionality requires careful evaluation of the risks and market dynamics.	P: Possible / I: Moderate	Mitigate: MOBILIST does not take as its starting point, concessionality or subsidy. Its deployment would require appraisal and sign-off from the MIC. DFID will work with CDC and investment experts to define if and how any concessional support could be deployed in support of market building and tactically. We would note that potentially no concessionality is required and simply signalling willingness by DFID to commit through an investment product is enough to catalyse private finance. Conversely, we recognise that government participation is most often associated with concessionality. We will not engage with the market on the basis that concessionality is on offer, nor will concessionality feature within project and competition documentation.	P: Possible / I: Minor	Programme is in-line with usual DFID appetite
Operational: Given specialist nature of products there is risk changes to DFID programme team results in team not having relevant skills and experience to (i) run quality RFP process leaving DFID open to challenge from bidders, or (ii) to undertake the commercial due diligence and structuring required for investments leading to poor investments/fiduciary risk.	P: Possible / I: Severe	Mitigate: Programme Team will be allocated a strong commercial advisor to work with the team day to day to ensure a robust RFP process is delivered as planned. Programme Team has also identified appropriate sourcing routes through which to secure required quality commercial, financial and legal advice required to support the process. Internal DFID review processes (that engage commercial, finance, legal expertise within DFID) will help pre-identify issues and sense check product design. Protection of resource will be managed by Head of PSD.	P: Rare / I: Severe	Programme is in-line with usual DFID appetite
Delivery: It is possible that DFID will receive no appropriate proposals from fund managers during the RFP process for new products, or only one appropriate proposal. Best case this may result in a time delay, worst case programme timetable of investments proves unfeasible at this time (purpose of MOBILIST to test this).	P: Possible / I: Major	Mitigate: The actual product options and timing would become evident as DFID works in collaboration with investors and in response to market conditions and investor demand. DFID has carried out early market engagement and has identified interested actors. As part of sourcing strategy DFID may choose to run a full market engagement event prior to issuing the EOI. / Treat/Accept: In this case DFID should engage directly with the invited bidders to obtain feedback from bidders to determine if DFID should revise and reissue, accepting associated programme delays. DFID would structure RFP to allow assessment of single product on its own merits if appropriate. If still no appetite– MOBILIST will adapt/close.	P: Possible / I: Minor	Given innovative nature of the programme - TBC
Delivery: If there are a lack of co-investors DFID might be required to act as anchor investor in a first private close in order to enable the vehicle to start building portfolio and track record. Even then, we envisage DFID to be one of several investors. If there is difficulty in getting interest from investors in an IPO, then DFID made the investment on its own the risk is that it could find itself negotiating its exit with several other private investors. There are HMT rules around majority ownership of private vehicles by government, covered under ‘Non-Departmental Public Body’ (NDPB) rules.	P: Possible / I: Moderate	Mitigation: There is zero appetite for NDPB, and legal advice will be secured to confirm this will not apply, even in a scenario where this delivery risk arises. Where a private close stage is needed DFID would ensure structure does not result in a NDPB classification. While identifying a co-anchor investor would reduce the risk of majority ownership, it does not necessarily negate control issues, and the approach could significantly increase the execution risk of the project; i.e. finding a co-anchor investor could add significant delays in the private launch of the vehicle. DFID will seek advice from Treasury spending team if there is any uncertainty over how the guidelines apply to a proposed investment opportunity.	P: Possible / I: Minor	Given innovative nature of the programme - TBC
Delivery: Investor interest may be there but in smaller quantities than envisioned and not be sufficient to immediately enable an IPO (Note: the duration of DFID’s investment is expected to be less than 5 years, based on the premise that DFID’s involvement is to help take the product to a listing (which by definition implies the crowding in of private investors) and thereafter to seek a managed exit).	P: Possible / I: Major	Mitigation: Robust upfront analysis of opportunity. EOI/RFP should be flexible enough to allow fund managers to design vehicle and portfolio mix likely to attract investors and will allow time for engagement between fund manager and listing agents and the LSEG (or local exchanges) to ensure vehicle is structured in such a way as to find sufficient investor demand; DFID will consider providing concessional capital to reduce risk of vehicle and improve risk-return profile relevant to product area; we will consider local listing on one of the more developed capital markets in Africa (Indonesia, South Africa, Nigeria, Kenya) while working towards a listing on the LSEG in the medium to long term.	P: Possible / I: Major	Given innovative nature of the programme - TBC
Context: It is possible that there is a significant change in the market between DFID’s anchor investment and intended IPO date such that the vehicle fails to launch as a listed product and meaning DFID is invested in a private asset.	P: Possible / I: Severe	Treat: Relevant exit strategies will be considered on a product by product basis both prior to EOI/RFP and prior to making any pre-IPO investment. They may include options to instruct the fund manager to liquidate the portfolio, but DFID needs to accept risk that it may need to hold the investment as a private asset for a period of time. Quantifying exactly how long this could be is difficult and determined by market externalities, but most likely it would be measured in months, (and not years).	P: Possible / I: Major	Programme is in-line with usual DFID appetite
Context: Lack of Deals – whilst there exist assets available both in debt and equity, the more restrictive the criteria (e.g. SDG aligned or Paris Treaty compliant) the harder to put together a portfolio of assets. Should market move toward local currency financing for infrastructure – vehicle may need to consider moving away from dollar only strategy.	P: Possible / I: Major	Mitigate: As part of RFP and commercial negotiations the bidder will conduct extensive investor engagement to quantify risk and propose mitigation strategy as part of the structure proposal. / In the short term, changes to market appetite present a range of risks, none less so than those that coincide with preparations for an IPO or fund-raising rounds. Strategically however, local currency financing and share class is a desirable, not something to be mitigated against.	P: Possible / I: Major	Programme is in-line with usual DFID appetite

Who will be responsible for Delivery?
DFID Private Sector Department will be responsible for delivery of HMG contribution to MOBILIST.
Investment decision making
1. The investment decision making process is governed by the MIC, chaired at Director level, and attended (at full member level) by i) Director EDI; ii) Head of PSD; iii) Programme SRO; DFID Commercial Delivery team lead; DFID PCD nominated lead. All investment decisions will be subject to discussion and agreement by this Committee, with final approval at Director level. Other DFID and HMG teams will be invited to attend as observers or full members as the need arises.
  [note] PSD Department Head is substitute, supported by MOBILIST SRO.
2. The MIC is responsible for ensuring that there is specific DFID appetite for each investment against identified risks and any decisions taken will require sign-off at Director-level.
3. Ongoing commercial, legal and investment expertise will be needed to support MOBILIST as and when required, and to support decision making by the MIC. For example, a team of relevant investment experts may be asked to provide analysis and recommendations in relation to potential investments and divestment decisions. This support is provided for under specific competition procurement(s) and/ or the TA component of MOBILIST.
4. At an operational level, MOBILIST is to be managed by the DFID PSD mobilisation team. Members of this team have considerable experience of implementing DFID’s investment programmes in PSD. They have worked with some of the leading financial institutions and Fund Managers, both in capacities as PSD team members and in previous private sector roles. As listed products are considered a strategic priority for UK and PSD mobilisation team, adequate staffing provisions have been made in the DFID PSD mobilisation team business plan.
5. The Senior Responsible Owner (SRO) will be a senior member of DFID PSD mobilisation team and will have overall responsibility for ensuring the delivery of the project and coherence with x-HMG priorities. The SRO is a former Fund Manager, responsible amongst other duties, for managing a series of large unit trusts with AUMs in excess of £1 billion for a leading international bank, and the Mobilisation team, and wider Private Sector Department, comprises a range of relevant professional skill sets that contributed to programme design, and will in future be engaged with programme implementation. The team’s nominated programme manager will be responsible for financial management of MOBILIST. This will include: ensuring compliance with corporate processes for establishing the programme; leading on financial management of the project; ensuring that DFID funds are used for the correct proposes; ensuring that progress and financial reports are submitted by the implementing partner(s) as set out in the contractual agreement; corporate reporting and supporting the SRO on project related communications. PCD will also allocate an experience commercial advisor who will have the capacity to provide day to day advice and support to structure and deliver the RFP process such that it is effective in selecting the best ideas and does not open DFID up to challenge, while supporting the team with wider sourcing considerations related to purchasing different TA services.
6. To maximise the impact and value for money of MOBILIST, the programme will include a minimum of 2 FTE (fill time equivalent).

Management Arrangements for the technical assistance component
1. The Technical Assistance component, budgeted at £13.6 million over 6 years, is expected to perform 4 distinct roles:
  1. Monitoring & Evaluation
  2. Learning
  3. Identification of product concepts
  4. Mobilisation as a policy agenda
2. The main delivery vehicle for the TA component is conceived of as a Technical Assistance Facility of facilities, which will be tendered for in Q1 2020, under an OJEU process. Facilities will play an important role in supporting delivery of MOBILIST objectives and will also work with DFID’s policy agenda on mobilisation to help develop PSD’s portfolio of mobilisation interventions as described in the Strategic Case. PSD will have an important role to play in identifying topics for detailed investigation and linking the programme to existing and emerging priorities.
3. Given the specialist nature of some of the product concepts e.g. the green covered bond route to market plan), it may be the case that a specialist TA intervention is required to bring that concept to listing. The TA component allows for this, as a separate consultancy on a call down basis under a framework agreement to be competitively tendered.
4. Overall responsibility for management and oversight of the TA component would rest with the SRO in the Mobilisation Team. The team will perform key operational oversight, maintain delivery plans and monitor risks and evaluation and also provide programme management support. Guidelines on the use of technical assistance would be developed and the team would monitor the use of this money.
Position	Department	Involvement
A1 Senior Adviser	PSD	SRO. Concept note and business case design. Commercial and management cases.
A2 Adviser	PSD	Lead on design, capitalisation and operation of UK Mobilisation Facility
A1 Team Leader / A2L/ B1	PSD / PSD	Concept note, business case design, strategic oversight and alignment to wider mobilisation strategy / Programme Manager

Expected phases of operation
1. Inception Phase (Nov 2019 – November 2020): Competition process commences including EoI; procurement of TA in relation to specific products and/ or facility.
2. Procurement Phase (Jan – November 2020): For initial products - initiations of tendering process, Issue RFP, Evaluation of bids
3. Mobilisation (June – Sept 2020): Negotiations of contributions agreements, finalisation on PPM Agreement of Investment Mandate, legal advice and approvals from listed products governance committee for investing in the listed products. Note that implementation across products likely to vary until resources are scaled.
4. Implementation (November 2020 – Mar 2025): Setting up of a MOBILIST Investment Committee, Capital Raising, Review of pipeline, deployment of funds
5. HMG Exit As stakes in investees are sold; realisations will be routed back to investors in the same proportion as their investments (2023-2025)
How progress and results will be monitored, measured and evaluated:
1. Progress will be monitored against the theory of change and log frame to be developed at least six months in advance of the first Annual Review. In addition, a product specific results-based M&E Framework will be designed in consultation with the Fund Manager, TA Facility manager, DFID PSD. The development work, in conjunction with DFID evaluation advisers has already commenced given the expected timeframe for contracting the TA Manager would risk the framework not being in place in H2 2020.
2. Ex-ante development impact will be assessed against a clear set of indicators with accompanying targets for the purpose of product selection. These will cover three types of metrics:
- Market building metrics will review the extent to which the product could potentially lay the foundations for future market approaches (e.g. developing transparent pricing, governance systems and demonstrating appropriate return)
- Portfolio metrics (e.g. jobs created, revenues, taxes transferred, third party capital mobilised); and
- Sector specific metrics depending on the focal sector for the product (e.g. power production, total sales, access to improved infrastructure etc.).
1. A narrative case will be made outlining the supporting argument and providing the evidence to substantiate the rationale and intended impacts of the investment (both on return, development impact, ESG and demonstrating how it will bridge the SDG financing gap).
  [note] DFID India NIIF has developed an ESG tracker that feeds into one log frame indicator, and this is a useful model that the team are considering in relation to specific products supported under MOBILIST.
2. The identified metrics will continue to be tracked during the implementation phase (i.e. ex post) and an assessment of success (defined as the demonstration of viability of the products to achieve both listing and SDG impacts) will be made against the agreed targets set on an annual basis.
3. The TA component will work with products to develop these in full logical frameworks for approval. The framework will capture results associated with both commercial and development returns, and the TA Facility Manager(s) will monitor and report on relevant metrics both to the programme team and (quarterly) to the MOBILIST Investment Committee.
4. However, in the short term, DFID will need to support the first 2 competitions assessments in-house (with TA support). In lieu of a bespoke framework for assessing development impact, MOBILIST will utilise the IMPs own impact assessment framework (see Fig 5). In accordance with the framework (and as a minimum benchmark) the assessment criteria by which the MOBILIST Investment Committee will select products would require an “investor contribution” score of ‘3’ or greater, and an “impact on the underlying assets” rating of ‘B.
  [note] This static scoring methodology is not a perfect fit for MOBILIST (because the level of development impact is intended to rise over the life of the programme as increasingly more sophisticated products are catalysed), but the IMP assessment framework provides a level of assurance that is appropriate until the TA Facility finalises the programmes own M&E Framework.
Table 4: M&E Roles & Responsibilities:
The SRO will develop an evaluation approach during the inception phase of the project that will focus on evaluating the innovative approach being taken forward and will ensure that this presented to the MOBILIST Investment Committee for approval by February 2020
The TA component will provide overall monitoring of the product result frameworks (including data quality control) and will agree on the split in data collection with the fund managers
DFID will ensure that M&E capacity exists within the TA component to oversee this during the tender process
DFID will review monitoring data on an annual basis through the Annual Review process.

Outcome to Impact level
1. Results and progress will be monitored through DFID annual review process (led by the DFID SRO). An independent mid-term review of progress will be conducted in 2022 and an independent end-of-project review in 2025. If the mid-term review reveals that the programme is not meeting the targets then necessary adjustments will be made, and in extreme cases funding will curtailed or stopped subject to compliance with relevant agreements. Appropriate clauses will be built into the contribution agreement.
2. Annual reviews will monitor progress, and follow-up against log frame targets and milestones (comprising a selection of the indicators in the results framework). The technical assistance Facility will include a strong monitoring, evaluation and learning component that will generate broader lessons on the effectiveness and impact.
Input to Output level
1. A detailed management information system will be put in place to track the status and contribution of each product. In addition, regular monitoring of the projects and partner institutions will be carried out to ensure adherence to the minimum benchmarks of the ESG framework as well as agreed targets.
2. To minimise transaction costs the monitoring and evaluation mechanisms will be agreed between all parties to avoid additional layers of reporting and evaluation where this is possible, and consistent with the programme’s objectives to demonstrate the commercial replicability of the approaches showcased. This will include standardisation of reports, frameworks, periodicity of data collection and reporting. Given the nature of the products and likely exposure that the programme seeks, it is inevitable that the reporting burden will be higher than it would otherwise be.
3. If this programme is selected as one of the samples for listed product level evaluation, we will work with the products Evaluation and Learning contractor (contracted through the TA facility) to implement this evaluation.

What is the internal DFID governance structure for making the investments stop/go decisions or authorising decision to invest e.g. Financial Transactions Steering Board (FTSB)?
1. MOBILIST will be overseen by a governance committee, known as the MOBILIST Investment Committee (MIC), comprising the implementation and control functions within DFID, e.g. DFID’s PSD, Finance, Commercial & Procurement Department (FCPD), as well as expertise and control stakeholders from other HMG Departments, e.g. HMT’s Financial Services Group. The MIC is also able to call upon external expert advice as required under the TA facility.
2. DFID’s Financial Transactions Steering Board (FTSB) are invited to attend MIC as full members and will review investment proposals on their forward look. The Finance Director needs to sign agreements and sign off on exits (as far as DFID controls timing of exits (in addition to the relevant Director-level Chair of MIC).
3. The SRO is responsible for day to day programme management and control.
What are the exit scenarios, indicators and strategies (i.e. when would/ could we divest from fund) e.g. First Close if does not attract other investors; or when an IPO what might be indicators of success and time for DFID to sell position?
1. MOBILIST will have in place strong disciplines to signal and execute disengagement in a timely, clear and commercially sensible process. Investment and divestment decisions will be subject to review and approval by the MOBILIST Investment Committee, with sign-off at Director level.
2. The desirable exit strategy for DFID from any investment is the public placements of its holding or a portion of its holding on the exchange where the product is listed. The buyer would likely be an institutional investor or combination of investors. The likely proceeds would be fairly-well forecast, given the ability to mark to market.
3. If divestment through public market sales is not practicable for reasons foremost amongst which could be the failure to list, then as an investor DFID does have options to exit its investment in an orderly fashion. These include private placements or the natural end of portfolio assets’ lives (in which case, capital proceeds would be returned to DFID as the shareholder rather than being re-cycled into new assets).
4. Should DFID wish to divest urgently i.e. a disorderly exit, private placement would likely be only achieved at a significant discount to market value, and we could expect to record a capital loss, the size of which is difficult to forecast.
5. As a further divestment strategy, DFID could theoretically transfer the asset to CDC, but this would require further consideration, and HMT approval would be required. There is precedence for this. More likely, we would trigger exit clauses negotiated in the investor agreement and divest from the investment outright.
Annexes

Annex A: DFID research “Frontier Markets Mobilisation: Facility Structure and Assets Study”, Sept 2018
Annex A (2) “Frontier Markets Mobilisation: Facility Structure and Assets Study Annex”
Annex B: DFID Mobilisation Phase II: Roadmap for African Infrastructure Fund
Annex C: Technical Assistance for Issuance of Frontier and Emerging Market Green Bonds
Annex D: Indicative Theory of Change for a Listed Infrastructure product
Annex E: DRAFT Log Frame

Annex D – Indicative Theory of Change for a Listed Infrastructure product
The problem is...	Many emerging markets suffer from a lack of both public and private investment. This limits productivity, and countries remain stuck in a low productivity-low investment trap. / Aid agencies and multilateral development banks (MDBs) intervene on the side of expanding public investments. DFIs seek to play that role for the private sector. Mobilisation seeks to play this role in relation to the large pools of institutional capital accumulated in developed economies and controlled by money managers in handful of international financial centres, including the City of London. / Infrastructure projects tend to be expensive and high risk. There is a huge need as well as opportunity in terms of establishing new infrastructure. However, there is a shortage of risk capital. In developed stable economies capital markets are able to match risk return preferences of investors. However, in less mature economies, both real and perceived risks of infrastructure projects are higher. Despite the recent spate of reforms and its consistently high growth, Frontier and Emerging Markets continue to be perceived as a high-risk country for infrastructure investments. This perception of Frontier and Emerging Markets even though there are significant prospects of business gains is significantly due to lack of information and understanding of the market. These market failures that need to be addressed.
Which has the following consequences	Higher private investment in poor economies increases the rate of capital accumulation. This is not just financial capital, but critically includes human capital, physical capital and institutional capital. / Raising productivity is the most effective approach to sustainable poverty reduction, because people cannot consume more than the economy can produce, unless they remain dependent on aid. / Investment and capital accumulation serve to increase labour productivity, which in turn leads to higher wages and reduces poverty. / Economic growth, jobs, livelihoods, and environmental improvements are constrained by lack of reliable and accessible, resilient infrastructure.
However, if we do (activities, inputs)	For this reason, a mobilisation strategy, and deployment of investment products, is seeking to increase private investment and capital formation in the countries to which the underlying assets relate. The need for public intervention arises because without it these countries will not see enough capital formation. This is primarily attributable to two basic facts: risks, perceived or real, are too high and/or expected returns are too low and this keeps private capital away. / A mobilisation programme can be at both ends, helping reduce risk, or increase expected returns in a bid to try and attract more private capital. / There is potentially an element of subsidy, explicit or implicit, depending on how government seeks to mitigate risks. Without this risk mitigation, that private investment would be suboptimal and many of the positive social externalities from private investment - such as the creation of knowledge about production possibilities, learning by doing, the formation of economic networks and supply of intermediate goods, increase in the quality of human capital, both a reduction in the cost of an increase in the demand for new activities - would not come about, because narrow considerations of private profit are not able to capture these. / There is then a powerful public economics case for providing subsidies for private investment, even though this sometimes generates rents for the private sector. That risk is minor compared to the risk of insufficient levels of investment in poor economies. / Promote and contribute a government-backed investment fund that pools capital, where risk is shared in selected sectors. / Procure a Fund Manager with credibility and expertise to add value to promising investments. / Support the Fund with a TA component that aids project preparation, financial structuring and addresses policy barriers to mitigate cost or risk to investors.
Then we expect (outputs)	Private investors to co-invest in the products, leading to additional projects being successfully financed; / Greater knowledge and awareness of market opportunities thereby creating value for investors; / Increase pipeline of projects and reduced policy barriers and risk in selected sectors.
Which should deliver (outcomes)	A model public infrastructure fund that demonstrates success (attractive risk-adjusted returns) over the medium and longer term
So that (impact)	The developmental impact derived from achieving greater private sector capital flows at scale, goes well beyond the amounts captured by the narrow financial measures of mobilisation more typically thought of as in terms of ‘leverage ratios.’ / Specifically, that the target countries for the mobilised investment product suffer from underinvestment and are often stuck in a low productivity-low investment-low savings trap, from which external support in the form of private investment can help rescue them by i) increasing the stock of capital, ii) making labour more productive and iii) providing the kind of risk absorbing long-term capital they lack. / The raison d'être of the mobilisation approach is therefore to aid capital formation. / There are other benefits from deepening capital markets and more developed financial infrastructure in countries. Often this is termed “financial efficiency.” It is important that financial efficiency is not defined only in its' own terms (e.g. via growth of financial assets or reduction of financial inter-mediation costs), even though these variables may play a positive role, but that the key criterion for measuring financial efficiency is its' contribution to mitigating the high welfare costs that financial inefficiency imposes upon the poor in particular, and its contribution in raising productivity to deliver sustainable poverty reduction. / Intermediating between large capital pools in developed economies and emerging market assets is a form of financial efficiency, creating a global public good that is indirect and cannot be captured quantitatively. The ‘good’ comprises i) reducing information asymmetry, ii) demonstration effects, iii) risk mitigation through sound due diligence, iv) reducing risks through the provision of sound capital, v) bringing institutional memory and skills to bear in aiding investee companies, and vi) through leveraging its sterling reputation. / Finally, from a UK national interest perspective, it should be noted that providing the global public good of financial stability and efficiency provides growing markets for UK exporters and increasing profitable opportunities for UK investors. Greater prosperity in these countries also reduces potential political instability there and greater pressure for migration to the UK, both of which could have negative effects for the UK. More capital is attracted to the infrastructure sector, in order to finance more projects and improve GDP, livelihoods and the environment. / London’s position as the partner of choice for raising finance for infrastructure is strengthened.
[note] In CDC’s words, for example, “growth and poverty reduction come from raising the productivity of ordinary people, which is what good businesses do. They bring together people at scale and specialization, making them dramatically more productive than they would be on their own.”