End of Phase II Evaluation of the IGC:
Synthesis Report
Contents

Tables

Text Boxes

Figures

Executive Summary
The International Growth Centre (IGC) is a multi-country research and policy influencing initiative, launched in 2008 and funded by DFID. Phase II began in April 2013 and was due to end in September 2017. The contract was extended several times, and is now scheduled to end in September 2019, when Phase III will be launched. The IGC’s mission is "to promote sustainable growth in developing countries by providing demand led policy advice based on frontier research". Through the provision of frontier academic research, the IGC aims to encourage good policymaking, which in turn should lead to stronger and sustainable growth. The IGC is largely funded by DFID but is independent in its engagement with policymakers and in delivering the programme's objectives. The IGC has an unusual and distinctive business model, which involves: access to “best in class” researchers working on economic growth, and a broad but focused research programme; a sustained “local” presence through its Country Offices, which allow it to establish long-term relationships with policymakers and to commission research that responds to the needs of these policymakers.
GDSI International, also referred to as the Independent Evaluation Board (IEB) was appointed by DFID to undertake an evaluation of Phase I and Phase II of the IGC. This report represents the end of Phase II evaluation.
The Management Committee for the evaluation comprised:
- Stephen Yeo, who had overall responsibility as well as responsibility for research programme and research uptake issues.
- Dena Lomofsky, who was responsible for methodology, the country programme, theory of change, and monitoring, adaptation and learning
- Pauric Brophy, who was responsible for contractual issues and team recruitment
The target audience for the evaluation findings are DFID, the IGC and the international community on policy influence. The ToR identified key intended uses of the evaluation, which are as follows:
- For the IGC and DFID to strengthen and improve the on-going performance of the IGC
- To inform DFID and the international community on policy influence, and make a significant contribution to the evidence base and academic debate surrounding the impact of research on policy making and the impact of growth-related research.
Since the end-term evaluation is taking place as Phase III of the IGC is being launched, another intended use was added in the inception phase: that the findings and recommendations of the evaluation should inform the design of Phase III.
This report concludes the evaluation of Phase II of the IGC, and builds on the mid-term review of the IGC, and various other evaluative pieces that have been produced by the IEB throughout Phase II.
The mid-term review was conducted in 2016 and several interim reports were produced in 2018 and 2019. These interim reports, as well as the reports from the mid-term review were treated as a documentary source in this evaluation. The data collected for the mid-term review was focused on the following:
- Refining the theory of change of the IGC and understanding the business model and the pathways of change and key assumptions.
- Examining the IGC's work on taxation in three countries (Pakistan, Rwanda and Uganda), tracing the contribution of a number of IGC activities to the policy environment and unpacking the processes by which policy influence has been achieved. This was done to provide a focus for the investigation of policy influence.
- Our initial explorations suggested that the IGC's Small Projects Facility (SPF) played an important role in these activities. We therefore widened the scope of our enquiries to include an examination of SPFs as well. A typology of the SPF was produced and survey was conducted with country programme teams about their SPFs. This was then analysed to understand how this funding mechanism complemented the research programme in terms of policy influence. The primary instrument for gathering data about SPFs was a questionnaire distributed to each Country Team, supplemented by a review of the IGC activities database and interviews with the IGC Country Teams during Growth Week and the subsequent country visits.
The end term evaluation of Phase 2 began with the approval of the evaluation framework in April 2019, which outlined the scope of the evaluation, key evaluation questions and methods. Various pieces of work were produced, including:
- A review of the research programme of the IGC (discussed in Section 4)
- Four country case studies and contribution stories of flagship projects in these countries and a review of the global influencing of the IGC with a focus on the Cities that Work initiative. (discussed in Section 5)
- A review of the monitoring, evaluation and learning of the IGC, cross-cutting issues and the use made of the Theory of Change (discussed in Sections 6, 7, and 8
DFID and the IGC have been closely involved in all aspects of the evaluation:
- An inception report in the form of an evaluation framework was submitted to DFID and the IGC for comment and feedback. Feedback was incorporated into the final framework.
- All instruments were approved by the IGC and DFID before going into field
- Verbal feedback sessions were held at the end of country visits with the IGC country team, and their feedback incorporated into the country case study reports.
- The first and second drafts of the report were submitted both the IGC and DFID for review and feedback was incorporated into the subsequent version of the report.
A theory-based evaluation has been conducted with an attempt to identify and understand the outcomes of the IGC and how they were achieved in Phase II. The evaluation also has a learning focus, to identify lessons that can inform the implementation of Phase III of the IGC. Contribution analysis has been applied to the evaluation of the flagship projects of the IGC. Thematic analysis was conducted of ‘less successful projects’ to identify any trends in why projects may not achieve the intended impact. The methodology for the end-of-project evaluation involved semi-structured interviews with a range of stakeholders (77 interviews), primary data collection and secondary data collection. The list of instruments used in the evaluation is included in the methodology and instruments section, and the instruments themselves are appended.
Thematic analysis and contribution analysis have been the primary data analysis methods used for the evaluation. Four case studies were produced of flagship cases that were identified as having a high impact, and contribution analysis was applied to these. The draft reports were reviewed and validated by the IGC and DFID, and the comments have been incorporated into this second draft.
Borrowing terminology from Outcome Harvesting, we define Substantiators as “individuals who are independent of the intervention (third party) but knowledgeable about one or more of the outcomes and the change agent’s contribution”. In order to improve triangulation, we gave high priority to identifying and interviewing two sets of substantiators: i) at the country level, those familiar with the activities of the IGC country office; ii) at the project level, those familiar with the flagship projects we examined. We adopted a snowball approach to identifying Substantiators, starting for example with the PIs of flagship projects in order to identify other researchers and other funders who might have been working on the same topic as well as knowledgeable individuals who are well acquainted with the policy issue addressed by the flagship project and the actors involved, but not involved in the IGC project.
Our evaluation of Phase II evaluation aimed to: i) assess the extent to which the IGC's work has influenced the adoption and implementation of credible growth policies in developing countries; ii) understand the mechanisms by which the IGC exerts this influence on policy; iii) identify the contextual factors that have contributed to this influence and iv) examine the effectiveness of the IGC as a model for achieving policy influence.
Section 3 examines how the IGC has developed and used its Theory of Change (ToC) and whether the ToC is adequate, given the goals the IGC has pursued and the activities it has undertaken in Phase II. The IGC engages in three intersecting work streams: the creation of knowledge, the application of knowledge to policy, and the communication of knowledge. The ToC developed as part of the mid-term evaluation was framed around these three work streams, and involved five strategic pathways. These pathways proved useful in analysing the contribution stories gathered as part of our mid-term review, and three (SP1, SP3 and SP5) turned out to be important in practice. Our end-term evaluation identified a number of weaknesses in the ToC: in particular it gave too little attention to the role of the Principal Investigator (PI) relative to the Country Office; and to the issues of policy implementation, mainstreaming and scaling up, and the sustainability of policy changes. The global influencing pathway (SP5) needs to be extended and refined to better reflect the experiences of the new Cities that Work (CtW) initiative. Overall, ToCs did not play an important role in the IGC's operations during Phase I, but their role has expanded in Phase II. The itself has developed its own version of the ToC, which has played a role in the IGC's plans for the future development of its impact indicators.
Section 4 analyses the extent to which the projects funded through the IGC’s Commissioning Boards in Phase II represented an effective research strategy for achieving the objectives of the IGC; and whether this strategy has been successful in generating and disseminating world class, policy-oriented research undertaken on developing country growth issues. We first examined how the IGC defined its Research Strategy, and then how it implemented this strategy. Overall, the strategy was clearly set out in a 2013 document, the four Evidence Papers produced in 2014 and the research priorities that were made available as part of the Calls for research proposals considered by the Commissioning Boards. These priorities were clear, but stated in very broad terms. We assessed the process by which the IGC commissioned research and implemented these research projects in Phase II, focusing on the processes put into place to ensure that IGC funded research was consistent with the IGC's core objectives. Overall, the Research Strategy made an effective contribution to achieving the goals of the IGC, in two important respects: it resulted in a more effective integration of the IGC's Research Programme and Country Programme, which was one of the key objectives of the IGC going into Phase II; and it did result in the creation of new knowledge about growth in low income countries which was published in leading peer reviewed journals. We also benchmarked the IGC's commissioning process against international best practice among research funders. We found that these processes were consistent with international best practice in most respects, and where there were departures, they could be justified on pragmatic grounds. We did, however, identify some areas where the processes can be improved for both commissioning and implementation. We also examined how the IGC oversaw and managed the implementation of its research projects in Phase II. We examine the processes and procedures for implementing projects from the point of project approval to project completion and how far this system succeeds in its aims and what particular challenges it faces. One of the questions we examine is whether the IGC devoted enough attention to monitoring scientific quality, and whether its procedures for monitoring this quality were applied proportionately across the IGC's different funding modalities, and consistently across the IGC's portfolio of projects. Overall, we found that the IGC's implementation system, while complex, was effective, well managed and appropriately resourced; and fit for purpose. It is broadly consistent with best practice among funding agencies, but the IGC does not as a matter of routine prepare a "project completion report" for all projects, "successful" or "unsuccessful". This is common practice among funding agencies. The decentralized structure of the IGC, with a central hub and a large number of country offices, creates particular challenges for the IGC in implementing its projects, in particular in ensuring their scientific quality across Country Offices. We make recommendations that address both this issue.
Section 5 assesses the IGC’s effectiveness as a “policy influencer”. Section 5.1 discusses the challenges and complexities involved in defining and measuring policy influence. Research can have influence by affecting decisions to adopt (or not adopt) particular policies, and the drafting of legislation and regulations to implement these policies. Studies of policy influence have, however, highlighted additional forms of influence: expanding policy capacities, broadening policy horizons and affecting decision regimes. The IGC’s definition of impact is closer to the first, “instrumental” notion. Section 5.2 explores the extent to which has the IGC has established and implemented an effective strategy at the country level that has allowed the IGC to influence policies relevant to growth at the country level and has provided country-specific, evidence-based, and timely advice to answer policymakers' questions. We set out how the IGC has established its country influencing strategies, through the drafting of the Country Strategy Notes, which set out broad priorities, to the revisions to these “country” priorities as part of the preparations for each Call for research proposals. In implementing these strategies the Country Teams must take advantage of “policy windows” that can open (and close) unexpectedly: this places a strong emphasis on the ability of the Country Directors to build relationships with key senior policymakers and to use these relationships to identify and exploit the issues for which the policy window is open and to prepare to exploit those issues where windows are likely to open in the future. This involves a high degree of adaptive management. One way of evaluating this form of management is to focus on the systems in place for learning (about emerging opportunities for influence in the future and about the influencing techniques that have worked (and not worked) in the past). We study the IGC’s learning strategies in Section 6, where we note that the IGC Hub changed its method of interacting with the Country Teams during Phase II, switching to a cycle of quarterly meetings between the relevant Hub staff and the Country Teams. The format of these meetings and the tools provided to structure the discussions seem to have proved effective, in particular in ensuring that the Country Teams stayed focused on the opportunities for the IGC to have an impact on policy. These meetings also seem to have contributed to a shift in the institutional culture within the IGC during Phase II, in which the strong focus on research quality in Phase I was balanced by a concern with the achievement of policy impact and became a widely shared goal among staff in both the Hub and the Country Offices in Phase II. These interactions with the Hub encouraged the Country Teams to articulate their influencing strategies and to stay focused on achieving their influencing goals.
Section 5.2.3.1 gives an overview of the IGC’s influencing activities across the countries in which it worked in Phase II, while Section 5.2.3.2 focuses on the distribution of Level 3 and Level 4 impact cases across countries and across types of activities.
The assignment of impacts is carried out within the IGC’s four level system of impact classification, first introduced in 2012. Section 5.2.3.3 assesses the quality of the IGC’s impact measurement system, and concludes that the processes for determining impact levels are thoroughly documented; the procedures were followed, the decisions were in accordance with the definitions of impact levels, and there was evidence available from both IGC and non-IGC sources to support the IGC’s decisions. Overall, we conclude that the IGC has implemented its system of impact measurement in an appropriate manner, which allows the system to serve as an appropriate tool for monitoring impact and progress towards impact on an annual basis.
The IGC’s system of impact measurement is more than an annual monitoring tool: it plays a role om judging whether the IGC achieves its Logframe Outcome: “Credible growth policies and programmes implemented in developing countries”. The Outcome has two Indicators: the “number of changes to growth related policies (based on IGC research and advice), indicated by number of L4 impact cases” and the “number of partner and non-partner countries where ideas emanating from IGC programme have influenced policy discussions, indicated by L3 and L4 impact cases.”
Section 5.2.3.4 assesses whether this impact measurement system is also useful in assessing the IGC’s progress towards achieving its Outcome and Impact, which involve longer-term change. The current system of impact measurement is suitable as a measure of policy influence and impact for some kinds of policy changes, but less so for others. “Blocking” or reversing unwise policies is a policy change that the current system of impact measurement captures very well. The system does, however, fail to address four issues that are key to assessing the importance of a policy change over the long run: sustainability; implementation, mainstreaming and scaling up, the importance or magnitude of the policy change; and the extent to which the policy change can be attributed to the IGC. We discuss each of these issue in turn, using as examples some of the IGC projects we studied in our mid-term and end-term evaluations.
Section 5.2.4 discusses the factors that affect the IGCs ability to influence policy. This draws on our findings in the mid-term evaluation and the evidence gathered for this end-term evaluation, in particularly the analyses of particularly successful projects as well as the analysis of that did not achieve a Level 3 or Level 4 impact. We identify both internal and external factors that affect the policy uptake of the IGCs work.
Four main internal factors seem to have affected the success of the IGC in Phase II: the structural characteristics of the IGC; the management and capacity of the IGC; its policy engagement strategy and capability; and its research process and outputs. With respect to structural characteristics, the Country Programme of the IGC is a critical success factor, as is the reputation and credibility of the IGC; its association with respected local institutions as host organisations, and the mixture of tools and tactics it is able to deploy. With respect to management and capacity of the IGC, the IGC’s balanced emphasis on policy and research is important, as are the structure and management of the Country Teams, the IGC’s ability to learn and adapt (at both the Hub and country levels) and its timeliness. With respect to research process and outputs, Country Strategy Notes are important, as is the Country Team's mastery of the research to policy field and its ability to form partnerships. With respect to research process and outputs, the co-generation model of research plays an important role, and the ability to communicate research findings, the ability of the Country Offices to fund research projects of interest to their country, and the ability to tap the IGC’s research networks are important as well. Among the external factors, we found that state effectiveness, government receptivity to research evidence and the nature of the political economy of research in the country, and the policy community.
Section 5.3 examines the extent to which the IGC has established and implemented a strategy for influencing global discussions of policies relevant to growth in low income countries, and the influence it has had on global discussions of these policies. In Section 5.2.3.1 we focus on the IGC’s CtW initiative, which was launched in 2016/17, and in Section 5.2.3.2 we assess the IGC’s use of online dissemination channels. The IGC recognised that urbanisation was becoming an increasingly important issue in the developing world, and that an initiative with this thematic focus on cities would fill an important gap. The task of CtW was to work closely with policymakers to identify their questions, and help them find answers based on the relevant academic research. This was done by producing synthesis papers based on the existing stock of knowledge, including IGC research, and has expanded into a range of other outputs and activities including events, both at a national level and globally. CtW developed a very useful synthesis product, the policy toolkit, that enables a rapid response because it focuses on key issues such as affordable housing, that can be quickly adapted for the questions posed by various cities. The prerequisite for CtW's success is that it is part of the IGC and is able to leverage the IGC “brand” to quickly establish trusted relationships with senior policymakers; and is able to access the other parts of the IGC, namely the country programmes, the research network and stock of knowledge, and of course the IGC's management. The strong team and highly capable policy-oriented manager has been an important part of the success of CtW, as has its association with leading academics in the field. The model is replicable within the IGC and working thematically across country to achieve policy influence seems valuable, particularly if the goal is to influence the global discussion.
Section 6 examines the extent to which the IGC monitors its own performance and uses this monitoring information to learn lessons and adapt its research and policy influencing strategies at both country and Hub levels. In Section 6.1 we present and discuss the key components of the IGCs MEL system, and the progress that has been made in terms of MEL as a tool for accountability and learning.
In Section 6.2 examine the IGC’s accountability monitoring and reporting. The main focus of the IGC MEL system for Output 1 in the Logframe has been the implementation of an accountability reporting system for DFID, and now also to other funders. The mid-term evaluation found that the monitoring systems were fairly rudimentary and were not systematically implemented. There has been much effort at the IGC to address this, and data is now collected and stored more systematically. The main focus has been establishing the system for tracking and reporting on impact scores, which are the main means by which the IGC is evaluated by DFID. Key to this are the Project Influence Plan and the Project Influence Report, which allow the IGC MEL team to regularly validate and substantiate the impact scores.
Section 6.3 examines the IGC’s use of monitoring data to identify patterns and trends that can inform its decision making and strategy. In Section 6.3.1 we examine learning at the Hub level. The “drivers of impact” document that the IGC has recently produced is an excellent example of formal learning at the Hub. It provides a clear analysis of the factors that have contributed to the impact Level 3 and 4 scores: these factors can be used to inform the management and strategy of the IGC. In Section 6.3.2 we discuss learning at the country level. The MEL strategy does not seem to facilitate learning at a country level, and we find variation across Country Teams. In Section 6.3.3 we find that opportunities for cross-country learning have dwindled over Phase II. Growth Week offered an effective opportunity for interactions among Country Teams, but has not been held since 2016 and there is a dearth of other opportunities.
In Section 7 we assess the extent to which the IGC has integrated the economic empowerment of women and girls into its work as a cross-cutting issue.
Conclusions: Section 8 sets out our principal conclusions and summarizes our recommendations.
Overall, we conclude that the projects funded through the Commissioning Boards have represented an effective research strategy for achieving the IGC’s objectives. We also conclude that the IGC’s research strategy has been successful in creating new knowledge about the factors influencing growth in low income countries. During Phase II IGC has supported research projects whose outputs have not only been published in high impact scientific journals. In addition, we found that this research, while of high academic quality, also influences policy in the IGC’s partner countries. Our analysis of the IGC’s impact scores revealed that 26% of the projects funded by the Research Programme in Phase II achieved a Level 3 or Level 4 impact. This is lower than the rates for SPFs (48%) or projects funded by the Country Programme (42%) but still an impressive achievement for research published in leading academic journals.
We examined the IGC’s Country Programme and found that has established and implemented an effective country strategy that responds to the priorities and needs of its partner countries. The IGC’s COs and the relationships they develop with their policy counterparts are the IGC’s most important route for applying knowledge and for ensuring the relevance of the work it carries out. The importance of the Country Offices in generating impact is confirmed by a broader analysis of the IGC’s impact cases: over 60% of the Level 3 and Level 4 impact cases in Phase II were associated either with SPFs or research projects funded by the Country Programme.
The range of policy issues addressed by the IGC is very wide, but the projects we examined in depth in the mid-term and end-term reviews involved issues that are of first order importance to the countries concerned and that in the right circumstances, IGC research has the potential to bring enormous change to the development trajectories of developing countries. These included tax collection and government revenue, reforms to the management of the public sector in order to improve performance of civil servants; and measures to strengthen the agency responsible for encouraging foreign direct investment.
Some of the cases we studied have a huge potential impact on the economy of the country. The possible introduction of a flat tax in Rwanda was a clear example of a policy, which if introduced, would have had a large and adverse impact on macroeconomic stability in the country. Our estimates confirmed that the impact of introducing the tax would have been very large indeed.
We found that the IGC’s country strategy and the tools it has developed to monitor the success of this strategy provide an effective approach to tracking individual projects and useful tools for monitoring their impact on policy. As a result, it was straightforward to assess the impact of individual policies and to aggregate these individual impacts into indicators of impact at the country or IGC level. It was more difficult for us to assess, for a given country, whether these project level impacts, taken together, were achieving a “step change” in the overall set of policies relevant to growth. Achieving such a step change is an enormous challenge, but looking to the future, we believe that the IGC can and should be more ambitious in Phase III: it should aim to influence (and measure its influence) at this broader, system-wide level as well as at the level of individual projects. This will require changes in both its strategy and its MEL systems. In addition, the IGC’s current approach does not address issues that are key to assessing the long run importance even of changes in individual policies: these include sustainability, and implementation / mainstreaming. The IGC needs to adapt both its strategy and its MEL systems to take more account of these issues. Here there is a question about whether the IGC and its researchers feel comfortable in dealing with questions of implementation. If not, then the IGC may need to involve more experts from disciplines outside of economics such as public administration and political science, more interest and experience in guiding the implementation of policy ideas that have been generated by the IGC.
Influencing global discussions of policies relevant to growth in low income countries has been one of the IGC’s objectives throughout Phase II. In the initial stages of Phase II its influencing strategy involved focusing on a small number of policy issues where the IGC thought it had research expertise and a track record of policy influence. There were “influencing” activities around these themes, but these were on a relatively small scale and seem to have had a limited impact. This changed with the launch of the Cities that Work (CtW) initiative, which has developed an influencing strategy that uses (among other things) synthesis products to bridge the communications gap between researchers and policy makers. CtW departs somewhat from the IGC’s “hub and country office model” by relying on “in house” researchers to produce synthesis products. This initiative has certainly had initial success and has generated a number of Level 3 and Level 4 impact cases recently. It is more difficult to determine the influence that the IGC has had on broader global discussions of policies relevant to growth in low income countries. To date the initiative has used the IGC’s system of annual impact monitoring to record its influence, and it has achieved Level 3 and Level 4 impacts. It is not clear, however, whether this approach is sufficient to capture all of the initiative’s impact and influence. Some of the synthesis products it publishes can be freely downloaded, which makes it more difficult to track their influence. The IGC’s online communications channels (the IGC blogs and VoxDev) face a similar challenge, since feedback on cases of influence is difficult to obtain. This points to need to develop a stronger ToC and results framework for these influencing efforts: the growth of these influencing activities may have outpaced the IGC’s processes for monitoring their impact and effectiveness.
We found that the IGC’s system of impact measurement is well suited for tracking annual progress. There is a clear and well documented system for assigning impact levels to their activities, and activities awarded a Level 3 or Level 4 impact are particularly important because they inform the Output and Outcome Indicators in the Logframe, and are presented and justified in the Annual Report and discussed as part of the Annual Review by DFID. We have examined the assignment of impact levels annually since 2015 and found that the IGC adhered to its documented process, the impacts awarded were in most cases consistent with the impact level definitions, and evidence was available to support the IGC’s justifications for the awards. There are some shortcomings in the system, but the IGC has pilots underway that should address these shortcomings.
The IGC’s impact system is less well suited to capture other important features of policy change: the sustainability, implementation, magnitude of policy changes, and their attribution to the IGC. Sustainability and implementation / mainstreaming are particularly challenging because they are inherently longer-term issues, and the cases we examined in our mid-term and end-term reports reveal that it is difficult to address these issues using only an annual monitoring tool. The IGC should instead develop other tools and approaches
The IGC’s MEL systems are effective for accountability and reporting, but less so for reflection and learning. The main thrust of the MEL system at the IGC in Phase II has been setting up systems that will enable reporting to DFID. The organisation has put in place some good systems, but the data in these systems is not yet systematically captured and analysed to draw out lessons for learning. The IGC needs to encourage a greater culture of active reflection and learning and implement more feedback loops from monitoring to decision making both at the Hub and country levels.
Overall, the issue of sustainability seems to have received relatively little attention during Phase II. Financial sustainability is very often a significant challenge for project-based interventions. In this respect it is interesting and encouraging to note that the IGC has made some progress in diversifying its sources of funding: DFID, for example, no longer funds the IGC’s activities in India, but the IGC has found alternative sources of funding for these activities. Capacity building is another aspect of sustainability, and the focus of the evaluation question. There are several ways in which the IGC’s activities could promote evidence informed policy making in its partner countries. It could influence the capacity and motivation to use evidence on the part of its policy counterparts in government, or it could build capacity in the local research community to carry out policy relevant research and interact with policymakers in government. Building capacity on a large scale in either the government or the local research community is beyond the remit (and the resources) of the IGC, but to the extent that the IGC has addressed capacity building, it seems to have focused more on the research community than policymakers. The IGC has taken steps to encourage more local researchers to submit proposals to the open calls and to strengthen the quality of their proposals. This seems a promising approach, but the reduction in the level of commissioning activity meant that it was not fully implemented. It should be revived in Phase III, even though its impact is likely to be felt in the long term.
This leads us to suggest that more attention be devoted instead to the IGC’s effect on capacity and motivation in the policy community, where the IGC is more likely to able to have – and demonstrate – and impact within a reasonable period of time. If the IGC has any effect on the use of evidence and research, it is likely to be in its key policy counterparts. Among these counterparts, one would expect more influence from projects that involve a high degree of co-creation or co-production. A closer analysis of co-production may be the simplest way of gauging whether the IGC is promoting the use of evidence in its partner countries, and this seems a worthwhile direction in which to extend the impact measurement system in Phase III.
We draw attention to a number of lessons from the IGC experience that may be useful in improving its performance in Phase III, and in designing similar projects in the future. Briefly, they include:
- Building and sustaining relationships is essential for policy influence
- Alliances with key senior reformers are very important
- Policy influencing often requires involvement in politically sensitive issues. The establishment of trusted relationships with policymakers is an important means of navigating the politics of policy change
- Reputation and credibility, both of individual researchers and of institutions, play an important role in policy influencing
- Quality of delivery and engagement matter as well
- “Synthesis products” are valued by policymakers and are much in demand
- Follow up can be as important as the research itself
- Drawing in other disciplines can sometimes help provide the right mix of advice
- The experiences of the IGC are consistent with those of other policy influencing projects funded by DFID such as BCURE
In terms of crosscutting issues, we focused on the economic empowerment of girls and women. We found that IGC has already done some good work on this issue, but it needs to integrate the issue more fully into its research strategy and research commissioning processes.
Theories of change (ToCs) did not play an important role in the IGC’s operations during Phase I, but their role has expanded in Phase II. Both the evaluators and the IGC itself developed ToCs: the evaluators in a participatory way with the IGC, as part of the mid-term review in 2016, and the IGC itself in 2017. One way in which the IGC has used its version of the ToC is in planning the development of the IGC’s impact indicators. These ToCs give too little attention to issues such as implementation and mainstreaming, as well as global influencing. Going forward, they could usefully be developed in order to maintain their fidelity and to inform subsequent evaluations of the IGC.
In terms of the overall purposes of the evaluation we also examined the mechanisms by which the IGC exerts its influence on policy and identified some of the contextual factors that have contributed to this influence.
The two key mechanisms underpinning the IGC in Phase II were open calls for research funding, with projects selected for funding by the Commissioning Boards; and Country Offices, which allow on the ground presence in a number of low-income countries. Our assessment is that these mechanisms both worked effectively during Phase II, and that their effectiveness increased over time. Our end-term visits and interviews did, however, suggest that these mechanisms worked less well towards end of Phase II because of the uncertainties created by delays in tendering for Phase III. Our end-term visits and interviews also highlighted the evolution of the IGC’s influencing mechanisms, with the launch of two additional influencing mechanisms towards the end of Phase II. The first of these mechanisms is “flexible engagement”, in which the IGC provides advice, synthesis products, etc. to policymakers in countries where there is no Country Office. Flexible engagements have had some impact on policy but is a relatively new initiative and one which operated during the final stages of Phase II, with its attendant uncertainty about the contract for Phase III. This makes it difficult to assess its effectiveness. Cities that Work is also a slightly different mechanism, which is focused on one research theme (cities), with more emphasis on creating and disseminating synthesis products based on existing knowledge. It is also a departure from the established mechanisms because the synthesis work is carried largely by “in house”, IGC staff (the Cities Economists) rather than by researchers from the IGC network. There is a more evidence available about the effectiveness of this mechanism, in particular a number of recent impact cases, but this too has been operating late in Phase II, a slightly unusual period for the IGC. Overall, both mechanisms show some promise. There is a case for examining the effectiveness of each of these mechanisms in more detail one or two years into Phase III
We also examined a range of contextual factors that have contributed to the IGC’s influence. There are clearly also a range of external contextual factors that affect the uptake of the IGCs research findings. The combination of heterogeneity in the policy research environment and heterogeneity across IGC country offices leads us to conclude that while contextual factors are important, it is more useful to consider instead how the IGC adapts to these contextual factors. Our work on this evaluation suggests to us that these external factors – “country context” are not particularly useful in explaining whether the IGC might be successful in a particular country. It seems instead to be more useful to focus instead on whether, and if so how, the IGC adapts to and works within the given context The key is whether IGC takes account of these factors and ensures that the country team is equipped to understand and take account of the context in which it operates, and to adapt to changes in this context when they occur (based on the evidence that they have gathered through the IGCs monitoring and review systems). This conclusion seems broadly consistent with the findings of the BCURE evaluation, which found it difficult to identify country level contextual factors that were good predictors of the success of BCURE’s capacity building interventions. Instead, as noted above, the final report of the evaluation focused on the characteristics of BCURE interventions that were associated with success. Our conclusion is that this is the most helpful way to view “context” for the IGC as well.
Recommendations: Our main recommendations are:
1. Both the independent evaluators and the IGC have developed versions of a ToC for the IGC. Each has its strengths and weaknesses: they could usefully be combined and extended along the lines recommended below in order to play a more important role in informing the IGC's strategy during Phase III and providing a clear and solid basis for future evaluations of the IGC. This would involve streamlining the existing TOCs and extending them to address issues that are likely to more prominent during Phase III, in particular the challenges around policy implementation, mainstreaming and scaling up.
2. The IGC should consistently map funded projects onto the IGC's research and country priorities: The IGC should conduct a research mapping exercise as part of the Commissioning Board Process, and this exercise should map the all projects funded (either by the Country Programme or the Research Programme) onto the priorities for the relevant research theme and the priorities for the relevant country.
3. The IGC should take steps to maintain the strength of the country voice in the selection of research projects
4. The IGC should make greater use of external referees to assess proposals submitted to the Commissioning Boards in certain specified circumstances
5. The IGC's procedures for documenting the process of selecting research projects is good, but could be improved in several ways:
6. The IGC should reconsider the role of the Country Director in the approval of project Progress Reports and Final Reports / Working Papers. We recommend that the Lead Academics be involved in these approvals as well, either as a joint approver, a second approver or with the Country Director designated as the approver for some (more policy oriented) projects and the LA for other (more research oriented) projects.
7. The IGC should introduce 'project completion reports'. These would be relatively short documents, one or two pages in length: succinct, confidential reflections of what goes wrong as well as right in terms of both research content and policy impact.
8. The Country Programme should remain a key instrument in the IGC's portfolio of policy-influencing tools. Our country visits suggested that the ability of Country Offices to achieve policy influence is constrained by the staff numbers and the time they have available for IGC work. The IGC should explore ways of addressing these constraints in order to increase the uptake of IGC research.
9. The IGC's Policy influencing strategies at the project level have improved during Phase II, but more can be done to strengthen them.
10. Country Teams often work in relative isolation, and their opportunities to interact with, and learn from, other teams in other countries have diminished over the course of Phase II. The IGC should devote more resources and attention to increasing the opportunities for cross-country learning, which our interviews suggested was highly valued by the Country Teams.
11. The IGC Country Programmes have developed effective strategies and tactics to achieve Level 3 and Level 4 impacts. These impacts often involve policy changes that are relatively discrete and self-contained (for example pilot projects exploring a promising new idea). The IGC needs to develop more explicit strategies and tactics to address the challenges of implementation, mainstreaming and scaling up of promising new ideas.
12. CtW is a model worth replicating, and the IGC can take the lessons identified and apply them to its new Fragility Initiative, and beyond that to similar initiatives that it is considering.
13. The CtW initiative is now moving into a phase where there is excess demand for its services, and it has to make choices. The initiative should therefore develop a longer-term strategy to help guide its decision making. Since CtW clearly is already influencing global discussions and is in a position to exert more influence in the future, it should also develop a more explicit global influencing plan. The strategy should incorporate the following:
14. There is scope to further exploit the synergies between CtW and the IGC's Cities research programme: on the one hand the feedback from the synthesis efforts could prove useful in identifying important knowledge gaps and guiding the research programme; on the other hand cities involved in CtW often have large quantities of data but little ability to analyse it, which could attract researchers to engage with the Cities research programme.
15. CtW can go further in developing new and impactful synthesis tools, in particular more policy toolkits and multimedia resources available online and should consider developing an online course offering on urban policymaking.
16. The IGC (and its partners) should continue their efforts to expand the readership of VoxDev. This involves expanding the range of content on VoxDev, making better use of automated tools to understand what drives traffic to the site, and expanding the efforts to better understand the profile and interests of the audience visiting the VoxDev site.
17. The output indicators for online activities in IGC logframe should be improved, and these improvements should be informed by a better articulated Theory of Change for online influencing activities.
18. VoxDev seems to play smaller role in showcasing IGC output than one might expect, at least in terms of articles: IGC content needs to be better identified and easier to locate on the VoxDev website (i.e. more visible on the relevant pages, and discoverable via the search function on the website).
19. The IGC should continue its efforts to extend and improve its MEL System, which deals well with successful cases of policy influence, but needs to address other dimensions of IGC activity, in particular:
20. The IGC should take steps to create and nurture a culture of active reflection and learning and implement feedback loops from MEL observations into decision making both at the Hub and country levels.
21. The economic empowerment of girls and women needs to be more fully integrated into the full range of the IGC's activities in Phase III, in particular in the formulation of the research strategy, and the research commissioning process:
22. The IGC could - and should - do more to draw more attention on a regular basis to its research relevant to economic empowerment of girls and women, and ensure that this research (or synthesis products based on it) makes a contribution to international discussions of economic issues relevant to "gender":
23. The gender markers used by the IGC cannot be mapped easily onto the markers defined by the OECD/DAC. If the IGC record wishes to use its own set of indicators, then it should ensure that the OECD/DAC indicators are recorded in its project database as well.

# Introduction
The International Growth Centre (IGC) is an international research and policy influencing initiative whose mission is “to promote sustainable growth in developing countries by providing demand-led policy advice based on frontier research.” IGC’s approach to fulfilling this mission is to “seek to help societies in less economically developed countries find their own solutions to key growth challenges. Through the provision of frontier academic research, the IGC encourages good policy decision making, which in turn means stronger and sustainable growth.”
[note] DFID. Terms of Reference for the External Evaluation of the International Growth Centre. January 2014, p 1.
[note] The International Growth Centre Communications Strategy – work in progress; Update for DFID 30th April 2014.
The IGC is funded by DFID, with additional funding secured under the auspices of the IGC. The IGC is administered by the London School of Economics (LSE) in partnership with the University of Oxford and headquartered at the LSE. A Steering Group consisting of faculty from the LSE, Oxford and the University of Chicago provides strategic direction.
The IGC was conceived of as a new approach to supporting the growth strategies of individual developing countries, which would access the skills of distinguished international researchers in order to enrich policy discussions in these countries. In order to fulfil its mandate, the IGC has developed an extensive research network involving top researchers from leading universities around the world. The IGC commissions rigorous, policy-relevant research from this network and disseminates the results widely through: publications in peer reviewed journals and books; policy briefs; conferences and workshops; meetings, dialogues and discussions with leading policy makers; and various online and social-media portals.
The IGC has an unusual and distinctive business model that defines its niche within the research / policy advice market:
i)	Access to “best in class” researchers working on economic growth: The IGC aims to attract leading researchers to work on important research questions and policy issues within each of its four principal research themes.
ii)	A broad but focused research programme: in Phase II IGC funded researchers carried out high quality research projects falling under its four primary research themes: Firms, State, Cities, and Energy.
iii)	Sustained local presence: The IGC has a presence “on the ground”, which allows IGC staff in its Country Offices to establish long-term relationships with local stakeholders. The IGC currently has this local presence in 11 partner countries: Bangladesh, Ethiopia, Ghana, Myanmar, Mozambique, Pakistan, Rwanda, Sierra Leone, Tanzania, Uganda and Zambia. The IGC operated two offices in India at the outset of Phase II (in Bihar and in Delhi). DFID no longer funds IGC activities in India, but the IGC continues to operate from these offices with support from the Gates Foundation. It also has or has recently had “flexible engagements” (i.e. activities, but no Country Office) in a further seven countries (Afghanistan, Jordan, Kenya, Lebanon, Liberia, Somaliland and South Sudan).
iv)	“Demand led” research: This presence in its partner countries also gives the IGC an opportunity to engage with local policymakers on a sustained basis, to work with them to identify key issues affecting growth in their country, and to stimulate new research by the IGC on these issues.
v)	Collaborative research leading to “locally owned” solutions: This sustained presence also gives the IGC an opportunity to work closely with government officials to design and then carry out research on topics that the government has identified as important.
This summary report integrates various pieces of work that have been undertaken for the end of project evaluation. These are:
A review of the research programme of the IGC (section 4 – the IGC as a knowledge influencer)
Four country case studies and contribution stories of flagship projects in these countries and a review of the global influencing of the IGC with a focus on the Cities that Work initiative. (Section 5 – the IGC as a policy influencer)
It also includes a review of the monitoring, evaluation and learning of the IGC, and cross-cutting issues.
The methodology for the evaluation is explained next.

# The evaluation methodology
GDSI International, also referred to as the Independent Evaluation Board (IEB) was appointed by DFID to undertake an evaluation of Phase I and Phase II of the IGC. This report represents the end of Phase II evaluation. The methodology is described below.
The Evaluation team is listed in Table 1 below. The Management Committee for the evaluation comprised:
- Stephen Yeo, who had overall responsibility as well as responsibility for research programme and research uptake issues.
- Dena Lomofsky, who was responsible for methodology, the country programme, theory of change, and monitoring, adaptation and learning
- Pauric Brophy, who was responsible for contractual issues and team recruitment

Table 1: Evaluation Team
	Role	Responsibilities
Stephen Yeo	Team Leader	Management committee, Mid-term evaluation core team member, Annual QA of impact cases,
Dena Lomofsky	Senior Evaluator	Management committee, evaluation methodology, Cities that Work, Ethiopia country visit, monitoring, adaptation and learning, Mid-term evaluation core team member
Pauric Brophy	Senior Evaluator	Management committee, Pakistan country visit (mid-term),
Alan Ahearne	Senior Evaluator	Research commissioning, Rwanda country visit (mid-term)
Michael Brewin	Country Evaluation Specialist	Pakistan country visit
Colin Jacobs	Country Evaluation Specialist	Sierra Leone country visit
Susan Joekes	Evaluation Specialist	Research implementation, economic empowerment of girls and women as a cross cutting issue
Charlotte Vaillant	Country Evaluation Specialist	Ghana country visit
Jean-Paul Kloppers	Research Assistant	General
Danielle Santana	Research Assistant	General

It is important to note that DFID and the IGC have been closely involved in all aspects of the evaluation as follows:
1. An inception report in the form of an evaluation framework was submitted to DFID and the IGC for comment and feedback. A meeting was held with the IGC MEL team in London to explain the evaluation matrix, which they discussed with the Senior Management Team. Feedback was incorporated into the final framework.
2. All instruments were approved by the IGC and DFID before going into field
3. Verbal feedback sessions were held at the end of country visits with the IGC country team, and their feedback incorporated into the country case study reports.
4. The first and second drafts of the report were submitted both the IGC and DFID for review and feedback was incorporated into the subsequent version of the report.
Evaluation purpose and questions: The end term evaluation of Phase 2 began with the approval of the evaluation framework in April 2019, which outlined the scope of the evaluation, key evaluation questions and methods. This is found in (IEB, 2019f).
The overall purposes of the Phase II evaluation are to:
1. assess the extent to which the IGC's work has influenced the adoption and implementation of credible growth policies in developing countries
2. understand the mechanisms by which the IGC exerts this influence on policy
3. identify the contextual factors that have contributed to this influence
4. examine the effectiveness of the IGC as a model for achieving policy influence
Detailed information on the approach and methodology, including the evaluation matrix, can be found in IEB (IEB, 2019f). For each question, more detailed sub-questions as well as methods, data sources and tools can be found in the Evaluation Matrix (IEB, 2019f, p.15).
The main evaluation questions are:
1. Research
  1. To what extent have the projects funded through the Commissioning Boards represented an effective Research Strategy for achieving the objectives of the IGC?
  2. To what extent has this strategy been successful in creating new knowledge about the factors influencing growth in low income countries?
2. Activities at the Country Level
  1. To what extent has the IGC's Country Programme established and implemented an effective Country Strategy that responds to the priorities and needs of its partner countries?
  2. To what extent has this strategy been successful in enabling the IGC to influence policies relevant to growth at the country level?
3. Activities at the Global Level
  1. To what extent has the IGC established and implemented a strategy for influencing global discussions of policies relevant to growth in low income countries?
  2. Has the IGC had influence on global discussions of these policies?
4. Learning and Adaptation
  1. To what extent does the IGC monitor its own performance? Does it make use of this information to learn lessons and adapt its research and policy influencing strategies at both country and hub levels?
5. Sustainability
  1. To what extent has the IGC made a sustainable contribution to evidence-based policymaking on issues related to growth in its partner countries?
6. Lessons learned
  1. What lessons can be learned about research to policy projects and what recommendations can be made to improve the performance of the IGC and similar projects in the future?
7. Cross-cutting issues
  1. To what extent has the IGC integrated cross-cutting issues into its work, including the economic empowerment of women and girls
8. Theory of Change
  1. How has the IGC developed and used its ToC?
Intended Uses
The target audience for the evaluation findings are DFID, the IGC and the international community on policy influence. The ToR identified key intended uses of the evaluation, which are as follows:
1. For the IGC and DFID to strengthen and improve the on-going performance of the IGC
2. To inform DFID and the international community on policy influence, and make a significant contribution to the evidence base and academic debate surrounding the impact of research on policy making and the impact of growth-related research.
Given that the end-term evaluation is taking place as Phase III is being launched, the findings and recommendations of the evaluation will inform the design of Phase III.
Approach: A theory-based evaluation has been conducted with an attempt to identify and understand the outcomes of the IGC and how they were achieved in Phase II. The evaluation also has a learning focus, to identify lessons that can inform the implementation of Phase III of the IGC. Contribution analysis has been applied to the evaluation of the flagship projects of the IGC. Thematic analysis was conducted of ‘less successful projects’ to identify any trends in why projects may not achieve the intended impact.
Timing of the evaluation:
This is an end of project evaluation. It concludes Phase II of the IGC, and builds on the mid-term review of the IGC, and various other evaluative pieces that have been produced by the IEB throughout Phase II.
The timing of this evaluation is significant because the IGC has been awarded a third phase, and the findings from this evaluation are timely and can inform the strategic and operational direction of the IGC during its next phase.
The mid-term review was conducted in 2016. The end-of-project evaluation was delayed somewhat because of the extensions granted to the IGC. The report of the mid-term review was treated as a documentary source in this evaluation.
The mid-term review (2016):
The data collected for the mid-term review was focused on the following:
- Refining the theory of change of the IGC and understanding the business model and the pathways of change and key assumptions.
- Examining the IGC’s work on taxation in three countries (Pakistan, Rwanda and Uganda), tracing the contribution of a number of IGC activities to the policy environment and unpacking the processes by which policy influence has been achieved. This was done to provide a focus for the investigation of policy influence.
- Our initial explorations suggested that the IGC’s Small Projects Facility (SPF) played an important role in these activities. We therefore widened the scope of our enquiries to include an examination of SPFs as well. A typology of the SPF was produced and survey was conducted with country programme teams about their SPFs. This was then analysed to understand how this funding mechanism complemented the research programme in terms of policy influence. The primary instrument for gathering data about SPFs was a questionnaire distributed to each Country Team, supplemented by a review of the IGC activities database and interviews with the IGC Country Teams during Growth Week and the subsequent country visits.
The methodology for the end-of-project evaluation is described below.
Methodology:
Semi-structured interviews with a range of stakeholders including IGC Directors, staff, bellwethers / substantiators, Lead Academics, principle investigators, policy counterparts and development actors.
Primary data collection:
Semi-structured interviews: Semi–structured interviews (SSIs) were conducted with all key stakeholders and other actors as identified in the Evaluation Matrix contained in the methodology appendix.
Semi-structured interviews were conducted with the following key stakeholders:
- Country Director
- Country Economist (IGC Country Team)
- Country Development Actors
- Country Team (IGC)
- Senior Management Team of the IGC
- MEL team of the IGC
- Policy Economists at the Hub
- Research Programme Director
- Policy counterparts (policy makers who worked with the IGC on research projects)
- Principal Investigator (of a research project or SPF)
- Bellwethers (substantiators) – people who have not worked directly with the IGC but who are knowledgeable about the country context and the kinds of outcomes identified in the flagship cases
Borrowing terminology from Outcome Harvesting, we define a Substantiator as “individuals who are independent of the intervention (third party) but knowledgeable about one or more of the outcomes and the change agent’s contribution” – also known as Bellwether respondents.
In order to ensure triangulation, we gave high priority to identifying and interviewing two sets of substantiators:
1. At the country level, those familiar with the activities of the IGC country office
2. At the project level, those familiar with the flagship projects we examined.
We adopted a snowball approach to identifying Substantiators, starting for example with the PIs of flagship projects in order to identify other researchers and other funders who might have been working on the same topic as well as knowledgeable individuals who are well acquainted with the policy issue addressed by the flagship project and the actors involved, but not involved in the IGC project.
A total of 77 interviews were conducted for the various sections of the end-term evaluation, broken down as follows:
Table 2: No. of qualitative interviews per component of the evaluation
Component	Number
Ethiopia Country Report	15
Ghana Country Report	14
Sierra Leone Country Report	17
Global influencing Report	15
Research commissioning Report	13
General	3
Total	77

Instruments:
The list of instruments used in the evaluation is included in the methodology and instruments section, and the instruments themselves are appended.
Since the IEB has been working with the IGC throughout Phase II, we have a good understanding of the types of questions and style of interviews that worked with the respondents. We used the insights from instrument design previous evaluations for the IGC to inform the design of these instruments. Further, the instruments were supposed to be tested in Ethiopia and then amended for the fieldwork to take place in other countries. However, due to delays in obtaining visas, it turned out that the Ghana fieldwork took place first. However, during the Ethiopia fieldwork which followed the instruments were refined and shared with the rest of the fieldwork team.
All instruments were reviewed by DFID and the IGC before going into field.

Secondary data sources:
Secondary data sources included documents from the IGC and DFID such as annual reports and annual reviews (please see reference list for a full list of the secondary data sources). This final evaluation also drew on other pieces done by the IEB during Phase II implementation (which also included both primary and secondary data collection), namely:
- A mid-term review of the IGC Phase II implementation (which included 3 country visits, and 6 contribution stories in the taxation thematic area; and a focus on the research commissioning and the small projects facility of the IGC). A summary can be found in IEB (2016e)
- A study of the economic outcomes of transition from a notch-based to a kink-based income tax system in Pakistan Arising from IGC Project No. 370001 (IEB, 2018a).
- Tax Policy and Reforms in Rwanda Evaluation of the economic impact of IGC advice to the government of Rwanda on the introduction of a proposed flat tax system (IEB, 2018a).
- Evaluation of the International Growth Centre's Research Commissioning (IEB, 2019i).
- Analysis of the IGC project data: The IGC’s activities (or project) data base (an Excel document) was analysed to obtain a comprehensive picture of the activities of the IGC in terms of geographic spread, type of award, impact cases, subsequent publication of IGC research in peer-reviewed journals, as well as other key factors.
Data analysis and report writing: Thematic analysis and contribution analysis have been the primary data analysis methods used for the evaluation. Four case studies were produced of flagship cases that were identified as having a high impact, and contribution analysis was applied to these. The draft reports were reviewed and validated by the IGC and DFID, and the comments have been incorporated into this second draft.
The instruments are attached to IEB (2019f). More detailed information on the approach and methodology can be found in IEB (2019f).
Bias and triangulation
Since the bulk of the primary and secondary data sources were provided by the IGC and DFID, there is the potential for the evaluation to be biased towards their perspectives. The main means of addressing this was including other development actors and substantiators into the sample. Triangulation was thus done by comparing four key data sources: The IGC, DFID, policy counterparts (who worked closely with the IGC), and substantiators.
To avoid bias towards successful cases, we included a review of less successful projects. These were the projects that received an impact score of 1 or 2. A thematic analysis was conducted to identify the reasons why there were not successful. This was done on a country level, and each country report was coded to produce the summary report.
The IGC did not accompany the evaluators to the interviews, unless it was deemed appropriate by the evaluator.
Ethical considerations
While no ethical clearance was needed for this evaluation, we abided by international best practice principles. The respondents are not identified by name in the reports. Because the samples were sometimes small (e.g. in some countries there are only three Country Team members), respondents were warned that their identity could not be completely concealed, as their names were appended to the reports. The original data sources will not be provided to the IGC or DFID.
Departures from the TOR, inception phase and / or original evaluation design & limitations
The inception report for the end of project evaluation (Evaluation Framework) suggested conducting a mapping study. The goal was to explore the extent to which the projects approved by the CBs were aligned with the research priorities or knowledge gaps identified in the Evidence Papers and in the Research Priorities document published before each of the Calls. For some calls, the IGC has already done this, but only for projects funded by the Research Programme. We were able to complete part of this exercise for two of the research themes (Firms and Cities) but the IGC’s activities database did not contain abstracts for some of the projects, and time constraints meant that we could not recover this information from the IGC’s document archives in order to complete the process. This would have filled a gap in our knowledge of the IGC’s research commissioning process.
We did not manage to interview any of the Lead Academics, for various reasons, including time constraints. This is a gap as they could have provided a different perspective on the country visits.
There were no other departures from the evaluation framework.

# The Theory of Change
This Section addresses Evaluation Question (EQ) 8.1:
[note] The Evaluation Questions can be found in IEB (2019f)
How has the IGC developed and used its ToC?
Since this is intended as a theory-based evaluation, we also consider the broader question of what ToC is adequate, given the goals the IGC has pursued and the activities it has undertaken in Phase II.
Theories of change did not play an important role in the IGC’s operations during Phase I, but their role has expanded in Phase II. Both the evaluators and the IGC itself have developed ToCs: the evaluators in a participatory way with the IGC, as part of the mid-term review in 2016 (IEB, 2016a); and the IGC itself in 2017 (IGC, 2017). The 2017 version of the ToC developed by the IGC has been developed and refined since then, and has been used, for example in planning the development of the IGC’s impact indicators (IGC, 2019b).
The IGC did not adopt the ToC developed by the IEB, but instead have integrated various aspects of it into the various versions of the 2017 ToC (the most recent being that which was included in the Phase III bid). For the purposes of this evaluation, the IEB has continued to work with the ToC developed during mid-term review, since it was accepted by the IGC and DFID at the time as comprehensive, and its strategic pathways provided a very useful basis for the contribution analyses carried out in the mid-term report and extended in the end-term reports.
A reflection on the ToC and how it could be adjusted based on the findings in this end of term evaluation is provided below.
## Strategic Pathways and the IGC Logic Model
The IGC engages in three main intersecting work streams: the creation of knowledge (largely but not exclusively through the Research Programme) and the application of knowledge to policy (largely but not exclusively through the Country Offices), and the communication of knowledge (largely but not exclusively through its influencing strategies). A ToC for the IGC can be framed around these three work streams.
A number of versions of the ToC have been developed over the course of Phase II, by the Independent Evaluation Board (IEB) and by the IGC itself (IGC, 2017). The version developed by the IEB during the 2016 mid-term review (IEB, 2016a) contained five pathways to impact or “strategic pathways”:
- Knowledge creation
  - Strategic Pathway 1: Open Calls for Research Proposals (SP1)
  - Strategic Pathway 2: Strategic commissioning (SP2)
- Knowledge application
  - Strategic Pathway 3: The IGC Country Programme (SP3)
  - Strategic Pathway 4: Indirect, via “Other Actors” (SP4)
- Knowledge communication
  - Strategic Pathway 5: Influencing Plans (SP5)

Table 16 on page 105 illustrates the relationship of these pathways to the IGC logic model or logframe.
In SP1 the IGC funds research via regular “open Calls” for research proposals, which are evaluated by the Commissioning Boards and funded (in Phase II) by the IGC’s Research Programme or its Country Programme. The research can be in varying degrees “supply led” or “demand led” (i.e. arising from the research agenda of the researchers concerned or generated through engagement with policy makers). In this way the IGC establishes itself as academically credible - it attracts leading researchers, supports innovative, cutting edge research and encourages longer-term engagement with researchers. The outcomes for this pathway are potentially both in terms of improved policy in the IGC’s partner countries, and in terms of the effect of “transformative ideas” on the IGC’s Research Programme and the wider research community.
In SP2 the IGC identifies significant gaps in knowledge about growth processes and policies and encourages researchers to fill these gaps in our knowledge. The IGC conducts reviews of the literature to identify these knowledge gaps and then encourages new research to address these knowledge gaps (via the open Calls or through other means). The reasoning behind this pathway is that if the IGC is “strategic" in the way that it encourages research to fill knowledge gaps, then the quality of the researchers involved with the IGC make it likely that the research will indeed fill the gaps, and the IGC can then disseminate this research nationally, regionally and globally to improve policy. This will stimulate policy maker interest, and possibly a demand for further research applying this new knowledge to the circumstances of particular countries or regions.
SP3 describes how the IGC “in country” promotes evidence-informed policymaking through direct interactions with government. Evidence can take the form of existing knowledge (via synthesis products) or the new knowledge (created through research). We call this the “direct” (government) channel since it relies on building relationships with key decision makers in government, understanding their needs and providing them with relevant research and evidence on a timely basis. The mechanism underlying this pathway is that an effective Country Office will facilitate evidence-informed policymaking by building strong relationships with local policy makers; and by having a good understanding of the concerns of these policymakers (i.e. what is on their policy agenda). If the IGC Country Office has established these relationships and understands the policy issues in country, then there is a higher chance that policy makers will look to the IGC for the evidence or assistance they need to inform their decisions. Key to establishing these relationships is the credibility of the IGC as a neutral, responsive policy player, that provides high quality and timely evidence to inform decision making. Because the Country Economists interact with the local policy community, the IGC Country Office will be able to identify "policy windows" that provide avenues for IGC research to enter the policy process (Kingdon, 1990).
In SP4 the IGC uses research to inform policy but through indirect (or non-governmental channels), such as through the local (in country) donor community, the local media, the private sector or even the IGC’s own national and regional workshops and conferences. The projects we studied in the mid-term evaluation did not feature the use of this pathway, perhaps because they focused on taxation and government revenue. As a result, we did not develop this path in as much detail as SP3. We did, however, encounter one project in which SP4 played a role when the direct government pathway was blocked because the relevant ministry was not receptive to research or to new policy initiatives.
The IGC's “influencing plans” form the basis of SP5. These influencing plans are primarily about amplifying the work of the IGC knowledge network and are focused on issues where the IGC thinks it has generated new knowledge and learned policy lessons of broader interest, which it wishes to share more widely. The mechanism for this pathway is that since the IGC is developing a body of knowledge on what policies are effective in low income countries, if it disseminates this knowledge effectively at different levels, it will influence discussions on this topic at the international and regional levels. Influence at these levels will in turn attract the attention of and influence attitudes at the national level, and this in turn will stimulate the uptake of research on these topics among policy makers in LICs.
These pathways proved useful in analysing the contribution stories gathered as part of the mid-term review, but our subsequent study of research commissioning (IEB, 2019i) suggested that in practice SP2 (“strategic commissioning”) has not played an important role in the IGC’s knowledge creation activities in Phase II. In practice open calls for research (SP1) have been the principal means by which the IGC has created new knowledge in Phase II. Decisions to fund proposals submitted under these calls are, of course, informed by the IGC’s research and country priorities, but they do not involve direct commissioning of research to fill a specific knowledge gap.
In terms of knowledge application (i.e. applying existing knowledge to policy), our mid-term findings suggested that SP3 (influencing policy by dealing directly with the government, via relationships developed by the IGC Country Office) was more important in practice than SP4, which involves influencing policy by acting via the private sector and / or civil society. The “flagship” projects that were the focus of attention during our country visits in 2019 did confirm the importance of SP3, since three of the four flagship projects involved influencing policy via interactions with the government. The projects in Ethiopia and Ghana (IEB, 2019a; b) revealed that the PI can also play an important role in establishing and sustaining these relationships, and SP3 therefore needs some modification to allow for this possibility.
More importantly, the Ethiopia, Ghana and Pakistan country studies (IEB, 2019a; b; c) identified an important weakness in the 2016 version of the ToC, having to do with the issue of policy implementation. The IGC’s four level system of impact monitoring is focused on whether IGC activities contribute to a change in government policy or a regulation, but not on the subsequent implementation of the policy or its impact. Both the Ghana project and the Pakistan project, having had considerable success in piloting their ideas, faced challenges when it came to mainstreaming or scaling up the ideas that had been piloted. The 2016 ToC, which reflected the IGC’s system of impact monitoring, gave too little attention to implementation of the policy changes inspired by IGC research (as well as the related issues of impact and sustainability). The Ethiopia and Ghana country studies proposed extensions to the ToC to take account of this important issue.
The Sierra Leone project involved interventions in the 2012 and 2018 elections involving both voters and political parties. This revealed another important weakness of the 2016 ToC. While SP4 does address policy, influence achieved via non-government actors, it is not sufficiently well developed to prove useful in analysing the work with political parties instead of government departments. The Sierra Leone report also sketches out how the ToC might be extended to address these sorts of “governance” interventions.
Finally, our analysis of the Cities that Work (CtW) initiative, reported in Section 5.3.2.1 below, revealed that the global influencing pathway (SP5) needs to be extended and refined to reflect the importance of the synergies between the knowledge creation, utilisation and communication pathways.
## Conclusions and Recommendations
Theories of change did not play an important role important role in the IGC’s operations during Phase I, but their role has expanded in Phase II. Both the evaluators and the IGC itself have developed ToCs, the evaluators as part of the mid-term review in 2016 (IEB, 2016a) and the IGC in 2017 (IGC, 2017). The 2017 version of the ToC developed by the IGC has been developed and refined since then, and have been used, for example in planning the development of the IGC’s impact indicators (IGC, 2019b).
With respect to the ToC for the IGC, we recommend the following:
[note] We assign a higher priority to recommendations that involve activities or processes that either have a large impact on the IGC's effectiveness, or are not working well and need to be fixed quickly. Given the timing of the evaluation with respect to the launch of Phase III, we also focus on measures that need to be initiated at the start of Phase III in order to be effective. Within each Section of the report, at the first level the order in which the recommendations are presented reflects their priority i.e. R1 is higher priority than R2, and at the second level.
R1 Both the IEB and the IGC have developed versions of a ToC for the IGC. Each has its strengths and weaknesses: they could usefully be combined and extended along the lines recommended below in order to play a more important role in informing the IGC’s strategy during Phase III and providing a clear and solid basis for future evaluations of the IGC. This would involve streamlining the existing TOCs and extending them to address issues that are likely to more prominent during Phase III, in particular the challenges around policy implementation, mainstreaming and scaling up.
1. The TOC could be streamlined by consolidating the pathways involving “Open Calls for research” and “strategic commissioning”. Strategic commissioning (SP2) has not played an important role in the IGC’s knowledge creation activities so far, and if there is no prospect of it playing a significant role in the future, SP2 could be consolidated with SP1 to simplify the ToC. It could be clarified with respect to the role of researchers in the pathway involving establishing and sustaining relationships with government (SP3). Our study of the flagship projects in Ethiopia and Ghana reminded us that the IGC researchers, as well as the Country Teams, can play an important role in developing and sustaining these relationships, and this should be reflected in the pathway.
2. The ToC should be extended to take into account the issues involved in policy implementation. The IGC’s system of impact monitoring is focused on whether IGC activities contribute to a change in government policy or a regulation, but less so on the subsequent implementation of the policy. This should be extended and enriched, using the proposals made in the Ethiopia and Ghana country studies. While SP4 does address policy influence achieved via non-government actors, it does not address well work on governance related topics, such as the work in Sierra Leone on elections. If IGC continues to work on these issues, the ToC should be extended, using the suggestions in the Sierra Leone report. The global influencing pathway (SP5) also needs to be extended and refined to reflect the experience of the CtW initiative and the growth of the IGC’s online communications channels during Phase II.

# The IGC As a Knowledge Creator
This Section addresses EQ 1:
- To what extent have the projects funded through the Commissioning Boards represented an effective Research Strategy for achieving the objectives of the IGC?
- To what extent has this strategy been successful in creating new knowledge about the factors influencing growth in low income countries?
and Output 2 in the IGC Logframe (DFID, 2018a)
World class policy-oriented research undertaken on developing country growth issues and widely disseminated
## How the IGC Defined Its Research Strategy
The IGC’s Research Strategy in Phase II was defined by its 2013 Research Strategy document (IGC, 2013), the four Evidence Papers, prepared at the beginning of Phase II; and the documents describing the current research and country priorities, prepared for each of the six Calls.
The Research Strategy document set out how the IGC’s research in Phase II would be focused around a smaller number of research themes, and described how the IGC would invite proposals for research and select the research it would fund.
[note] There were four research themes in Phase II: State Effectiveness, Firm Capabilities, Cities, and Energy. There were ten themes in Phase I.
Box 1: Cities Research Priorities
“Agglomeration economies / The establishment of affordable and effective housing markets / Infrastructure and service provision / Migration

For each of the four research themes, the IGC prepared an Evidence Paper (EP), which summarised the frontier state of knowledge for that theme and identified key knowledge gaps (Azulai et al., 2014; Bloom et al., 2014; Greenstone, 2014; Moretti, 2014). These EPs were not revised during Phase II, but a revised list of priority research issues was prepared for each of the Calls issued during Phase II. While the EPs were fairly detailed, the priority research themes for the Calls were set out at a very general level. By way of an example, Box 1 shows the Cities research priorities for the final Commissioning Board (CB6), which are very broad indeed.
In addition, Country Strategy Notes (CSNs) were available for each IGC partner county. These CSNs, formulated when the Country Office was established and revised from time to time thereafter, set out the policy issues on which the government and the IGC agreed the IGC’s work would focus. The country priorities were also updated for each Call and made available to applicants.
## How the IGC Implemented Its Research Strategy
Most of the research funded by the IGC in Phase II was assessed and selected through the Commissioning Boards (CBs) established at the start of Phase II. The IGC’s Research Strategy document described in some detail the proposed CBs and how they would operate, but this was essentially an competition open to all researchers, and guided by the priorities set out in the EP and the priorities documents prepared for each Call.
[note] There are also "out of cycle" research proposals, which were approved for funding outside the CBs, but only 9 of these were funded in Phase II (versus 540 projects funded through the CBs), so they were not a focus of this evaluation.
Table 3: Commissioning Board Schedule
Commissioning Board	1	2	3	4	5	6
Call opened	October 2013	March 2014	October 2014	April 2015	November 2015	October 2016
Call Closed	November 2013	May 2014	December 2014	June 2015	January 2016	December 2016
Meetings	February 2014	July 2014	February 2015	September 2015	March 2016	March 2017

In Phase II the IGC funded research projects from two separate funding streams, the Research Programme (RP) and the Country Programme (CP). The RP primarily focused on the supporting cutting edge or frontier research that was of publishable quality (i.e. had the potential to be published in a leading peer reviewed journal), but was also policy-relevant, informing policymaking in one of the IGC’s partner countries. The CP focused on supporting research that addressed the specific policy needs of the IGC’s partner countries, but was nevertheless of sufficiently high quality to satisfy the IGC’s minimum quality threshold.
### Commissioning Research Projects
To achieve its research objectives in Phase II, the IGC commissioned 540 research projects through six separate Calls for proposals over the period from 2013 to 2017, with an average value of around £40,646 per proposal funded. These projects were funded from both the IGC’s Research Programme and its Country Programme. By offering funding through the CB mechanism, the IGC aimed to attract proposals from leading researchers to carry out “frontier” research on issues of importance to growth in LICs, and so establish a reputation as a source of innovative “ideas for growth”.
[note] We do not include in our analysis the round of Commissioning (“S18”) that took place in 2018.
[note] The strapline of the IGC website (www.theigc.org)
In addition to the projects funded by the CBs, the IGC’s other main funding modality in Phase II was the Small Project Facility (SPFs), which funded short-term projects initiated by the Country Offices and costing less than £20K. 290 SPFs were funded over the period 2013 to 2017 by the individual country programmes.
[note] 347 including 2018-19.
Commissioning process
In our study of the IGC’s research commissioning process (IEB, 2019i) we assessed the process by which the IGC commissioned research in Phase II, focusing on the processes put into place to ensure that IGC funded research was consistent with the IGC’s core objectives.
Our report benchmarked the IGC’s commissioning process against international best practice among research funders. In terms of consistency with best practice, the report examined
1. Appropriateness of Timeframes
2. Appropriateness of Record Keeping
3. Clarity and relevance of assessment criteria
The reference timeline for the Calls involved approximately a three-month lag between the date for the closing of a Call and the time when applicants would be notified of the Boards' decisions. Such a timeframe strikes the right balance between the need for prompt turnaround of applications and for sufficient time to evaluate carefully the proposals. In our interviews and in responses to our survey of Country Directors (CDs), we heard no complaints about timeframes. Participants generally did not feel unduly pressed for time during the process.
A related issue relates to the frequency of Calls. At the beginning of Phase II, Calls were issued at roughly six-monthly intervals, with the exception of Call 6, which was issued about one year after Call 5. This frequency strikes a reasonable balance between maintaining the IGC’s visibility in the research community through frequent Calls, and the administrative burden associated with a large number of Calls.
Keeping proper minutes is important for the integrity of the commissioning process: they support the decisions made and demonstrate that the funding decisions are arrived at through a justifiable, coherent, and consistent process. The IGC’s Research Strategy committed the IGC to record written minutes for each funding decision, a commitment that is in line with best practice. The records were to include information on any Conflicts of Interest (COIs) and how they were handled; which Board members were involved in making the decisions, and the reasons for approving or rejecting each proposal (without attribution to individual members of the relevant Board). Overall, the minutes were of good quality, and presented the required information in a clear fashion. The details of the information presented in these minutes did change somewhat over the course of Phase II. On balance we think the practice adopted in the early CBs, in which the proposals funded by both the RP and the CP were presented, is preferable to the practice adopted in later CBs of presenting only the projects funded by the Research Programme.
The criteria template used by CBs to evaluate proposals are simple and straightforward:
1. Academic Merit
2. Policy Merit
3. Contribution to Local Capacity
4. Quality of Research Team
5. Budget
The same criteria are used by both the Research Programme and the Country Programme evaluators. The system for assigning ranks to the five criteria might be criticised for being qualitative rather than numerical. There are no weightings assigned to the criteria and indeed it is likely that the Research Programme and the Country Programme assigned different weights to criteria 1 and 2. In practice, the responses to question 8 by the RP and the CP were used by the Research Programme team (RPT) to assign proposals to categories, and the CB meeting considered the proposals in each category in turn. Funding constraints meant that in practice the available budget for the Call was often exhausted after considering the “Yes / Yes”, “Yes / Maybe”, and “Maybe / Yes” categories. Overall, the selection process represented a reasonable procedure for allocating a limited budget across a large number of proposals of varying quality.
Overall, we found that the IGC’s Commissioning Board process was consistent with best practice among funding agencies, with one important exception. In contrast to most other funding agencies, the IGC did not use external referees to evaluate proposals: instead, the assessments are carried out by: the Research Programme Director(s) for the relevant research theme, other researchers closely associated with the IGC, and the Country Teams for the IGC country that is the focus on the research. The IGC justified this departure from best practice by arguing that: i) external referees often do not deliver their assessments in a timely manner, and relying on them would delay the commissioning process; and ii) the IGC possesses sufficient “in-house” expertise to assess most proposals. We viewed this as a reasonable argument, and while external referees would be desirable, their absence did not result in a significantly less effective commissioning process. We did, however, note two occasions on which the IGC should – but did not – make use of external referees. First, the IGC seems to have ignored one of the rules set out in its Research Strategy document, namely that proposals with a value exceeding £150K should be evaluated by a researcher external to the IGC. This rule should be implemented in Phase III, even if this does result in a slower commissioning process. Second, proposals involving a Research Programme Director (RPD) were not externally refereed. RPDs do not, of course, participate in the assessment or discussions of their own proposals but in our view external referees should be asked to evaluate these proposals.
Greater integration of the Research Programme and the Country Programme through the commissioning process
One of the goals in Phase II was greater integration of the Research Programme and the Country Programme and so we also examined whether the commissioning process strengthened the “country voice” in the selection of research projects. The IGC’s Research Programme seeks to combine frontier research knowledge with local knowledge relevant to the circumstances of individual countries in order to influence policies on growth in developing countries.
Significant changes to the process of commissioning research were introduced in Phase II aimed at increasing the “voice” of the Country Teams (CTs) in the commissioning process. Our report examined the extent to which these changes improved the integration of IGC’s Research Programme and its Country Programme. These changes included:
- CTs had the opportunity at each Call to review and, if necessary, revise their respective parts of the research and country priorities document that was included in the guidance to applicants in each Call for proposals. Our survey of CDs found they strongly believed that making the list of priority research topics available as part of the Call helped to improve the relevance of the proposals for their countries.
- CTs contributed to the Proposal Review Quality Assessment by completing the Country Evaluation Sheets. The evidence suggests that the CTs put both time and energy into considering and commenting on the proposals. In practice, the evidence suggests that proposals that were graded “No” by the CTs were very unlikely to be funded by the CBs.
- The Country Programme was well represented in the Commissioning Board meetings that selected projects for funding. The information we gathered suggests that in addition to the participation of CDs and Lead Academics (LAs), the Country Programme Director (CPD) and the Executive Director acted as important advocates for the Country Programme in the meetings.
  [note] CDs and LAs, if not present in the meeting, typically joined the discussion by telephone when projects relevant to their country were discussed.
- The Country Programme had some success in persuading the CBs to fund projects that they deemed very worthwhile, even when the RP did not judge them to be at the frontier in terms of academic merit. One example is instructive: 3 of the 14 proposals classified as “Maybe” were funded by the CB6 Firm Capabilities Board. All three had been ranked No by RPD and Yes by the CTs. The comments recorded for one of these projects are revealing:
  [note] Project No. 146
“Methodology on frontier production estimates not modern and suffers from standard identification problems, will lower quality of findings. Low proposal quality, low value for money (fees far too high and need to be cut). Approved because of support from Country Team and relationship-building value with Ministry.”
All this is in sharp contrast with the procedures followed in Phase I, in which CTs were given little time to assess and provide comments on research proposals. Fields, in his 2011 report on IGC research reported that
“One Country Team leader reported that the turnaround time was impossibly quick: 50 proposals to be reviewed by the close of business two days later. Consequently, only a cursory review could be given.” (Fields, 2011, p.7)
The outcomes of the CBs also suggest that not only was there an opportunity to exercise voice, but the exercise had an impact on the selection of projects to be funded:
- More than half the funding for CB approved projects came from the Country Programme: 370 projects with budgets totalling £13,013K versus 170 projects with budgets of totalling £8,936K
- As will be seen in Section 5.2.3 below, research funded by the Country Programme was more likely to achieve a Level 3 or 4 impact (42% versus 26%), which suggests that the stronger country voice increased the likelihood of choosing projects with policy impact.
While not part of the changes to the commissioning process, the creation of a new position, that of CPD, also strengthened the “country voice”. The CPD could attend all the CB meetings, ensuring that the views of all the CTs were represented more consistently and effectively during the discussions. There was a significant delay in recruiting this post: it was only filled in 2015 and then fell vacant again in 2017. The delays in tendering for the Phase III contract and uncertainty about future funding made it difficult to recruit a successor, and so the post has remained unfilled for over two years. The ED (with the assistance of the CPM) served as an interim CPD during this period, but this meant that an important channel for the views of the Country Offices was weakened for a considerable period. Recruiting and retaining an effective CPD should be a high priority in Phase III.
Effect of delays in the Phase III bid
The delays in tendering for the Phase III contract had an unexpected but important effect on the research commissioning process: there was a decline in the number of research projects commissioned after 2016 and a sharp decline after March 2017. There were four CBs in 2014 and 2015, one March 2016 and in March 2017. There was no other commissioning after March 2017, aside from a small round of projects of short duration commissioned in 2018. The absence of research commissioning seems to have been due at least in part to the delays in the tendering for the Phase III contract, and the resulting uncertainty about the budget for research and constraints on the duration of research projects. Our four country studies (IEB, 2019a; b; c; d) confirmed the importance of this shift, and revealed that in the last two years of Phase II (2017 to 2019) the Country Offices (COs) had responded to the decline in research commissioning by relying more heavily on the SPF. SPFs are an effective mechanism for funding short-term activities (one year or less) and many of them achieve high impact levels. They are not, however, designed to support longer-term, multi-year research projects, and so they are at best an imperfect substitute for the funding that was available via the CBs. Our country visits and interviews confirmed that this was an obstacle to building strong research portfolios at the country level during the last two years of Phase II.
[note] This round was called S18
### Managing the Implementation of Research Projects
In 2019 we extended our study of research commissioning, discussed in Section 4.2 above, with a study of how the IGC oversaw and managed the implementation of its research projects (IEB, 2019h). The study examined the research projects funded by the IGC from the point at which the funding decision was taken to the point where the final deliverables were submitted to and approved by the IGC.
The IGC's organisational arrangements, procedures and staff efforts to ensure that projects are implemented effectively constitute its “project implementation system”. Project implementation is divided into three main parts: contractual administration, and content monitoring and project support, and content monitoring and quality assurance. They overlap but are conceptually distinct. We examine the processes and procedures for implementing projects from the point of project approval to project completion and how far this system succeeds in its aims and what particular challenges it faces. One of the questions we examine is whether the IGC devoted enough attention to monitoring scientific quality, and whether its procedures for monitoring this quality were applied proportionately across the IGC's different funding modalities, and consistently across the IGC's portfolio of projects.
Overall, we found that the IGC’s implementation system, while complex, was effective, well managed and appropriately resourced; and thus fit for purpose. It is broadly consistent with best practice among funding agencies, with one exception: the IGC does not as a matter of routine prepare a “project completion report” for all projects, “successful” or “unsuccessful”. This is common practice among funding agencies, and if implemented in a proportionate fashion would have significant benefits for the IGC.
The decentralized structure of the IGC, with a central hub and a large number of country offices, creates particular challenges for the IGC in implementing its projects, in particular in ensuring their scientific quality. This makes it difficult for the IGC to maintain its internal coherence and creates a risk for the IGC.
Projects approved by the CBs and funded by the Research Programme (Research Programme Awards) face fewer challenges in terms of receiving robust monitoring and quality assurance. These projects’ research content is monitored at all reporting stages by a small number of staff, all members of the Research Programme Team and based in the Hub. The RPT is also responsible for organizing the calls for proposals and the meetings of the CBs to select the projects to be funded, and so is closely involved in these projects from the outset. As a result (and not surprisingly) the RPT seems to have a strong sense of “ownership” of Research Programme Projects. Although the small size of the RPT may create heavy workloads on occasion, it does make it easier to ensure consistency of monitoring and quality assurance: the same individuals are involved for all projects, and they interact intensively since they are all based in the hub.
The situation with country programme projects (Country Project Proposals and SPFs) is more complicated. These projects rely on scrutiny from the CD and (under some circumstances) the LA as well. Both have wide ranging responsibilities, but are only engaged by the IGC on a part-time basis, for a relatively small number of days each year. This creates a significant amount of pressure, especially on the CD, and it would not be surprising if the approval and quality assurance task did not have the highest priority. This might have an adverse effect on the timeliness of the approvals process. In addition, Country Project Proposals) projects are primarily aimed at meeting the needs of policymakers, but subject to a minimum standard of research quality. It is worth noting that some of these projects have been published in peer reviewed journals, and so have a significant research content. Other projects will place more emphasis on policy relevance. This suggests that there are some projects for which review by the LA may be more appropriate, and others review by the CD. At the moment the primary responsibility lies with the CD.
Ensuring the consistency of the approvals and quality assurance process across country programme projects from different countries would also be desirable: uniform standards would be important in upholding the IGC’s reputation for supporting high quality research. This is another area in which Research Programme projects face fewer challenges than Country Programme projects: the same team is responsible for signing of on all Research Programme outputs, making consistency relatively easy. Ensuring this is a bigger challenge for Country Programme outputs, which are reviewed by many different CDs (with different backgrounds in research and policy), and on occasion by LAs as well. There is no simple solution to this challenge: a review of the decisions of the CDs and LAs, either ongoing or periodic is one possibility, but would seem too time consuming and resource intensive. In the absence of any simple and inexpensive solution it seems best to recognize this as a risk that the IGC faces because of its decentralized structure.
### Conclusions and Recommendations
Other funding modalities such as SPFs have certainly played a role, but most of the knowledge created by the IGC has been through open research calls with projects selected by the Commissioning Boards. The IGC’s research commissioning process follows best practice and only needs minor changes. We examined the IGC’s knowledge creation activities, in particular the open Calls for research proposals and their subsequent evaluation by the CBs. We found the research commissioning process to be largely consistent with best practice: we suggest some improvements but they are mostly minor, having to do with the use of external refereeing in some circumstances. One aspect of commissioning that does need improvement is the “mapping” of funded projects onto the IGC’s announced research and country priorities. This was not done consistently in Phase II, and the IGC would benefit from more frequent collective reflection on the directions it has taken as a result of its funding decisions.
We conclude that the projects funded through the Commissioning Boards have represented an effective research strategy for achieving the IGC's objectives. The IGC has created processes for commissioning and implementing research projects that have enabled it to achieve one of its key objectives: to identify key growth policy issues and mobilise world class researchers to address these issues. These processes also enabled the IGC to overcome one of the key challenges it faced in Phase II: to better integrate its Research Programme and its Country Programme. It is important to note as well that the research commissioning process has also played an important role in integrating the Research Programme and the Country Programme, through a range of measures that have enhanced the “country voice” in the decisions taken by the Commissioning Boards. This was a key objective for the IGC during Phase II.
The IGC’s research strategy has also been successful in creating new knowledge about the factors influencing growth in low income countries. During Phase II IGC has supported research projects whose outputs have not only been published in high impact scientific journals, but have also influenced policy in its partner countries.
With respect to research commissioning, we recommend the following:
R2 The IGC should consistently map funded projects onto the IGC’s research and country priorities: The IGC should conduct a research mapping exercise as part of the Commissioning Board Process, and this exercise should map the all projects funded (either by the Country Programme or the Research Programme) onto the priorities for the relevant research theme and the priorities for the relevant country.
R3 the IGC should take steps to maintain the strength of the country voice in the selection of research projects:
1. The Country Programme Director: The CPD played a key role in articulating the “country voice” in the commissioning process, but the position is now vacant. We recommend that a new CPD is appointed as soon as possible in the next Phase so that they are in place before any research is commissioned in the new Phase.
2. The “dual funding” system for funding research that operated in Phase II should be maintained, since it seems to have helped the Country Offices influence the selection of research projects
R4 The IGC should make greater use of external referees to assess proposals submitted to the Commissioning Boards in certain specified circumstances:
1. COIs: The IGC needs to be able to demonstrate that it has carried out a thorough and objective appraisal of all the projects it funds. This applies even more strongly to proposals submitted by researchers closely associated with the IGC. Proposals involving RPDs should be evaluated by a researcher external to the IGC.
2. Use of External Referees: The Phase II Research Strategy undertook to seek external reviews of proposals with a value exceeding £150K. The evidence suggests that during Phase II the IGC did not follow this rule. We recommend that the IGC implement this rule so that all “high value” proposals funded by the IGC receive external scrutiny, adjusting the rule as necessary so that it does not require an unmanageable number of external reviews.
R5 The IGC’s procedures for documenting the process of selecting research projects is good, but could be improved in several ways:
1. The IGC comprehensively documented its commissioning process in 2017. Going forward, this documentation should be updated on an ongoing basis to reflect any changes in the IGC's procedures.
2. Documenting the Funding Decisions: Overall, the minutes of CB meetings were of good quality: they were prepared in accordance with the procedures set out in the Research Strategy and presented information in a clear fashion. Minutes for the later CBs only presented information on projects funded by the RP: in contrast minutes from the earlier CBs presented information on proposals funded by both the RP and the CP. The CP is a larger source of funding than the RP for projects approved by the CBs. We recommend that the IGC return to its earlier practice of presenting to DFID information on all the funded proposals, not just those funded by the RP.
3. Documenting Participation in the Decisions: The minutes prepared by the IGC clearly indicate who participated in each CB meeting. Information on the participants in the meeting should indicate whether they participated in person or via telephone (a practice adopted in the minutes of later CBs). For those participating by telephone (in particular the CDs), we recommend that the minutes record which proposals were discussed when they did participate in the meeting.
4. “Pre-Screening” of Proposals: The IGC should also provide a report to DFID after each CB on the criteria used for pre-screening, as well as a list of the topics and PIs for the pre-screened (i.e. rejected) proposals.
5. Information on the Proposals Submitted: The quality of the data available for the entire set of submissions is less satisfactory, particularly for CB1 and CB2. The IGC should be interested, if only from a learning perspective, in the characteristics of the researchers who submit proposals, even if they are unsuccessful. This information will be very useful in future external evaluations of the IGC. We recommend that the IGC devote more resources to ensuring that it maintains comprehensive information on all submissions to each CB, and that this information is comparable across CBs.
6. Participation of “local” researchers: The analysis in the 2016 IGC paper on the participation of “local” researchers required some staff time to complete, but was very informative and worthwhile. Carrying out this exercise when proposals are evaluated would, however, require relatively little additional work, and we recommend that the IGC compile - and report - this information on a regular basis in future.
7. Cross-Project Linkages: The IGC’s database of proposals submitted to the CBs do not include a field indicating whether the proposal is linked to an SPF or to another IGC activity. This information is usually mentioned in the proposal narrative or otherwise known by the IGC staff, and we recommend that these linkages be identified in the documentation submitted to the CBs and recorded in the proposal database, and that the linkages to SPFs in particular are tracked and reported annually by the IGC.
We examined the IGC’s oversight of research implementation and concluded that it too was largely consistent with best practice. The Research Programme has a strong sense of ownership of projects funded by the Research Programme, and the COs have ownership of SPFs. There seems to be less sense of ownership of research projects funded by the Country Programme, and some inconsistency across COs in the procedures for oversight of their research content. The process for managing research mostly follows best practice, but LAs could be used more effectively.
With respect to research implementation, we recommend the following:
R6 The IGC should reconsider the role of the CD in the approval of approving project Progress Reports, and Final Reports / Working Papers. We recommend that the LA be involved in these approvals as well, either as a joint approver, a second approver or with the CD designated as the approver for some (more policy oriented) projects and the LA for other (more research oriented) projects.
R7 The IGC should introduce ‘project completion reports’. These would be relatively short documents, one or two pages in length: succinct, confidential reflections of what goes wrong as well as right in terms of both research content and policy impact.
# The IGC As a Policy Influencer
## Defining and Measuring Policy Influence
Research can influence policy in a variety of ways. The IGC’s system of “impact scoring” reflects what is sometimes termed the “instrumental” use of research, in which research has influence through its effect on a specific policy decision, law or regulation. As Carden (2009) and others have argued, research can have other effects on policy that may be just as if not more important in the longer term. Research can:
1. expand policy capacities
2. broaden policy horizons
3. affect decision regimes
More details can be found in Box 2 below, drawn from Carden.
Box 2: What is influence?
“IDRC’s evaluation of development research projects around the world, in very different political contexts, confirmed three overall categories that describe how research can affect policy. / First, research can expand policy capacities. Research can strengthen the institutional framework supporting policymaking by enhancing the policy community’s own collective ability to assess and communicate innovative ideas, and by cultivating new talents for analysing and applying incoming research advice. / Second, research can broaden policy horizons. Policy is often frustrated by a scarcity of choices. Research can improve the intellectual framework surrounding policymaking by introducing new ideas to the policy agenda, by ensuring that information comes to policymakers in a form and language they can quickly grasp and use, and by fostering helpful dialogue between researchers and decision makers. Researchers win the respect and gratitude of policymakers by providing new insight or information that can unlock those zero-sum, ‘either-or’ policy dichotomies that so often seem to constrict debate and decision. / Third, research can affect decision regimes. The quality of a policy can be determined as much by the procedures of deliberation and decision as by its content. Research findings can improve the policy-process framework by helping to open and rationalise the procedures of legislating, administering, and evaluating government policies and programmes. Skills and attitudes characteristic of good research — not least, a spirit of curiosity and fact-based argument — can improve the operations of government. / The crucial point about these three categories of influence is that they go well beyond changing particular policies. The most meaningful and lasting influence is less about specific policy change than about building capacity — among researchers and policy people — to produce and apply knowledge for better development results. This kind of influence can take years, or even decades, to take effect or become apparent. But it is no less important for that.”
Source: Carden (2009, pp.20–1)

In practice, the IGC’s approach to measuring impact in Phase II has been based around the instrumental view – which is essentially the definition of a Level 4 impact (see Box 3 below). This is reasonable, given that the impact levels were created as an annual monitoring tool that could be applied to a large number of cases in a relatively short time frame. The other dimensions of policy influence take longer to manifest themselves and are harder to measure, and it is unrealistic to think they could be tracked on an annual basis. IGC is of course aware of these other dimensions and has proposed ways in which they might be reflected in the impact measurement system in the future (IGC, 2019b).
The IGC’s four level system of impact scoring made its first appearance in the 2011-12 Annual Report. (IGC, 2012) and has been part of the IGC’s annual reporting process since then. The definitions of the impact levels have remained broadly unchanged since 2012, though the process of selecting the cases and gathering evidence to support the impact claims has improved significantly over time, in particular since 2015.
Box 3: IGC Impact Level Measurement
“Level 1 denotes ‘ideas created/mobilised’. The IGC produces work analysing a policy question, but this work has not yet fed through to senior government officials or other policy stakeholders, often because it is at an initial stage. / Level 2 signifies ‘disseminated to government’. IGC outputs have been formally conveyed to the relevant senior policymakers, but not yet discussed in depth with them. / Level 3 signifies ‘high level hearing’. Outputs in this category have been disseminated to senior policymakers, and 'internalized' in the sense of having been discussed in detail and follow-up work and discussions having been requested. / Level 4 signifies that ideas and outputs created by the IGC are reflected in policy responses and reforms. This can be evidenced by policy documents – laws, strategies, cabinet papers, decisions, etc. – being changed in ways that reflect the IGC's analysis.”
Source: IGC Annual Report for 2014-15 (IGC, 2015, p.39)

The number of Level 3 and Level 4 “impact cases” is Output Indicator 1.2 (“Number of IGC projects (cumulative from baseline) that have substantially contributed to the policy process”) in the IGC Phase II logframe. The most recent version of the logframe (DFID, 2018a) defines Levels 3 and 4 slightly differently:
- “Level 3: hearing with senior/influential policymakers, with evidence that recommendations were internalized and/or that exchanged ideas have influenced policy discussions”
- “Level 4: policy decision demonstrably and substantially informed, caused or influenced by the IGC”
The IGC reports on the number of impact cases in its Annual Reports and they are discussed as part of DFID’s Annual Review. As part of our evaluation, we reviewed a random sample of these impact cases each year: we summarise the results of these reviews in Section 5.2.3.3 below.
## Achieving Policy Influence at the Country Level
This Section addresses EQ 2 and EQ 5.1:
- To what extent has the IGC’s Country Programme established and implemented an effective Country Strategy that responds to the priorities and needs of its partner countries?
- To what extent has this strategy been successful in enabling the IGC to influence policies relevant to growth at the country level?
To what extent has the IGC made a sustainable contribution to evidence-based policymaking on issues related to growth in its partner countries?
and Output 1 in the IGC Logframe (DFID, 2018a)
Country-specific, evidence-based, and timely advice provided to answer developing country policymakers' growth questions.
### How Did the IGC Define Its Policy Influencing Strategies?
In formal terms, the strategies for each IGC partner country are defined by the CSNs. These set out – at a broad level – the issues on which the IGC will work, and the departments and ministries with which they will work on these issues. The CSNs are revised from time to time, but not on a regular basis. The priority issues for each partner country were, however, revised more frequently as part of the preparations for the CBs. Each Country Team listed the current set of issues that were viewed as high priority for their country, and these lists, along with the priorities for each Research Programme theme, were made available to applicants. As a result of the scheduling of the CBs, these priorities were updated frequently in 2014 and 2015, once in 2016 and once in 2017 (see Table 3).
### How Did the IGC Implement Its Policy Influencing Strategies?
In his “multiple streams” approach to understanding public policy processes, Kingdon (1990) argues that issues acquire salience and importance – and “policy windows” open – when there is a confluence of three “streams” – problems, policy and politics. These windows can open and close suddenly and unpredictably, and in order to exploit them, policy entrepreneurs must be alert to these new opportunities and be prepared to move quickly to exploit them. This introduces an element of “opportunism” into the strategies of think tanks and other policy research institutes. In the case of the IGC, the CDs will have to use their relationships with senior policymakers to understand what issues are currently high priority, as well as what issues are likely to emerge as high priority in the near future. Evaluating their effectiveness in doing this is challenging, because it is a form of “adaptive management”, in which the precise activities and outputs cannot be specified in advance, but change in response to changing circumstances. In these circumstances, evaluation has to examine whether there are reliable systems for gathering information about the changing environment and effective processes for responding to these changes.
In Section 6 below we examine in detail the IGC’s systems for adaptation and learning. In this Section we outline the systems through which the IGC’s Hub staff and Senior Management Team interact with each Country Team in order to monitor the progress of the country strategies, including discussions of existing activities and their impact on policy, as well as discuss potential new research and policy influencing initiatives.
In 2014/15 the IGC changed its method of interacting with the CTs, and switched to a cycle of quarterly meetings between the relevant Hub staff and the CTs. Of the four meetings each year, the first and fourth quarter dealt with the most substantial issues. The Country Review Meetings (CRMs) have taken place quarterly and deal with programme management. Meetings to discuss the PMT and associated reporting have also taken place, but these are slightly separate from the CRMs because they focus on the MEL reporting processes. There would be advantage in linking the two meetings more closely, but this has not happened to date.
The “Project Monitoring Tool” was developed in 2017 and provided a key tool used to structure these interactions and to record information so that it was available to a wider set of staff in the Hub and in the Country Office. The PMT is well constructed and comprehensive and seems to have provided the structure necessary to help the IGC manage a large number of COs, each with only a small number of (generally very busy) staff. Many of the interactions that took place in the quarterly meetings involved discussions of the potential for policy impact of the various activities already underway in the country, with perhaps less discussion of potential future activities. Our interviews (as well as the evidence provided as part of the annual QA exercise for the IGC’s impact cases) suggested that the interactions with the COs in these meetings, as well as telephone and email exchanges were frank and forthright, particularly when they focused on impact cases. This undoubtedly helped with what some of our interviewees described as the change in the IGC’s organisational culture in Phase II, in which the strong focus on research quality in Phase I was balanced by a concern with the achievement of policy impact and became a widely shared goal among staff in both the Hub and the Country Offices.
These quarterly meetings were the basis for “bilateral” interactions between the Hub and each individual Country Team. What they did not provide were opportunities for interactions between different CTs. “Growth Week”, the annual conference that brought together (in London) the Hub staff, researchers from the IGC network, the CTs, and some of their key policy counterparts did provide such an opportunity for cross-country interactions. Although some meetings still took place on a regional basis, it is unfortunate that Growth Week did not take place after June 2016, since our interviews suggested that this significantly reduced the cross-country learning taking place among the CTs. From this point of view, relaunching Growth Week would be an important step in improving the learning taking place across the IGC. We discuss these issues in more detail in Section 6 below.
### How Much Influence Did the IGC Have on Policies at the Country Level?
#### Activities at the country level
During Phase II the IGC undertook 1585 activities in 29 countries. This is shown in more detail in Table 4 and Table 6 below, which are drawn from the IGC’s Project Database. After Events, the most common activity type was Rapid Response and SPF activities, which accounted for 27% of all activities. Country Project Proposals and Research Programme Awards are proposals for longer-term research projects, submitted to the CBs and funded by the Country Programme and Research Programme respectively. They account for 23% and 11% of activities undertaken. Activities without a specific programme budget but which draw on the resources of the IGC are captured in a separate category called “In House Projects” and these activities made up 10% of all activities. Other categories or types of activities include “publications”, “policy engagement output” and “country visits”: these, along with “unassigned” activities together account for only 1.8% of activities.
[note] The database is commonly referred to as the “Project Database” but it consists not only of projects (in the sense of research projects) but a wide range of other activities. A more accurate description would be the “Activities Database”.
[note] Rapid Response Projects were utilised in Phase I and also existed at the start of Phase II but were later replaced by the SPF
[note] The terminology can cause confusion. “Research Projects” is a Phase I term for research projects, which in Phase II were called either “Country Project Proposals” or “Research Programme Awards”, depending on whether they were funded by the Country Programme or the Research Programme. There were a small number of Phase I “Research Projects” still active at the start of Phase II: they are combined with Research Programme Awards.
[note] This includes, for example, activities formerly termed “zero budget activities” and activities undertaken by the CTW initiative.
Table 4: Activity types in Phase II
Activity type	Count	Percentage
Event	426	27%
Country Project Proposal	370	23%
Research Programme Award	170	11%
Research Project	31	2%
SPF / Rapid Response	401	25%
In House Project	158	10%
Other	29	2%
Total	1585	100%

The countries in which these activities took place either had an embedded Country Team, a strategy of flexible engagement or no established country presence. The “flexible engagement” model was developed for countries with more challenging policy environments, where the IGC does not have a full Country Team presence but can build on existing relationships between IGC researchers and in countries where the IGC had decided to scale back its local presence but still remain engaged.
IGC partner countries are shown in Table 5 below. Initially there were 14 CTs. In 2016/17 a strategy of flexible engagement was launched in Jordan, Lebanon and Somaliland, while in Liberia and South Sudan the IGC COs were closed and replaced by flexible engagement. In 2017/18 IGC activities in India were no longer funded by DFID, but were instead supported by the Gates Foundation, and a planned Country Office in Kenya was scaled back to a flexible engagement. Afghanistan was also added as a country with flexible engagement in the same year.
[note] India based activities, despite the change in funder, were still awarded impact levels.
Table 5: IGC country presence
2013/14	2014/15	2015/16	2016/17	2017/18	2018/19
				Afghanistan	Afghanistan
Bangladesh	Bangladesh	Bangladesh	Bangladesh	Bangladesh	Bangladesh
Ethiopia	Ethiopia	Ethiopia	Ethiopia	Ethiopia	Ethiopia
Ghana	Ghana	Ghana	Ghana	Ghana	Ghana
India	India	India	India	Not funded by DFID	Not funded by DFID
			Jordan	Jordan	Jordan
			Kenya	Kenya	Kenya
			Lebanon	Lebanon	Lebanon
Liberia	Liberia	Liberia	Liberia	Liberia
Mozambique	Mozambique	Mozambique	Mozambique	Mozambique	Mozambique
Myanmar	Myanmar	Myanmar	Myanmar	Myanmar	Myanmar
Pakistan	Pakistan	Pakistan	Pakistan	Pakistan	Pakistan
Rwanda	Rwanda	Rwanda	Rwanda	Rwanda	Rwanda
Sierra Leone	Sierra Leone	Sierra Leone	Sierra Leone	Sierra Leone	Sierra Leone
			Somaliland	Somaliland	Somaliland
South Sudan	South Sudan	South Sudan	South Sudan	South Sudan	South Sudan
Tanzania	Tanzania	Tanzania	Tanzania	Tanzania	Tanzania
Uganda	Uganda	Uganda	Uganda	Uganda	Uganda
Zambia	Zambia	Zambia	Zambia	Zambia	Zambia

Country Office
Flexible Engagement
[note] Two offices in operation, in Bihar and in Delhi.
[note] Merged with the Sierra Leone office.

Table 6 below shows how activities were distributed across countries. There were 1410 activities in countries with a Country Team or with flexible engagement, accounting for 89% of all activities, while the 127 non-country-specific activities accounted for 8%, and the remaining 48 activities across 22 countries accounted for 3% of all activities.
Table 6 also shows the distribution across countries of activity types, grouped by Research Programme Award, Country Project Proposal and Research Project activities, Rapid Response and Small Projects Facility, and In House Projects. The category Other includes Policy Engagement Output, Publication, and Country Visit types and represents 1.8% of all activities
[note] “Research Projects” was the term used in Phase I for all research activities with no distinction made between whether the Country Programme or the Research Programme provided the funding. In Phase II, Research Projects only occurred in at the beginning of the Phase.
[note] Introduced in October 2014
Of the countries with a Country Office or which use flexible engagement, eight of them had fewer than 5% of all activities. And of those, seven at some point used flexible engagement strategies. Across countries with a country presence, the majority of activities (38%) were focused on research (Country Programme Proposals and Research Programme Awards and Research Projects); shorter-term activities (SPFs and RRs) represented 29%; and Events accounted for 26% of activities.
For countries that did not have a Country Office or which were not part of the flexible engagement strategy, more of the activities tended to be research projects, or, in the case of non-country-specific activities, events.
Table 6: Activity types by country
Country	Count of activities undertaken in partner countries					Proportion of activities undertaken in partner countries
	Country Project Proposal	Research Programme Award	Research Project	SPF / RR	In House Project	Event	Other	Total	Country Project Proposal	Research Programme Award	Research Project	SPF / RR	In House Project	Event	Other
Afghanistan*	0	3	0	3	2	1	0	9	0%	33%	0%	33%	22%	11%	0%
Bangladesh	20	6	0	17	2	29	1	75	27%	8%	0%	23%	3%	39%	1%
Ethiopia	23	3	2	17	1	23	0	69	33%	4%	3%	25%	1%	33%	0%
Ghana	33	6	1	14	3	26	0	83	40%	7%	1%	17%	4%	31%	0%
India	86	49	3	22	11	45	1	217	40%	23%	1%	10%	5%	21%	0%
Jordan*	0	0	1	2	1	2	0	6	0%	0%	17%	33%	17%	33%	0%
Kenya*	2	4	0	5	0	2	0	13	15%	31%	0%	38%	0%	15%	0%
Lebanon*	0	0	1	3	2	0	0	6	0%	0%	17%	50%	33%	0%	0%
Liberia†	14	1	1	19	2	9	0	46	30%	2%	2%	41%	4%	20%	0%
Mozambique	14	1	3	21	9	22	0	70	20%	1%	4%	30%	13%	31%	0%
Myanmar	13	3	0	43	20	21	1	101	13%	3%	0%	43%	20%	21%	1%
Pakistan	42	17	2	54	7	10	0	132	32%	13%	2%	41%	5%	8%	0%
Rwanda	24	2	4	44	42	15	1	132	18%	2%	3%	33%	32%	11%	1%
Sierra Leone	16	2	0	26	7	19	0	70	23%	3%	0%	37%	10%	27%	0%
Somaliland*	0	0	0	0	1	1	0	2	0%	0%	0%	0%	50%	50%	0%
South Sudan†	3	0	2	7	4	19	0	35	9%	0%	6%	20%	11%	54%	0%
Tanzania	27	5	6	26	6	29	2	101	27%	5%	6%	26%	6%	29%	2%
Uganda	23	6	0	49	16	34	0	128	18%	5%	0%	38%	13%	27%	0%
Zambia	30	9	2	19	12	42	1	115	26%	8%	2%	17%	10%	37%	1%
Not country-specific	0	34	0	4	1	66	22	127	0%	27%	0%	3%	1%	52%	17%
No country presence	0	19	3	6	9	11	0	48	0%	40%	6%	13%	19%	23%	0%
All countries	370	170	31	401	158	426	29	1585	23%	11%	2%	25%	10%	27%	2%

#### Measured impact at the country level
The IGC uses impact levels to report on policy change across the project portfolio. Section 5.1 and Section 6.2 discuss in more detail the IGC’s method of measuring and classifying its policy impacts; in this Section we provide a cross-country overview of the impact scores achieved during Phase II.
[note] Since 2015 the IGC's MEL systems, processes and capacity have increased, and this may account for at least some of the sharp increase in, and then levelling off, of recorded impact cases.
A third of the IGC’s activities are categorised as having a policy impact in the project database, in the sense that they had an impact Level of 3 or more, awarded at least once.
Table 7: Policy impact across all activities
Policy Impact	Number	Percentage
Yes	588	37%
No	973	61%
Uncategorised	24	2%

Of the 588 activities categorised as having policy impact, 213 (36%) were categorised as having Level 4 impact, 35 (6%) were categorised as having a Level 3-High impact, and 340 (58%) were categorised as having Level 3 impact.
[note] Stratification of Level 3 cases was introduced by the IGC in 2018/19 to enable better understanding of the extent of engagement, dissemination and internalization. A ‘high’ Level 3 represents a ‘stronger' degree of stakeholder internalization. A ‘low’ Level 3 represents a ‘weaker’ degree of internalisation.

Figure 1: Policy impact levels for activities between 2013/14 and 2018/19
Impact levels assigned to activities during Phase II are shown in Table 8 below. The totals in Table 8 exceed the 588 activities categorised as having policy impact because an activity may have multiple instances of policy impact. Indeed, for activities with policy impact, the average number of impacts per activity was 1.3 with a maximum of four impacts assigned in five cases. As the IGC notes, the ability to have multi-year impact depends on the nature of the project, but also on opportunities identified by the CTs for engagement during and beyond the project lifecycle. Level 3 impact means that policy discussions have been influenced and most (66%) of the IGC’s policy impact relates to this type of influence (bearing in mind that activities may have multiple impacts).
Table 8: Number of impact cases by year, Phase II activities only
[note] These figures include only activities assigned to Phase II in the Project Database, and so differ from the figures reported in the Logframe and Annual Reports, which include as well projects from Phase I having an impact in Phase II. This makes a difference in the early part of Phase II, but the effect falls over time.
Impact level	2013/14	2014/15	2015/16	2016/17	2017/18	2018/19	Level total
Level 3	27	41	78	107	117	73	443
Level 3 - high						40	40
Level 4	12	19	45	62	48	61	247
Year Total	39	60	123	169	165	174	730

These figures include only activities assigned to Phase II in the Project Database, and so differ from the figures reported in the Logframe and Annual Reports, which include as well projects from Phase I having an impact in Phase II. This makes a difference in the early part of Phase II, but the effect diminishes over time. Table 9 shows the number of impact cases when Phase I activities are included as well.
Table 9: Number of impact cases by year, Phase I and II activities
Impact level	2013/14	2014/15	2015/16	2016/17	2017/18	2018/19	Level total
Level 3	38	41	82	107	117	73	458
Level 3 - high						40	40
Level 4	16	22	46	64	48	61	257
Total	54	63	128	171	165	174	755

Table 10 below shows the main activity types and the proportion of each that were assigned a policy impact. SPFs are designed to respond rapidly to policy requests from government and to develop new opportunities for policy engagement. This activity has the highest proportion (48%) of activities which were categorised as having policy impact. Country Project Proposals (42%), Research Projects (32%) and Research Programme Awards (26%) had the next highest proportions of activities categorised as having policy impact. These activities all had a higher proportion categorised as having policy impact compared to Events and other activities. Of the Events which achieved policy impact, however, 74% were Level 3 impact which is consistent with the ability of Events to influence policy discussions as opposed to higher level impact which requires influencing of policy decisions.
[note] In House Projects have a higher ratio (72%) but this is misleading. In House Projects are activities undertaken by IGC Staff (e.g. Country Economists or City Economists) as part of their normal duties and not as part of a particular project with a budget allocation. When these “normal” activities do have a Level 3 or Level 4 policy impact then an In House Project is created to which the impact case is attached. As a result, a high proportion of In House Projects are associated with impacts.
Table 10: Policy impact by type of activity
Activity type	Activities with policy impact			Activity policy impact levels
	Number of activities with policy impact	Number of activities with policy impact	Proportion of activities with policy impact	Level 3	Level 3 - high	Level 4
Country Project Proposal	370	155	42%	136	9	74
Event	426	73	17%	58	5	15
Research Programme Award	170	44	26%	38	2	16
Research Project	31	10	32%	8	0	2
RR / SPF	401	192	48%	142	14	93
In House Project	158	113	72%	61	10	46
Other	29	1	3%	0	0	1

Table 11 compares activities in countries with a Country Office versus those with Flexible Engagement countries. For flexible engagement countries, 31.1% of activities have impact, while for countries with a Country Team, 34.4% of activities have impact.
Table 11: Activity and impacts across countries with a country team or with flexible engagement
Country	Activities with policy impact			Policy Impacts by country
	Number of activities	Number of activities with policy impact	Proportion of activities with policy impact	Level 3	Level 3 - high	Level 4
Afghanistan	9	4	44%	2	1	1
Bangladesh	75	28	37%	26	2	8
Ethiopia	69	24	35%	23	2	7
Ghana	83	33	40%	25	1	14
India	217	60	28%	42	1	27
Jordan	6	2	33%	1	1	0
Kenya	13	2	15%	2	0	0
Lebanon	6	2	33%	2	0	0
Liberia	46	16	35%	14	1	6
Mozambique	70	34	49%	36	2	15
Myanmar	101	46	46%	37	5	14
Pakistan	132	63	48%	42	3	41
Rwanda	132	71	54%	40	5	40
Sierra Leone	70	30	43%	16	4	18
Somaliland	2	2	100%	2	0	0
South Sudan	35	6	17%	6	0	1
Tanzania	101	36	36%	25	2	15
Uganda	128	60	47%	48	3	24
Zambia	115	43	37%	36	3	11
Total for country office and flexible engagement	1410	562	40%	425	36	242
Not Country-Specific	127	7	6%	5	2	1
No country presence	48	19	40%	13	2	4
Programme total	1585	588	37%	443	40	247

Countries with IGC Offices denoted in bold, Flexible engagement countries in italics

As shown in Table 12, in general activities that have been categorised as having policy impact are more expensive than those which do not. Exceptions here are the Other category, which includes country visits, policy engagement output and publications, and Research Projects.
Table 12: Average cost of activity types
	Average cost of activity with policy impact	Average cost of activity without policy impact	Average cost of activity
Country Project Proposal	£45109	£28003	£35169
Event	£11643	£7759	£8407
In House Project	£0	£0	£0
Other	£1043	£15924	£15411
Research Programme Award	£69106	£46791	£52566
Research Project	£12995	£20347	£16350
SPF / Rapid response	£12779	£10436	£11558
Total	£26749	£17877	£20752

#### Quality of the IGC’s impact measurement system
The IGC reports on the number of impact cases in its Annual Reports and they are discussed as part of DFID’s Annual Review. As part of our evaluation, we reviewed a random sample of these impact cases each year: a 20% sample for 2015/16 and 2016/17 (IEB, 2016f, 2017); and a 12% sample for 2017/18 (IEB, 2018b). Our reviews examined, for the sample of cases:
1. whether the impact levels assigned by the IGC corresponded to the definitions of the impact levels
2. whether the IGC treated the cases in the sample in a consistent manner
3. the quality of the evidence held by the IGC to support its assignments of impact levels.
Overall, we found that the IGC’s assignment of impact levels did correspond to the definitions in the logframe: there were exceptions, but they were small in number and in most cases a matter of judgement. In 2017/18, for example, we found that in 2 of the 19 cases we examined the assignment did not seem to satisfy the definition. Both cases involved Level 3 impacts, which we found to raise more issues than did Level 4 impacts (IEB, 2018b, pp.10–11). In 2016/17 there was one similar case and in 2015/16 two. Part of the difficulty with Level 3 cases is that it is difficult to find convincing evidence for “internalisation” of research results. In response to this difficulty, the IGC has in 2018/19 piloted a revised system of indicators in which the Level 3 impact cases are divided into two categories (IGC, 2019b).
In practice the Level 3 impacts raised the most questions in our review, partly because providing convincing evidence of “internalisation” is inherently challenging, and partly because the nature of the impacts varies very widely across Level 3 cases. For this reason, we think the IGC’s recent proposal to divide the Level 3 cases into two categories (“High Level 3” and “Low Level 3”) seems appropriate (IGC, 2019b, pp.8–9). The “Low Level 3” category could be retained, since it seems to be useful as an indicator of progress towards impact, while the “High Level 3” category seems to correspond better to the notion of impact that has not reached the level of changed policy. It would also seem sensible to take into account only the High Level 3 cases in any future logframe indicators, and in the annual selection of Level 3 and Level 4 impact cases. The IGC has demonstrated in Phase II that it can deliver an impressive number of impact cases each year, and so this seems like an opportune moment to concentrate more on the “quality” and less on the quantity of cases.
Our reviews of the impact cases also examined the relevance and quality of the evidence held by the IGC. Evidence includes email exchanges, requests from policymakers for materials to disseminate among colleagues, requests for follow-up discussions/projects, follow-up meetings, minutes of meetings detailing internalisation of IGC work prepared by the IGC and which are then sent to policymakers participating in the meetings. Not surprisingly, the “quality” of the evidence varied across impact cases. For some cases the evidence was particularly convincing: it was drawn from both IGC and external sources, and each piece of evidence was clearly relevant to the claimed impact. The evidence provided for other impact cases in the sample did not always meet this high standard, but the overall quality of the evidence showed a steady improvement over the three years. Over time, there were more exemplary cases of well-argued justifications supported by relevant evidence from a range of sources, and fewer examples of weakly argued justifications and limited evidence.
We found that the IGC’s processes for determining impact levels are thoroughly documented; and for the sample of cases we inspected, these procedures were followed, the decisions were in accordance with the definitions of impact levels, and there was evidence available from both IGC and non-IGC sources to support the IGC’s decisions.
Overall, we would therefore conclude that the IGC’s system of impact measurement is a suitable and appropriate tool for monitoring impact and progress towards impact on an annual basis. The number of Level 3 and Level 4 cases are also used in the logframe as Indicators for Output 1 (DFID, 2018a), and this also seems appropriate, given the shorter run nature of logframe outputs.
#### Suitability of the IGC’s impact measurement system
These impact levels do, however, have a role that goes beyond annual monitoring: they also play a role judging whether the Logframe Outcome has been achieved. This Outcome is “Credible growth policies and programmes implemented in developing countries” and has two Indicators:
- “Number of changes to growth related policies (based on IGC research and advice), indicated by number of L4 impact cases.”
- “Number of partner and non-partner countries where ideas emanating from IGC programme have influenced policy discussions, indicated by L3 and L4 impact cases.”
Achievement of the Outcome rests, then, on the number and distribution of impact cases identified by the IGC.
The values of Indicator 1 for the Outcome in the IGC Logframe (DFID, 2018a) are based on the number of L4 impact cases.
[note] The "achieved" values for Indicator 1 recorded in the Logframe (and in the relevant Annual Reports) do not, however, agree with those calculated using the project database in all cases. The reasons for this discrepancy are unclear. The figures from the Project Database suggest that the planned value of the Indicator was not achieved in 2013/14

Figure 2: Outcome Indicator 1 - Number of changes to growth related policies
Outcome Indicator 2 is the number of partner and non-partner countries in which there was policy impact. As shown in Figure 3 below, the number of partner and non-partner countries in which there was policy impact exceed the target except for the first year of Phase II. The initial targets were based on the expectation that policy impact (i.e. achieving a Level 3 or 4 impact) would be achieved in each of the partner countries and was increased in later years to include non-partner countries.

Figure 3: Outcome Indicator 2 - Number of partner and non-partner countries where ideas emanating from IGC programme have influenced policy discussions

As discussed above, the current system of impact level measurement is suitable as a monitoring tool compiled on an annual basis. It may be asking too much of such a tool to expect it to serve as well to assess how the IGC’s progress towards achieving its Outcome and Impact, which involve longer-term change.
The current system of impact measurement is suitable as a measure of policy influence and impact for some kinds of policy changes, but less so for others. “Blocking” or reversing unwise policies is a policy change that the current system of impact measurement captures very well. First, there is seldom any need to wait for the impact to manifest itself: a policy is blocked and this is usually immediately apparent. Sustainability can sometimes be an issue, but issues of implementation seldom if ever arise in “blocking” cases. We found several examples of “blocking” in the case studies we carried out for our mid-term report in 2016. Box 4 describes one of these cases, from our mid-term report (IEB, 2016c).
Box 4: A Flat Tax for Rwanda
In the early 2010s Rwanda was underperforming in terms of attracting inflows of FDI, and the government of Rwanda was attracted to policy reforms such as a flat tax, which apparently had boosted inflows of FDI in other small countries. In October 2011, senior officials at MINECOFIN asked the IGC Country Office to provide an analysis of a proposal to introduce a flat tax system for personal and corporate taxation in Rwanda. In response, the IGC commissioned a paper reviewing the international experience with flat tax systems. The paper raised questions about the supposed benefits of flat taxes, and analysed the potential impact on tax revenues of introducing a flat tax system in Rwanda. The analysis found that a flat personal income tax rate of 15% (as proposed by the government) would result in a loss of between 39% and 44% of government tax revenues. These findings were presented to the Minister of Finance and Economic Planning and his senior officials in December 2011 and the idea was subsequently abandoned. The IGC assigned this a Level 4 impact, claiming that the IGC's work "directly led to the abandonment of a potentially harmful flat tax proposal" (IGC, 2012, vol.I). Our contribution analysis of the project supported this claim.
Source: IEB (2016c)

The current system does, however, fail to address four issues that are key to assessing the importance of a policy change over the long run:
1. Sustainability: How likely is it that the policy change be abandoned or even reversed at some later date?
2. Implementation / Mainstreaming: Can a policy that has been successfully piloted be implemented on a wider scale?
3. The importance of the policy change: The IGC system in effect treats all policy changes as equal, no matter what their likely impact on the country or its growth rate.
4. The extent to which the policy change can be attributed to the IGC: Any policy change is likely to be the result of the interplay of a number of social and political forces, as well as the actions taken by a range of policy actors (the IGC and others).
i) Sustainability: Will the policy change be sustained over the long term, or will it be abandoned or reversed? Sustainability is an important issue, and one that is very difficult to capture in an annual monitoring and reporting cycle. It arises in a range of projects, and is emerging as an important issue as we;; in connection with Randomized controlled trials (RCTs) (Miguel, 2019).
This issue arose in the Sierra Leone and Ghana flagships cases that we examined earlier this year (IEB, 2019b; d). Box 5 highlights the sustainability issues that arose in the Sierra Leone elections project.
Box 5: Elections in Sierra Leone
We examined a cluster of IGC projects that explored the behaviour of both candidates and voters during the 2012 and 2018 elections in Sierra Leone. The projects organised a series of debates to make voters better informed about the policies of the candidates, and the candidates more willing to be held accountable to the voters. RCTs were used to study the impacts on voters and candidates, comparing voters exposed to the debates to control groups that were not. There were significant impacts on both voters and politicians, and since the impact assessment was done using RCTs, we can be fairly confident about the causality involved. Voters were better informed about the candidates and the candidates displayed more willingness to attend “accountability meetings” held after the elections. / The challenge facing such projects is that elections take place infrequently – in Sierra Leone every six years. As a result, there may not be any opportunities to sustain the changes in the behaviour of voters, candidates and political parties and after six years have passed, the individuals and institutions you have dealt with may have changed and the behavioural changes dissipated. One solution might be to embed these projects within a longer-term strategy about governance reform, but this would require a longer-term strategy and a clearer theory of change
Source: IEB (2019d)

ii) Implementation / Mainstreaming: The IGC has supported a range of pilots, some involving RCT, to explore new ideas and policy innovations. Many of these pilot interventions have demonstrated significant impacts. But it is not obvious how you can go from a small-scale pilot to a policy change implemented across an entire government or country. Even if the pilot was carried out using a rigorous methodology such as an RCT, the rigorous methodology can only ensure “internal validity”, not “external validity” (i.e. can the results be extrapolated to other contexts). This is another issue that has emerge as an important issue in the development research community in recent years.
This issue arose in the mid-term report on the tax system in Pakistan. Creating stronger incentives for tax inspectors to collect tax revenue had a large impact in the pilot studies, but the revenue authorities found they were not able to introduce an incentive system for some of their staff and not others. We examined this case in both our mid-term report in 2016 and during our visit to Pakistan earlier this year (IEB, 2016b, 2019c). Details can be found in Box 6.
Box 6: Incentives for tax collectors in Pakistan
We examined in both our mid-term and end-term reports a cluster of projects involving tax collection in Pakistan. The projects were the first large-scale field experiment examining impact of introducing performance pay for tax collectors. Under the experiment carried out by the project 482 property tax units in Punjab were assigned to one of three performance-pay related schemes or to a "control" group. The scheme with rewards based entirely on revenue did best, increasing tax collections by 46%, compared to a 28% increase in the comparison group over the same period of time. The experiment confirmed that incentives had significant effects, but it proved difficult to implement the incentives scheme across the department because other groups of civil servants were not in a position to benefit from it. A more recent project involving the same researchers tested the effects of using a non-financial incentive on performance. Tax collectors could choose place of their next posting if they performed well. This too seemed to have an impact on revenue collected, but this too proved hard to implement because of same issue – how can you let one group of civil servants in the department (the tax inspectors) choose their next postings, without giving the other civil servants the same opportunity? The engagement is still ongoing, and so there may be further progress in the future, but for the moment, implementation is not moving forward.
Source: IEB (2016b, 2019c)

iii) Significance of the policy change: The IGC system treats all policy changes as equal, no matter what their likely impact on the country or its growth rate: one Level 4 impact counts for as much as any other Level 4 impact. One of our interim reports addressed this issue, and attempted to quantify the impact of two policy changes that we had examined in our mid-term review (IEB, 2018a). One of them was the Rwanda tax change (a "blocking" change) and we summarize our results in Box 7.
Box 7: The Impact of Avoiding a Flat Tax in Rwanda
One of our interim reports we evaluate the returns from advice provided by the IGC in relation to the implementation of a flat tax in Rwanda. The proposed change would have had an impact on both total tax revenue and on the distribution of income. The objective of this evaluation report is to convert these changes into a single "money metric" measure. We used Atkinson's concept of Equally Distributed Equivalent (EDE) income to combine the distributional and aggregate changes from the policy change into a single number. Converting the EDE into a money metric amount and using a mid-ranked aversion to inequality, we find that introducing the proposed 15% flat tax reform would have reduced EDE in the region of $230m to $254m US dollars, depending upon whether the reform was funded by an increase in VAT or a reduction in public expenditure reduction respectively. The IGC's advice allowed Rwanda to avoid a costly policy mistake.
Source: IEB (2016c, 2018a)

This example demonstrates that some policy changes, in particular those with “systemic” effects, can result in very large losses or gains to the country concerned. The IGC’s current system of impact measurement should ideally take this account by differentiating between policy changes according to the magnitude of their effects. But not all policy changes can be quantified as easily as the Rwanda flat tax proposal, and quantification would certainly not be feasible for a large number of impact cases within the Annual Review cycle. This does, however, represent an important challenge to the current system of impact measurement. It could be addressed in more than one way: the IGC could undertake a periodic evaluation of a limited number of impact cases and try to quantify the benefits of the policy change that had taken place. Alternatively, for projects where quantification seems feasible and informative, the research team itself could be asked to undertake these calculations as part of their final project report.
iv) Attribution
Any policy change is likely to be the result of the interplay of a number of social and political forces, as well as the actions taken by a range of policy actors, including, but not limited to the IGC. Controlling for the other casual influences affecting a policy decision is a significant challenge in studies of the impact of research on policy decisions.
Contribution Analysis (CA) has been proposed as one possible solution to this dilemma. CA offers a pragmatic yet coherent approach to applying the principles of theory-based evaluation to situations in which the programme is one of many potential contributory causes and where it is not possible to measure attribution directly via creation of a scientifically-valid counterfactual.
[note] There are, of course, other approaches, for example the realist approach described in Pawson (2006) and subsequent works.
We applied CA to the impact cases we examined in our mid-term report IEB (2016b; c; d). We examined nine taxation case studies, drawn from Pakistan, Rwanda and Uganda in order to understand how the IGC influences policy. The case studies explored the contexts and causal mechanisms contributing to observed outcomes in order to help us identify a specific set of causal pathways leading from policy research to policy influence and the contexts in and mechanisms by which policy influence does (or does not) occur that can be generalised to other situations. The first step involved identifying the relevant IGC activities and impact cases to be analysed. For the mid-term report we had decided to focus on projects related to taxation, and so gathered data on projects by focusing on and visiting three countries with a significant number of taxation related activities.
Box 8: Contribution versus Attribution
“CA argues that if one can verify or confirm a ToC with empirical evidence - that is, verify that the steps and assumptions in the intervention ToC were realised in practice, and account for other major influencing factors - then it is reasonable to conclude that the intervention has made a difference, i.e. was a contributory cause for the outcome.” (Befani and Mayne, 2014) / Befani and Mayne set out four conditions necessary to infer causality via CA: / Plausibility: the intervention is based on a reasoned ToC: the chain of results and assumptions behind why the intervention is expected to work are plausible, sound, informed by existing research and literature, and supported by key stakeholders / Fidelity: The intervention was implemented as outlined in the ToC / A verified ToC: The ToC is verified by evidence: the chain of expected results occurred, and the causal assumptions held / Accounting for other influencing factors: Context and other factors influencing the intervention are assessed and are either shown not to have made a significant contribution, or, if they did, their relative contribution is recognised and included in the ToC, as part of a larger causal package that the ToC captures as faithfully as possible.
Source: (IEB, 2016e)

Determining the IGC's contribution to these policy changes was challenging. We took into account recent advances in contribution analysis literature, in particular the work of Delahais and Toulemonde (2017) on the impact of research on forestry policy in West Africa. In particular we noted their decision to restrict the range of alternative causal explanations:
Such additional explanations deserve to be qualified as ‘alternative’ if they are of the same nature and magnitude as the initial logical chains. This was not the case in the context of our evaluation. As explained above, it was understood from the beginning that CIFOR and CIRAD had not been the main drivers to the observed changes in SFM. An example of such a major driver was the 20-year endeavour of a handful of international NGOs. Calling their sustained powerful efforts an ‘alternative explanation’ would have been senseless. They definitely were more than an ‘alternative’ to the tiny influence of the evaluated research. (Delahais and Toulemonde, 2017)
This lent support to our approach of focusing on the activities of other policy research actors in our ToC, and not on the full range of socio-economic forces at work in each policy episode. There were certainly a number of important other actors (for example the IMF or local policy research institutes) that were actively engaged in addressing the same critical issues as the IGC does In order to approach this issue as carefully as possible, we have constructed our accounts of policy change as "Contribution Stories", using a common template based on the Rapid Outcome Assessment (ROA) approach, taking particular care to identify the potential contribution of these other actors. These "Contribution Stories" represented the first step in our analysis of these episodes of policy change using CA. It allowed us to make well informed - albeit still informal - assessments of the IGC's contribution to these policy changes, and to state with some confidence that the IGC did indeed contribute to the policy changes we analyse.
In our end-term report we analysed a smaller number of projects, but these projects were much more diverse in terms of their subject matter: they included measures to improve the performance of civil servants in Ghana; strengthening the Ethiopian Investment Agency, projects examining how the provision of additional information affected the behaviour of voters and candidates in elections in Sierra Leone and measures to build capacity in local government in Pakistan. In general, we found that while there some cases where it was difficult to formulate the most appropriate contribution claim, the close relationships between the relevant policymakers, the IGC Country Office and the IGC researchers, plus close working with policymakers to co-generate or co-produce the research meant that there was no particular difficulty in attributing the policy changes to the activities of the IGC. The only partial exception was the Sierra Leone projects, which involved a close collaboration between the IGC, J-PAL, and the NGO “Search for Common Ground”. IGC funded the work, and the key researchers were closely associated with the IGC, but accounting within our ToC for the different roles played by the three actors proved difficult.
The challenge with the end-term projects proved to be rather different, and in some ways unexpected. As noted in Section 3 above, some of the causal mechanisms at work in the end-term projects were not well captured within our 2016 version of the ToC. This was particularly evident for Ghana and Sierra Leone. Revising the ToC is, of course one of the steps involved in CA, but the changes initially sketched out were significant, and suggest that more work is necessary to enrich the ToC if it is to be useful going forward.
Overall, though, we did not have any difficulties in attributing the policy changes we examined in the end-term report to the activities of the IGC.
### Country Level Influence: Mechanisms and contextual factors
The factors that affect the IGCs ability to influence policy are discussed in this Section. They are drawn from the observations in the mid-term evaluation and the evidence gathered for this end-term evaluation, in particularly the contribution studies of the flagship cases and the analysis of the “less successful” projects (those that got an impact score of 1 or 2).
There are both internal and external factors that affect the policy uptake of the IGCs work, these are discussed below. The internal factors can be considered mechanisms of change, whereas the external factors are contextual change.
#### Internal factors that affect policy influence – mechanisms of change
There are four main internal factors that affected the success of the IGC in Phase II:
1. The structural characteristics of the IGC
2. The management and capacity of the IGC
3. Policy engagement strategy and capability and
4. Research process and outputs.
i) Structural characteristics of the IGC: The following are the most salient characteristics of the IGC that affect policy influence. As identified in the mid-term review, there is significant heterogeneity across the IGC’s COs and strategies, so there are variations in results, but most of these characteristics relate to the IGC as whole.
- The Country Programme of the IGC is a critical success factor: The Country Programme encourages the establishment of longer-term relationships with policy counterparts, helps build the reputation and credibility of the IGC in country, and provides improved understanding of the political economy in country which is important for influencing strategies. There is some evidence that the researchers do not always use the experience and expertise of the CTs, and so do not draw on this benefit enough.
- The credibility of the IGC: This is the next critical success factor. The association of the IGC with the two leading UK Universities (LSE and Oxford) is an important part of its success. Also, as an academic institution it is perceived (and thinks of itself) as having no agenda besides the provision of good evidence to inform decision making.
- The association with respected local institutions as host organisations is another factor that helps to embed the IGC in the local research and policy community, and lends credibility to the IGC. This is likely to be less important in Phase 3 as the IGC’s brand is now well established.
- A mixture of tools and tactics: The IGC has a number of tools and tactics that it can combine to facilitate policy influence, these include high quality, evidence-based academic research; rapid response mechanisms through SPFs, the CtW synthesis strategy, events, communications and direct and continuous engagement with policy makers. The ability of the CTs to combine and use these mechanisms strategically to influence policy is a critical success factor. This is discussed in more detail in point 3 below.
ii) IGC management and capacity
- Balanced emphasis in the IGC on policy and research: In Phase II the IGC Senior Management Team (SMT) has put emphasis on ensuring that the policy impact of the IGC’s work was given equal status to the research. This has had positive results for policy impact, and is reflected in the increasing importance of the Project Influence Plans (PIPs) and Project Influence Reports (and PIRs) that are now prepared for all research projects (and SPFs) in order to encourage researchers to focus on policy impact at the beginning of their work and to monitor it as the research progresses. The emphasis on policy orientation from the start of the research process with the PIPs is a success factor. In practice, however, some PIPs are not well conceptualised, however, and there is evidence that projects that are less successful had poorly conceptualised PIPs (IEB, 2019c).
- Structure and management of the Country Team: A key part of the success of the CTs is the structure, capacity, experience and reputation of the Country Team. It is important in some countries for the Country Team to have local expertise, and be led a local country director. This increases the reputation of the IGC as having good local knowledge. All the CDs are employed by the IGC on a part-time basis. It was necessary in the early days for the IGC to find experienced CDs who had high personal credibility in order to help establish the IGC’s credibility and reputation in country. As the IGC’s reputation has grown and the scale of its operations has increased, and the review of the IGC country programme suggests that some country programmes would benefit from more hands-on management by their CDs. In Phase II the IGC increased recruited Country Economists with more experience, and also provided them with more incentives to remain the job (e.g. ability to be involved in research), and this has helped to boost the capacity of the CTs. The main function of the CEs is however to facilitate and help manage research projects, maintain stakeholder relationships in country and drive the dissemination and uptake of IGC research. This is good use of their time, and they could be doing more synthesis work which local stakeholders would find valuable. An example is a presentation that was done by CE in Ethiopia on the IGCs (and other) research on labour market issues in Ethiopia for a World Bank event.
- Ability to learn and adapt: The IGC has shown an ability to respond to challenges and improve its systems and processes. It is responsive to the recommendations arising out of the Annual Reviews to DFID. The regular meetings and improvement plans that have been put in place are facilitating ongoing improvement. More can be done to implement improvements based on the analysis of the evidence in its own MEL system. This is discussed in more detail in the Section on MEL below.
- Timeliness: In policy influencing timing is important. The research or advice must be not only credible and relevant but also timeous if it is to be used. The SPFs do allow CTs to be responsive to policy makers interests more speedily that the Research Programme, but there are still some challenges with contracting for SPFs specifically, the availability of CDs to approve deliverables (which can cause delays), and the availability of researchers in the IGCs network to carry out the work.
iii) Policy engagement strategy and capability (Strategies used to enhance receptivity to evidence): The IGC does not consciously work with any theory of policy influence (and there are many), but the one that we have found most relevant to the IGC is that of Kingdon (1990) discussed in Section 5.2.2 above.
- CSNs: It is important that the CSNs are based on a good scoping of the main priorities and concerns in each country. They should, and are usually, prepared in a consultative manner with key stakeholders in country, particularly policy makers and development counterparts, so that the IGC is aligned to what other actors are doing and thinking. They are best when they include some forward-looking agenda setting elements as well, that the Country Team can feed into the IGC’s Research Programme.
- Country Team’s mastery of the research to policy field: The ability of CTs to use the tools available through the IGC is a critical part of the success of a Country Team, and there are CTs that are very good at this. The strategic thinking and policy entrepreneurship of the CTs are important. Part of this is their ability to understand strategic dissemination, stakeholder engagement and communications. These are key tools that they need to have in their toolbox, and not all CEs have them. We found examples in our discussion and analysis of the “less successful” projects where a project could have achieved impact if the Country Team had used an SPF to encourage dissemination of the research, or to provide some “evidence-oriented” technical assistance (such as feasibility studies) to assist the state to implement the recommendations.
- A key part of this is understanding policy communities and spheres of influence, and to not limit themselves to deep relationships with a few high-level decision makers, because as will be shown in the context Section below, there is often churn among these decision makers.
- Partnerships: Partnerships with other development actors can be important for ensuring the uptake of IGC research into policy. Partners can convey messages, build support for results and even finance the implementation of the IGC’s ideas (as in the Ethiopia Flagship case, in which John Sutton’s work with the Ethiopian Investment Commission was continued with funding from DFID). Partnerships are also important for scaling up and implementation. Both the IDRC and Y-RISE are currently building a body of knowledge around scaling science, and it would be useful for the IGC to exploit this knowledge in their work. The IGC in some countries is cautious about partnerships because of the perceived risk of being associated with a donor with particular agendas, but this does not seem to be a universal concern amongst all IGC actors, and the risk can be managed. CtW and the IGC in Ethiopia, for example, are developing close relationships with the World Bank, arguably (one of) the most controversial players in the development space.
iv) Research process and outputs
- Co-generation research model: Ongoing close working relationship between the researcher and the policy counterpart throughout the process is a predictor of success as it facilitates the relevance of the insights and recommendations arising out of the research findings.
- Communicating research findings: Research findings must be communicated in a way that is accessible to policy makers, and the insights and recommendations should be practical and applicable. The implications of the findings for policy need to be made clear – even good projects can lead to research findings that are too academic and technical to be of use to policy makers.
- Funding from the Country Programme: The introduction of dual sources for funding CB projects (i.e. from the CP as well as the RP) has contributed to increased impact.
- The IGC research networks: To be demand driven the IGC needs to have a very good sense of who is available and interested in what among its research network. Growth Week was a good way for the IGC CTs to become familiar with the IGC research network and interest them in certain work. The IGC can do more to build, nurture and share the capability of its research network. The CtW methodology of having in-house research team and synthesis products can address this responsiveness to a limited extent. There could be more researchers dedicated to this function, who can be allocated to support synthesis work depending on demand (this has been demonstrated to be useful in times of higher demand).
#### External factors that affect policy influence – Contextual factors
There are a number of key contextual factors that affect the uptake of the IGCs research findings into policy. It is our current understanding, also informed by the findings of a recent evaluation of the Building Capacity to Use Research Evidence (BCURE) initiative (Vogel and Punton, 2018b), is that that these contextual factors are not necessarily predictors of success or failure, but rather it is how the organisation adapts to and works within the given context that is the success factor. It is thus incumbent upon the IGC to note the factors below and ensure that their teams are equipped to address them and to adapt to changes in the context when necessary (based on the evidence that they have gathered through the IGCs monitoring and review systems). The main themes are:
1. State effectiveness
2. Receptivity to research evidence and
3. The nature of the political economy of research in the country, and the policy community.
i) State effectiveness
The ability of the state to implement the findings of the IGC research is a key success factor. The country reports identify limited human resource capacity, the inability to make decisions in highly bureaucratised and hierarchical environments and a lack of funding to implement recommendations as three key concerns. This can vary from institution to institution within a given country.
ii) Receptivity to research and evidence: Receptivity to evidence is discussed above and is well documented. The country reports identify the following factors related to receptivity that the IGC should note.
- Firstly, the civil service in some countries is highly politicised which means that Ministers follow their own political agenda and appoint their own team of advisers. As a result, some issues of interest to bureaucrats may not be a priority for the politicians. (this is noted in the Ghana case study). This factor should be adequately addressed in the PIPs.
- Secondly, the levels of academic training (and experience of doing research) among officials influences their ability to engage with the research process and findings. This will influence the engagement strategy of the PIs and a close relationship between the PIs and the CEs will assist with this.
- Thirdly, the motivation of civil servants to draw on evidence is influenced by the chance that this will be used. This indicates that working with reform minded institutions will increase the chance of success. This has been highlighted in the Ethiopia report in relation to the Ethiopian Investment Commission (EIC). Good communications and the use of events and policy briefs is another important way to increase the motivation and opportunity for civil servants to share the findings of the IGC research more widely with their colleagues.
iii) Policy community: The availability of local researchers can help with a number of the factors mentioned above – relationships with policy makers, understanding of the local context, working together with the CEs. The extent to which there is a strong local research community also influences receptivity to evidence among decision makers as they can help to amplify and convey the ideas of the IGC to policy makers. They can do this by inviting the IGC to events or meetings for example, or to fund the update of IGC ideas. However, it also means that there is more information available to decision makers, and the IGC may be drowned out if it is not strategic in its communication and engagement with policy makers.
#### Conclusions and recommendations for improving policy influence at Country Level
The IGC's Country Programme has established and implemented an effective Country Strategy that responds to the priorities and needs of its partner countries. The IGC's COs and the relationships they develop with their policy counterparts are the IGC's most important route for applying knowledge and for ensuring the relevance of the work it carries out. The importance of the Country Offices in generating impact is confirmed by a broader analysis of the IGC's impact cases: over 60% of the Level 3 and Level 4 impact cases in Phase II were associated either with SPFs or research projects funded by the Country Programme.
The IGC's system of impact measurement does not, however, take into account whether the policies that it influenced were important or significant. For this we must turn to the subset of projects we examined in depth in our mid-term and end term reports. The range of policy issues addressed by the IGC is very wide, and the projects we examined in depth in the mid-term and end-term reviews was not chosen randomly. But even given the purposive nature of our sampling, we found that the issues addressed by these projects were of first order importance to the IGC's partner countries.
The IGC’s country strategy, and the tools it has developed to monitor the success of this strategy, provide an effective approach to tracking individual projects and useful tools for monitoring their impact on policy. As a result, it was straightforward to assess the impact of individual policies and to aggregate these individual impacts into indicators of impact at the country or IGC level. It was more difficult for us to assess whether, for a given country, whether these project level impacts, taken together, were achieving a “step change” in the overall set of policies relevant to growth.
It is important to be realistic: there is no consensus around a single suite of policies that are guaranteed to achieve structural change and permanently higher rates of growth in low income countries. The IGC’s focus in Phase II on individual projects (or in some cases on clusters of projects) seems to us to have been pragmatic and sensible. Looking forward to the future, we believe that the IGC can and should be more ambitious in Phase III: it should aim to influence (and measure its influence) at a broader, system-wide level as well as at the level of individual projects. This will require changes in both its strategy and its MEL systems.
With respect to the IGC’s Country Programme, we recommend

R8 The Country Programme should remain a key instrument in the IGC’s portfolio of policy-influencing tools. Our country visits suggested that the ability of Country Offices to achieve policy influence is constrained by the staff numbers and the time they have available for IGC work. The IGC should explore ways of addressing these constraints in order to increase the uptake of IGC research.
1. For Country Offices where impact is constrained by capacity, the IGC should consider buying more of the time of the CDs (who are currently part-time). If the CDs cannot devote more time to IGC work, then a Senior Advisor could be hired to take up some of the burden of influencing work.
2. CEs play an important role in influencing as well and where their capacity limits the opportunities for influence, the IGC should consider hiring additional high-quality CEs. If overall budget constraints make this difficult, the IGC could explore the possibility of obtaining local (or other non-DFID) funding to “sponsor” the work of a CE.
3. Investing in the professional development of its CEs is another way in which the IGC can make its policy influencing activities at the country level more effective. The work of CEs calls for a range of skills, both hard and soft (policy entrepreneurship, communications and presentation skills, etc.). These skills should be reviewed as part of the annual performance reviews, and where needed, training or other capacity-building interventions should be designed and delivered.
4. Some of this additional capacity should be invested in broadening IGC’s networks amongst the policymaking community of partner countries. This would help reduce the IGC’s dependence on its relationships with a small number of high-level decision-makers.
R9 The IGC’s Policy influencing strategies at the project level have improved during Phase II, but more can be done to strengthen them.
1. PIPs need to take into account not only what the research is likely to “supply” in terms of outputs, but also “demand” – what policymakers are likely to demand and be have the capacity to absorb. PIPs have improved over Phase II but are now stronger on the supply side. They would be more effective if they took more explicit account of external factors (state effectiveness, receptivity to research evidence and the policy community, etc.).
2. These improvements may require the IGC to provide more support to PIs in preparing the PIPs. It may be useful to assign an IGC staff member to provide technical support to researchers on the preparation of their PIPs.
3. In cases where researchers do not have pre-existing relationships with policymakers on the ground, a stronger management function for the CT should be envisaged over the course of the project. Similarly, local researchers may help to bridge such relationship gaps.
4. Projects may fail to achieve a Level 3 or Level 4 impact for a wide range of factors (many of them external to the IGC). The IGC should carry out regular reviews of these projects (as well as its Level 3 and Level 4 projects) to determine why they did not achieve the maximum possible impact, and whether the IGC’s strategy and tactics should be modified to consider whether the findings of those projects might now be more relevant. As a minimum, the findings of these projects should be synthesised and recorded in a database of policy ideas.
5. There is often a tension in policy research projects between the timescales of the researcher and the policymaker. In many cases, the time horizons of policymakers are much shorter than those of the researcher. This can sometimes lead to a feeling of disconnect between the stakeholders and a question mark over the relevance of the research to the policymaker. For longer-term projects in particular, the IGC should design more "interim" outputs and policy recommendations in order as intermediate steps in a longer-term policy change.
R10 Country Teams often work in relative isolation, and their opportunities to interact with, and learn from, other teams in other countries have diminished over the course of Phase II. The IGC should devote more resources and attention to increasing the opportunities for cross-country learning, which our interviews suggested was highly valued by the Country Teams.
1. “Growth Week”, the annual meeting attended by members of the Country Teams, Hub staff, researchers from the IGC network and policymakers, has not been held since 2016. It offered an important opportunity for the Country Teams in particular to learn from each other and to engage with members of the wider research network. The IGC should revive Growth Week as an annual event in Phase III.
2. The IGC needs to take steps to improve its knowledge management. It has produced a large and impressive portfolio of research during its first decade: there are almost 2000 activities registered in the IGC activities database and retrieving information on all the IGC activities relevant to a particular policy issue is not always a simple matter, especially if the IGC has not yet produced a synthesis product on the issue. Even if some of these projects have not had an immediate policy impact, most have yielded interesting policy proposals (or, at least, contain important policy implications). So as to enable a more comprehensive overview of its policy-relevant work, the IGC should consider building a readily accessible and user friendly “IGC database of policy ideas” which would summarise the conclusions of research projects in a way that would be easily accessible to all IGC staff, both in the Hub and the Country Offices.
R11 The IGC Country Programmes have developed effective strategies and tactics to achieve Level 3 and Level 4 impacts. These impacts often involve policy changes that are relatively discrete and self-contained (for example pilot projects exploring a promising new idea). The IGC needs to develop more explicit strategies and tactics to address the challenges of implementation, mainstreaming and scaling up of promising new ideas.
1. Addressing these challenges may require expertise that goes beyond that of economics. The IGC should consider whether, in order to meet these challenges, it needs to draw on the expertise from other disciplines, such as government and public administration, political science and law.
2. Implementation may require partnerships with other institutions that have specialist expertise and/or greater resources. Projects that are likely to involve significant implementation challenges should take into account ex ante the need for (and prospects of) such partnerships. These institutions often have their own agendas, and so the need for such partnerships needs t0 be balanced against the IGC’s reputation for providing independent advice to policymakers.
## Achieving Policy Influence at the Global Level
This Section addresses EQs 3.1 and 3.2:
- To what extent has the IGC established and implemented a strategy for influencing global discussions of policies relevant to growth in low income countries?
- Has the IGC had influence on global discussions of these policies?
and Output 3 in the IGC Logframe (DFID, 2018)
Strengthen IGC's relations with its stakeholders and communicate the IGC`s work globally and locally.
The “global” level means “not at the national policymaking level”, so could be regional or global, or (for CtW) regional or global networks of local government policymakers.
### How Did the IGC Define Its Policy Influencing Strategies at the Global Level
The Global Influencing Strategy of the IGC has four main channels for communication – journal publications, online media (website and VoxDev), events for disseminating information and digital and print publications. In addition, over the last three years, the CtW initiative has developed into a global influencing strategy that uses synthesis products to bridge the communications gap between researchers and policy makers. The report on global influencing is contained in IEB (2019g), which focuses on the CtW initiative and online communications.
Part of the mandate of the IGC has been to influence international or global debates on key themes of the IGC.
The IGC recognises the importance of global engagement and that “communicating the IGC’s research is a vital part of achieving policy impact and thought leadership” beyond the project boundaries and at a global level (IGC, 2016).
Global communications are promoted through the Global Communications Strategy, agreed at a 2014 meeting of the IGC Governance Committee (Leape and Lyness, 2014). There is the most recent version made available to the IEB.
The main thrusts of the strategy are that the IGC will:
- build on its strengths of having a global network of leading researchers and embedded CTs;
- focus its communications around a smaller number of themes (e.g. the Sustainable Development Goals, urbanisation, tax, energy, Ebola);
- develop tailored influencing plans for each topic;
- Use improved channels to communicate on key topics and expand its presence into more popular platforms;
- Build its network and presence in the global policy arena; and
- Build on current researcher’s activities.
The communications function of the IGC is described in Output 3 of the IGC’s logframe (DFID, 2018a) which emphasises stakeholder relationships and communication through participation in international debates through conferences and events; through communication to global and local audience through the media (traditional and online); and in country (through the Country Programme).
Influencing papers were produced for Tax and Urbanisation in 2015; and for Cities and Energy in 2016, when the tax influencing plan was also updated. These documents were provided to the evaluators. According to the DFID Annual Review (2017), the IGC submitted influencing plans on fragile states and industrialisation as well, but we do not have copies of these plans.
The CtW initiative is explored as an example of how the IGC achieves global influence through research, events and country level relationships (mainly indicators 3.1 and 3.3). Section 5.3.2.1 presents information on the online channels used by the IGC (Indicator 3.2). The report also attempts to draw out what the key success factors of the CtW initiative are, that could be useful for replication.
### How Did the IGC Implement Its Policy Influencing Strategies at the Global Level?
#### Cities that Work Initiative
The Initiative was launched in 2016/17 (publicly in 2017/18). It was the brainchild of Paul Collier (a member of the IGC’s Steering Group) who wanted to ensure that policy makers have their questions answered through evidence-based on the available stock of research knowledge. Since 2010 Collier has been actively promoting the need for economics focused work on cities, recognising that there is “… some urgency in urbanisation – if city managers make the wrong decisions now, we will live with the problems for decades” (respondent). The IGC recognised whereas much of the focus in development economics has traditionally been on rural development, urbanisation was becoming an increasingly important issue in the developing world, and that a thematic focus on cities was needed to rapidly fill this gap. Further much of the work on cities was being done by architects and planners, not economists and so was not focused on growth issues. Cities that Work (CtW) fitted well with the IGC’s influencing plan for cities and urbanisation (Leape and Lyness, 2014). The trio of economists who drove CtW are Paul Collier, Tony Venables (also a member of the IGC’s Steering Group) and Ed Glaeser, RPD for the IGC’s Cities theme.
“Policymakers across the developing world are at a critical juncture; decisions taken now to address rapid urbanisation will shape whether cities become engines or obstacles for national growth. Cities that Work is an initiative of the International Growth Centre (IGC) that has brought together a committed network of policymakers, researchers, and urban practitioners in developing and applying a practical synthesis of knowledge to guide urban policy in this critical period.” (IGC, CtW overview, 2019)
The task of the CtW programme was thus to work closely with policy makers to identify their questions, and help them to apply the relevant academic research. This was done by producing synthesis papers based on the existing stock of knowledge, including IGC research, and has expanded into a range of other outputs and activities including events, both at a national level and globally, as described below.
CtW is led by a Council chaired by Edward Glaeser, thus integrating CtW with the Cities research programme of the IGC. The role of the Council is to provide knowledge leadership and ensure that the initiative has policy impact. The Council is comprised of members of the policymaking, academic and practitioner communities, who have an in depth understanding of the opportunities and challenges in urban policymaking globally (IGC, 2019a).
[note] https://www.theigc.org/research-themes/cities/cities-that-work/council/
There is an increasing focus on cities among development actors, and it might be argued that there are already many sources of policy advice in this space. The findings from this evaluation suggest that CtW makes a valuable and distinctive contribution precisely because it brings research by economists to the attention of urban policy makers, whose main sources of advice tend to be architects and urban planners. Policymakers find the economics tool set useful for making decisions about how the development of cities can support growth.
The CtW initiative has achieved remarkable growth and success in terms of its network, its visibility and its impact cases in the short time since it has been established. The critical success factors are that it was set up to be demand led and policy-oriented; it is highly responsive with quick time frames because it uses the existing stock of knowledge and so does not need to wait for research to create new knowledge; it provides cities with access to high quality evidence and advisers who are leaders in the field. It provides the IGC with a powerful tool to connect its research and country programmes. Perhaps the biggest difference between CtW and the rest of the IGC is that it uses synthesis research as the basis for engagement (not primary as is in the country model), and it offers technical assistance based on the stock of available evidence. This allows for more impact scores, but not necessarily of a more systemic nature.
The power of CtW is that it connects knowledge generation (research from the IGC and other), through synthesis work, to global influencing opportunities – so in a sense, it ensures that the ideas generated through research are diffused broadly into policy and programming discussions.
An example of collaboration on the annual World Bank Conference on Urbanisation and Poverty is provided in Box 9, which illustrates how CtW made strategic use of opportunities to expand their influence over the agenda and nature of the conference (i.e. that it become more policy-oriented), and how synthesis work has been used to influence global discussions.
Box 9: CtW influencing the agenda of global conferences
The IGC has collaborated with the World Bank at a conference at George Washington University over the last 2 years. Participation in the first year was arranged through the IGCs Cities Research Theme, and focused mainly on research, with Collier and Glaeser giving key note speeches. CtW saw the conference as an opportunity to connect policymakers with the high-level researchers attending the conference, but were confronted with the problem of how to get the policymakers into the event in the first place, since the event was designed as a research conference. Their strategy was to hold a side event before the conference, to which they would invite policymakers. The first version of the agenda for the side event was structured around questions that they were receiving from policymakers on issues such as land tenure, housing, redevelopment of land. CtW wanted to explore what evidence they had a realistic chance of getting from the academics. Policymakers were then invited to attend the main conference as well and identify areas of potential research in their countries. In 2019 CtW are co-hosting the event with the World Bank, and are focusing on practical issues of concern to policy makers.

CtW developed a very useful synthesis product, the policy toolkit, that enables a rapid response because it focuses on key issues such as affordable housing, that can be quickly adapted for the questions posed by various cities. So far six policy toolkits have been produced (IGC website). The toolkits are available online for download, and adapted for various cities on request. The IGC is not able to provide a record of this.
The prerequisite for CtW’s success is that it is part of the IGC and is able to leverage the IGC “brand” to quickly establish trusted relationships with senior policymakers; and is able to access the other parts of the IGC, namely the country programmes, the research network and stock of knowledge, and of course the IGC’s management. The strong team and highly capable policy-oriented manager has been an important part of the success of CtW, as has its association with leading academics in the field. The model is replicable within the IGC and working thematically across country to achieve policy influence seems valuable, particularly if the goal is to influence the global discussion. CtW has been successful in entering into and influencing global discussions because it has very practical and useful lessons to share from countries, and because it has developed specialised expertise in sharing these lessons. Also, the in-house team allows CtW to participate in many events, and they are then able to spread lessons based on IGC research and to influence the agenda of these global discussions.
One of the biggest contributions of CtW has been to bring its network of policymakers into these international discussions, so that they have a strong voice and can engage directly with those (e.g. the World Bank) who have the power to make decisions that will affect them, such as choices about finance and programme design for cities. This ensures that there is a platform for the southern voice to be heard in spaces dominated by developed country institutions and academics.
CtW fits into IGCs flexible engagement strategy because it does not only work in the partner countries of the IGC (which are low income countries). This puts CtW in a unique position to provide advice and services to global programmes, and this could be another way for them to influence global initiatives.
Hence, even though CtW was not designed to be part of the global influencing strategy of the IGC, it has proved to be an effective tool for pursuing this objective.
#### Online channels
In Phase II the IGC made use of two principal online channels with global impact: i) the IGC website and blog and ii) VoxDev.
The IGC website was launched in 2009, and has undergone several revamps since then, most recently during Phase II. In many respects www.theigc.org serves as a “project” website, reporting on events and making available the outputs of research projects and SPFs as documents and in some cases in multimedia format.
The “blogs” on the website (www.theigc.org/blog/) are something of a new departure: although they have been a feature of the site for some time, their use grew sharply in 2014/5, as part of a revamp of the IGC’s overall communications strategy.(IGC, 2014). The aim was to post between 2 and 4 new blogs a week, and that these would be based on IGC outputs as well as other content commissioned after discussions within the IGC communications team. IGC researchers were allowed to prepare a blog post instead of writing a policy brief as one of the output requirements, and this seems to have made it easier to generate a steady flow of IGC content.
The blogs are mainly articles, although there is some multimedia content (video but no audio). Video content, particularly in “documentary” format, is regarded as highly effective from a communications point of view, but production costs are very high for good quality video, and so budgetary constraints limit its use.
The blogs on the IGC website are a worthwhile innovation: they are informative and well written and attract a reasonably large audience, judging by the traffic figures provided. They are a more effective way of communicating the outcomes of individual projects than a more conventional policy brief. Unfortunately, the pages containing the blogs do not print properly from a browser and so cannot fully replace policy briefs that can be distributed in print format (e.g. at meetings and conferences). The addition of a suitable print facility on the website would therefore be useful.
The ratio of unique page views to users for the blogs is 1.27, while for VoxDev and VoxEU the ratio is 2.45 and 2.19. This suggests that visitors to VoxEU and VoxDev spend more time browsing the site for content than do visitors to the IGC blogs. This may be due to the larger amount of past columns available on VoxEU and VoxDev, which may tempt users who arrive to looking for a specific article to browse other content. One way to tempt readers of the blog pages to browse other pages on the site would be to add a “Related content” box to each blog post, with the related content chosen by an IGC staff member. This is the procedure used on VoxEU, and is likely to be more effective than the algorithmically generated suggestions via “People who were interested in this post were also interested in …”.
VoxDev, although drawing on the model of VoxEU (and other policy portals), has a somewhat different editorial process and seems to target a more academic audience than VoxEU. After two years, there is a steady flow of content on VoxDev, and traffic is healthy, which is a significant achievement. After adjusting for the narrower focus of VoxDev, the flow of new content on VoxDev seems to have been higher than one would expect compared to VoxEU, but the number of users and page views is lower than one might expect. This suggests that there is still scope to expand the traffic on VoxDev, but this may require a range of content that appeals to a wider audience than seems to be targeted at present.
Plans to expand VoxDev content are particularly interesting. One idea is to feature summaries of the survey or synthesis articles on development economics, another is to introduce more audio content on the site. The former seems more likely to appeal to VoxDev’s current audience in the research community than to new audiences in the policy community. In addition, VoxDev might consider adapting some of the ideas for new content types recently proposed by I4I.
What is unclear is the extent to which VoxDev serves to showcase IGC output. VoxDev articles have an “Editors’ note” indicating whether the research originates with the IGC or PEDL. Only a small number of VoxDev articles are identified as originating with the IGC (or with PEDL). These figures are likely to be underestimates, since not all IGC or PEDL content may have been identified correctly, but they do suggest that VoxDev could be used to greater effect to disseminate IGC output. As it is, VoxDev has an important role to play, providing an important public good at relatively low cost.
### Global Influence – Conclusions and Recommendations
#### Cities that Work
CtW is a model worth replicating, and recommendations identified below and be used to inform other policy initiatives of the IGC. Have a strong team of in-house researchers produce synthesis papers under the guidance of top academics in the field is a good model as it allows lessons to be drawn across countries, and ensures a quick response rate. CtW still relies on the connections and insights made at country level though. CtW makes an important contribution to global discussions by ensuring that policy makers are present in these spaces to voice their concerns and interests. The following recommendations will enhance CtW and other policy initiatives of the IGC.
R12 CtW is a model worth replicating, and the IGC can take the lessons identified in Section 5.3.2.1 and apply them to its new Fragility Initiative, and beyond that to similar initiatives that it is considering.
R13 The CtW initiative is now moving into a phase where there is too much demand for its services, and it has to make choices. The initiative should therefore develop a longer-term strategy to help guide its decision making. Since CtW clearly is already influencing global discussions and is in a position to exert more influence in the future, it should also develop a more explicit global influencing plan. The strategy should incorporate the following:
1. The strategy can help them choose which cities to engage with, and also which international initiatives or events to be a part of. It should also help them guide their decisions as they need to become more selective in their engagements. If they do not become more strategic, they risk diffusing their impact, and burn-out of the team.
2. The CtW team develop a strategy to activate its network of Policy Affiliates so that they can feed more into the Initiative – and infuse the programme itself with more policy maker perspectives from the developing world. This will also foster cross-city learning.
3. The strategy should also support the CtW team in their own professional development, since they are mainly managed remotely. This should be done together with the new Policy Manager and the Communications and Development Manager of the IGC, with input from the CtW Manager and team. The need for training and development is also relevant to Country and Policy Economists, but this has not been explored in depth in the evaluation, and should be investigated during Phase III as the organisation matures.
R14 There is scope to further exploit the synergies between CtW and the IGC’s Cities research programme: on the one hand the feedback from the synthesis efforts could prove useful in identifying important knowledge gaps and guiding the research programme; on the other hand cities involved in CtW often have large quantities of data but little ability to analyse it, which could attract researchers to engage with the Cities research programme:
1. Since the CtW team is synthesising knowledge across the field they are in a very good position to be able to identify gaps in the knowledge base, and there should be more discussion about how they can feed this into the Commissioning Board. CtW is well placed to do this, since the Cities RPD chairs the CtW Council, which should facilitate a flow of ideas between the two programmes.
2. CtW can build (jointly with the Cities research programme) a stronger network of younger researchers that need to publish, and who can benefit from having longer-term relationships with cities, including those from the developing world. Cities often have data, but limited research capacity, particularly in certain fields of economics such as urbanisation, and IGC researchers can fill this gap.
R15 CtW can go further in developing new and impactful synthesis tools, in particular more policy toolkits and multimedia resources available online and should consider developing an online course offering on urban policymaking:
1. The IGC should replicate the policy toolkits as a means of synthesising the existing body of knowledge in other thematic areas of the IGC, as they facilitate the rapid response to requests from policymakers received, for example by the IGC’s Country Offices.
2. CtW should further develop the free multimedia resources it already makes available online, which serve as very useful learning tools for individual policymakers and also facilitate cross-city exchanges of experience. CtW already has short videos on key topics that urban policymakers could access in their own time: the videos with Glaeser and with developing country policymakers are very well produced and effective, and more material of this quality should be created. The IGC could also repackage some of its existing multimedia offerings (such as the interviews with Paul Collier) in a more engaging style.
  [note] https://www.theigc.org/multimedia/the-spacial-structure-of-cities-in-developing-countries/ and https://www.theigc.org/multimedia/land-rights-in-developing-countries-insights-from-policymakers/
3. More ambitiously, the IGC’s academic partners (Oxford and the LSE) could develop a MOOC on cities and urban policymaking. Procurement issues make it very difficult for city staff to participate in paid online courses (unless they pay for it themselves), so a MOOC would enable many more policymakers from developing countries to access to the IGC’s body of knowledge and expertise.
#### Online channels
The blogs on the IGC website are a worthwhile innovation: they are informative and well written and attract a reasonably large audience, judging by the traffic figures provided. They are a more effective way of communicating the outcomes of individual projects than a more conventional policy brief. Some improvements are possible and relatively easy to implement.
VoxDev, although drawing on some aspects of the model used by VoxEU (and other “policy portals”) has a somewhat different editorial process and seems to target a more academic audience than VoxEU. After two years, there is a steady flow of content on VoxDev, and traffic is healthy, which is a significant achievement. There is still scope to expand the traffic on VoxDev, but this may require a range of content that appeals to a wider audience than seems to be targeted at present. VoxDev includes content originating with the IGC (as well as with PEDL), which is an important benefit to the IGC of its involvement in VoxDev. Identifying IGC (or indeed PEDL) output was more difficult than it should be, and ways should be found to make it easier, and IGC content more visible.
Measuring the impact of policy portals has proved to be challenging, since the target audience is not easy to define precisely, and the intended changes in their behaviour are difficult to measure. Like VoxEU, VoxDev does not carry out any systematic assessment of its impact via the website: it does not, for example, solicit feedback from website visitors via questionnaires or surveys. It has used polls on Twitter to gather feedback on the website. This seems to have been useful in developing new content streams and exploring new issues and should be continued, and even expanded with short user surveys triggered by landing on VoxDev.
With respect to the IGC’s use of online communications channels, we recommend the following:
R16 The IGC (and its partners) should continue their efforts to expand the readership of VoxDev. This involves expanding the range of content on VoxDev, making better use of automated tools to understand what drives traffic to the site, and expanding the efforts to better understand the profile and interests of the audience visiting the VoxDev site.
1. There are already plans to expand VoxDev’s content: one is to feature summaries of the survey or synthesis articles on development economics published in the Annual Review of Economics (annualreviews.org/loi/economics), and to introduce more audio content on the site. Other ideas currently under discussion include a series on gender, and “synthesis” articles organized in a “wiki” style. In order to expand the range of content, VoxDev might also consider adapting some of the ideas recently proposed for I4I by its Editor in Chief.
2. This requires a better understanding of what has driven (and will in the future drive) traffic to the site. The editorial team should be provided with tools to gather in an automated way the disparate pieces of analytics information from social media and the web into a dashboard that would make it easier to instantly see the connection between a sudden spike in in views and a corresponding trigger in, for example a Tweet or a Facebook post. At the moment this must be done manually and so is slow and often not done because of time pressure.
3. In common with many other online communications channels, VoxDev (and the IGC blogs) has only a very general idea of who it is actually reaching (i.e. the visitors to the websites). VoxDev should develop a strategy for gathering more information about their users, and eliciting feedback from these users in order to inform the development of new content and to demonstrate impact. VoxDev’s Twitter polls seem to have been useful, and should be continued. It would be worthwhile trialling similar polls or questionnaires on the VoxDev website itself: if short and not time consuming, they may generate responses that provide useful additional information about the broader audience visiting the website.
R17 The output indicators for online activities in IGC logframe should be improved, and these improvements should be informed by a better articulated Theory of Change for online influencing activities.
1. The logframe indicators for online communications outputs are fragmentary and inadequate. They should be revised in line with current good practice in communications. Cassidy and Ball (2018) would be a good starting point.
2. These factors influencing the impact of the IGC blogs and VoxDev are not articulated in detail in the ToC for the IGC prepared in 2016 (IEB, 2016a). Some of the key elements of Strategic Pathways SP3 and SP4 seem relevant to this impact. It would be useful for the IGC to develop a “mini-TOC” for its online communications that takes into account some of the factors specific to these policy portals.
R18 VoxDev seems to play smaller role in showcasing IGC output than one might expect, at least in terms of articles: IGC content needs to be better identified and easier to locate on the VoxDev website (i.e. more visible on the relevant pages, and discoverable via the search function on the website).

# Monitoring, Learning and Adaptation
This Section addresses EQ 4.1:
To what extent does the IGC monitor its own performance? Does it make use of this information to learn lessons and adapt its research and policy influencing strategies at both country and Hub levels?
and Output 4 in the IGC Logframe (DFID, 2018a)
The IGC is well managed and responsive
## What Monitoring (MEL) System is in Place in the IGC at the Hub Level?
In this Section we present the key components of the IGCs MEL system, and discuss the progress that has been made in terms of MEL as a tool for accountability and learning.
### Logical Framework and Theory of Change
A MEL system usually has at its core a Logical Framework and / or a ToC. The IGC has both. The Logical Framework is part of its contractual agreement with DFID, and is the basis of DFIDs monitoring of the IGC. It was last updated in 2018 (DFID, 2018a). The main features of the logframe are objectives, indicators, data sources and assumptions. The DFID logframe also includes targets and milestones.
[note] The assumptions in the logframe are typical logframe assumptions that identify factors in the external environment that need to be in place for the project to work. The assumptions in the ToC also include the internal mechanisms of change, and speak more to the IGCs methodology, and how one would expect the target groups to respond to the IGCs interventions.
The IGC has a ToC (presented in Section 3), that was developed by the IEB in order to conduct a theory-based evaluation. It was developed through a participatory process with the IGC during the Phase 1 evaluation, and was then updated during the mid-term evaluation based on our findings and validated with both the IGC and DFID. The IGC has iterated on this ToC, most recently in 2017.
It is the assumptions in the ToC that often underpin the lines of enquiry in a MEL system when it comes to learning and evaluation. Many of the assumptions in the ToC are implicitly understood by the IGC MEL team, and the IGC’s four level impact scoring system also reflects the causal logic of the logic model, but the IGC does not yet have a learning framework, with questions for learning based on the assumptions of the ToC.
The indicators in the logframe are measurable, but the DFID 2018 Annual Review (DFID, 2018b) requires the IGC conduct a thorough review of their reporting metrics, and to assess the relevance and appropriateness of different indicators where applicable. There are indicators in the current logframe where milestones cannot be exceeded, specifically when they refer to “all IGC countries.”
### The MEL Team
The IGC has built up a competent MEL team of four full time staff, an increase from one part-time position at the start of Phase 2. The MEL team is led by the Impact and Learning Director, two full time Senior Monitoring, Evaluation and Learning Officers, and one full MEL officer. There is also a full time Research Knowledge and Reporting Manager who is dedicated to the implementation of SPEAR (a Salesforce based information management system). Implementation of SPEAR has started with the operational management side of the IGC, and it will be extended to the monitoring functions in due course.
### Guideline Document
A key element of a MEL system is a guideline document or MEL Framework that explains the MEL system in terms of the organisation’s approach to MEL, and importantly defines key terms such as indicators, roles and responsibilities, outlines systems and procedures for MEL. Besides an explanation of the impact scoring system, the IGC has a comprehensive MEL strategy document, which outlines key areas of data capture, reporting and analysis. This is a challenge for standardisation in data capture and analysis. For example, there are no definitions for the key variables used by the IGC in the projects data base. The lack of explanation of key variables is a challenge because it allows inconsistency in data capture and also makes it difficult for any new comers or those outside the IGC (such as the IEB) to analyse the data in a way that is consistent with the IGC’s understanding of it.
There are some definitions and explanations in the logframe, but it is not comprehensive.
### Data Gathering, Management and Reporting
Any MEL system needs tools for data collection, management and reporting. It also builds on project documents that provide critical information for MEL such as all the planning tools (see Table 13 below).
The main focus of the MEL systems so far has been to be enable the IGC to provide DFID with an Annual Report on the impact scores they have achieved. Hence the CSNs, Impact Scores and Project Database have played an important role during Phase II, and the role of the PIP and PIR have grown in importance over Phase II. Country Review Meetings were introduced in late 2014 or early 2015 and have played an important role since then. These tools have replaced and improved upon tools such as the Line of Site Tool and others as the MEL system has evolved.
There is a publications data base that tracks the journals in which IGC funded research has been published. For communications the data source in the logframe is identified as tracking of media reporting of IGC work, but we have not been provided with any tools that systematically track the communications indicators in the logframe. We can assume that these analytics are drawn up at reporting times.
In terms of electronic systems, there is a shared drive, some excel spreadsheets and an email inbox. However, the IGC has invested in a Salesforce-based system, which will include MEL, that is called SPEAR. This will require a large effort to on-board all the CTs.
Table 13: Main tools in the IGC MEL toolbox
Planning tools (countries, projects set out their plans and intended results)	Electronic systems / (electronic means for storing information)	Reports and reporting tools / (ways that projects report on their	Monitoring meetings	Other key means of verification (not exhaustive)
CSNs / Project Influence Plan / Event Project Influence Plan	Shared drive / Project Monitoring tool, including a meeting tracker (Excel) / IGC MEL Inbox / Project data base (Excel) / Publications database (Excel) / SPEAR (based on Salesforce Customer Relationship Management Software) (Coming soon)	Project Influence Reports / Event reports / Event Influence Report / Annual Report to DFID / Mid-year country programme review to DFID (2015, 2016) / Annual Report, including impact justification scores	Country Review Meetings with Hub and Country Team (quarterly) / Mid-year review meetings with Hub and CTs / Impact Calls - biannual Calls with Country Teams	Event ToR / Minutes of meetings / Media references / Online analytics / Email chains

Box 10: Key terms and tools in the IGC MEL system
Country Review Meetings: Country Review Meetings (CRMs) are quarterly discussions via Skype, introduced in 2014/15 around the time of the informal Performance Improvement Plan. They involved the CPD, Country Director and Lead Academic for the Country, the Country Economists, the relevant Hub Economists, the Executive Director and the Research and Policy Director. These are not within the direct responsibility of the MEL team/ function. / Project Monitoring Tool (PMT) (Google sheets): Used by the CEs and MEL team to track progress and activities of projects, and can also be utilised by the Policy Economists. The projects within, particularly from an impact perspective, are the responsibility of the Country Economists. The PMT is used prior to the “impact Calls” which take place twice a year ahead of a) the mid-year review and b) the Annual Report at the end of the year. Before these meetings the PEs review the PMT and cross check the information in it with what has been received from the projects, the PIPs and PIRs. The MEL team will discuss the PMT with the CT, focusing on dissemination and when that will happen. The mid-year review is a very useful stocktaking exercise, the results of which are submitted to DFID. / Project Influence Plan: The PIP is a required formal deliverable for all activity. It is a standard form that PIs are contractually required to complete at the beginning of each research project funded through the CBs and for off-cycle activities, and which describes the actions to be taken as part of the research project to increase its policy influence. PIPs were extended to SPFs at some point in Phase II. / Project Influence Report: The PIR is a standard form that PIs are expected to complete at the end of each research project funded through the CBs and for off-cycle activities, describing actions taken as part of the research project to increase its policy influence. / PIRs were extended to SPFs at some point in Phase II. In 2015/16, the MEL team was given responsibility for signing off on PIPs and PIRs. / Project Database (Excel): The project database is a comprehensive and detailed record of research and other outputs produced by the IGC. However, the data was not collected systematically from the Country Programme during Phase I and data for 2009/10 - 2012/13 has only been compiled retrospectively during Phase II. Coding and filters allow the spreadsheet to be disaggregated by programme, country, theme and sub-theme. There is also considerable administrative detail (Principal and other Investigators, contract dates, implementation schedule and financial data) making this a potentially powerful MEL tool. / Publications database (Excel): This spreadsheet captures information on articles that are published by IGC researchers in academic journals. It does not capture the quality of the journal (quartile), which it could easily do.

## Accountability Monitoring and Reporting
The main focus of the IGC MEL system for Output 1 in the Logframe has been the implementation of an accountability reporting system for DFID, and now also to other funders. The mid-term evaluation found that the monitoring systems were fairly rudimentary and were not systematically implemented. There has been much effort at the IGC to address this, and data is now more systematically collected and stored.
The main focus has been establishing the system for tracking and reporting on impact scores, which are the main means by which the IGC is evaluated by DFID. Key to this are the PIP and the PIR. These tools allow the IGC MEL team to regularly validate and substantiate the impact scores. However, the PIP and the PIR are captured periodically. They are not yet included in SPEAR, but the plan is that they should be. This will mean that they can be completed online.
In 2018 the IGC was able to validate 100% of its impact scores for the first time, as reported in IGC (2018):
“According to our impact level definitions, the IGC must be able to justify substantive impact within the relevant financial year in order for a project to be assigned a particular impact level. For the first time, 100% of impact case of 2017/18 had evidence in the form of meeting minutes, email chains between researchers, the Country Team and policymakers, relevant documentation reporting project influence (event reports, Project Influence Reports, for example) or policy documentation. This reflects the improved reporting between researchers, COs and the London Hub, as well as more robust measures to track and capture impact.”
The main factor that has contributed to the improved collection of this data is that it is now a requirement for the IGC MEL team to review the PIPs and PIRs. This was introduced in 2016/17, and according to the IGC (IGC, 2018) has resulted in more level 3 and 4 cases being identified, especially in instances where the engagement has been driven by researchers, and also in non-partner countries. MEL review of PIPs and PIRs have also allowed for better oversight of dissemination activities and evidence collection.”
The process of tracking impacts, collecting evidence and assigning impact levels is the central part of the MEL process as is outlined in Box 11 below:
Box 11: Assigning Impact Levels
1. Quarterly reviews to identify potential impact cases: Impact cases are identified in the CRMs, held each quarter between the Hub and the Country Office on strategy, achievements, finance and challenges. These discussions highlight achieved and expected Level 3 and Level 4 impact cases. / 2. Initial review of potential cases by the MEL team: When preparations begin for the Annual Report, the MEL team identifies a full set of impact cases to investigate in more detail. This will comprise cases indicated during the CRMs, a review of the prior year's impact and any notes for follow-up, any impact identified during review of PIRs and discussions with teams around their overall portfolio of work, including zero-budget engagements. This initial review leads to an iterative process of discussions with CTs around the proposed impact cases and levels. / 3. Collection and recording of evidence: Evidence is submitted to the MEL team on an ongoing basis throughout the year. During the preparations for the Annual Report and in finalising the number of Level 3 and 4 cases at the end of the year, the MEL team may ask COs to provide more information or evidence to support different impact levels. These discussions, and the availability or otherwise of evidence, may lead to certain 'cases' being confirmed and others being disregarded. Each impact case will have a folder on the IGC server containing copies of relevant evidence available to support any particular impact level, e.g. copies of emails, documents, letters minutes etc. / 4. Preparation of impact case justifications: Every Level 3 or 4 case will have an accompanying justification which details why a particular project has been assigned the relevant Level. A selection of the impact cases will also have a full write-up in the Annual Report. / 5. Final review of impact cases: The final set of impact cases for a country must be reviewed and approved by Country Director. Finally, the set of all impact cases is reviewed and approved by the SMT at the Hub.

The IGC has started to adopt a more nuanced approach to this impact scoring system, by dividing Level 3 into a “High” Level 3 and a “Low” Level 3.
The IGC is able to report on the other aspects of its programme based on the indicators in the logframe such as publications, citations and communications. It is notoriously difficult to collect data on publications and citations, because of the time lag and because researchers are not good at reporting back when their articles are published. The MEL team do search themselves for publications periodically, but it is hard because title of journal article might not be same as title of project. The IGC does not capture the quality of journals from SCImago in the data base, which would be useful. It is easy to do on an ongoing basis, but more difficult to do periodically.
The extent to which communications information is analysed frequently for management purposes is less clear.
The IGC also introduced systematic tracking of gender-related work through the project database, following a recommendation from the 2015 DFID Annual Review (DFID, 2015). Gender marker analysis associated with commissioned projects was not possible, due to their being no commissioning board in 2017/18, and hence this is not reported in the 2017/18 Annual Report to DFID.
The IGC identifies improved impact reporting as one of the reasons that its impact scores are increasing. It reports that it has been steadily improving its reporting processes between COs, researchers and with the London Hub, specifically around tracking and capturing impact (IGC, 2018).
### Challenges and the IGC’s Response
There are a number of challenges for the IGC MEL, including the process for reviewing the PIP and PERS; the MEL system for the research network,
The PIP and PIR have to be approved by the Country Director and the MEL team to see that they are accurately and completely filled out. The system is not yet as efficient as it could be and the MEL team are working to improve it. One suggestion is to allow the CEs to take over the verification from the CDs, and to ensure that the data is core complete before it gets to the MEL team for sign-off. The plan is also for both forms to be digitised through SPEAR, which it is hoped should increase the accuracy of data capture.
According to feedback from a few PIs, the reporting load for researchers from the IGC is said to be higher than for other funders, and disproportionate to the amount of funding received, relative to other funders. Further, the macros in the current form that is being used do not work well with Apple Mac operating system, and it is also not easy to cut and paste into them. The following quote below highlights these issues:
“Some of the reporting requirements are demanding and static. I am doing a $1.8m research project, and IGC supports $38, 000 which is a small proportion, but it has a pretty large and disproportionate effort on reporting. I am happy to do it because of the longer-term engagement, and as a future academic I would see them as an important source of funding, and networks. I am also quite patient, but my co-author is very impatient, and is a hardcore academic, and if she is not able to cut and paste something she wrote on an airplane then she is not interested in it.” (PI interview)
The MEL system for the research side of the IGC is less well developed. The research network is captured as inputs in the ToC. Hence, while there are assumptions linked to the incentives for researchers to participate in the IGC, these are not linked explicitly to mechanisms of change and outcomes for researchers.

Figure 4 Extract from IGC ToC – research network is captured as an input, and activities that flow are about building the research agenda, not growing and maintaining the network
This is an area that can receive future attention, especially since there are indications from some of the interviews that attracting appropriate researchers who are also interested in policy engagement in developing world countries is not always easy.
Secondly, the IGC has not yet developed a systematic way to understand how they are commissioning thematically, and what influence this is having on the discourse in that field. According to the IGC it is developing an impact scoring system for academic impact, that will measure how the IGC research is pushing the research frontier, and how this is changing discourse, or informing or framing debate, and also to understand how they are commissioning clusters of work in areas that are important for growth. This is a positive step as it will expand the impact monitoring to take account of the knowledge side of the IGC.
The most recent version of the logframe (DFID, 2018a) includes a data source called a Special Call Mapping Report, with this explanatory note: “All commissioned projects are expected to be aligned with the relevant country’s CSN. IGC will rank alignment as ‘strong’, ‘moderate’ and ‘low’, as detailed in the proposed methodology. A justification will be provided for the ranking.” This was done for the work commissioned in summer 2018, and was excluded from the evaluation.
The IGC MEL team would like to provide the RPDs with more feedback on their commissioning, and the outcomes thereof, and include the LAs in this process as well.
Thirdly, the MEL team is not directly linked up to the Policy Economists (they do not participate in review meetings for example), and rely on reported data. They would like to respond to this by implementing an annual impact monitoring visit to COs on a rotational basis – replicating the types of visits that the IEB undertook for this evaluation (meeting the Country Team, meeting with policy makers and so on).
## Learning
Learning from monitoring data requires systematic analysis of the data and periodic review and reflection discussions among team members to identify patterns and trends that can inform decision making and strategy.
As highlighted, the focus of the IGC system has been on accountability reporting and not yet learning. They are aware of this and the MEL team intends to focus more on learning in Phase 3, although they may have to motivate and advocate for formal learning processes as these do require organisational time beyond the MEL team, and it will mean a culture change for the IGC. A closer look at learning, both at the Hub and the country level is provided below.
### Hub Level
The MEL team is keen to engage in a more active application of MEL for adaptive management in Phase 3. The IGC MEL team demonstrates that it is able to work with the data in their MEL to identify trends. For example, the drivers of impact document that the IGC has produced is the best example of formal learning at the Hub that we have found so far. It provides a thematic analysis of the factors that have contributed to the impact level 3 and 4 scores. The predictors of success identified in this document can be used to inform the management and strategy of the IGC.
The purpose of this work was mainly to project the number of impact levels for the following year, to anticipate success. However, the MEL team indicated that they then tested their assumptions to these predictors of success to see what the drivers of impact actually were.
This information has not been shared with the Country Team which would be valuable for them to help sharpen their strategic engagement.
Another example is that the MEL team have calculated the lag time between project start, end and publication. The main purpose of this analysis seems to be to be able to predict academic impact as the following quotation from the 2017/18 Annual Report indicates:
“The 2017/18 financial year saw a high level of academic impact recorded against IGC projects. Given that a large number of projects are coming to maturation, with many reaching the approximate 2-year time lag we identified between project completion and publication, we can expect to continue seeing relatively high levels of academic impact in the coming years.” (IGC, 2018, p.42)
Further, there seems to be a tension between MEL for communications purposes and MEL for learning – there is a tendency to use MEL to showcase what the IGC does rather than using the data to inform strategy and planning. This is also a side effect of setting up the system for accountability purposes.
The MEL team recognise that moving towards more learning will require a culture change and possibly additional capacity in the IGC MEL team.
“We do want to think about how we use everything that we have now to inform decision making in a more concrete way. A lot happens organically, and if we could we could start more consciously tracking trends, and have a more systematic change in the way we think about MEL as a valuable resource for an institution then it can provide powerful data for management, as yet there is no real systematic way to work with and learn from the data.” (MEL team)
The most recent Annual Review from DFID also encourages the IGC to do more systematic learning from the PIPs and PIRs, and also to think about a way to capture the capacity building outcomes of the IGC, which are a positive by-product of the IGCs work. In response, the IGC undertook to analyse its available data around policy influence, using the PIP and PIR data. The approach and format of this piece of work was to be agreed in advance with DFID.
### Country Level
At a country level, some teams are better at learning than others. Even within our four case study countries conducted for this evaluation, we found variation among the teams. While some teams have regular internal meetings where they review their successes and challenges, others are focused more on forward planning. All teams are involved in some level of problem solving to address their work plans, but the degree to which there is any systematic analysis of their successes and challenges is not clear. For example, the IEB asked teams to reflect on their least successful cases, and for Ethiopia at least, this was the first time they had taken stock of their projects that did not succeed to have an impact in order to understand why they have not achieved the desired impact. This analysis provided instructive, and with enough cases one can get a sense of the Country Team’s policy influence strategy and ability to adapt given their circumstances.
The periodic CRMs include a reflection on successes and challenges. The minutes that we have reviewed reflect that the SMT also provides mentoring to the CTs on how to address these challenges and to think about their policy influence strategy and how to engage researchers.
The MEL strategy does not facilitate learning at a country level, for example is it not comparing the data from country level against the CSNs, and besides the monitoring Calls, the system is mostly extractive (i.e. pulling data out of the country level but not feeding it back, or encouraging active participation in the analysis of the data).
### Cross-country Learning
Events are the most effective way to encourage cross-country learning and Growth Week was a good formula because it brought together policy makers, researchers, the IGC CTs and Hub staff to discuss programmatic and thematic issues.
The IGC has started implementing a thematic community of practice which is just for the internal IGC stakeholders, and this allows an honest and open discussion and reflection on successes and failures.
They also have thematic news letters to share knowledge synthesised by the PEs.
Because the PEs have insights into what is going on in more than one country, they do share their insights and lessons from other countries, and try to link people up with one another, but this is not systematised.
The IGC had an internal conference at the end of 2018 for the CDs, SMT and it was suggested in the 2018 DFID Annual Review that they would focus on core learnings across country programmes. A report of this event has not been made available to the IEB.
Box 12: Changes in Phase 2 that indicate that the IGC has learned in an organic and strategic way
Establishing the niche of the IGC by bringing the research and policy sides of the organisation closer together. This was achieved by using a common commissioning process for research projects funded by the Research Programme research and the Country Programme, / The introduction of the SPFs (a more flexible vehicle than Rapid Responses used in Phase I) was a critical part of this strategy as it enabled better scoping opportunities for researchers (“first mile” projects), and helping to ensure dissemination and uptake by policy makers (“last mile” projects), and a number of other benefits. / Viewing each project as having potential for policy impact. The PIPs and PIRs were a key part of this strategy. / Changing the culture of the institution to one that values both research and policy influence. Because IGC is hosted within an academic institution, there was a tendency to value and incentivise research above everything else. The IGC needed to change this to differentiate themselves from other institutions, and managed this shift by creating different incentives that encouraged staff to value policy engagement as well as research.
Source: Interview with SMT member

## Conclusions and Recommendations
In sum, the main thrust of the MEL system at the IGC in Phase II has been setting up systems that will enable reporting (primarily on policy influence) to DFID. The organisation has put some good systems in place, but it seems that the data is not yet systematically and regularly captured and analysed to draw lessons out for learning. This is reasonable progress given the time frames, the incentives of the MEL system and the size of the MEL team. The MEL team has been trying to keep a balance between demonstrating effectiveness and challenging themselves internally as an organisation. To do this properly the IGC will need to encourage a greater culture of active reflection and learning, and implement feedback loops for MEL observations into decision making both at the Hub and country levels.
With respect to monitoring, learning and adaptation, we recommend that:
R19 Continue its efforts to extend and improve its MEL System, which deals well with successful cases of policy influence, but needs to address other dimensions of IGC activity, in particular:
1. Continue its efforts to develop a more comprehensive MEL system around the research commissioning and the researcher network (e.g. what has been commissioned thematically, research impact and how to engage and motivate researchers for Policy Engagement and Global Influencing), and undertake more analysis on the mechanisms of change within the IGC’s research network.
2. Continue to review and refine the impact scoring system (and the Theory of Change (cross reference here)) to better capture the nuances of policy engagement, in particular those involving implementation, mainstreaming and scaling up
3. Carry out a regular and systematic analysis of projects that achieve only a Level 1 or Level 2 impact, along the same lines as the analyses of “drivers of impact” for Level 3 and Level 4 projects.
4. Develop a comprehensive MEL guideline or framework document that explains their approach to MEL, and how it is linked to their logframe and ToC; and sets out a “data strategy” that identifies how all the pieces of data that the IGC are gathering will be integrated into the overall MEL system.
R20 the IGC should take steps to create and nurture a culture of active reflection and learning, and implement feedback loops from MEL observations into decision making both at the Hub and country levels.
1. The IGC should establish a high-level learning framework based on the assumptions in the ToC that can guide its drive towards learning. The IGC could consider hiring an external learning facilitator who can help the organisation to develop its learning culture. The facilitator could help the IGC set up learning processes at the Hub, across countries, between the Hub and the Country Programmes, within CTs and within thematic areas.
2. The effectiveness of any learning framework depends in part on the visibility and strength of support it receives from the organization’s senior management. This raises the issue of where responsibility for learning should reside. One possibility is to combine this with the responsibility for the MEL function; another is to have a separate position responsible for learning. Adding responsibility for learning to the already demanding task of overseeing accountability reporting may prove challenging in practice. Separating these duties may have the advantage of signalling management interest in and support for learning from past experience in an ongoing way. The IGC should analyse the issue of responsibility for learning as it develops its learning framework and strategy in Phase III.
3. Encourage greater integration of MEL into the policy engagement work of the IGC – there could be more avenues for the MEL team to engage with the PEs and directly with the CTs through country MEL visits for example. The new Policy Director could help to facilitate this integration if the person views learning as part of programme management, and draws on the MEL team as a resource.
# Cross-cutting Issues
This Section addresses EQ 7.1:
To what extent has the IGC integrated cross-cutting issues into its work, in particular the economic empowerment of women and girls.
## Economic Empowerment of Girls and Women
This Section draws on our work in 2019 and reported in IEB (2019e).
The economic empowerment of women and girls is essential to an understanding of ‘inclusive growth’, which has been the driving theme of the IGC's work since its inception. At the macro level there is a growing realisation among economists of the growth enhancing potential of increased female labour force participation. At the micro level there is also an awareness of the negative effects of gender inequality on household wellbeing, health, income, human capital formation, and intergenerational poverty alleviation. Thanks to empirical research there is now an impressive body of evidence available on the mechanisms at work and there is scope for policy design to be improved by research-based formative evaluations. IGC has a research presence in many of these areas.
The highlighted projects did achieve policy impact in terms of the IGC’s metrics. Five of the nine highlighted projects involved had already completed at the time. Of those five, four had achieved policy impact Level 4, and the fifth (on urban transport in Pakistan) had achieved Level 3. The remaining 4 projects, noted as ‘ongoing’ when the Appendix was prepared, were assessed later and all given a Level 3 Policy Impact rating. Once assessments were complete for all the projects, however, 60% had received a Level 3 or Level 4, a higher proportion that is achieved by IGC projects overall.
IGC measures academic impact in terms of publication in peer reviewed journals. Given the lags in journal publication, the academic impact of 9 of the projects was unlikely to have been known, since these all finished in 2017 or later. One of the highlighted projects, on garments in Bangladesh, did result in a publication in a leading journal (The American Economic Review), which is evidence of academic impact. No publications seem yet to have emerged for the other highlighted projects, so it may be too early to claim strong academic impact overall.
As the ratio of ongoing to completed projects may suggest, the Appendix also noted a rise in the share of gender marked IGC projects over time, doubling from 5% to 10% over the period 2009/10 to 2016/17. In 2015/2016 10% of starting projects had gender-specific analysis as a principal theme and 7% as a significant theme. Moreover, the number of projects where gender is the project’s principal sub-theme relative to those where it was ‘significant’ increased from 7% in 2016/17 to 12% the following year.
Although the Project Database is not IGC's only depository for project information, it is an important way in which IGC can systematically access its research findings on gender or any other cross-cutting theme. The information it provides can also provide a means for selecting projects for the purposes of reporting or synthesis. The project database contains two sources of information on the gender dimension of IGC activities: projects can have “gender” as a keyword, and the IGC has introduced a set of gender markers for projects.
The gender markers are a useful addition to the database: they pick up a much larger share of gender-related projects in the total than the Gender Keyword indicator. The markers may not, however, have been applied consistently, at least for older projects, and the IGC may need to invest more resources in ensuring that the markers for its older projects are correct in order for the project database to be a useful and reliable tool for reporting and analysis.
Bilateral donors, including DFID, use the OECD/DAC definition of gender markers to share information on the strength of the gender contents of aid projects. The markers used by the IGC are defined in a different fashion, and are not easily mapped onto the OECD/DAC definitions. This may cause difficulties in future in using the information reported by the IGC for the purpose of international reporting. In this respect it might be better to include both sets of markers in the database
It is clear, nevertheless, that the IGC has a good presence in the gender field. Going forward, it should be possible for the IGC to make a larger contribution to policy debates on gender equality than it has done to date.
## Conclusions and Recommendations
IGC has already done some good work on gender, but it needs to integrate this issue more fully into its research strategy and research commissioning processes. The IGC only began tracking this issue in 2014, and so historical data is not readily available, but the evidence we have suggests that the IGC has a good - possibly substantial - presence in this field and that it should be possible for the IGC to make a larger contribution to policy debates on gender equality than it has done to date.
With respect to the IGC’s treatment of the economic empowerment of girls and women as a cross-cutting issue, we recommend that:
R21 This cross-cutting issue needs to be more fully integrated into the full range of the IGC’s activities in Phase III, in particular in the formulation of the research strategy, and the research commissioning process:
1. When CSNs and EPs are refreshed for Phase III, specific consideration of gender needs to be built in as a cross cutting issue ex ante.
2. Proposal applicants / Principal Investigators (PIs) should be asked to indicate in their proposals whether the gender marker(s) should be applied to their project, and if so, the 'strength' of the gender content.
3. Explicit mention of gender should be made in the CB Evaluation templates under Phase III. Similarly, the mapping reports prepared after each call should also contain this gender information. This would make it easier to ensure that gender information is added to the project database on a regular basis.
R22 The IGC could – and should – do more to draw more attention on a regular basis to its research relevant to economic empowerment of girls and women, and ensure that this research (or synthesis products based on it) makes a contribution to international discussions of economic issues relevant to “gender”:
1. The IGC should repeat the Gender Assessment in its Annual Report on a regular basis. This will be easier to do if the information relevant to gender is comprehensively and consistently entered into the IGC project database. If necessary, additional resources should be invested in ensuring that gender information is recorded consistently, particularly for older projects.
2. The IGC should prepare more synthesis products on its gender relevant research findings, on topics where there is a critical mass of IGC project results either by theme (e.g. within the Firms theme perhaps training, worker productivity, microcredit, digital finance) or by country e.g. Zambia. There may also be a critical mass of relevant research on some other topics, e.g. health and education.
3. The IGC could to use such synthesis products to contribute to international debates on other economic topics that have high profile in current gender discussions. These could include the questioning of gender norms (regarding fertility, women’s effectiveness as entrepreneurs, ‘identity’ and so on), the extent and economic implications of women’s unpaid care work, and the gender dimension of trade, employment and enterprise, which would feed into countries’ efforts to shape their policies in the wake of the WTO Declaration on Women and Trade (WTO, 2017).
R23 The gender markers used by the IGC cannot be mapped easily onto the markers defined by the OECD/DAC. If the IGC record wishes to use its own set of indicators, then it should ensure that the OECD/DAC indicators are recorded in its project database as well.
# Overall Conclusions and Recommendations
## The Evaluation Questions
1. Research
  1. To what extent have the projects funded through the Commissioning Boards represented an effective Research Strategy for achieving the objectives of the IGC?
  2. To what extent has this strategy been successful in creating new knowledge about the factors influencing growth in low income countries
Overall, we conclude that the projects funded through the Commissioning Boards have represented an effective research strategy for achieving the IGC's objectives.
The IGC has created processes for commissioning and implementing research projects that have enabled it to achieve one of its key objectives: to identify key growth policy issues and mobilise world class researchers to address these issues. These processes also enabled the IGC to overcome one of the key challenges it faced in Phase II: to better integrate its Research Programme and its Country Programme. It is important to note as well that the research commissioning process has also played an important role in integrating the Research Programme and the Country Programme, through a range of measures that have enhanced the “country voice” in the decisions taken by the Commissioning Boards. This was a key objective for the IGC during Phase II.
Other funding modalities such as SPFs have certainly played a role, but most of the knowledge created by the IGC has been through open research calls with projects selected by the Commissioning Boards. The IGC’s research commissioning process follows best practice and only needs minor changes. We examined the IGC’s knowledge creation activities, in particular the open Calls for research proposals and their subsequent evaluation by the CBs. We found the research commissioning process to be largely consistent with best practice: we suggest some improvements but they are mostly minor, having to do with the use of external refereeing in some circumstances. One aspect of commissioning that does need improvement is the “mapping” of funded projects onto the IGC’s announced research and country priorities. This was not done consistently in Phase II, and the IGC would benefit from more frequent collective reflection on the directions it has taken as a result of its funding decisions.
We examined the IGC’s oversight of the research projects funds and found this too was largely consistent with best practice. The Research Programme has a strong sense of ownership of projects funded by the Research Programme, and the COs have ownership of SPFs. There seems to be less sense of ownership of research projects funded by the Country Programme, and some inconsistency across COs in the procedures for oversight of their research content. The process for managing research mostly follows best practice, but LAs could be used more effectively.
The IGC’s research strategy has also been successful in creating new knowledge about the factors influencing growth in low income countries. During Phase II IGC has supported research projects whose outputs have not only been published in high impact scientific journals, but have also influenced policy in its partner countries.
In 2016 RAND Europe carried out a study (RAND Europe, 2016) of the IGC and five other DFID-funded research programmes. The study counted, for each programme, the number of research outputs that had appeared in peer-reviewed journals, and assessed the “quality” of the journals in which they were published (based on the average number of citations of articles published in that journal). The study identified 59 IGC research outputs published in journals and found that, of these outputs, a very high proportion (52 out of 59) were in journals ranked in the first quartile by citations, and this proportion was higher than for the other five DFID programmes.
We repeated this exercise for the IGC with more complete information for Phase I and Phase II. The new data revealed that journal publications are associated mainly with “Research Projects” in Phase I and “Research Programme Awards” in Phase II, but in Phase II we were surprised to note that a significant number of journal publications were associated with SPFs and with Commissioning Board projects funded by the Country Programme. If success is defined as publication in a peer reviewed journal, the “success rate” for Phase I Research Projects is 31.3%, and for Phase II Research Programme Awards 23.3%. This apparent fall should be interpreted with caution: the long lag in the journal publications process means that the more recent Phase II projects are likely to give rise to additional journal publications, and we expect the Phase II success rate to rise over time.
If we follow the RAND study and define the “quality” of published IGC research outputs by the journal citation measures, we find that the “quality” of publications in Phase II is almost as high as in Phase I. In other words, the changes to the IGC’s research commissioning process in Phase II to strengthen “country voice” and policy relevance do not appear to have had a significantly adverse effect on the quality of its publications. We find this to be a striking and impressive result. It is also worth noting that the IGC quality measures based on the 2019 data are higher than the 2016 quality measures for the other DFID research programmes examined in the RAND study. If we take these other programmes as a benchmark, then the IGC does seem to be highly successful in producing high quality research. This is also impressive, given that the IGC gives more emphasis to policy relevance in its funding decisions than do these other programmes and that many of these projects do achieve policy impact.
It is also worth noting that this research, while of high academic quality, also influences policy in the IGC’s partner countries. Our analysis of the IGC’s impact scores revealed that 26% of the projects funded by the Research Programme in Phase II achieved a Level 3 or Level 4 impact. Not surprisingly, this is lower than the rates for SPFs (48%) or projects funded by the Country Programme (42%) but still an impressive achievement for research published in leading academic journals.
1. Activities at the Country Level
  1. To what extent has the IGC’s Country Programme established and implemented an effective Country Strategy that responds to the priorities and needs of its partner countries?
  2. To what extent has this strategy been successful in enabling the IGC to influence policies relevant to growth at the country level?
The IGC’s Country Programme has established and implemented an effective Country Strategy that responds to the priorities and needs of its partner countries. The IGC’s COs and the relationships they develop with their policy counterparts are the IGC’s most important route for applying knowledge and for ensuring the relevance of the work it carries out. For projects we examined in our mid-term review, the third Strategic Pathway in our ToC (influencing policy by dealing directly with the government via relationships developed by the IGC Country Office) was very important. The “flagship” projects that were the focus of attention during our country visits in 2019 addressed a broader range of policy issues, but these too confirmed the importance of this pathway: three of the four flagship projects involved influencing policy via interactions with the government. The importance of the Country Offices in generating impact is confirmed by a broader analysis of the IGC’s impact cases: over 60% of the Level 3 and Level 4 impact cases in Phase II were associated either with SPFs or research projects funded by the Country Programme.
The IGC’s system of impact measurement does not, however, take into account whether the policies that it influenced were important or significant. For this we must turn to the subset of projects we examined in depth in our mid-term and end term reports. The range of policy issues addressed by the IGC is very wide, and the projects we examined in depth in the mid-term and end-term reviews was not chosen randomly. But even given the purposive nature of our sampling, we found that the issues addressed by these projects were of first order importance to the IGC’s partner countries.
In our mid-term report, we examined a set of IGC projects dealing with taxation and government revenue. Raising taxes is essential if a government is to provide essential services to its citizens. In high income countries the ratio of tax revenue to GDP is about 30%; in Low Income Countries around 13%. One of the key challenges facing the governments in the countries we visited is the need to generate more tax revenue in order to finance essential government expenditures. We carried out a detailed investigation of the IGC's taxation related activities in three countries: Rwanda, Uganda and Pakistan. It was clear that, at least with respect to these activities, the IGC is addressing problems of first order importance to the countries concerned and that in the right circumstances, its research has the potential to bring enormous change to the development trajectories of developing countries. Some of the cases we studied have a huge potential impact. The possible introduction of a flat tax in Rwanda is a clear example of a policy, which if introduced, would have had a large and adverse impact on macroeconomic stability in the country. Evidence provided by the IGC suggested that the introduction of a flat tax as envisaged by the government would reduce government revenues by over 40% and our more detailed estimates confirmed that the impact of introducing the tax would have been very large indeed. The IGC’s work in Pakistan on the detection of tax evaders using third party consumption data, suffered political setbacks, but nevertheless has the potential to add billions of rupees to the state treasury. Its later work on improving the performance of tax collectors by offering them pecuniary and non-pecuniary incentives to collect more taxes is another example of a reform with even greater potential impact. Moreover, these reforms could radically alter the landscape of tax collection in Pakistan and, over time, erode the culture of evasion amongst taxpayers. The projects we examined in our end-term visits addressed a broader range of issues, not just taxation: in Ghana, reforms to the management of the public sector in order to improve performance of civil servants; in Ethiopia measures to strengthen the agency responsible for encouraging foreign direct investment, an important element in the government’s strategy to boost growth and increase employment; in Sierra Leone experiments to determine whether political accountability could be improved by providing more information to voters through election debates, and by encouraging newly elected parliamentarians to meet regularly with their constituents.
The IGC’s country strategy, and the tools it has developed to monitor the success of this strategy, provide an effective approach to tracking individual projects and useful tools for monitoring their impact on policy. As a result, it was straightforward to assess the impact of individual policies and to aggregate these individual impacts into indicators of impact at the country or IGC level. It was more difficult for us to assess whether, for a given country, whether these project level impacts, taken together, were achieving a “step change” in the overall set of policies relevant to growth.
It is important to be realistic here: there is no consensus around a single suite of policies that are guaranteed to achieve structural change and permanently higher rates of growth in low income countries, and so IGC’s focus in Phase II on individual projects (or in some cases on clusters of projects) seems to us to have been pragmatic and sensible.
Looking forward to the future, we believe that the IGC can and should be more ambitious in Phase III: it should aim to influence (and measure its influence) at a broader, system-wide level as well as at the level of individual projects. This will require changes in both its strategy and its MEL systems. In addition the IGC’s current approach does not address issues that are key to assessing the long run importance even of changes in individual policies: Sustainability (How likely is it that the policy change be abandoned or even reversed at some later date?); Implementation / Mainstreaming (Can a policy that has been successfully piloted be implemented on a wider scale?); and Magnitude of the policy change (The IGC system in effect treats all policy changes as equal, no matter what their likely impact on the country or its growth rate. Is this reasonable?). The IGC needs to adapt both its strategy and its MEL systems to take more account of these issues. In particular the IGC needs to devote more attention to designing projects in such a way that requires (or allows for) proper engagement on policy implementation issues (in particular after the research has been completed and the findings published). Here there is a question about whether its researchers feel comfortable (or interested) in dealing with questions of implementation. If so, then the IGC may need to involve more experts from disciplines outside of economics (government and public administration, political science, etc.) and/or policy practitioners (ex-politicians, senior civil servants, etc.) who have more interest and experience in guiding the implementation of policy ideas that have been generated by the IGC.
1. Activities at the Global Level
  1. To what extent has the IGC established and implemented a strategy for influencing global discussions of policies relevant to growth in low income countries?
  2. Has the IGC had influence on global discussions of these policies?
Influencing global discussions of policies relevant to growth in low income countries has been one of the IGC’s objectives throughout Phase II. In the initial stages of Phase II its influencing strategy involved focusing on a small number of policy issues (for example taxation, urban policy, and enterprise maps) where the IGC thought it had research expertise and a track record of policy influence. There were “influencing” activities around these themes, but these were on a relatively small scale and do not seem to have achieved much influence. This situation changed in 2016/17 with the launch of the CtW initiative. This initiative has developed a global influencing strategy that uses synthesis products to bridge the communications gap between researchers and policy makers. It is not entirely clear the extent to which this was a deliberate strategic choice, or an innovation that grew out of a confluence of demand from urban policymakers for economics-based policy advice, the commitment of leading IGC academics to provide such advice, and the ability of the IGC to mobilize financial and human resources to exploit this opportunity. But innovations do not have to be the result of a deliberate strategy in order to be worthwhile and successful.
The Cities the Work initiative has certainly had initial success, due to its brand, staff, management, and commitment of leading academics. A key factor in the success of CtW is that it is part of the IGC and is able to leverage the IGC “brand” to quickly establish trusted relationships with senior policymakers; and is able to access the other parts of the IGC. The strong team and highly capable policy-oriented manager have been an important part of the success of CtW, as has its association with leading academics in the field. The model is replicable within the IGC and working thematically across countries to achieve policy influence seems valuable, particularly if the goal is to influence the global discussions. CtW departs from the IGC’s “hub and country office model” by relying on “in house” researchers to produce synthesis products, participate in many events at the regional and global level, and so spread lessons based on IGC research and to influence the agenda of these global discussions.
It is more difficult to determine the influence that the IGC has had on broader global discussions of policies relevant to growth in low income countries. In the initial stages of Phase II the answer is relatively little influence, mainly because the scale of activities and resources devoted to them was small. With the advent of CtW later in Phase II the answer is more complicated. To date the initiative has used the IGC’s system of annual impact monitoring to record its influence, and it has achieved both Level 3 and some Level 4 impacts. It is not clear, however, whether this approach is sufficient to capture all of the initiative’s impact and influence. The IGC’s current system of impact measurement does rely on the kinds of interactions that take place between the IGC Country Teams and their policy counterparts: the records of these interactions signal potential impact cases and often provide some of the eventual narrative justification for the impact cases. The situation with CtW is somewhat different – some of the synthesis products it publishes can be freely downloaded. It is more difficult to track the influence these products have on specific policy discussions and decisions since there may be is no direct contact with the policymaker. A similar problem affects the IGC’s online communications channels (the IGC blogs and VoxDev), where it is also difficult to measure impact without knowledge of the audience that is being reached and without mechanisms for obtaining user feedback. This points to need to develop a stronger ToC and results framework for these influencing efforts: the growth of these influencing activities has outpaced the IGC’s processes for monitoring their impact and effectiveness.
1. Learning and Adaptation
  1. To what extent does the IGC monitor its own performance? Does it make use of this information to learn lessons and adapt its research and policy influencing strategies at both country and hub levels?
The IGC’s system of impact measurement is well suited for tracking annual progress. The IGC have a clear and well documented system for assigning impact levels to their activities. Activities awarded a Level 3 or Level 4 impact are particularly important: they inform the Output and Outcome Indicators in the Logframe, are presented and justified in the Annual Report and discussed as part of the Annual Review by DFID. We have examined the assignment of impact levels for 2015/16, 2016/17 and 2017/18. Overall, we found that the IGC adhered to the documented process, the impacts awarded were in most cases consistent with the impact level definitions, and evidence was available from both the IGC and external sources to support the IGC’s justifications for the awards. The main weakness we detected is in the definition of Level 3 impacts, which allows for a wide range of impacts and the criterion of “internalisation” can be difficult to apply in practice in a convincing manner. We support the trial in 2018/19 to create a “strong” and a “weak” Level 3. We would also recommend that only strong Level 3 cases should be considered in assessing IGC performance. Overall, though, we think that the present system of impact measurement is a credible approach to tracking, on an annual basis, the IGC’s progress towards impact.
The impact system is less well suited to capture other important features of policy change: the sustainability, implementation, magnitude of policy changes, and their attribution to the IGC. Sustainability and implementation / mainstreaming are inherently longer-term issues. Both of these issues are important, as the cases in our mid-term and end-term reports reveal, but an annual monitoring tool is unlikely to address these issues in a satisfactory manner. The IGC should instead develop other tools and approaches: one possibility is a periodic assessment that revisits impact cases after several years have passed to see whether the policy changes that formed the basis for the impact award have been implemented, and if implemented, whether they have been sustained. The “importance” of a policy change, in the sense of the quantitative magnitude of its effects, is also not captured at all in the current system of impact measurement. Our interim reports did provide such estimates for two impact cases: this demonstrated that the task is feasible and the results sometimes surprising. Policy changes of a “systemic” nature can have large impacts, much larger than the IGC’s own budget. To estimate these effects for dozens of impact cases every year is clearly impractical. Nevertheless, such estimates should be of interest to the IGC, if only to ensure that if is focusing its resources on important policy changes. Estimates for a selection of Level 4 projects could be prepared as part of the periodic assessments described above, or the researchers themselves could be encouraged to prepare such estimates as part of their final reports.
The IGC’s MEL systems are effective for reporting; less so for reflection and learning. The main thrust of the MEL system at the IGC in Phase II has been setting up systems that will enable reporting to DFID. The organisation has put in place some good systems, but the data in these systems is not yet systematically and regularly captured and analysed to draw out lessons for learning. This is reasonable progress given the time frames, the incentives of the MEL system and the size of the MEL team. The MEL team has been trying to keep a balance between demonstrating effectiveness and challenging themselves internally as an organisation. To do this properly the IGC will need to encourage a greater culture of active reflection and learning, and implement feedback loops for MEL observations into decision making both at the Hub and country levels.
1. Sustainability
  1. To what extent has the IGC made a sustainable contribution to evidence-based policymaking on issues related to growth in its partner countries?
Overall, the issue of sustainability seems to have received relatively little attention during Phase II. There are a number of different aspects of sustainability. Financial sustainability is very often an issue for project-based interventions: is there funding available that would allow the project’s activities continue beyond the end of the current funding? This is often a significant challenge, but here it is interesting and encouraging to note that the IGC has made some progress, at least in diversifying its sources of funding: DFID no longer funds the IGC’s activities in India, but the IGC has found alternative sources of funding from the Gates Foundation and from the Tata Foundation (for Ideas for India). The recent creation of a senior management post with responsibility for development is also encouraging in this respect. Another aspect of sustainability involves whether the impact of the IGC’s interventions (i.e. its projects) is likely to be sustained over time: are the policy changes to which the IGC contributes likely to be reversed, or their impact to diminish over time. As noted above, the IGC’s system of impact measurement, with its annual cycle of reporting on new impact cases, is not well suited to track the impact of policy changes over the longer term. This would require revisiting policy changes, and may not always yield clear cut conclusions. So, while in principle desirable, we think this is not a high priority for the IGC.
The aspect of sustainability identified in the evaluation question is, however, worth pursuing. There are several ways in which the IGC’s activities could promote evidence informed policy making in its partner countries. It could influence the capacity and motivation to use evidence on the part of its policy counterparts in government. The IGC could also build capacity in the local research community (universities and think tanks) to carry out research that is policy relevant, and to establish relationships with policymakers in government.
Building capacity on a large scale in either the government or the local research community is beyond the remit (and the resources) of the IGC, but to the extent that the IGC has addressed capacity building, it seems to have focused more on the research community than policymakers. The IGC’s logframe, for example has an indicator based on the number of local researchers involved in the research teams for IGC funded projects, and it has taken steps in CB5 to encourage more local researchers to submit proposals to the open calls by circulating the call to a much wider range of potential applicants. This resulted in an increased number of applications from researchers based in the global south, but the quality of their proposals was weak and not many were funded. The IGC’s response was imaginative: to try to pair teams that had submitted promising but weak proposals with stronger researchers, with the aim of improving the quality and chances of success of the proposals. This seems a promising approach, but the reduction in the level of commissioning activity meant that it was not fully implemented. It should be revived.
Although tertiary education in general, and research capacity in particular, is improving in many of the IGC’s partner countries, our experience outside this evaluation suggests that improving the quality of local research so that it is internationally competitive will almost certainly be a very long term process, and may have little impact on the IGC’s commissioning even in Phase III.
This leads us to suggest that more attention be devoted instead to capacity and motivation in the policy community, where the IGC is more likely to able to have – and demonstrate –impact within a reasonable period of time. Building capacity across the whole of government is clearly well beyond the resources available to the IGC: this must be addressed by projects such as BCURE (and its successors) or as part of wider civil service reforms. It should be possible for the IGC to have an impact on its key policy counterparts – either at the level of the individual policy maker or their organization. And within the set of policy counterparts, one would expect more influence from projects that involve a high degree of co-creation or co-production. In order to assess impact, the IGC would need baselines, and so retrospective analyses of these projects will not be enough: measuring changes in counterparts’ use of evidence and research would need to be built in to the plans for research co-production. We suggest this might be a useful direction in which to extend the IGC’s impact monitoring system.
1. Lessons learned
  1. What lessons can be learned about research to policy projects and what recommendations can be made to improve the performance of the IGC and similar projects in the future?
The majority of our recommendations are aimed at improving the performance of the IGC itself. In this section we highlight a few of our findings that we think have more general applicability to policy influencing projects.
Building and sustaining relationships is essential for policy influence: A key finding from both our mid-term and end-term country visits is that it is crucially important for the IGC’s ability to influence policy that members of the Country Team have access to senior policymakers and that they maintain good relationships with these policymakers. These relationships operate at different levels (e.g. Country Director with Minister; Country Economist with a senior civil servant). The evidence from Ghana, Rwanda, Sierra Leone Uganda, in particular suggested that relationships between Country Economists and mid- to senior-level civil servants is particularly important. In part, this seemed to be due to the ability to meet frequently, sometimes at short notice. Country Directors, especially if they are non-resident and / or cover several countries, do not have as many opportunities to meet their counterparts. Their meetings with policy counterparts, because they are less frequent, tend to be more strategic in nature. The relationships that the Country Economists build and maintain with these officials are what enables much of the IGC’s work to be done and sustain policymakers’ interest in an issue while longer term research projects are underway. From the Country Economist’s perspective, maintaining close relationships requires hard work, consistent engagement, and perhaps certain personality traits that not all economists possess. Reliance on these relationships does, of course, entail risks: relationships can be disrupted at short notice if officials change jobs or retire. And individual reformers, even if senior and influential, do not necessarily have enough political capital and power within their institutions to bring about large scale systemic change.
Alliances with key senior reformers are very important: This could be seen clearly in Uganda, where the Deputy Governor of the Central Bank and the (now) Permanent Secretary in the Ministry of Finance were the IGC’s key interlocutors when the Country Office was established in 2012 and continued to work closely with the IGC thereafter. The IGC’s association with these reformers has played a role in building a broader set of relationships with other parts of the government. Individuals seem to have played a slightly less important role in in Rwanda, perhaps because commitment to development goals seems to be shared among many policymakers. In Pakistan, the IGC worked closely with one reformer, who initiated a whole series of very important tax-related research projects with the IGC. He was eventually dismissed as an election approached, and many believe his dismissal was linked to his intention to pursue a large cohort of people who had been estimated by IGC researchers to have underreported their incomes. In the Ghana projects we examined in our end-term visit, the researchers’ close working relationship with the head of the Ghanaian civil service seems to have played a key role in the impact these projects achieved. In some cases, it is the Country Team that establishes and maintains the relationship, in other cases the PI or other members of the research team play this role as well.
Policy influencing often requires involvement in politically sensitive issues. The establishment of trusted relationships with policymakers is an important means of navigating the politics of policy change: This is not a new or surprising finding, but our mid-term investigation of the IGC’s work in three countries underscore how political sensitivity is often important in its work. One example was in our mid-term visit to Pakistan, where politics brought one taxation reform effort to a halt, and lack of political may be part of the reason why a second reform stalled before it could be mainstreamed. Not all taxation research is politically sensitive, however: in one of the projects we examined in Pakistan, the policies recommended by IGC researchers were incorporated into the 2012 Finance Act with little if any controversy. In the other two countries, the role of politics was less dramatic but could still be discerned. In Rwanda, the government was sued (successfully) by a group of businesses in order to block the introduction of Electronic Business Machines (EBMs), whose use would make tax evasion more difficult. In Uganda the government’s initial interest in EBMs diminished during the run up to the Presidential elections. Interest then seems to have revived, possibly due to the IGC’s work in keeping the issue alive. This is linked to timeous nature of policy influence and policy windows. At certain times policy windows may be closed, e.g. politicians dislike discussing tax issues near election times, but at other times (e.g. if the IMF is putting pressure on the Government to generate more revenue), then even if the issue is politically sensitive, there may be an opportunity for the IGC to introduce evidence into the policy process. The role of the Country Office in being able to identify these policy windows is critical. They do this by maintaining on-going relationships with policy makers (at different levels as discussed previously), by keeping policy makers engaged through IGC activities (e.g. conferences, or events) and through participation in policy community activities (e.g. donor forums). We also found that these relationships play another important role: they help the IGC navigate the politics and political sensitivities that arise in its work.
Reputation and credibility, both of individuals and institutions, play an important role in policy influencing: Institutional reputations are important. We found that the IGC’s reputation is important: Policymakers turn to the IGC because of its reputation for independence and neutrality. Our interviews in the countries we visited brought out very strongly the point that the IGC is trusted by senior policymakers because it is seen as not having a hidden agenda. That gives the IGC an advantage over the IFIs and some other organisations in the policy advice sphere. These “competitors” are, rightly or wrongly, often associated with particular economic policies and agendas. How did the IGC establish such a reputation and how does the IGC cultivate it? Part of the answer may stem from the IGC’s association with prestigious academic institutions, which seems to offset the fact that it is financed by a foreign government. This reputation is preserved by delivering high-quality, rigorous research, and through discussions and on-going engagement with policymakers in which IGC researchers come across as “straight shooters”. Experience suggests that a good reputation is hard-won and easily lost, and this is clearly an important risk in any ToC for a policy influencing project.
Researchers’ credibility matters as well: the contribution stories in Pakistan, for example, suggested that the credibility of the research team may be at least as important as the quality of the research itself. In some cases at least, policymakers do not appear to make independent assessments of the technical quality of the research work produced by the IGC’s projects. Instead, their receptivity to the advice appears to be more linked to the reputation of the research team and the quality of its communications and interaction with the policymaker.
[note] It may be, of course, that the fact that it was IGC research was sufficient to indicate its quality.
Quality of delivery and engagement matter as well: The quality of communications and interaction with policymakers is very important. The property tax experiment in Pakistan that we examined offers an example of best practice in genuine researcher engagement with stakeholders throughout the research project cycle. IGC researchers were commended in our field interviews in Rwanda for presenting the results of their studies in a clear, understandable way, and in a manner that explained the consequences of taking certain actions rather than advising on a course of action per se. Moreover, in Rwanda the IGC were viewed as offering sustainable solutions, not just quick fixes, to the problems facing the government. A related point is that the IGC is seldom involved in the media debate about policy issues, which helps build trust between the government and the IGC.
“Synthesis products” are valued by policymakers and are much in demand: Many problems and challenges that policymakers face have been faced before in other countries. Policymakers usually realize there is no point reinventing the wheel, and take seriously the international experience. They invariably are keen to learn how other countries addressed those problems and whether solutions adopted by others could work in their own country. The IGC, with its international network, can deliver case studies and stories from other countries and has done so throughout Phase II. SPFs, because they can be implemented quickly and flexibly have proven to be very well suited to the delivery of such synthesis products. The experience of the CtW initiative seems to confirm the demand for synthesis products by policymakers, provided these products are assessible and well written, authoritative and credible, and packaged in innovative ways.
Follow up can be as important as the research itself: The initial failure of a project to result in a policy change should always give cause to ponder whether anything further can be done. In some cases there may be a need for some further intervention so as to clear the various institutional and other bottlenecks that are preventing the policy from being taken. In some cases SPFs may be sufficient, but larger scale interventions often seem to require a “technology transfer” facility that would aim to transform a good policy idea into a practical policy measure. In some cases, the policy ideas emerging from the research may be of such importance that involvement of other donors may be necessary in order to move from piloting to scaling up and implementation.
Drawing in other disciplines can sometimes help provide the right mix of advice: In some circumstances, the input of economists may not be sufficient for the uptake of their research. There may be a need as well for inputs from political scientists, specialists in public administration or lawyers. In Rwanda and Uganda we noted that the IGC Country Offices brought in specialists in municipal finance, whose work has had a discernible influence on policy. In the case of the tax evasion project in Pakistan, it might have been useful to review global experience on how unpopular tax policy measures were made politically palatable in other countries. In some cases, particularly in political sensitive areas, advice on the public presentation of a policy change may be as important as the technical aspects of the proposal itself.
The experiences of the IGC are consistent with those of other policy influencing projects funded by DFID: We were encouraged to find that many of these lessons are consistent with some of experiences of the DFID-funded programme Building Capacity to Use Research and Evidence (BCURE). BCURE was a DFID-funded project comprised of six linked projects across 12 low and middle-income countries in Africa and Asia. It used different interventions to build capacity for evidence use in single ministries and working across whole government systems.
The evaluation of BCURE (Vogel and Punton, 2018a; b) found three cross-cutting ‘ways of working’ associated with greater impact across all six countries included in the evaluation. The evaluation of BCURE concluded that its projects had greater success where they followed the principles set out in Box 13.
Box 13: Some Lessons from BCURE
Locating an entry point in a sector or government institution where there was existing interest in evidence, clear incentives for reform, and a mandate for promoting evidence use… / Taking an advantage of a window of opportunity – timing and prior relationships were often key. All six projects had most success where they capitalised on national and local opportunities for partnership and reform … Personal relationships should also not be underestimated … connections were often made and buy-in bolstered through the networks, prior experience and credibility of individual staff members and consultants. / Identifying individual champions within partner institutions and nurturing these relationships… senior officials acted as ‘gatekeepers’ to the institutional partnership … These champions also frequently acted as ‘cheerleaders’ for the programme, helping bring other senior stakeholders on board and identify further opportunities for partnership … they had significant seniority and power and they were personally committed to (often described as passionate about) reform. However, there are risks in tying a programme too closely to an individual champion, given the likelihood of senior staff turnover …

Cross-cutting issues
  1. To what extent has the IGC integrated cross-cutting issues into its work, including the economic empowerment of women and girls
IGC has already done some good work on gender, but it needs to integrate this issue more fully into its research strategy and research commissioning processes. The economic empowerment of women and girls is essential to an understanding of “inclusive growth”, which has been the driving theme of the IGC's work since its inception. The IGC only began tracking this issue in 2014, and so historical data is not readily available. The evidence suggests that the IGC has a good - possibly substantial - presence in the gender field and it should be possible for the IGC to make a larger contribution to policy debates on gender equality than it has done to date. While the IGC does now track the gender component in its research, it uses its own measures, which differ from the standard OECD/DAC indicators. There is no harm in using different indicators, but this may cause problems for DFID in its reporting in the future, so recording both seems sensible. In addition, gender could be better integrated into the preparation of any new Evidence Papers, and in the submission forms and appraisal templates for the Commissioning Boards.
1. Theory of Change
  1. How has the IGC developed and used its ToC?
Theories of change did not play an important role in the IGC’s operations during Phase I, but their role has expanded in Phase II. Both the evaluators and the IGC itself developed ToCs: the evaluators in a participatory way with the IGC, as part of the mid-term review in 2016 (IEB, 2016a); and the IGC itself (IGC, 2017). One way in which the IGC has used its version of the ToC is in planning the development of the IGC’s impact indicators (IGC, 2019b).
Since this is intended as a theory-based evaluation, we also considered the broader question of what ToC is adequate, given the goals the IGC has pursued and the activities it has undertaken in Phase II. For the purposes of this evaluation, the IEB continued to use the ToC developed during the mid-term review, since it was accepted by the IGC and DFID at the time as comprehensive, and its strategic pathways provided a very useful basis for the contribution analyses carried out in the mid-term report and extended in the end-term reports.
The ToC for Phase II of the IGC prepared by the evaluators is based on creating, applying and communicating knowledge. It has proved useful, is fit for purpose, and has evolved in interesting directions during Phase II, but requires some updates. The projects in Ethiopia and Ghana that we examined during our end-term visits helped us identify an important weakness in our 2016 ToC. Both the Ghana project and the Pakistan project faced challenges when it came to mainstreaming or scaling up the ideas that had been piloted. The 2016 version of the ToC gave too little attention to implementation of the policy changes inspired by IGC research. The Ethiopia and Ghana country studies proposed extensions to the ToC to take account of this important issue and improve the fidelity of the ToC.
Overall, the IGC made better use of its ToC in Phase II, but there would be advantages in integrating it with the version developed by the IEB and extending it to address the issue of implementation and to give a more detailed treatment of its global influencing activities.
## Overall purposes
The overall purposes of the evaluation were to:
1. assess the extent to which the IGC's work has influenced the adoption and implementation of credible growth policies in developing countries
2. understand the mechanisms by which the IGC exerts this influence on policy
3. identify the contextual factors that have contributed to this influence
4. examine the effectiveness of the IGC as a model for achieving policy influence
Questions i) and iv) have been addressed in the discussions of EQ 1 and EQ2 above. Here we provide additional discussion of questions ii) and iii).
The mechanisms by which the IGC exerts influence on policy
The two key mechanisms underpinning the IGC in Phase II were:
1. open calls for research funding, with projects selected for funding by the Commissioning Boards
2. the Country Offices, which allows on the ground presence in a number of low-income countries
These mechanisms are discussed in some detail in this report. Our assessment is that these mechanisms both worked effectively during Phase II, and that their effectiveness increased over time. Our end-term visits and interviews did, however, suggest that these mechanisms worked less well towards end of Phase II because of the uncertainties created by delays in tendering for Phase III. there was only one (relatively small) round of research commissioning after early 2017, and replacing departing staff was more difficult because of the short but uncertain time remaining in Phase III. The Country Offices adjusted to the decline in research commissioning by making greater use of SPFs, and the IGC displayed flexibility in coping with staff shortages, but there seems little doubt that the IGC model faced some difficulties at the end of Phase II – just as it did at the end of Phase I, when there were also delays in tendering for the Phase II contract. In this respect the longer duration of the Phase III contract seems a sensible step by DFID.
Our end-term visits and interviews also highlighted the evolution of the IGC’s influencing mechanisms, with the launch of two additional influencing mechanisms towards the end of Phase II.
The first of these mechanisms is “flexible engagement”, in which the IGC provides advice, synthesis products, etc. to policymakers in countries where there is no Country Office. This resembles mechanism ii) but without the Country Team. Instead of relying on relationships established by a CT, this mechanism relies on existing relationships between key policymakers and IGC researchers, RPDs or Hub staff. This is not an entirely new mechanism: it has been used in cases where Country Offices have been closed (e.g. for security reasons) but where the IGC wished to continue its activities. But starting in 2016/17 this practice was formalized and extended to a larger number of countries.
Flexible engagements have been awarded some impacts, but is a relatively new initiative and one which operated during the final stages of Phase II, with its attendant uncertainty about the contract for Phase III. This makes it difficult to assess its effectiveness: there is as yet relatively little evidence and that evidence is drawn from a slightly atypical period.
Cities that Work is also a slightly different mechanism, which is focused on one research theme (cities), with more emphasis on creating and disseminating synthesis products based on existing knowledge. It is also a departure from the established mechanisms because the synthesis work is carried largely by “in house”, IGC staff (the Cities Economists) rather than by researchers from the IGC network. There is a more evidence available about the effectiveness of this mechanism, in particular a number of recent impact cases, but this too has been operating late in Phase II, a slightly unusual period for the IGC.
Overall, both mechanisms show some promise, and the IGC plans to introduce another initiative on fragility based on the CtW experiences
There is a case for examining the effectiveness of each of these mechanisms in more detail one or two years into Phase III
The contextual factors that have contributed to the IGC’s influence
The environment for policy research differs widely across countries the countries in which the IGC operates: In our mid-term and end-term visits, for example, we found strong contrasts between Ghana, Pakistan, Uganda and Rwanda. Looking only at the supply of policy research, one illustration of the differences is the size and composition of the local “policy research community” (i.e. think tanks, policy research institutes, university research centres, etc.). Rwanda has really only a single think tank dealing with economic policy issues. Ghana and Uganda have two large institutes and several smaller think tanks. Pakistan is very different – there are large number of think tanks as well as policy research centres based in universities, and the IGC is only one among a number of domestic policy research actors. These institutional differences, as well as with differences in human capital (i.e. the number of PhD economists in the country) mean that the “local market” for policy research is much more concentrated in some IGC partner countries, and in some countries there are significantly more highly qualified policy analysts than in others.
There is heterogeneity across the IGC’s country offices and their strategies: Within the three countries visited for our mid-term report, we found two distinct ‘styles’ of country office, one (Pakistan) in which the Country Office is staffed by nationals of the country, and two other offices (Rwanda and Uganda) where the staff are drawn from both nationals and expatriates. Both Pakistan and Rwanda are viewed by the IGC as demonstrating good performance, and we did not find any evidence to suggest that one style is more effective than the other (and indeed each may have been chosen in response to local conditions). We found as well that the role of strong interlocutors or champions within the government differed across countries as well. It seemed to play an important role in the "non-local" offices, especially in their early stages, for example in Rwanda, where the Finance Minister (who later became the Central Bank Governor) was an important interlocutor. In Pakistan, the role of interlocutors or champions is less clear: the programme is built on the impressive personal networks of the Country Directors and Lead Academics. These networks are hugely important and have had a direct and meaningful impact on the success of individual projects.
There are clearly also a range of external contextual factors that affect the uptake of the IGCs research findings. The combination of heterogeneity in the policy research environment and heterogeneity across IGC country offices leads us to conclude that while contextual factors are important, it is more useful to consider instead how the IGC adapts to these contextual factors. Our work on this evaluation suggests to us that these external factors – “country context” are not particularly useful in explaining whether the IGC might be successful in a particular country. It seems instead to be more useful to focus instead on whether, and if so how, the IGC adapts to and works within the given context The key is whether IGC takes account of these factors and ensures that the CT is equipped to understand and take account of the context in which it operates, and to adapt to changes in this context when they occur (based on the evidence that they have gathered through the IGCs monitoring and review systems). This conclusion seems broadly consistent with the findings of the BCURE evaluation, which found it difficult to identify country level contextual factors that were good predictors of the success of BCURE’s capacity building interventions. Instead, as noted above, the final report of the evaluation focused on the characteristics of BCURE interventions that were associated with success. Our conclusion is that this is the most helpful way to view “context” for the IGC as well.
## Recommendations
Table 14: Summary of Recommendations
[note] We assign a higher priority to recommendations that involve activities or processes that either have a large impact on the IGC's effectiveness, or are not working well and need to be fixed quickly. Given the timing of the evaluation with respect to the launch of Phase III, we also focus on measures that need to be initiated at the start of Phase III in order to be effective. Within each Section of the report, at the first level the order in which the recommendations are presented reflects their priority i.e. R1 is higher priority than R2, and at the second level.
Main Recommendation	Detailed Recommendations
R1 Both the IEB and the IGC have developed versions of a ToC for the IGC. Each has its strengths and weaknesses: they could usefully be combined and extended along the lines recommended below in order to play a more important role in informing the IGC’s strategy during Phase III and providing a clear and solid basis for future evaluations of the IGC. This would involve streamlining the existing TOCs and extending them to address issues that are likely to more prominent during Phase III, in particular the challenges around policy implementation, mainstreaming and scaling up.	The TOC could be streamlined by consolidating the pathways involving “Open Calls for research” and “strategic commissioning”. Strategic commissioning (SP2) has not played an important role in the IGC’s knowledge creation activities so far, and if there is no prospect of it playing a significant role in the future, SP2 could be consolidated with SP1 to simplify the ToC. It could be clarified with respect to the role of researchers in the pathway involving establishing and sustaining relationships with government (SP3). Our study of the flagship projects in Ethiopia and Ghana reminded us that the IGC researchers, as well as the Country Teams, can play an important role in developing and sustaining these relationships, and this should be reflected in the pathway.
	The ToC should be extended to take into account the issues involved in policy implementation. The IGC's system of impact monitoring is focused on whether IGC activities contribute to a change in government policy or a regulation, but less so on the subsequent implementation of the policy. This should be extended and enriched, using the proposals made in the Ethiopia and Ghana country studies. While SP4 does address policy influence achieved via non-government actors, it does not address well work on governance related topics, such as the work in Sierra Leone on elections. If IGC continues to work on these issues, the ToC should be extended, using the suggestions in the Sierra Leone report. The global influencing pathway (SP5) also needs to be extended and refined to reflect the experience of the CtW initiative and the growth of the IGC's online communications channels during Phase II.
R2 The IGC should consistently map funded projects onto the IGC’s research and country priorities: The IGC should conduct a research mapping exercise as part of the Commissioning Board Process, and this exercise should map the all projects funded (either by the Country Programme or the Research Programme) onto the priorities for the relevant research theme and the priorities for the relevant country.
R3 the IGC should take steps to maintain the strength of the country voice in the selection of research projects	The Country Programme Director: The CPD played a key role in articulating the “country voice” in the commissioning process, but the position is now vacant. We recommend that a new CPD is appointed as soon as possible in the next Phase so that they are in place before any research is commissioned in the new Phase.
	The “dual funding” system for funding research that operated in Phase II should be maintained, since it seems to have helped the Country Offices influence the selection of research projects.
R4 The IGC should make greater use of external referees to assess proposals submitted to the Commissioning Boards in certain specified circumstances	COIs: The IGC needs to be able to demonstrate that it has carried out a thorough and objective appraisal of all the projects it funds. This applies even more strongly to proposals submitted by researchers closely associated with the IGC. Proposals involving RPDs should be evaluated by a researcher external to the IGC.
	Use of External Referees: The Phase II Research Strategy undertook to seek external reviews of proposals with a value exceeding £150K. The evidence suggests that during Phase II the IGC did not follow this rule. We recommend that the IGC implement this rule so that all "high value" proposals funded by the IGC receive external scrutiny, adjusting the rule as necessary so that it does not require an unmanageable number of external reviews.
R5 The IGC’s procedures for documenting the process of selecting research projects is good, but could be improved in several ways:	The IGC comprehensively documented its commissioning process in 2017. Going forward, this documentation should be updated on an ongoing basis to reflect any changes in the IGC's procedures.
	Documenting the Funding Decisions: Overall, the minutes of CB meetings were of good quality: they were prepared in accordance with the procedures set out in the Research Strategy and presented information in a clear fashion. Minutes for the later CBs only presented information on projects funded by the RP: in contrast minutes from the earlier CBs presented information on proposals funded by both the RP and the CP. The CP is a larger source of funding than the RP for projects approved by the CBs. We recommend that the IGC return to its earlier practice of presenting to DFID information on all the funded proposals, not just those funded by the RP.
	Documenting Participation in the Decisions: The minutes prepared by the IGC clearly indicate who participated in each CB meeting. Information on the participants in the meeting should indicate whether they participated in person or via telephone (a practice adopted in the minutes of later CBs). For those participating by telephone (in particular the CDs), we recommend that the minutes record which proposals were discussed when they did participate in the meeting.
	"Pre-Screening" of Proposals: The IGC should also provide a report to DFID after each CB on the criteria used for pre-screening, as well as a list of the topics and PIs for the pre-screened (i.e. rejected) proposals.
	Information on the Proposals Submitted: The quality of the data available for the entire set of submissions is less satisfactory, particularly for CB1 and CB2. The IGC should be interested, if only from a learning perspective, in the characteristics of the researchers who submit proposals, even if they are unsuccessful. This information will be very useful in future external evaluations of the IGC. We recommend that the IGC devote more resources to ensuring that it maintains comprehensive information on all submissions to each CB, and that this information is comparable across CBs.
	Participation of “local” researchers: The analysis in the 2016 IGC paper on the participation of "local" researchers required some staff time to complete, but was very informative and worthwhile. Carrying out this exercise when proposals are evaluated would, however, require relatively little additional work, and we recommend that the IGC compile - and report - this information on a regular basis in future.
	Cross-Project Linkages: The IGC’s database of proposals submitted to the CBs do not include a field indicating whether the proposal is linked to an SPF or to another IGC activity. This information is usually mentioned in the proposal narrative or otherwise known by the IGC staff, and we recommend that these linkages be identified in the documentation submitted to the CBs and recorded in the proposal database, and that the linkages to SPFs in particular are tracked and reported annually by the IGC.
R6 The IGC should reconsider the role of the CD in the approval of approving project Progress Reports, and Final Reports / Working Papers. We recommend that the LA be involved in these approvals as well, either as a joint approver, a second approver or with the CD designated as the approver for some (more policy oriented) projects and the LA for other (more research oriented) projects.
R7 The IGC should introduce ‘project completion reports’. These would be relatively short documents, one or two pages in length: succinct, confidential reflections of what goes wrong as well as right in terms of both research content and policy impact.
R8 The Country Programme should remain a key instrument in the IGC’s portfolio of policy-influencing tools. Our country visits suggested that the ability of Country Offices to achieve policy influence is constrained by the staff numbers and the time they have available for IGC work. The IGC should explore ways of addressing these constraints in order to increase the uptake of IGC research.	For Country Offices where impact is constrained by staff capacity, the IGC should consider buying more of the time of the CDs (who are currently part-time). If the CDs cannot devote more time to IGC work, then a Senior Advisor could be hired to take up some of the burden of influencing work.
	CEs play an important role in influencing as well and where their capacity limits the opportunities for influence, the IGC should consider hiring additional high-quality CEs. If overall budget constraints make this difficult, the IGC could explore the possibility of obtaining local (or other non-DFID) funding to “sponsor” the work of a CE.
	Investing in the professional development of its CEs is another way in which the IGC can make its policy influencing activities at the country level more effective. The work of CEs calls for a range of skills, both hard and soft (policy entrepreneurship, communications and presentation skills, etc.). These skills should be reviewed as part of the annual performance reviews, and where needed, training or other capacity-building interventions should be designed and delivered.
	Some of this additional capacity should be invested in broadening IGC’s networks amongst the policymaking community of partner countries. This would help reduce the IGC’s dependence on its relationships with a small number of high-level decision-makers.
R9 The IGC’s Policy influencing strategies at the project level have improved during Phase II, but more can be done to strengthen them.	PIPs need to take into account not only what the research is likely to “supply” in terms of outputs, but also “demand” – what policymakers are likely to demand and be have the capacity to absorb. PIPs have improved over Phase II but are now stronger on the supply side. They would be more effective if they took more explicit account of external factors (state effectiveness, receptivity to research evidence and the policy community, etc.).
	These improvements may require the IGC to provide more support to PIs in preparing the PIPs. It may be useful to assign an IGC staff member to provide technical support to researchers on the preparation of their PIPs.
	In cases where researchers do not have pre-existing relationships with policymakers on the ground, a stronger management function for the CT should be envisaged over the course of the project. Similarly, local researchers may help to bridge such relationship gaps.
	Projects may fail to achieve a Level 3 or Level 4 impact for a wide range of factors (many of them external to the IGC). The IGC should carry out regular reviews of these projects (as well as its Level 3 and Level 4 projects) to determine why they did not achieve the maximum possible impact, and whether the IGC’s strategy and tactics should be modified to consider whether the findings of those projects might now be more relevant. As a minimum, the findings of these projects should be synthesised and recorded in a database of policy ideas.
	There is often a tension in policy research projects between the timescales of the researcher and the policymaker. In many cases, the time horizons of policymakers are much shorter than those of the researcher. This can sometimes lead to a feeling of disconnect between the stakeholders and a question mark over the relevance of the research to the policymaker. For longer-term projects in particular, the IGC should design more "interim" outputs and policy recommendations in order as intermediate steps in a longer-term policy change.
R10 Country Teams often work in relative isolation, and their opportunities to interact with, and learn from, other teams in other countries have diminished over the course of Phase II. The IGC should devote more resources and attention to increasing the opportunities for cross-country learning, which our interviews suggested was highly valued by the Country Teams.	“Growth Week”, the annual meeting attended by members of the Country Teams, Hub staff, researchers from the IGC network and policymakers, has not been held since 2016. It offered an important opportunity for the Country Teams in particular to learn from each other and to engage with members of the wider research network. The IGC should revive Growth Week as an annual event in Phase III.
	The IGC needs to take steps to improve its knowledge management. It has produced a large and impressive portfolio of research during its first decade: there are almost 2000 activities registered in the IGC activities database and retrieving information on all the IGC activities relevant to a particular policy issue is not always a simple matter, especially if the IGC has not yet produced a synthesis product on the issue. Even if some of these projects have not had an immediate policy impact, most have yielded interesting policy proposals (or, at least, contain important policy implications). So as to enable a more comprehensive overview of its policy-relevant work, the IGC should consider building a readily accessible and user friendly “IGC database of policy ideas” which would summarise the conclusions of research projects in a way that would be easily accessible to all IGC staff, both in the Hub and the Country Offices.
R11 The IGC Country Programmes have developed effective strategies and tactics to achieve Level 3 and Level 4 impacts. These impacts often involve policy changes that are relatively discrete and self-contained (for example pilot projects exploring a promising new idea). The IGC needs to develop more explicit strategies and tactics to address the challenges of implementation, mainstreaming and scaling up of promising new ideas.	Addressing these challenges may require expertise that goes beyond that of economics. The IGC should consider whether, in order to meet these challenges, it needs to draw on the expertise from other disciplines, such as government and public administration, political science and law.
	Implementation may require partnerships with other institutions that have specialist expertise and/or greater resources. Projects that are likely to involve significant implementation challenges should take into account ex ante the need for (and prospects of) such partnerships. These institutions often have their own agendas, and so the need for such partnerships needs t0 be balanced against the IGC’s reputation for providing independent advice to policymakers.
R12 CtW is a model worth replicating, and the IGC can take the lessons identified in Section and apply them to its new Fragility Initiative, and beyond that to similar initiatives that it is considering.
R13 The CtW initiative is now moving into a phase where there is excess demand for its services, and it has to make choices. The initiative should therefore develop a longer-term strategy to help guide its decision making. Since CtW clearly is already influencing global discussions and is in a position to exert more influence in the future, it should also develop a more explicit global influencing plan. The strategy should incorporate the following:	The strategy can help them choose which cities to engage with, and also which international initiatives or events to be a part of. It should also help them guide their decisions as they need to become more selective in their engagements. If they do not become more strategic, they risk diffusing their impact, and burn-out of the team.
	The CtW team develop a strategy to activate its network of Policy Affiliates so that they can feed more into the Initiative – and infuse the programme itself with more policy maker perspectives from the developing world. This will also foster cross-city learning.
	The strategy should also support the CtW team in their own professional development, since they are mainly managed remotely. This should be done together with the new Policy Manager and the Communications and Development Manager of the IGC, with input from the CtW Manager and team. The need for training and development is also relevant to Country and Policy Economists, but this has not been explored in depth in the evaluation, and should be investigated during Phase III as the organisation matures.
R14 There is scope to further exploit the synergies between CtW and the IGC’s Cities research programme: on the one hand the feedback from the synthesis efforts could prove useful in identifying important knowledge gaps and guiding the research programme; on the other hand cities involved in CtW often have large quantities of data but little ability to analyse it, which could attract researchers to engage with the Cities research programme.	Since the CtW team is synthesising knowledge across the field they are in a very good position to be able to identify gaps in the knowledge base, and there should be more discussion about how they can feed this into the Commissioning Board. CtW is well placed to do this, since the Cities RPD chairs the CtW Council, which should facilitate a flow of ideas between the two programmes.
	CtW can build (jointly with the Cities research programme) a stronger network of younger researchers that need to publish, and who can benefit from having longer-term relationships with cities, including those from the developing world. Cities often have data, but limited research capacity, particularly in certain fields of economics such as urbanisation, and IGC researchers can fill this gap.
R15 CtW can go further in developing new and impactful synthesis tools, in particular more policy toolkits and multimedia resources available online and should consider developing an online course offering on urban policymaking.	The IGC should replicate the policy toolkits as a means of synthesising the existing body of knowledge in other thematic areas of the IGC, as they facilitate the rapid response to requests from policymakers received, for example by the IGC’s Country Offices.
	CtW should further develop the free multimedia resources it already makes available online, which serve as very useful learning tools for individual policymakers and also facilitate cross-city exchanges of experience. CtW already has short videos on key topics that urban policymakers could access in their own time: the videos with Glaeser and with developing country policymakers are very well produced and effective, and more material of this quality should be created. The IGC could also repackage some of its existing multimedia offerings (such as the interviews with Paul Collier) in a more engaging style.
	More ambitiously, the IGC’s academic partners (Oxford and the LSE) could develop a MOOC on cities and urban policymaking. Procurement issues make it very difficult for city staff to participate in paid online courses (unless they pay for it themselves), so a MOOC would enable many more policymakers from developing countries to access to the IGC’s body of knowledge and expertise.
R16 The IGC (and its partners) should continue their efforts to expand the readership of VoxDev. This involves expanding the range of content on VoxDev, making better use of automated tools to understand what drives traffic to the site, and expanding the efforts to better understand the profile and interests of the audience visiting the VoxDev site.	There are already plans to expand VoxDev’s content: one is to feature summaries of the survey or synthesis articles on development economics published in the Annual Review of Economics (annualreviews.org/loi/economics), and to introduce more audio content on the site. Other ideas currently under discussion include a series on gender, and “synthesis” articles organized in a “wiki” style. In order to expand the range of content, VoxDev might also consider adapting some of the ideas recently proposed for I4I by its Editor in Chief.
	This requires a better understanding of what has driven (and will in the future drive) traffic to the site. The editorial team should be provided with tools to gather in an automated way the disparate pieces of analytics information from social media and the web into a dashboard that would make it easier to instantly see the connection between a sudden spike in in views and a corresponding trigger in, for example a Tweet or a Facebook post. At the moment this must be done manually and so is slow and often not done because of time pressure.
	In common with many other online communications channels, VoxDev (and the IGC blogs) has only a very general idea of who it is actually reaching (i.e. the visitors to the websites). VoxDev should develop a strategy for gathering more information about their users, and eliciting feedback from these users in order to inform the development of new content and to demonstrate impact. VoxDev’s Twitter polls seem to have been useful, and should be continued. It would be worthwhile trialling similar polls or questionnaires on the VoxDev website itself: if short and not time consuming, they may generate responses that provide useful additional information about the broader audience visiting the website.
R17 The output indicators for online activities in IGC logframe should be improved, and these improvements should be informed by a better articulated Theory of Change for online influencing activities.	The logframe indicators for online communications outputs are fragmentary and inadequate. They should be revised in line with current good practice in communications. Cassidy and Ball (2018) would be a good starting point.
	The factors influencing the impact of the IGC blogs and VoxDev are not articulated in detail in the ToC for the IGC prepared in 2016 (IEB, 2016a). Some of the key elements of Strategic Pathways SP3 and SP4 seem relevant to this impact. It would be useful for the IGC to develop a “mini-TOC” for its online communications that takes into account some of the factors specific to these policy portals.
R18 VoxDev seems to play smaller role in showcasing IGC output than one might expect, at least in terms of articles: IGC content needs to be better identified and easier to locate on the VoxDev website (i.e. more visible on the relevant pages, and discoverable via the search function on the website).
R19 The IGC should continue its efforts to extend and improve its MEL System, which deals well with successful cases of policy influence, but needs to address other dimensions of IGC activity, in particular:	Continue its efforts to develop a more comprehensive MEL system around the research commissioning and the researcher network (e.g. what has been commissioned thematically, research impact and how to engage and motivate researchers for Policy Engagement and Global Influencing), and undertake more analysis on the mechanisms of change within the IGC’s research network.
	Continue to review and refine the impact scoring system (and the Theory of Change (cross reference here)) to better capture the nuances of policy engagement, in particular those involving implementation, mainstreaming and scaling up
	Carry out a regular and systematic analysis of projects that achieve only a Level 1 or Level 2 impact, along the same lines as the analyses of “drivers of impact” for Level 3 and Level 4 projects.
	Develop a comprehensive MEL guideline or framework document that explains their approach to MEL, and how it is linked to their logframe and ToC; and sets out a “data strategy” that identifies how all the pieces of data that the IGC are gathering will be integrated into the overall MEL system.
R20 the IGC should take steps to create and nurture a culture of active reflection and learning, and implement feedback loops from MEL observations into decision making both at the Hub and country levels.	The IGC should establish a high-level learning framework based on the assumptions in the ToC that can guide its drive towards learning. The IGC could consider hiring an external learning facilitator who can help the organisation to develop its learning culture. The facilitator could help the IGC set up learning processes at the Hub, across countries, between the Hub and the Country Programmes, within CTs and within thematic areas.
	The effectiveness of any learning framework depends in part on the visibility and strength of support it receives from the organization’s senior management. This raises the issue of where responsibility for learning should reside. One possibility is to combine this with the responsibility for the MEL function; another is to have a separate position responsible for learning. Adding responsibility for learning to the already demanding task of overseeing accountability reporting may prove challenging in practice. Separating these duties may have the advantage of signalling management interest in and support for learning from past experience in an ongoing way. The IGC should analyse the issue of responsibility for learning as it develops its learning framework and strategy in Phase III.
	Encourage greater integration of MEL into the policy engagement work of the IGC – there could be more avenues for the MEL team to engage with the PEs and directly with the CTs through country MEL visits for example. The new Policy Director could help to facilitate this integration if the person views learning as part of programme management, and draws on the MEL team as a resource.
R21 The economic empowerment of girls and women needs to be more fully integrated into the full range of the IGC’s activities in Phase III, in particular in the formulation of the research strategy, and the research commissioning process:	When CSNs and EPs are refreshed for Phase III, specific consideration of gender needs to be built in as a cross cutting issue ex ante.
	Proposal applicants / Principal Investigators (PIs) should be asked to indicate in their proposals whether the gender marker(s) should be applied to their project, and if so, the 'strength' of the gender content.
	Explicit mention of gender should be made in the CB Evaluation templates under Phase III. Similarly, the mapping reports prepared after each call should also contain this gender information. This would make it easier to ensure that gender information is added to the project database on a regular basis.
R22 The IGC could – and should – do more to draw more attention on a regular basis to its research relevant to economic empowerment of girls and women, and ensure that this research (or synthesis products based on it) makes a contribution to international discussions of economic issues relevant to “gender”:	The IGC should repeat the Gender Assessment in its Annual Report on a regular basis. This will be easier to do if the information relevant to gender is comprehensively and consistently entered into the IGC project database. If necessary, additional resources should be invested in ensuring that gender information is recorded consistently, particularly for older projects.
	The IGC should prepare more synthesis products on its gender relevant research findings, on topics where there is a critical mass of IGC project results either by theme (e.g. within the Firms theme perhaps training, worker productivity, microcredit, digital finance) or by country e.g. Zambia. There may also be a critical mass of relevant research on some other topics, e.g. health and education.
	The IGC could to use such synthesis products to contribute to international debates on other economic topics that have high profile in current gender discussions. These could include the questioning of gender norms (regarding fertility, women’s effectiveness as entrepreneurs, ‘identity’ and so on), the extent and economic implications of women’s unpaid care work, and the gender dimension of trade, employment and enterprise, which would feed into countries’ efforts to shape their policies in the wake of the WTO Declaration on Women and Trade (WTO, 2017).
R23 The gender markers used by the IGC cannot be mapped easily onto the markers defined by the OECD/DAC. If the IGC record wishes to use its own set of indicators, then it should ensure that the OECD/DAC indicators are recorded in its project database as well.
[note] https://www.theigc.org/multimedia/the-spacial-structure-of-cities-in-developing-countries/ and https://www.theigc.org/multimedia/land-rights-in-developing-countries-insights-from-policymakers/

# Annexes
## References
Azulai, M., Bandiera, O., Blum, F., Kleven, H., La Ferrara, E., Padró, G. and Tejada, C.M., 2014. Evidence Paper: State Effectiveness, Growth, and Development. London: International Growth Centre.
Befani, B. and Mayne, J., 2014. Process tracing and contribution analysis: a combined approach to generative causal inference for impact evaluation. IDS Bulletin, Special Issue: Rethinking Impact Evaluation for Development, 45(6), pp.17–36.
Bloom, N., Fischer, G., Rasul, I., Rodriguez-Clare, A., Suri, T., Udry, C., Verhoogen, E., Woodruff, C. and Zane, G., 2014. Evidence Paper: Firm Capabilities and Economic Growth. London: International Growth Centre.
Carden, F., 2009. Knowledge to policy: making the most of development research. [online] Ottawa: SAGE and IDRC. Available at: <https://www.idrc.ca/en/book/knowledge-policy-making-most-development-research>.
Cassidy, C. and Ball, L., 2018. Communications monitoring, evaluating and learning toolkit. [online] London: Overseas Development Institute. Available at: <https://www.odi.org/publications/11040-communications-monitoring-evaluation-and-learning-toolkit>.
Delahais, T. and Toulemonde, J., 2017. Making rigorous causal claims in a real-life context: Has research contributed to sustainable forest management? Evaluation, [online] 23(4), pp.370–388. Available at: <https://doi.org/10.1177/1356389017733211> [Accessed 3 May 2018].
DFID, 2015. IGC Annual Review 2015. [online] London: Department for International Development. Available at: <http://iati.dfid.gov.uk/iati_documents/5062127.odt>.
DFID, 2018a. 43897069 IGC Logframe Phase II - Published December 2018. [online] London: Department for International Development. Available at: <http://iati.dfid.gov.uk/iati_documents/43897069.xlsx>.
DFID, 2018b. IGC Annual Review 2018. [online] London: Department for International Development. Available at: <http://iati.dfid.gov.uk/iati_documents/21576134.odt>.
Fields, G., 2011. Evaluation of International Growth Centre Research.
Greenstone, M., 2014. Evidence Paper: Energy, Growth, and Development. London: International Growth Centre.
IEB, 2016a. IGC Phase II evaluation mid-term report - Appendix 1: Theory of Change. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2016b. IGC Phase II evaluation mid-term report - Appendix 2: Pakistan Contribution Stories. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2016c. IGC Phase II evaluation mid-term report - Appendix 3: Rwanda Contribution Stories. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2016d. IGC Phase II evaluation mid-term report - Appendix 4: Uganda Contribution Stories. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2016e. IGC Phase II evaluation mid-term report - Synthesis Report. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2016f. Quality Assurance of 2015/16 Performance Indicators. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2017. Quality Assurance of 2016/17 Performance Indicators. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2018a. IGC Phase II evaluation interim report - Tax Policy and Reforms in Rwanda Evaluation of the economic impact of IGC advice to the government of Rwanda on the introduction of a proposed flat tax system. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2018b. Quality Assurance of 2017/18 Performance Indicators. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2019a. IGC Phase II evaluation end-term report - Country Programme Report including Flagship Projects and Contribution Analysis – Ethiopia. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2019b. IGC Phase II evaluation end-term report - Country Programme Report including Flagship Projects and Contribution Analysis – Ghana. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2019c. IGC Phase II evaluation end-term report - Country Programme Report including Flagship Projects and Contribution Analysis – Pakistan. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2019d. IGC Phase II evaluation end-term report - Country Programme Report including Flagship Projects and Contribution Analysis – Sierra Leone. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2019e. IGC Phase II evaluation end-term report - Cross-cutting issues. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2019f. IGC Phase II evaluation end-term report - Evaluation Framework and Instruments. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2019g. IGC Phase II evaluation end-term report - Global Influencing. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2019h. IGC Phase II evaluation end-term report - Research Implementation. Independent Evaluation Board. Galway: Galway Development Services International.
IEB, 2019i. IGC Phase II evaluation interim report - Evaluation of the International Growth Centre’s Research Commissioning. Independent Evaluation Board. Galway: Galway Development Services International.
IGC, 2012. Annual Report 2011-12. London: International Growth Centre.
IGC, 2013. IGC Phase II Research Strategy. London: International Growth Centre.
IGC, 2014. Communications Strategy – work in progress - update for DFID. London: International Growth Centre.
IGC, 2015. Annual Report 2014-15. London: International Growth Centre.
IGC, 2016. Annual Report 2015-16. London: International Growth Centre.
IGC, 2017. Theory of Change and Narrative. London: International Growth Centre.
IGC, 2018. Drivers of Impact over 2017/18 and Proposed Targets for 2018/19. London: International Growth Centre.
IGC, 2019a. Cities that Work: Overview. London: International Growth Centre.
IGC, 2019b. IGC Impact Methodology Development Plan. London: International Growth Centre.
Kingdon, J.W., 1990. Agendas, alternatives, and public policies. New York: Harper Collins.
Leape, J. and Lyness, S., 2014. A Global Communications Strategy for the IGC. London: International Growth Centre.
Miguel, E., 2019. RCTs in the long run. VoxEU.org. Available at: <https://voxeu.org/vox-talks/rcts-long-run> [Accessed 9 Aug. 2019].
Moretti, E., 2014. Evidence Paper: Cities and Growth. London: International Growth Centre.
Pawson, R., 2006. Evidence-based policy: a realist perspective. London ; Thousand Oaks, Calif: SAGE.
RAND Europe, 2016. Review of Six DFID-funded Growth Research Programmes.
Vogel, I. and Punton, M., 2018a. Executive Summary: Final Evaluation of the Building Capacity to Use Research Evidence (BCURE) Programme. [online] ITAD. Available at: <http://itad.com/reports/final-evaluation-building-capacity-use-research-evidence-bcure-programme/>.
Vogel, I. and Punton, M., 2018b. Final Evaluation of the Building Capacity to Use Research Evidence (BCURE) Programme. [online] ITAD. Available at: <http://itad.com/reports/final-evaluation-building-capacity-use-research-evidence-bcure-programme/>.
WTO, 2017. Joint Declaration on Trade and Women’s Economic Empowerment on the Occasion of the WTO Ministerial Conference in Buenos Aires. Geneva: World Trade Organization.
## Abbreviations
Table 15: Abbreviations
BCURE	Building Capacity to Use Research Evidence
CA	Contribution Analysis
CB	Commissioning Board
CD	Country Directors
CE	Country Economist
CIFOR	Center for International Forestry Research
CIRAD	Centre de coopération internationale en recherche agronomique pour le développement
CP	Country Programme
CPD	Country Programme Director
CSN	Country Strategy Note
CT	Country Team
CtW	Cities that Work
DFID	Department for International Development
EDE	Equally Distributed Equivalent
EIC	Ethiopian Investment Commission
ED	Executive Director (IGC)
EP	Evidence Paper
EQ	Evaluation Question
FDI	Foreign Direct Investment
GDP	Gross Domestic Product
IDRC	International Development Research Centre
IDS	Institute for Development Studies
IEB	Independent Evaluation Board
IGC	International Growth Centre
IMF	International Monetary Fund
LA	Lead Academic
LSE	London School of Economics and Political Science
MEL	Monitoring, Evaluation and Learning
MOOC	Massive Open Online Courses
NGO	Non-governmental organisation
OHCS	Office of Head Civil Service
PEDL	Private Enterprise Development in Low Income Countries
PI	Principal Investigator
PIP	Project Influence Plan
PIR	Project Influence Report
PMT	Project Monitoring Tool
QA	Quality Assurance
RCT	Randomized controlled trials
ROA	Rapid Outcome Assessment
RP	Research Programme
RPD	Research Programme Director
RPRI	Research Priorities (document)
RPT	Research Programme team
RR	Rapid Response
SFM	Sustainable forestry management
SIP	Strategy Implementation Plan
SMT	Senior Management Team
SPF	Small Projects Facility
SSRN	Social Science Research Network
ToC	Theory of Change
WTO	World Trade Organization

## Logic Model and Strategic Pathways
Table 16: Overview of the IGC logic model and Strategic Pathways
IMPACT: Sustainable growth in developing countries			Indicator: Number of countries identified in the 2011 DFID Bilateral Aid Review with real GDP growth rates of 5% or above.
OUTCOME: Credible growth policies and programmes implemented in developing countries.			Outcome Indicator 1: Number of changes to growth related policies (based on IGC research and advice) / Outcome Indicator 2: Number of partner and non-partner countries where ideas emanating from IGC programme have influenced policy discussions

Knowledge generation		Knowledge application			Knowledge communication
Research Programme		Country Programme			Communications
SP1 Open Calls for research proposals / SP2 Strategic commissioning		SP3 Direct relationships with policy makers / SP4 Through other actors			SP5 Influencing Plans
Outputs	Indicators	Outputs		Indicators	Outputs	Indicators
Output 2: World class policy-oriented research undertaken on developing country growth issues and widely disseminated	2.1 Number of peer reviewed articles and IGC standard working papers and conference papers produced by projects funded by the IGC Research Programme, in Phase 2, cumulative / 2.2 Number of articles accepted for publication (including “revise and resubmit”) produced by projects funded by IGC Research Programme in Phase 2, cumulative. / 2.3 Cumulative number of peer reviewed articles achieving ten or more citations in other academic articles, funded by the IGC in Phase 2, (cumulative total Phase 1 and 2) / 2.4 Number of Phase 2 commissioned research or country studies to be authored or co-authored by ‘local researchers’, cumulative. / 2.5 Proportion of Research Programme grants (by value) research projects having at least one PI outside the IGC research network at the time of application / 2.6 Value of projects approved by CBs in the IGC Research Programme Phase 2 and signed off by DFID, cumulative	Output 1: Country-specific, evidence-based, and timely advice provided to answer developing country policymakers’ growth questions		1.1 Number of country programmes fully functioning with demonstrated stakeholder engagement / 1.2 Number of IGC outputs (cumulative from baseline) that have substantially contributed to the policy process* / 1.3 Number of IGC country programmes with at least two new outputs that have substantially contributed to the policy process* / 1.4 Number of non-partner countries, regional organisations or multilateral organisations that have been engaged with for policy advice and/or advice on regional issues that have been met by IGC engagement	Output 3: Strengthen IGC`s relations with its stakeholders and communicate the IGC`s work globally and locally.	3.1 IGC demonstrates active participation in international debates, as demonstrated by: / Number of IGC publications on a global debate/issue. These papers should be specific to the issue (not the general synthesis papers). / Representation of the IGC at external events (such as WTO, IMF/World Bank Annual Meetings). / 3.2 IGC communicates to a broad global and local audience as demonstrated by: / Increased number of unique visitors on the main IGC website / Increased engagement (Twitter followers) / Global communications / 3.3 IGC engages and communicates in country, as demonstrated by number of countries that have: / Instigated new relationships and / or maintained existing relationships with targeted influential senior stakeholders and partners / Engaged with the general public, as measured by the number of written press (print and web), radio or television mentions.
Source: (IEB, 2016a)

## Terms of Reference
TERMS OF REFERENCE FOR THE EXTERNAL EVALUATION OF THE INTERNATIONAL GROWTH CENTRE
January 2014
DFID seeks to appoint an Independent Evaluation Body (IEB) to design and implement an independent evaluation of DFID funded activities of the International Growth Centre (IGC). This will include full and separate evaluations of Phase I (October 2008 - March 2013) and Phase II (April 2013 - February 2017) of the programme. The IEB will be appointed to develop an evaluation design for the programme and to implement this through the Phase I evaluation in 2014, a Mid-term Evaluation in 2016 and a Final Evaluation in 2017.
Background and context
The IEB evaluations will provide an independent and rigorous assessment of the programme. The IEB will work in consultation with the IGC.
Description of the IGC
The IGC’s mission is to promote sustainable growth in developing countries by providing demand-led policy advice based on frontier research.
The IGC’s strategy has four key elements:
1. Country engagement is sustained and demand-driven: in all its partner countries, the IGC has resident country teams and works with government, private sector and civil society to identify policy priorities and define the research agenda
2. This demand is met by frontier research in both its stock and flow dimensions, thus creating a bridge between academia and the policy world.
3. Drawing on its research outputs, and through conferences and communications, IGC contributes to national and international debates on policies for economic growth
4. IGC is both autonomous and independent in order to guarantee the credibility of the research it produces and the policy advice it delivers.
In the IGC’s demand-led model, key policymakers and stakeholders are consulted on the major growth challenges to ensure IGC’s research is policy-relevant. In many projects, there is close and continual engagement with policymakers and government institutions during the inception of the research, implementation and in communicating research findings. This close collaboration with governments throughout the research process ensures that the findings are locally-owned and of immediate, practical use. It also facilitates policy impact even before the results are finalised through dissemination of intermediate results and local capacity building. A Theory of Change (ToC) representing this highly non-linear and complex process can be found in Annex 1.
Implementation
The IGC is implemented by LSE in partnership with Oxford University. It was initiated and is fully funded by DFID.
The IGC has 15 active country programmes in 14 countries (Bangladesh, Ethiopia, Ghana, India (Bihar state and Central), Liberia, Mozambique, Myanmar, Pakistan, Rwanda, Sierra Leone, South Sudan, Uganda, Tanzania and Zambia) as well as four research programmes on state effectiveness, firm capabilities, energy, and cities. The IGC is composed of a team working in London (See Annex 2 – Organogram) as well as a team working in each of the country programmes, which typically comprise of one Country Director (resident or non-resident), one or two Lead Academics (non-resident), and two Economists (resident).
In order to fulfil its mandate, the IGC has developed an extensive research network, involving top researchers from leading universities and research centres around the world. The IGC commissions rigorous, policy-relevant research from this network and disseminates the results widely. This is done through: (i) publications in peer reviewed journals and books, (ii) policy briefs, (iii) conferences and workshops, (iv) meetings, dialogues, and seminars with leading policy makers, and (v) various online and social-media portals (e.g. “Ideas for India”).
The IGC manages a complex system of projects. For example, in 2012-13, IGC staff and sponsored researchers produced 25 short policy responses for partner countries, 49 policy briefs, and 91 working papers from the different research projects. Additionally, by March 2013, IGC and linked researchers had published 16 papers in high-class academic journals. The IGC also sponsored 57 events. Short policy response projects typically last for about a month, while full-fledged research projects can span many years.
The IGC does not have a focus on any particular cross-cutting growth issues, but inclusiveness emerges as a cross-cutting theme in much of the IGCs research and country programme work.

DFID Support to the IGC
The IGC is completely funded by the UK Department for International Development (DFID). DFID allocated £30 million for Phase I and has recently approved £51 million for Phase II (see Business Case attached). The contract, renewed in February 2013, includes a terms of reference for the operations of the IGC.
Further information on the IGC's objectives and theory of change can be found in the DFID Business Case, which can be found on the DFID website or made available on request.
 (https://www.gov.uk/government/organisations/department-for-international-development) .
The findings from previous reviews of IGC are available on request.
[note] Including DFID annual reviews, project completion report and Phase I research review.
Purpose and Objectives
The purpose of the evaluation is to assess the extent to which the IGC’s work has influenced the adoption and implementation of credible growth policies in developing countries and the factors which have contributed to this. The objective is to learn lessons on the mechanisms of policy influence in order to:
- Assess the effectiveness of the IGC as a business model to influence policy, including the interplay between research and country programmes;
- Learn lessons to strengthen and improve on-going performance of the IGC;
- Learn lessons for DFID and the international community on policy influence, and make a significant contribution to the evidence base and academic debate surrounding the impact of research on policy making and the impact of growth related research. The evaluation should allow for generalisation from the projects/programmes selected for evaluation and should identify key contextual factors expected to affect impact.
More specifically, it will assess the extent to which the IGC has been successful in (i) implementing projects and achieving policy influence, (ii), defining priorities and building a research portfolio to support policy influence (iii) producing high-quality outputs, (iv) achieving value for money and (v) managing the programme effectively.
In addition, the IEB will have a recurring role within Phase II to independently quality assure a small number of performance indicators that are reported on an annual basis as part of DFID’s Annual Review process.
Scope
The evaluation reports produced by the IEB will cover
1. Evaluation of Phase I (2008-2013)
2. Evaluation of Phase II (2013-2017)
The Phase I evaluation will use retrospective evaluation techniques and the Phase II evaluation will use a mix of retrospective and prospective evaluation techniques. A mid-term review of the Phase II evaluation should also be produced, to report interim findings. Within each of these evaluations, the IEB will evaluate the IGC’s Country Programme, which responds to specific policy demands from countries on issues of economic growth; the IGC’s Research Programme, which hopes to generate innovative ideas for economic growth through academically rigorous economic research; and, finally, the management and operational effectiveness of the IGC. The evaluation of the three components above should be integrated and carried out as a joint exercise. The whole of the programme will be evaluated but a portfolio approach should be taken to allow a more in-depth look at a sample of countries/project areas. This will help DFID to better understand the detail of what factors influence the success of IGC interventions.
Using and revising the ToC as shown in Annex 1 where necessary, the IEB will look to evaluate as far down the impact chain as possible. It is anticipated that this will involve advanced evaluation methodologies for policy impact, including theory-based evaluation methods.
Phase I Evaluation
The Phase I evaluation will cover the whole IGC programme. In addition, the IEB will undertake a more in-depth evaluation of a sample of components of the programme including the following:
- Three to four country programmes, to be selected by the IEB; and
- Three of IGC’s ten research programmes, to be selected by the IEB.
For these in-depth reviews, DFID anticipates that this will look both at the impact of individual outputs, as well as the effectiveness of a strategic combination of these outputs. The approach and comprehensiveness of outputs reviewed for each programme will be determined by the IEB, and outlined in the proposal.
Phase II Evaluation
In Phase II, research and country programmes will work in a more integrated way. Under Phase II commissioning boards under each research theme will contain representation from both the IGC Research and Country Programmes. Furthermore, all research funding will be conditional on researchers remaining in close contact with the relevant country teams in discussions with country policymakers and stakeholders whenever opportunities arise within the context of IGC work. As a result the methodology will be expected to be different to Phase I, and will look at the research and country programmes jointly, paying special attention to how effectively they interact with each other and how the linkages could be strengthened. Furthermore, unlike Phase I (in which the evaluator will have to rely on retrospective data) the Phase II evaluation can include new data collection methods to achieve a deeper evaluation.
The Phase II evaluation will evaluate the IGC’s work initiated during this Phase and where appropriate it may continue longitudinal evaluations of interventions from Phase I that are having a policy impact during Phase II.
In addition to an evaluation of the whole programme, the IEB will undertake a detailed evaluation of a sub-sample of the IGC’s operations. It will cover:
- Three to four country programmes, to be selected by the IEB; and
- Two of IGC’s four research programmes, to be selected by the IEB.
  [note] In Phase II of the programme the number of research themes was streamlined from 10 to 4.
The approach and comprehensiveness of outputs reviewed for each programme will be determined by the IEB, and outlined in the proposal.
Approaches for both the Phase I & Phase II Evaluations should be developed in a participatory way with the IGC in order to maximise the usefulness of the evaluation to the IGC’s operations.
Quality assurance of on-going performance indicators
Each IGC outputs (about 250 per year) is rated internally by the IGC against an impact score (on a scale of 1-4), depending on the level of policy impact achieved. To ensure robustness of these scorings, the IEB will annually quality assure the scoring that IGC gives to its outputs, by providing a small-sample review (10-15%) of outputs. The evaluator should seek positive assurance that the ratings themselves are accurate and appropriate. This will involve a light desk based review of each sample output (which is provided in the IGC Annual Report), supplemented where appropriate by telephone interviews with IGC staff and IGC clients. More details on IGC’s impact scoring system are provided in Annex 3.
Recipient
The target audience for the evaluation includes the IGC, DFID, partner governments, institutions, researchers, policymakers, other donors, civil society, and other organisations working in the field of policy advice for international development. DFID will be the recipient of services for the evaluation.

 Evaluation Questions
The IEB will evaluate the extent to which IGC successfully influences the adoption and implementation of credible growth policies in developing countries, and influences global debates. The IEB should be guided by considering the evaluation questions below, but are free to set their own, and ensure alignment with the evaluation purpose and objectives set out in Section 2 above as well as recognised evaluation criteria (the DAC evaluation criteria).
Achieving policy influence (at the country, cross-country and global levels)

- How effective has the IGC’s policy engagement been in impacting growth-related policies?
- What have been the key mechanisms that have driven impact?
- Is the success of these mechanisms applicable more widely?
- What explains the difference between successful policy influence and examples where impact has been low?
- Is the work of the IGC tailored towards the demands of policy makers in IGC’s partner countries?
- Has the IGC been successful in generating local ownership of policies and ensuring long-term policy influence?
- Has the IGC successfully expanded its engagement with various stakeholders and facilitated research uptake in-country?
- Have there been any unintended impacts (positive or negative) from the IGC’s work?
- To what extent have the efforts of the IGC built or strengthened stakeholders’ abilities to produce and interpret economic evidence?
- Has the IGC successfully engaged and influenced global policy on growth issues?

Defining priorities and building a research portfolio

- How effective has the IGC been in identifying research gaps and defining research priorities that would support policy influence in-country?
- To what extent were the IGC’s activities aligned to those research priorities?
- How strategically coherent has IGC’s portfolio been, and how has this affected the impact of the IGC at the country and international level?
- Has the IGC engaged with a broad pool of researchers?
- To what extent has the IGC’s policy advice and research addressed cross-cutting issues, in particular the economic empowerment of women and girls?
- Is there scope for the IGC to improve the way that cross-cutting issues are integrated into their policy and research work?

Producing high-quality outputs

- Are outputs of sufficient quality?
- Does the IGC have a reputation for producing high-quality, relevant and specific outputs?
- To what extent have the IGC’s research activities added to the existing growth and policymaking literatures and lead to further developments of this literature?

Organisational Management

- How adequate is the IGC’s management structure to achieving its goals?
- How responsive is the IGC to new demands and changes in the external environment?
- Does the IGC pro-actively manage poorly performing programmes?
- Does the IGC have an effective mechanism for monitoring and improvement?
- Have lessons been learnt from previous reviews?
- What are the most useful metrics for the IGC to measure its policy influence? Are there any specific steps IGC could take to better capture this information in the future?
- What are the most useful metrics for the IGC to measure the quality of the IGC’s research outputs? Are there any specific steps IGC could take to better capture this information in the future?
- Do IGC activities represent value for money in terms of quantity and quality of outputs, and cost?

The IEB will not be limited to the list of questions above. Bidders will be expected to review and revise this set of questions as part of their bid document.

Methodology
During the inception phase, the IEB will develop a comprehensive evaluation framework for the IGC, which will be developed in consultation with the IGC. The proposed evaluation framework should include details on the nature of the evidence to be used, the proposed methodology, and efforts to mitigate identified evaluation challenges.
Bidders are free to propose the most appropriate design and should ensure that the proposed design and methods reflect the following issues:
- Between 2013 and 2017, the IGC will be starting several new projects of various sizes and objectives. The general approach and methods suggested must show how the bidders intend to deal with the fact that the life cycles of projects will vary substantially both in length and start-dates throughout the evaluation periods. It should also show how it will link evaluations, both at the country and regional level, with the overall programme evaluation.
- Identifying lessons and the opportunities for replication is very important. The evaluation design should allow for generalisation from the projects/programmes selected for evaluation and should identify key contextual factors expected to affect impact.
- Bidders must specify the data collection methods that they expect to use and the expected scale of data collection that will be undertaken, including indications of how sample sizes will be established, number of case studies etc.
- Bidders are expected to consult external evaluation specialists with expertise both on policy advice evaluation and on the specific methodologies, where relevant, that they are proposing to undertake. The external experts are expected to be proposed as part of the general evaluation bid.
- Finally, bidders must clearly set out the standards they will use for ensuring rigour and credibility.
Evidence
For the Phase I evaluation, there is limited systematic evidence at the project-level. The influence metrics used will thus be based on data collected post-project. For the Phase II evaluation, we expect the IEB to develop metrics to collect information on projects’ intended and achieved influence both during and after the completion of the projects.
In its Inception Report, the IEB will propose an evaluation framework that will use (i) existing information collected by the IGC, (ii) information, which the IGC will collect in the future, and (iii) information to be collected by the IEB. It will include details of the methodologies to be used and will be agreed upon by both the IGC Governance Committee and DFID. The IEB will also work with the IGC to further develop a theory of change, which will form a basis for further developing the evaluation questions and methodologies.
In order to capture the iterative nature of the IGC’s work, a variety of evaluation approaches could prove useful in evaluating the outcome and impact of the IGC projects and programmes. The approach must be sufficiently rigorous to deliver evaluation findings that can contribute to the academic debates on the impact of growth related research on policy making.
[note] For example: modular matrices, RAPID, process tracing, most significant change.
While the IEB will ultimately be in charge of choosing a methodology, DFID is keen to explore theory-based evaluation as a way to rigorously assess IGC’s activities. The following questions should be considered when selecting the mix of evaluation methods to be used:
- Since there is no natural control group for the work of the IGC, how can one best demonstrate what would have happened in the IGC’s countries of engagement had it not been for the IGC’s contribution?
- How can we evaluate the effectiveness of different aspects of the IGC approach, given the complexity and breadth of the IGC’s activities?
- How can we take into account the unintended consequences and positive spill-overs of the IGC’s work?
- Given the multitude of factors influencing policy outcomes, how can we best identify and assess the IGC’s influence?
- How can we divide between the contribution to and attribution of policy impact with respect to the IGC’s work? How can we effectively isolate and measure each?
The methodology should take into account the monitoring and internal learning that the IGC’s own Internal Evaluation will perform in order to reduce duplication of effort.
The IEB must comply with both the DAC Quality Standards for Development Evaluation and DFID’s Ethical Guidance for Research and Evaluation in undertaking the evaluation.
Outputs
Quality assurance of on-going performance indicators
Annually from 2014-2017, the IEB will provide a short written report to DFID to comment on the accuracy of a sample of IGC output scores (as contained in the IGCs Annual Report).

Inception Report and Evaluation Framework

The Inception Report and Evaluation Framework will:
- Detail the evaluation questions, design, methods, and work plan for the Phase I evaluation and provide an initial framework for Phase II (which will be revised at the end of the Phase I evaluation).
- Describe how the Phase II evaluation design is expected to build on the evaluation work conducted during Phase I. The Phase II evaluation framework should take into account changes in the IGC’s structure as it has entered Phase II and opportunities for longitudinal evaluation of interventions that are yet to be initiated under Phase II and those initiated under Phase I that are expected to have policy impact.
- Present a communication and dissemination strategy.

Bidders must specify in their proposals an initial evaluation approach that is guided by the evaluation objectives identified above, the initial set of evaluation questions and the sampling approach identified in this ToR. It is expected that this approach will be refined during the inception phase, in consultation with DFID.
The Evaluation Framework should set out the following elements:
- The finalised evaluation design and methods for Phase I and an initial design for Phase II;
- A review of and comment on the theory of change and discussion of implications for the evaluation design;
- A review of the evaluation questions and proposals for how they might be amended or their range expanded;
- A communication and dissemination strategy;
- A review of the main risks and challenges for the evaluation and how these will be managed;
- A proposal on the collection of primary data and division of responsibilities between the IGC and the IEB;
- A primary data collection strategy;
- A discussion on how to ensure that the design and application of methods will be ethically sound and which relevant ethical standards will be applied; and
- Both a work plan and projected costs.

Phase 1 Evaluation Report
The Phase I Evaluation Report should comprise:
- Executive summary – highlighting the main findings, conclusions, recommendations and any overall lessons;
- Introduction - including the policy, institutional and development context and their influence on the impacts and outcomes;
- Description of theory of change;
- Methodology;
- Evaluation findings;
- Conclusions and lessons learned;
- Recommendations for the remainder of the programme;
- A presentation to be given to DFID and IGC, and other accessible communication tools (e.g. summary report in non-technical language).

Revised Phase II Evaluation Framework

The Phase II Evaluation Framework will be outlined as part of the IEB’s Inception Report. However, a Revised Phase II Evaluation Framework should be submitted after the Phase I evaluation in order to take into account the lessons learned through the implementation of the Phase I evaluation and to identify opportunities for longitudinal evaluation of interventions initiated under both Phase I and Phase II.

The IEB will be able to draw upon existing IGC data collection, and have the opportunity to propose new data collection that can be undertaken by the IGC to assist with the evaluation process for Phase II. It is expected that there will be a specific section of the Phase II evaluation framework devoted to discussing the IGC’s monitoring framework and, importantly, outlining the way in which it will be used by the IEB as part of the evaluation. Part of this section should also include suggestions for how to further tailor the monitoring framework towards the needs of the evaluation framework. Advice to the IGC should include, but not be limited to:
[note] Including impact scores (described in Annex 3), stories of impact, reporting against the logframe and project summaries.
- Identification of the programme monitoring data required from the IGC to meet evaluation needs and timings for this;
- Suggestions for revisions to the programme’s theory of change based on an assessment of the relevant evidence;
- Discussion of the relative responsibilities for primary data collection throughout the evaluation period;
- Recommendations regarding the overall data collection system; and
- Plans for the on-going monitoring and evaluation support to be provided during the on-going evaluation work.
The evaluation design report should then be finalised incorporating DFID feedback as per the timeline in Section 6.
Phase II mid-term report

The mid-term evaluation will follow the requirements of the evaluation design. It is anticipated that the evaluation will:
- Focus on the evaluation questions as defined in the evaluation design report. Where possible the evaluation will identify the emergent trajectory of change associated with the programme.
- Review the primary data collected to date and make changes to the data collection requirements as required.

The Mid-term evaluation report should include:
- Executive summary – highlighting the main findings, conclusions, recommendations and any overall lessons;
- Evaluation findings including an assessment of the outcomes achieved by the IGC;
- Conclusions and lessons learned including suggestions on how the IGC’s work might be adjusted to enhance its overall impact and recommendations for any subsequent work; and
- A specific high level report, presentation, and other accessible communication tools using the mid-term findings and conclusions. These will be disseminated to senior DFID, IGC, and other stakeholders outlining the potential for replication. The IEB is expected to participate in the presentations regarding the findings of the mid-term evaluation.

At this stage, it may not be possible adequately to identify impact. However the mid-term evaluation will identify the trajectory of change and allow revisions to the evaluation design and methodology, where applicable and possible, to be implemented in preparation for the final evaluation.
Phase II Final Report

The Final evaluation will take place in 2017 and will focus on the evaluation questions specified above. As discussed above in the methodology section, the final evaluation must be based on a rigorous evaluation methodology that allows for a robust assessment of the programme’s contribution to its intended impact. The methodology should be of sufficient depth to provide insights and understanding on the conditions for success and effectiveness of the IGC’s work.
The final evaluations are expected to take place during 2017. The draft final evaluation report will be subject to independent quality assurance by DFID.
The final report should comprise:
- Introduction - including the policy, institutional and development context and their influence on the impacts and outcomes;
- Description of theory of change;
- Methodology;
- Evaluation findings;
- Conclusions and lessons learned;
- Recommendations for any future programming in this area;
- A specific high level report, presentation, and other accessible communication tools using the final evaluation findings and conclusions. These will be disseminated to senior DFID, IGC, and other stakeholders. The IEB is expected to participate in presentations regarding the findings of the final evaluation.

Following the final report a peer reviewed journal article describing the learning from applying theory based evaluation methods for the impact of research on policy making should be produced.

Budget
The budget for the project should be in the range of £600,000 - £900,000. DFID will be expecting bidders to demonstrate excellent Value for Money when budgeting for this programme and should only include costs that are necessary to deliver the programme outputs.

Proposed Timeline
The timeline for delivery of accepted outputs is shown below.

Date	Output	Description

April/ May 2014	Quality assurance of 2013-14 performance indicators	Short report on quality assurance of on-going performance indicators
June/ July 2014	Inception Report; / Evaluation Framework	This involves a first inception report for the evaluation and submission of the evaluation framework for Phase I and Phase II.
October / 2014	Phase I Evaluation Report	This is the final evaluation report for the retrospective evaluation of the Phase I of the IGC project.
November / 2014	Revised Phase II Evaluation Framework and Review of the IGC’s monitoring framework	This is the submission of the revised evaluation framework for Phase II of the IGC programme. This will include a review of the IGC’s monitoring framework.
April 2015	Quality assurance of 2014-15 performance indicators	Short report on quality assurance of on-going performance indicators
January 2016	Phase II Mid-Term Report/Workshop	This is the first full evaluation of Phase II of the IGC. It evaluates the IGC from the start of the IGC's Phase II project until the Mid-Term period.
April 2016	Quality assurance of 2015-16 performance indicators	Short report on quality assurance of on-going performance indicators
April 2017	Quality assurance of 2016-17 performance indicators	Short report on quality assurance of on-going performance indicators
August / 2017	Phase II Final Report	This is the final evaluation report for the evaluation of Phase II of the IGC project. It will include a full evaluation of the whole of the Phase II project as well as a more specific evaluation of the IGC since the 2016 Mid-Term Report.
November / 2017	Peer Reviewed journal article	Describing the learning from applying theory based evaluation methods for the impact of research on policy making

Governance and management arrangements
The governance and management arrangements for the evaluation will be as follows:
1. Governance Committee: The Governance Committee is the body responsible for giving strategic direction to the IGC on a range of issues. The committee will give high level comments on the evaluation, including the chosen evaluation methodology and all reports/outputs. The IGC Governance Committee comprises IGC and DFID representatives. DFID has final sign-off responsibility of all outputs of the evaluation. DFID will determine the IEB tender committee.
2. Evaluation Management Group (EMG): An EMG will be responsible for the day-to-day oversight of the evaluation. It will facilitate the work of the IEB, present the work to the governance committee, and generally manage the project. It will be staffed by members from both the IGC and DFID. This group will be the IEBs main point of contact for day-to-day issues and logistical support.
3. Evaluation Reference Group (ERG): The ERG will comprise evaluation specialists from DFID and external evaluation experts in the relevant fields. The role of the ERG will be to review the key outputs from the evaluations (e.g. evaluation bids, inception report, mid-term report, final report). It will provide comments on the quality of these outputs to the EMG in writing. The EMG will need to explain when and why recommendations made by the ERG have not been incorporated.
Implementers:
Independent Evaluation Body (IEB): The IEB will be the external body appointed by DFID to undertake the evaluation of the programme. It will report to the EMG and may make use of the work of the IGC’s internal evaluation unit.
IGC: The IGC will implement internal monitoring and evaluation activities that will contribute to data collection as part of the evaluation. . The role of the IGC will be detailed as part of the evaluation framework, and data collection is subject to external verification by the IEB. This work will be supported by the IGC Evaluation/Communications Director, two hub economists, and, possibly evaluation experts from the LSE and Oxford.
More specifically, the roles of the IEB and IGC in undertaking the evaluations will be as follows:
IEB
The IEB will be responsible for conducting the independent evaluation of Phases I and II of the IGC. It takes full precedence for the whole evaluation, including and going beyond any internal work conducted by the IGC.
The IEB will define, through an evaluation framework, the overall programme of work required to address the agreed evaluation questions. It will determine the appropriate methodologies and data requirements.
The IGC will play a large role in collecting required data identified in the evaluation framework. The IEB will be expected to work with the IGC wherever appropriate, and will guide, utilise, quality assure and complement the data collection of internal IGC processes. The IEB will help to shape and draw upon regular monitoring and reporting processes of the IGC, and should do so in a way that will not overburden IGC staff. In addition, it will collect supplementary evidence in order to verify and elaborate on existing information where required. In order to carry out its evaluation activities, the IEB will also be expected to go on field visits as necessary and to interview relevant IGC staff, researchers, and targeted stakeholders. Plans for country visits should be discussed with the IGC.
The IEB will produce and be fully responsible for the reports listed in the Outputs section. Non-confidential data can be shared with the IGC throughout the process as deemed appropriate by DFID and the IEB. Any data or material which is produced by the Service Provider as part of this programme shall be the property of the Service Provider but DFID shall have a world-wide, non-exclusive, irrevocable, royalty-free licence to use all the material.
IGC
The role of the IGC will be to collect and analyse both monitoring and learning data in order to improve its management and for the use of the IEB. As part of its own monitoring framework, the IGC will collect project-level information and analytical ‘stories of change’. The IEB may validate and make use of these stories of change and will advise the IGC on how this type of data should be gathered to meet independent evaluation requirements.
In addition, whenever required for internal monitoring purposes, the IGC will periodically evaluate the quality of the IGC’s operations. Non-confidential parts of those evaluation reports will be shared with the IEB.
Existing Information Sources
The IEB will have an array of information available for its use. The following is a non-exhaustive list of key documents and sources that will be made available to external evaluators:
- Annual Reports produced by the IGC for 2009-10, 2010-11, 2011-12, and 2012-13
- Country and Research Programme outputs, including policy briefs, project summaries and working papers
- Project Proposals – available for each project
- Project Final Reports – available for a subset of projects
- IGC quarterly dashboard – internal monitoring tool
- Website(s) information
- Country Strategy Notes – each of the 15 will be ready by the end of December 2013
- Research Strategy Documents
- IGC Log frame
- IGC Business Case – produced by DFID
This evaluation will build on earlier evaluations and reviews, which will also be made available to the IEB. These include:
- The 2011 Evaluation of the IGC done by Gary Fields;
- The Independent Review of the IGC Programmes on Bangladesh, Bihar, Ethiopia, Ghana, Pakistan and Bangladesh done by John Williamson and Alan Gelb;
- The 2013 Project Completion Review done by DFID on IGC’s Phase I.
Skills and Qualifications
It is essential that the IEB team have the following expertise and/or experience:
- Experience evaluating research-based organisations;
- Thorough understanding of economics and, particularly, growth economics;
- Thorough understanding of the policy-making process, in particular of the challenges encountered in developing countries;
- Acute awareness of the challenges involved in evaluating policy advice activities and, particularly, of the challenges involved in attributing growth outcomes to policy advice and research;
- In-depth knowledge of different approaches to impact evaluation, particularly theory-based evaluation, and of the range of relevant quantitative and qualitative metrics, as well as of their limitations; and
- Experience in designing and managing multi-country research or evaluation studies, which test across contexts and are concerned with external validity.
In addition to displaying strong skills in evaluation and growth economics, the IEB team should have the following expertise and/or experience:
- Proven experience of evaluating policy advice programmes;
- Experience conducting process evaluation;
- Knowledge and experience of theories of change and log frames;
- Knowledge of international evaluation standards, and research ethics;
- A strong communications record; and
- Good knowledge on assessing value for money.
The IEB will need to comply with DFID’s policies on fraud and anti-corruption and cooperate with any checks required from them for the duration of the evaluation (e.g. annual audited statements, policies on management of funds, etc.). There are no nationality requirements although any use of local consultants (from IGC partner countries) would be encouraged.
Reporting and Contracting Arrangements
DFID will be contracting the IEB, who will report to the EMG. Bidders should propose a payment plan using payment by results (outputs). There will be a break clause in the contract after the Phase I evaluation output at which point DFID reserves the right to terminate the contract if they are not satisfied with the IEB outputs.
DFID reserves the right to scale up/back the contract to respond to changing requirements. DFID may choose to extend the contract in the case of unforeseen circumstances, however it is anticipated that the evaluation will conclude no later than the end of 2017.
Logistics and Procedures
The IEB will be responsible for all logistical arrangements for members of the evaluation team. The IGC will facilitate convening of meetings and site visits where necessary. All relevant expenses should be covered by the evaluation contract budget.
Duty of Care
The Supplier is responsible for the safety and well-being of their Personnel (as defined in Section 2 of the Contract) and Third Parties affected by their activities under this contract, including appropriate security arrangements. They will also be responsible for the provision of suitable security arrangements for their domestic and business property. DFID will share available information with the Supplier on security status and developments in-country where appropriate.

All Supplier Personnel will be offered a security briefing by the British Embassy/DFID on arrival. All such Personnel must register with their respective Embassies to ensure that they are included in emergency procedures. A copy of the DFID visitor notes (and a further copy each time these are updated), which the Supplier may use to brief their Personnel on arrival.

The Supplier is responsible for ensuring appropriate safety and security briefings for all of their Personnel working under this contract and ensuring that their Personnel register and receive briefing as outlined above. Travel advice is also available on the FCO website and the Supplier must ensure they (and their Personnel) are up to date with the latest position.

This Procurement will require the Supplier to operate in flood and seismically active zones considered at high risk of earthquakes. Minor tremors are not uncommon. Earthquakes are impossible to predict and can result in major devastation and loss of life. There are several websites focusing on earthquakes, including http://geology.about.com/library/bl/maps/blworldindex.htm. The Supplier should be comfortable working in such an environment and should be capable of deploying to any areas required within the region in order to deliver the Contract (subject to travel clearance being granted).

This Procurement will require the Supplier to operate in conflict-affected areas and parts of it are highly insecure. Travel to many zones within the region will be subject to travel clearance from the UK government in advance. The security situation is volatile and subject to change at short notice. The Supplier should be comfortable working in such an environment and should be capable of deploying to any areas required within the region in order to deliver the Contract (subject to travel clearance being granted).

The Supplier is responsible for ensuring that appropriate arrangements, processes and procedures are in place for their Personnel, taking into account the environment they will be working in and the level of risk involved in delivery of the Contract (such as working in dangerous, fragile and hostile environments etc.). The Supplier must ensure their Personnel receive the required level of training.

Tenderers must develop their Tender on the basis of being fully responsible for Duty of Care in line with the details provided above and the initial risk assessment matrix prepared by DFID (see Annex 4 of this ToR). They must confirm in their ITT Response that:
· They fully accept responsibility for Security and Duty of Care.
· They understand the potential risks and have the knowledge and experience to develop an effective risk plan.
· They have the capability to manage their Duty of Care responsibilities throughout the life of the contract.

If you are unwilling or unable to accept responsibility for Security and Duty of Care as detailed above, your ITT will be viewed as non-compliant and excluded from further evaluation.
Acceptance of responsibility must be supported with evidence of capability and DFID reserves the right to clarify any aspect of this evidence.

Duty of Care Questions
Please state ‘Yes’ or ‘No’ to each of the Duty of Care questions detailed below in the boxes provided. Please refer to any information provided on Duty of Care within the ITT Pack (Terms of Reference, Terms and Conditions, Additional Information Documents) before completing this section. / Your responses must be supported by evidence (no more than 8 x A4 pages) attached as a separate Annex and must include a statement confirming that you (as the Lead Organisation) fully accept responsibility for Security and Duty of Care (including any personnel and subcontractors) throughout the life of the Contract. The supplier must demonstrate their capability to take on this responsibility in terms of knowledge, experience and resources. / DFID reserves the right to clarify any aspect of this evidence or to request additional evidence/information where we deem appropriate. We may also decide to conduct an interview where appropriate. / If you are unwilling to accept responsibility or assessed by DFID as not having the capability to provide Security and Duty of Care for any contract awarded under this procurement, your ITT Response will be excluded from any further Technical Evaluation and Scoring. / Note: this assessment of supplier capability does not form part of the Technical Evaluation and Scoring and should not be viewed as DFID setting any standard for Duty of Care requirements, which is for the supplier to determine.
1	Have you completed an initial assessment of potential risks that demonstrates your knowledge and understanding, and are you satisfied that you understand the risk management implications (not solely relying on information provided by DFID)?
2.	Have you prepared an outline plan that you consider appropriate to manage these risks (or will you do so if you are awarded the contract) and are you confident/comfortable that you can implement this effectively?
3.	Have you ensured or will you ensure that your staff are appropriately trained (including specialist training where required) before they are deployed and will you ensure that on-going training is provided where necessary?
4.	Have you an appropriate mechanism in place to monitor risk on a live / on-going basis (or will you put one in place if you are awarded the contract)?
5.	Have you ensured or will you ensure that your staff are provided with and have access to suitable equipment and will you ensure that this is reviewed and provided on an on-going basis?
6.	Have you appropriate systems in place to manage an emergency / incident if one arises?

Annex 1 –Theory of Change – Working Draft*

* Please note that this Theory of Change is a work in progress and represents a highly simplified version of what is a non-linear complex process of influence. The IGC will be welcoming feedback and suggestions on its Theory of Change.
Annex 2 – Organogram

Annex 3 – Impact Scoring

The IGC give all outputs an impact score. The relationship between research and policy is complex and non-linear – indeed, the work of the IGC is not just about affecting a certain number of policies, but also about providing an analytical resource that can help developing countries achieve stable growth paths. It is nonetheless useful to place the IGCs work within an impact framework and it is for this reason that a scoring system was devised to look at how influential work done by the IGC has impacted policy.
The scoring system was devised by IGC and scoring is done by IGC. The scoring is defined as follows:
- Level 1 policy impact denotes ‘ideas created/mobilised’. This is where the IGC produced work analysing a policy question, but it has not yet fed through to senior government officials or other policy stakeholders. This is often because the work is at an initial stage.
- Level 2 policy impact signifies ‘disseminated to government’. These are outputs that have been formally conveyed to the requesting minister or permanent secretary (or other senior policy stakeholder) but not yet discussed in depth.
- Level 3 signifies ‘high level hearing’. Outputs in this category went to government, usually to ministers or permanent secretaries (or other senior policy stakeholders), and were ‘internalised’ in the sense that they were discussed in detail and follow-up work and discussions have been requested.
- Level 3: hearing with senior/influential policy-makers, with evidence that recommendations were internalized and/or that exchanged ideas have influenced policy discussions
- Level 4 signifies that policy decision were demonstrably and substantially informed, caused or influenced by the IGC.
The scoring methodology is currently being revised, but the broad levels are likely to remain as above.

Annex 4 – Duty of Care

A three year detailed evaluation of the IGC will include in-country visits to 3-6 countries at various stages of development.

The overall risk of travel to all 14 IGC countries is assessed as high, although most are medium risk. The detail is set out below.

Many of the locations are in countries where there is a substantial threat of terrorist or violent attack. There is a medium risk of natural disaster in most countries, while some are located in earthquake zones.

Roads and driving conditions in most countries is poor and travelling after daylight is not recommended. Incidences of car- jacking and violent crime have been reported.

Medical facilities in all countries are below UK standard and particularly poor in some. There are many health hazards include the risk of malaria and dengue disease.

Bangladesh

Theme	DFID Risk score	DFID Risk score
	Dhaka	Other Parts of Bangladesh
OVERALL RATING	MEDIUM	MEDIUM
FCO travel advice	Medium	Medium
Transportation	Medium	Medium
Security	Medium	Medium
Civil unrest	Medium	Medium
Violence/crime	Medium	Medium
Terrorism	Medium	Medium
War	Low	Low
Hurricane	Medium	Medium
Earthquake	Medium	Medium
Flood	Medium	Medium
Medical Services	Medium	Medium
Nature of Project/Intervention	Low	Low

Burma

Theme	DFID Risk score	DFID Risk score
	Rangoon	Other Parts of Burma
OVERALL RATING	MEDIUM	MEDIUM
FCO travel advice	Medium	Medium
Transportation	High	High
Security	Medium	Medium
Civil unrest	Medium	Medium
Violence/crime	Low	Low
Terrorism	Medium	Medium
War	Low	Low
Hurricane	Medium	Medium
Earthquake	Medium	Medium
Flood	Medium	Medium
Medical Services	Low	Medium
Nature of Project/Intervention	Low	Low

Ethiopia

Theme	DFID Risk score	DFID Risk score
	Addis Ababa	Other Parts of Ethiopia
OVERALL RATING	MEDIUM	MEDIUM
FCO travel advice	Medium	High
Transportation	Medium	Medium
Security	Medium	Medium
Civil unrest	Medium	Medium
Violence/crime	Medium	Medium
Terrorism	High	High
War	Low	Low
Hurricane	Low	Low
Earthquake	Low	Low
Flood	Low	Low
Medical Services	Medium	Medium
Nature of Project/Intervention	Low	Low

Ghana

Theme	DFID Risk score	DFID Risk score
	Accra	Other parts of Ghana
OVERALL RATING	LOW	LOW
FCO travel advice	Low	Low
Transportation	Medium	Medium
Security	Low	Low
Civil unrest	Low	Low
Violence/crime	Medium	Medium
Terrorism	Low	Low
War	Low	Low
Hurricane	Low	Low
Earthquake	Low	Low
Flood	Low	Low
Medical Services	Medium	Medium
Nature of Project/Intervention	Low	Low

India

Theme	DFID Risk score	DFID Risk score
	Delhi	Other Parts of India
OVERALL RATING	MEDIUM	MEDIUM
FCO travel advice	Medium	Medium
Transportation	Medium	Medium
Security	Medium	Medium
Civil unrest	Low	Medium
Violence/crime	Medium	Medium
Terrorism	High	High
War	Low	Low
Hurricane	Low	High
Earthquake	Low	Medium
Flood	Medium	Medium
Medical Services	Low	Medium
Nature of Project/Intervention	Low	Low

Liberia

Theme	DFID Risk score	DFID Risk score
	Monrovia	Other Parts of Liberia
OVERALL RATING	MEDIUM	MEDIUM
FCO travel advice	Medium	Medium
Transportation	Medium	High
Security	Medium	Medium
Civil unrest	Low	Medium
Violence/crime	High	High
Terrorism	Low	Low
War	Low	Low
Hurricane	Low	Low
Earthquake	Low	Low
Flood	Low	Low
Medical Services	High	High
Nature of Project/Intervention	Medium	Medium

Mozambique

Theme	DFID Risk score	DFID Risk score
	Maputo	Other Parts of Mozambique
OVERALL RATING	MEDIUM	MEDIUM
FCO travel advice	Medium	Medium
Transportation	Medium	Medium
Security	Low	Low
Civil unrest	Low	Low
Violence/crime	Medium	Medium
Terrorism	Medium	Medium
War	Low	Low
Hurricane	Medium	Medium
Earthquake	Low	Low
Flood	Medium	Medium
Medical Services	High	High
Nature of Project/Intervention	Low	Low

Pakistan

Theme	DFID Risk score	DFID Risk score
	Islamabad	Other Parts of Pakistan
OVERALL RATING	HIGH	HIGH
FCO travel advice	High	High
Transportation	Medium	High
Security	Very High	Very High
Civil unrest	High	High
Violence/crime	Medium	Medium
Terrorism	Very High	Very High
War	Low	Medium
Hurricane	Low	Low
Earthquake	Low	Low
Flood	Medium	Medium
Medical Services	Medium	Medium
Nature of Project/Intervention	Medium	Medium

Rwanda

Theme	DFID Risk score	DFID Risk score
	Kigali	Other Parts of Rwanda
OVERALL RATING	LOW	LOW
FCO travel advice	Low	Low
Transportation	Medium	Medium
Security	Low	Low
Civil unrest	Low	Low
Violence/crime	Medium	Medium
Terrorism	Low	Low
War	Low	Medium
Hurricane	Low	Low
Earthquake	Low	Low
Flood	Low	Low
Medical Services	Medium	Medium
Nature of Project/Intervention	Low	Low

Sierra Leone

Theme	DFID Risk score	DFID Risk score
	Freetown	Other Parts of Sierra Leone
OVERALL RATING	LOW	LOW
FCO travel advice	Low	Low
Transportation	Medium	Medium
Security	Low	Low
Civil unrest	Low	Low
Violence/crime	Medium	Medium
Terrorism	Low	Low
War	Low	Low
Hurricane	Low	Low
Earthquake	Low	Low
Flood	Medium	Medium
Medical Services	High	High
Nature of Project/Intervention	Low	Low

South Sudan

Theme	DFID Risk score	DFID Risk score
	Juba	Other Parts of South Sudan
OVERALL RATING	HIGH	HIGH
FCO travel advice	High	High
Transportation	High	High
Security	High	High
Civil unrest	High	High
Violence/crime	High	High
Terrorism	Medium	Medium
War	Low	Medium
Hurricane	Low	Low
Earthquake	Low	Low
Flood	Low	Low
Medical Services	High	High
Nature of Project/Intervention	Low	Low

Tanzania

Theme	DFID Risk score	DFID Risk score
	Dar Es Salaam	Other Parts of Tanzania
OVERALL RATING	MEDIUM	MEDIUM
FCO travel advice	Low	Low
Transportation	Medium	Medium
Security	Medium	Medium
Civil unrest	Medium	Medium
Violence/crime	Medium	Medium
Terrorism	Medium	Medium
War	Low	Low
Hurricane	Low	Low
Earthquake	Medium	Medium
Flood	Low	Low
Medical Services	Medium	Medium
Nature of Project/Intervention	Low	Low

Uganda

Theme	DFID Risk score	DFID Risk score
	Kampala	Other Parts of Uganda
OVERALL RATING	MEDIUM	MEDIUM
FCO travel advice	Low	Medium
Transportation	Medium	Medium
Security	Medium	Medium
Civil unrest	Medium	Medium
Violence/crime	Medium	Medium
Terrorism	Medium	Medium
War	Low	Low
Hurricane	Low	Low
Earthquake	Low	Low
Flood	Low	Low
Medical Services	Medium	Medium
Nature of Project/Intervention	Low	Low

Zambia

Theme
	Lusaka	Other Parts of Zambia
OVERALL RATING	LOW	LOW
FCO travel advice	Low	Low
Transportation	Medium	Medium
Security	Low	Low
Civil unrest	Medium	Medium
Violence/crime	Medium	Medium
Terrorism	Low	Low
War	Low
Hurricane	Low	Low
Earthquake	Low	Low
Flood	Low	Low
Medical Services	Medium	Medium
Nature of Project/Intervention	Low	Low