Type of Review: Project Completion Review

Project Title: Private Sector Development Project

Date started: April 2007	Date review undertaken: February 2012

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
The project was initially funded at £1,113,000 for the period April 2007 – March 2010. No-cost time extensions followed in parallel with the extension of the related Montserrat Development Corporation (MDC) project to end-March 2012. Management of the PSDP was one of the core activities with which the newly created MDC was tasked. Due to a range of institutional and staffing difficulties, MDC achieved only a very limited execution of the project. However, project activity and expenditure increased substantially following the Charette in October 2011, including re-development of the master plan and prospectus for the development of Little Bay town.

What were the expected results?
The Goal (“Impact”) of the Private Sector Development project (PSDP) was to increase Montserrat’s GDP and GoM’s revenue take from an expanded private sector. The Purpose (”Outcome”) was to implement an agreed long-term PSD strategy to create an effective enabling environment for the private sector. / The PSDP was based on a design to deliver nine components: / business counselling / business training / business consultancy fund / loan guarantee fund / enterprise equity fund / investment promotion / export promotion / business premises / outsourcing / The particular emphasis of the PSD Project was to address the weaknesses of the private sector in planning, realising business growth and mobilising related capital and recurrent finance.

What was the context in which UK support was provided?
Pre 1995 – contribution of the private sector / Prior to 1995, Montserrat had a balanced budget and the private sector (tourism, agriculture, real estate and housing, retail, wholesale, export and construction) activities all contributed to a fairly thriving economy. Residential tourism contributed an estimated 20-35% of GDP. With the destruction of Plymouth, many of the small businesses that constituted the private sector ceased to trade, and their owners, together with their remaining capital resources, emigrated. At the time , government services contributed averaged 19% to GDP. / Post 1995 – decline of the private sector / The destruction of Plymouth in 1995-1997 resulted in a much reduced private sector, an uncertain investment climate, a decrease in the Montserrat population by two thirds, and significant negative impacts on the island’s infrastructure. From 1996-2001 government services contribution to GDP increased to 31% and in 2005 to 37%. Government services and construction – both dependent on aid from the British Government – dominated the economy, contributing a combined average of 50% of GDP. / A 2006 Chamber of Commerce and Industry survey found that the biggest obstacles to doing business in Montserrat were insufficient customers (89%), erratic growth of the Montserrat economy (77%), difficulties with air access (65%) and lack of sea access (66%). The survey further revealed that 61% of respondents were planning no investment, with the volcano continuing to thwart economic growth. The few businesses actually contemplating new investment were planning to access external sources of finance or grants, as internal capital was negligible or non-existent. A subsequent survey in 2007 identified access to finance as the main constraint on growth (75%). Other challenges were identified as the decline in visitor arrivals to the island following the termination of the ferry service in 2005 and inadequate external transportation for the export and import of goods. Government red tape and customs duties were also cited as obstacles. / Current situation / Montserrat continues to face the challenges common to many small island economies such as a small population with low numbers in the economically active age group, government revenue insufficient to meet the cost of providing essential services and limited economic development opportunities. The global recession since 2009 has hit the Caribbean particularly hard including a decline in tourist numbers. This has had a direct impact the growth of the private sector in a small and open economy which is susceptible to exogenous shocks. Additionally Montserrat faces the uncertainties around a still active volcano. / The private sector comprises of some 200 business establishments employing some 600 people. Just over 25% of all its business is involved with the provision of financial, professional, personal and other household services, / Why UK support was provided / HMG recognised that one of the key planks to repopulate and rebuild the island’s economy was to nurture private sector growth and assist the transformation away from a public sector-dominated economy to a private sector-led one. The goal of DFID’s support to Montserrat’s private sector was to increase the sector’s contribution to GDP and GoM revenues, through the creation of an appropriate business enabling environment / A tourism-led strategy was seen as optimal to build new and expand existing businesses with the lead driver being a new physical commercial/residential/government centre of gravity being created at Little Bay. Today the tourism-led strategy remains but, following the Charette in October 2011, a new masterplan for Little Bay is being developed with the port and ferry terminal being relocated to neighbouring Carr’s Bay. Funding from the PSD project has been used to undertake a series of studies that will inform the development of the master plan for a revamped Little Bay and Carr’s Bay development in addition to the preparation of a prospectus that sets out the investment opportunities and incentives.

## Section A: Detailed Output Scoring

Output 1:A financially sustainable MDC is established to coordinate inputs to PSD and providing effective support services to the private sector
Output 1: final score and performance description: C / The MDC has not been able to attain financial self-sustainability for a number of reasons; (i) Project was approved in 2007 however the MDC was only operational in late 2008; (ii) DFID appointed consultancy to manage the MDC under performed and failed to implement an appropriate institutional structure; (iii) Delay in development of a viable master plan, prospectus, and marketing strategy meant that Little Bay land sales were delayed and thus vital income streams were not realised; (iv) GoM delay in the vesting of Little Bay Estate (LBE) lands to the MDC on account of its concerns about the lack on capacity in MDC to manage the Little Bay land transactions.
A limited number of inputs and services were provided in the first 2 years of the project (e.g. training and counselling, two venture capital grants, mining industry reforms). The last year of the project has seen extensive activity all focused on undertaking a series of studies to facilitate the development of a new master plan and prospectus of the revamped town and port development. Overall the position is one of serious underperformance due to factors highlighted above. / Impact Weighting (%): 20 / Revised since last Annual Review? Y/N No / Risk: Low/Medium/High Medium / Revised since last Annual Review? Y/N No

Output 2: Effective business counselling and consultancy services being provided at all levels of business and achieving measurable results in terms of business development
Output 2: final score and performance description: B / There was a long delay before these services were established which was mainly due to the delay in the setting up of the MDC. A Business Counsellor was hired in February 2010 and only then was significant progress made in the execution of this component of the PSD strategy. Nevertheless since the appointment, business advisory services and training modules have been oversubscribed and received positive feedback. Key achievements include; (i) securing membership of Business Mentoring Institute which provided access to a database of business people prepared to act as mentors to local business people; (ii) negotiating a counselling and training relationship with Community Futures Development Corporation of Nadina (Canada) that provided access to video training programmes, obtain copyrighted training documents without fee and get access to a cadre of trainers and advisors “on-line” on a complimentary basis.
Final results: / There has been only limited private sector growth over the project period. This is due mainly to factors beyond the provision of B2B services such as low tourist numbers, global economic downturn, volcanic activity affecting the investment environment and perceived high interest rates at the banks (c. 8%). / Impact Weighting (%): 20 / Revised since last Annual Review? Y/N No / Risk: Low/Medium/High Medium / Revised since last Annual Review? Y/N No

Output 3: Skills and management training programmes being provided at subsidised rates and achieving measurable results in terms of participants future actions
Output 3: final score and performance description: B / As at early 2011 at least 24 workshops covering a range of activities such as business planning, customer services, accounting and financial management had been organised involving 360 participants and earning £6000 in participant contributions. In the absence of follow-up surveys it is not possible to comment on the extent to which the training brought realisable benefits to participants.
Impact Weighting (%): 10 / Revised since last Annual Review? Y/N No / Risk: Low/Medium/High Medium / Revised since last Annual Review? Y/N No

Output 4: MDC establishes export promotion and inward investment units which illustrate measurable effects on increasing the level of exports and amount of inward investment
Output 4: final score and performance description: B / The export promotion and foreign direct investment components figured late in the project planning and development activities and there was only very limited activity.
There was an increase in exports of mined sand but that has no clear connection with MDC actions. There is no cadre of export-ready companies and with no manufacturing base on the island there is only limited export potential anyway. Export potential has to come on the back of an enlarged domestic market. / Inward investment is very much hinged around tourism and the delays in bringing the Little Bay development on stream, the 2010 volcanic eruption and sea and air access limitations made for a negative investment environment. / Impact Weighting (%): 10 / Revised since last Annual Review? Y/N No / Risk: Low/Medium/High High / Revised since last Annual Review? Y/N No

## If the project involved more than 4 Outputs please copy the box above and paste below.
Output 5: Loan Guarantee Fund operational, supported by local banking institutions and meeting the financial needs of the private sector
Output 5: final score and performance description: C / The Fund never became operational and no funding support was made. A number of surveys were undertaken in 2006 and 2007 which indicated that access to finance was a constraint on the private sector development. Consequently, the MDC commissioned a study to design a business financing facility which is yet to be implemented given the limited capacity within the MDC. / The managers of the two locally-based banks report no shortage of available loan capital but a dearth of viable business plans.
The most tangible result has been the design of a BFF facility. A report on how to implement this has been completed but due to a lack of capacity within the MDC, progress has been delayed. GoM are still keen to implement it though. / Impact Weighting (%): 10 / Revised since last Annual Review? Y/N No / Risk: Low/Medium/High Medium / Revised since last Annual Review? Y/N No
Output 6: A sustainable venture capital finance company established and operational with investment contributions to the VCF from outside investors, and a number of successful investments which meet the needs of the private sector
Output 6: final score and performance description: A / The Fund was functioning but investment activity was limited to two key investments to improve access to the island: Fly Montserrat and Twin Island Ferry Services. / 1. EC$ 250,000 equity stake in twin island ferry services as part of an effort to establish a sea link between Montserrat and Antigua - 2010 / 2. EC $ 150,000 equity stake in Fly Montserrat to enable them to start a scheduled service between Montserrat and Antigua – 2009.
Final results: / Access has been improved for both people and goods although currently the Twin Island ferry is not in operation. The investment in Fly Montserrat has provided the island with (i) reliable scheduled services (ii) emergency medical evacuation capability and (iii) opened up charter activities to the neighbouring islands. / Impact Weighting (%): 10 / Revised since last Annual Review? Y/N No / Risk: Low/Medium/High Medium / Revised since last Annual Review? Y/N No
Output 7: GoM outsourcing policy and plan approved and being successfully implemented in accordance with key indicators which meet overall Project targets regarding proportion of private/public sector contributions to GDP / Final score and performance description: B / Outsourcing policy, manual and list of target services (e.g. cleaning of government premises) prepared but delays to implementation by GoM. / Final results: The outsourcing process did not achieve momentum. Responsibility for implementation has now being moved to the Ministry of Finance with a view to restart it in 2012 as a part of public service reform programme / Impact Weighting (%): 10 / Revised since last Annual Review? Y/N No / Risk: Low/Medium/High High / Revised since last Annual Review? Y/N No

Output 8: At least 7,050 square feet of industrial/business premises constructed in accordance with agreed priority plan, with each premise rented within six months of completion of construction
Final score and performance description: B / Policy and plans prepared, no actual construction has occurred. A few small incubator units alongside MDC Administration offices at Brades Factory and Public Market have been made available.
Impact Weighting (%): 10 / Revised since last Annual Review? Y/N No / Risk: Low/Medium/High High / Revised since last Annual Review? Y/N No

## Section B: Results and Value for Money.

1. Achievement and Results

1.1 Has the logframe been changed since the last review? Y/N No / 1.2 Final Output score and description: / B Outputs moderately did not meet expectation.
Direct feedback from beneficiaries / There have been some positive developments towards the implementation of a long-term PSD strategy and the creation of an enabling environment; however, this has been limited, due to the past delays in implementation the project and the delay in recruiting a dedicated PSD officer. / Neither of the bank managers (BoM; RBC) were aware of either the Loan or Equity schemes nor the interim General Manager of the St Patrick’s Cooperative Credit Union under the umbrella of which the National Development Foundation (set up in the 1980s to provide loans to small businesses) now sits. The BoM Manager was aware there had been some training delivered locally in how to prepare a business plan but had not seen much evidence of the learning flowing through: in 3 years in the job he had received only 6 business plans for financing with funding given to 3 of these. The view of the banks is that credit availability is not a problem, the flow of bankable business propositions is.
1.4 Overall Outcome score and description: B – Outputs moderately did not meet expectation. / 1.5 Impact and Sustainability / The project goal was to achieve increased GDP and GoM revenues from expanded private sector activity with GDP per capita at constant prices increasing by min 5% per annum. These were not achieved. / Montserrat GDP and GDP per capita are EC$129.15million (US$47.8 million) and EC$25,800 (US$9,520) respectively in 2010. GDP in current prices has gradually increased since 2003 (CDB AER 2003-2007), while GDP per capita in constant prices has decreased in real terms (PEFA 2009). / The government services sector continues to be the largest contributing sector to the overall economy. The sectors contribution to GDP in 2009 was 43.2% has increased to 45.2% in 2010 with the private sector contracting due to the volcanic eruption in early February 2010. / GoM 2009 tax revenue was EC$41.5 million with 2010 recording a decline to EC$ 35.58 million again due to the disruption caused by the February 2010 eruption and the knock on effects of the global financial crisis.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Y/N No / There was a significant underspend in the first three years of the project however this has been reversed in the final year of the 2 year extension of the project ending 31st March 2012. / 2.2 Key cost drivers / The largest cost components were the Business Finance Facility and the Investment Fund / which were not effectively mobilised (Outputs 5 and 6 refer). / 2.3 Was the project completed within the expected timescale: Y/N No / No, it was extended beyond the initial timeframe by 2 years.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / 1. There is no clear evidential link between changes to the size of the private sector and changes to GDP. / 2. Assumption made in project design about political will to drive outsourcing did not hold. Need more work / convincing evidence to persuade decision makers on benefits of it where conditions are right. / 3. The October 2011 Charette produced evidence that Port would be better located at Carr’s Bay thereby giving Little Bay site more scope as viable high end tourist destination. / 4. Without the appropriate institutional capacity within the MDC, the implementation of the PSD project was virtually impossible. / 5. Assumption in original project design over-estimated maturity & capacity of existing private sector, for example, capacity to prepare and deliver effective business plans, export readiness. / 3.2 Set out what plans are in place for an evaluation. / No current plans for an evaluation

4. Risk
4.1 Risk Rating (overall project risk): Low/Medium/High High / Did the Risk Rating change over the life of the project? Y/N No / 4.2 Risk funds not used for purposes intended / Financial expenditure and forecast reports were required prior to release of each tranche of funding. In addition annual audited accounts for MDC were produced / 4.3 Climate and Environment Impact / Kato / Christine – can you add anything here?

5. Value for Money
5.1 Performance on VfM measures / This project was designed and well underway before DFID’s current VfM procedures were introduced. Financial self-sufficiency of the MDC (through land sales revenue) did not materialise. However, limited VfM was achieved through competitive processes before award of contracts and by re-allocation of funds away from poor performing components to activities that delivered tangible results (see 5.4 below). / 5.2 Commercial Improvement and Value for Money / The project was started before the latest DFID VfM procedures were introduced. Some VfM was achieved through competition and negotiation with suppliers. In any future similar interventions, use of performance related pay and / or contractual penalties to address poor performance should be considered. / 5.3 Role of project partners / MDC (the institution responsible for implementing the PSD project) failed to recruit and retain appropriate international expertise and local counterparts. This, along with sub-optimal governance / institutional arrangements had an adverse impact on PSD implementation and VfM. / 5.4 Did the project represent Value for Money : Y/N No / However, the lessons from the weak start up to the project were taken on board and changes introduced accordingly, e.g. reallocating funds to high priority private sector-focussed actions, such as the Charette, revised masterplan, Little Bay prospectus to help improve the PSD and investment environment.

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions
The implementation of the PSD project hinged entirely on its implementing agency, the MDC, achieving effective delivery. As the MDC foundered so did project implementation – there was no “Plan B”. Delays to the Little Bay development, which was seen as the main dynamo of PSD growth, were also a significant hindrance. / Lessons have been learned, in particular going forward: / the proposals for a restructured and managerially strengthened MDC; / a new masterplan and sales dynamic for the LBE; / surer GoM commitment to PSD (e.g. relaunch of outsourcing initiative).
-

8. Review Process
Desk study and 1 day of 4 day on-island visit (for 3 PCRs) by interim OTD PSD Adviser with DFID Programme Representative – Montserrat. / Local consultations with representatives/members of: / Montserrat Development Corporation; Ministry of Finance and Economic Management; Montserrat Chamber of Commerce and Industry; Montserrat Small Business Association; Farmers Association; Bank of Montserrat; Royal Bank of Canada; St Patrick’s Cooperative Credit Union.