Annual Review – LIFT
December 2020

Title: Land Investment for Transformation (LIFT), Ethiopia
Programme Value £ (full life): £72.7 million		Review Date: November 2020
Programme Code: 202900	Start Date: February 2014	End Date: July 2021

Summary of Programme Performance
Year	2014/15	2015/16	2016/17	2017 (MTR)	2017/18	2018/19	2019/20
Programme Score	A	B	A	A+	A+	A++	A+
Risk Rating	High	High	High	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.FCDO.gov.uk/projects/GB-1-202900/documents
DevTracker Link to Logframe:	https://devtracker.FCDO.gov.uk/projects/GB-1-202900/documents

A. SUMMARY AND OVERVIEW

Acronyms
AR	Annual Review
CALM	Climate Action through Landscape Management
ECA	Environment & Conservation Agriculture
EEU	Economic Empowerment Unit
FCDO	Foreign, Commonwealth & Development Office
FHH	Female-Headed Household
GESI	Gender Equality and Social Inclusion
GoE	Government of Ethiopia
ITSP	Implementing Technical Service Provider
iWoRLAIS	Interim Woreda Rural Land Administration Information System
LAC	Land Administration Committee
LIFT	Land Investment for Transformation
LRSP	Land Rental Service Provider
MFI	Microfinance Institution
MoA	Ministry of Agriculture (Ethiopia)
NRLAIS	National Rural Land Administration Information System
PAC	Public Awareness and Communication
PD	Public Display
RLAS	Rural Land Administration System
RLAUD	Rural Land Administration & Use Directorate of Ethiopia’s Ministry of Agriculture
SIGN	SLLC Implementation Guidance Note
SNNPR	Southern Nations, Nationalities and Peoples’ Region
ToC	Theory of Change
SLLC	Second-Level Land Administration
VfM	Value for Money
WLAO	Woreda Land Administration Office

Description of programme
The Foreign, Commonwealth & Development Office (FCDO), through the Land Investment for Transformation (LIFT) programme, has supported the Government of Ethiopia’s (GoE) efforts to increase rural land tenure security. LIFT’s objective is to improve the incomes of the rural poor and support inclusive economic growth through land certification, improved land administration systems, and the development of the rural land sector to enhance productivity and investment. Complementary market systems interventions, through LIFT’s Economic Empowerment Unit (EEU), are designed to ensure that the benefits of land certification and administration are maximised. An additional component of the programme supports GoE in addressing cross-cutting policy issues by reviewing existing proclamations and regulations to improve land tenure security and the transparency of land allocation, in line with international good practice and human rights obligations.
Specifically, LIFT aims to:
- Enable provision of map-based, Second-Level Land Certificates (SLLCs) to farmers in four highland regional states (Amhara, Oromia, Southern Nations, Nationalities and Peoples’ Region and Tigray) through support for the production of aerial imagery; development of a digital cadastre; engaging farmers to identify their land parcels on the resulting photographic map and resolve any disputes; and issuance of land use rights certificates;
- Strengthen capacity in the Rural Land Administration System (RLAS) to register, update and enforce rights through developing land administration systems backed by IT; training land administrators; refining and documenting administrative processes;
- Facilitate increased investment and productivity through support to the development of the land market, based on detailed analysis and research; and
- Strengthen the existing land policies and procedures, with the aim of enhancing security of tenure for communal landholdings, pastoralists and customary land use and improving the transparency of land allocation.

LIFT will come to an end on the 31st July 2021 and will be followed by the LIFT UP programme, which will aim to bring transformative, systemic and sustainable change to Ethiopia’s land certification and market systems in the four highland regional states.

Summary supporting narrative for the overall score in this review
LIFT has scored an A+ for this annual review as all outputs moderately exceeded expectation. It continues to be a high-performing programme at the output level, having already surpassed a number of end-of-programme targets. Up to November 2020, LIFT has navigated a series of challenges (including COVID-19, an unpredictable security situation, political instability and reforms) to continue to deliver results towards effective land certification and administration, improving farmers’ access to finance, facilitating the expansion of the land rental market, improving access to environmentally sustainable inputs, and strengthening land policies.

Major lessons and recommendations for the year ahead

Lessons learned

1. Timely research on how COVID-19 impacts on LIFT’s outputs and outcomes has allowed the programme to adapt to the new context well: LIFT conducted a comprehensive data collection exercise to understand the impact of COVID-19 on programme activities in May and June 2020 and summarised lessons learned in a separate note. For instance, LIFT has since adapted the Second-Level Land Certification (SLLC) implementation process to COVID-19 health and safety guidelines; liaised with GoE to raise awareness and distribute communications material on COVID-19 through the programme’s network; and worked with partner microfinance institutions (MFIs) to adapt products to a COVID-19 environment by introducing mitigating measures for SLLC-linked loan holders and exploring digitisation strategies for MFIs.
2. Addressing informal transactions: Both the Satellite Woreda approach and the Light-Touch Communication campaign have shown an increase in the number of registered transactions.
3. LIFT’s key theory of change (ToC) assumptions hold: LIFT has carried-out several surveys throughout 2019 and 2020 to probe its key theory of change assumptions relating to SLLC, RLAS and EEU. Strong evidence was found that assumptions relating to tenure security, increased investment and economic benefits hold, implying high VfM for the entire programme.

Recommendations

SLLC & RLAS
- Recommence Public Display (PD) events in outstanding woredas. Timing – as soon as it is permissible; Woreda PD teams.
  [note] Woredas, or districts, are the third-level administrative divisions of Ethiopia. They are further divided into kebeles (wards or neighbourhood associations).
- Ensure that the regions maintain their commitment to distributing LIFT’s SLLC certificates and specifically ensure that Southern Nations, Nationalities and Peoples’ Region (SNNPR) recommences COVID-19 compliant certificate distribution events. Timing – once the regional restrictions are lifted; Regional Governments/ Land Bureaus.
- Scale up the Model Woreda and Satellite Woreda approaches and formalise the Public Awareness & Communication (PAC) strategy. Timing – as soon as possible; Woreda Land Administration Offices (WLAOs)/ Implementing Technical Service Provider (ITSP)/ Ministry of Agriculture’s Rural Land Administration and Use Directorate (RLAUD).
- Implement the phasing out strategy for RLAS operations. Timing – by 30th June 2021; in close cooperation with the World Bank/ GoE’s Climate Action through Landscape Management (CALM) programme, RLAUD and regional offices.
  [note] To learn more about the CALM programme, whose objective is to increase adoption of sustainable land management practices and to expand access to secure land tenure in Ethiopia’s non-rangeland rural areas, please see https://projects.worldbank.org/en/projects-operations/project-detail/P170384.
- Ensure the smooth transfer of woredas with operational land administration systems (RLAS/iWoRLAIS/NRLAIS) to CALM and that synergies with CALM are maintained. Timing – by 30th June 2021; RLAUD/ WLAOs/ ITSP.
  [note] Rural Land Administration System, Interim Woreda Rural Land Administration Information System and National Rural Land Administration Information System, respectively.
Encourage political commitment by: increasing the awareness of decision-makers on the importance of RLAS; incentivising RLAS (e.g. promoting the use of RLAS data to enhance tax collection); supporting CALM strategies to guarantee the sustainability of RLAS. Timing – up to the end of the programme and during transition to the subsequent programme, LIFT UP; FCDO/ ITSP to engage regularly with Regional Governments/ Woreda Offices and GoE/ Ministry of Finance.
EEU
- Ensure implementation of the exit strategy for all interventions, making sure that there is clear ownership of activities by the relevant partners in the sectors in which the EEU is active. Timing – by July 2021; MFIs/ Land Rental Service Providers (LRSPs)/ Environment & Conservation Agriculture (ECA) partners.
- Advocate for ratification of relevant policies and legal framework to support existing interventions and ensure their sustainability. Timing – by July 2021; ITSP/ MFI partners.
- Onboard the relevant actors that will take over the facilitation and coordination functions of the market systems interventions which LIFT has undertaken so far. Timing – by July 2021; ITSP.
Policy
- Promote LIFT’s Knowledge Hub to wider audiences to ensure that the research and knowledge that LIFT has produced is disseminated to as many stakeholders as possible. Timing – January/February 2021; ITSP.
- Ensure SLLC/RLAS sustainability at the policy level and GoE financing of operations post project. Timing – up to July 2021; ITSP.

LIFT UP
- Ensure LIFT’s sustainability and use its data, lessons learned and recommendations to inform LIFT UP’s inception phase, particularly vis-à-vis the transfer to CALM. Timing – ongoing; FCDO.
- Ensure that ambitious outcome and output targets are set early on. Timing – LIFT UP’s inception phase; FCDO.
Ensure a long lead time for the potential procurement of aerial photography (minimum 12 months). Timing – LIFT UP’s inception phase; FCDO/ ITSP.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case
No changes were made to the programme’s ToC. The core logic underpinning the ToC of most land programmes is well-established: namely, that if landholders feel secure in their tenure of their land and are not concerned that someone may take their land away from them, then they are more likely to invest in and improve their land and, coupled with complementary market interventions, incomes will rise as a result. To ensure that security of tenure is sustainable, rather than being a one-off resulting from the registration and certification of land, a land administration system is introduced to record any changes to tenure and to ultimately ensure that the land certification is kept up to date. In the case of LIFT, this is RLAS.
What makes LIFT unique and innovative is firstly the scale and speed at which the programme is working, and secondly the fact that it has a Market Systems Development (MSD) component, in the shape of its EEU. The purpose of the EEU is to address a critical missing link between interventions to increase tenure security (SLLC and RLAS) and increased investment in land, leading to higher incomes. Its aim is to address any market constraints that might prevent landholders from investing in their land, whether due to a lack of capital (addressed through the EEU’s Access to Finance interventions), land rental disputes and concerns over the benefits of formally registering land rental transactions (the Land Rental interventions), or a lack of access to agricultural inputs and how to use them appropriately (the Environment & Conservation Agriculture interventions). This strategy, of using a market systems-based approach to magnify and accelerate the impacts of land certification, has not been tried anywhere else in the world. This basic logic and how SLLC, RLAS and the EEU interrelate is spelled out in LIFT’s revised ToC. The way in which RLAS underpins and ensures the sustainability of both SLLC and the EEU by guaranteeing ongoing security of tenure is made more explicit in the revised ToC diagram. The way in which the three main clusters of EEU interventions can interact with one another (e.g. a farmer might use an SLLC-linked loan or rent from a parcel of land to purchase improved agricultural inputs) is also highlighted.
Evidence to test these programme’s key ToC assumptions outlined above has been provided through several recent large-scale household surveys. The EEU impact surveys (2019 and 2020) confirmed the assumptions relating to the economic benefits of land rental formalisation and the SLLC-linked loan, including how these incentivise increased investment and lead to increased incomes for farmers. It was also found that the EEU’s rental formalisation intervention in particular led to an expansion of the rental market, including through drawing in new landlords and tenants but also expanding rented land area, contract duration, investment on the rented land, and diversification of inputs and crops. The SLLC outcome survey (2019) focussed on how LIFT implemented the SLLC process and how SLLC is contributing to perceptions of tenure security, reduced disputes, and empowered women, especially married women. It was also found that SLLC has played a role in making investment decisions in beneficiary households, confirming one of the programme’s key ToC assumptions. Lastly, the programme has conducted additional analysis of the 2019 RLAS transaction survey and found evidence to support the claim that EEU innovations incentivise the formal registration of land transactions. Findings were summarised in a paper that was submitted for the 2020 World Bank Land Conference (see below).
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
LIFT has undertaken quantitative and qualitative research over the year, providing evidence that the programme is on track to achieve its intended outcomes. Whilst evidence on informal registrations and overall sustainability of the programme will not be provided until the RLAS Transaction Survey is completed in 2021, LIFT collaborated closely with the External Evaluation Technical Service Provider (EETSP) and FCDO in agreeing the approach and methodology for each survey listed below:
- 2019 SLLC Outcome Survey was conducted in November 2019 to provide evidence on LIFT’s ToC assumption of SLLC resulting in increased tenure security, decreased disputes, and increased investment. Evidence from this survey also confirms certificate collection rates (Outcome 3) and some evidence on productivity increases could also be derived, which is discussed further under impact below.
- 2020 EEU Impact Survey (Outcome 2B) was conducted in February/March 2020 to provide evidence on whether the EEU’s Access to Finance and Land Rental interventions have led to increased investment, productivity, and incomes (two to three years after these were first accessed). This survey followed-up on the same respondents as the 2019 survey, allowing for robust analysis of investment, productivity, and income effects using a matching panel data set.
- In addition to the two surveys above, LIFT also conducted two desk-based research pieces that contributed to providing evidence relating to LIFT’s ToC: a paper for the World Bank Land Conference on “The catalytic impact of market systems innovations in land certification programmes”, focussing on how LIFT’s EEU component contributes to a more sustainable rural land administration system by setting incentives for households to formally register land transactions; and a study on subsequent transactions to identify whether the rights of women are maintained over time (Outcome 1B).
  [note] Paper available online (https://www.conftool.com/landandpoverty2020/index.php?page=browseSessions&form_session=582#paperID705).

The above surveys and studies provided further evidence to show how LIFT’s outputs have led to the anticipated outcomes and, in the case of EEU, contributed to anticipated impact-level results. Some of the results under the outcome headings below confirm key ToC linkages.
There are two more surveys planned to provide evidence on LIFT’s ToC and will feed into the programme’s project completion review in June 2021. Another RLAS Transaction Survey is planned to take place during Q1/Q2 2021 to provide quantitative evidence on the percentage of subsequent land transactions that are formally registered, considering social and economic factors, and proximity to WLAOs. This survey will follow-up on the June 2019 RLAS transaction survey and will be used to report on Outcome Indicator 1A.

Outcomes. LIFT exceeded all outcome targets, as shown in the table below. With reference to Outcome Indicator 1A, data are not available as the 2020 RLAS transaction survey was postponed due to COVID-19. However, there is sufficient qualitative evidence that LIFT’s interventions are contributing to an increase in formal registration rates.
No.	Outcome Description	Target for 2020 AR (Oct 2020)	Result
3	Number of certificates distributed by woreda land offices to landholders in programme woredas	10,900,000	12,372,771
1.A	1.A. Percentage of land transactions which are formally registered in RLAS in programme woredas in which RLAS is operational, disaggregated as follows: / - Total / - Rental / - Loan / - All other transactions	Total: 32.5% / Rental: 20% / Loan: 100% / Other: 30%	TBC
1.B	Percentage of SLLC that are held: / - in joint ownership by a male and a female; / - in sole name of a female; or / - in sole name of a male; / after subsequent transactions.	M&F: 50% / F: 15% / M: 5%	M&F: 72.95% / F: 19.50% / M: 7.55%
2.A	Number of farmers with SLLC that have directly accessed an innovation introduced by LIFT’s EEU component	10,1271	130,224
2.B	Percentage of farmers with SLLC that have directly accessed EEU interventions and as a result have invested/increased investment in improved inputs and other/new income-generating activities, disaggregated by gender	70% / (20% of which will be women)	76.1% / (21% of which are women)
4	Number of land policy reports, regulations, procedures, strategies and plans produced or informed by LIFT which have been adopted or otherwise implemented by the Government of Ethiopia (whether at federal, regional, woreda or kebele level) or development partners to strengthen land certification and administration structures and processes	37	39
[note] All other transactions include inheritance, gifting, exchange, divorce/marriage, consolidation, correction of a boundary and replacement/correction of a certificate.

Impact. The 2020 EEU Impact Survey followed-up on the same beneficiaries that were previously sampled in 2019 and provided evidence on how the SLLC-linked loan and land rental formalisation have led to farmers increasing productivity and incomes over time. This supports LIFT’s assumption that the EEU’s market systems-based approach magnifies and accelerates the impact of land certification. Furthermore, the SLLC Outcome Survey provided preliminary evidence that SLLC incentivises new investments, which in turn contribute to increased land productivity.
To further investigate the impact on incomes and inform the project completion review in June 2021, the FCDO requested LIFT to conduct an Income Study in lieu of the EETSP’s endline survey, whose contract was cancelled in June 2020. Despite this being an unplanned activity, LIFT managed to identify efficiencies and savings to cover a smaller, qualitative study. LIFT agreed the Terms of Reference with the FCDO in September 2020. A detailed methodology will be agreed with the FCDO in December and the timing and scope of the study are under discussion, considering COVID-19 and conflict risks.
Explain major changes to the log frame in the past year
In response to the annual review (AR) in October 2019 and the costed 12-month programme extension, the LIFT team undertook a series of revisions to the programme’s logframe. Changes were made to the previous version (V16.2) of LIFT’s logframe, and a new logframe (version 17) was developed as part of LIFT’s 12-month extension which was approved by the FCDO in July 2020.
The changes in version 17 mainly relate to targets being affected by COVID-19 as opposed to indicator wording or definitions (apart from one change to Output Indicator 3.2). This follows the recommendations from the 2019 AR and is in line with the programme’s expectation that indicator definitions should not be amended in the final year of the programme for consistency of measurement.
Except for Output Indicator 1.1C, targets for the postponed 2020 AR were not reduced and were kept at the levels prior to COVID-19. Limited additional increases are suggested for the new end of programme targets by May 2021, as can be expected within the seven months between 31st October 2020 and 31st May 2021.
Output Indicator 3.2 – number of Land Rental Service Providers (LRSPs): under version 17, LIFT did not change its target for the number of active LRSPs (525) but moved the cut-off point for measuring this to the 31st March 2020, before the COVID-19 crisis. This is because measuring the number of active LRSPs has become challenging due to COVID-19 restrictions that were in place during the peak season for rental contracts (April to July leads up to the main agricultural season where historically most rental contract facilitations are expected). As a result, LRSPs’ facilitation activities have been restricted since they involve house-to-house awareness raising and frequent travels and contacts with farmers and local officials. LIFT however introduced a new “market actor” to measure the sustainability of the LRSP intervention defined as “Licensed LRSPs”. This helps measure the programme’s activities relating to expanding licensing of LRSPs, which will make the LRSP model more sustainable in the long run.

Describe any planned changes to the log frame as a result of this review
N/A

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

LIFT is coming to an end in July 2021 with no planned gap between it and the subsequent programme LIFT UP. LIFT’s Exit Plan and RLAS Phasing Out Strategy, including the handover of LIFT-supported RLAS woredas and responsibilities to CALM, have been developed.
## C: DETAILED OUTPUT SCORING

Output Title	Second-Level Land Certificates (SLLCs) issued recognising rights of joint, polygamous and female-headed household (FHH) landholders
Output number per LF		1	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	No

Indicators	Milestones for this review	Progress (as of 31 October 2020)
1.1A. Cumulative number of parcels supported by LIFT for demarcation	15,500,000	15,752,269
1.1B. Cumulative number of parcels supported by LIFT for certificates approved	14,000,000	14,002,541
1.1C. Cumulative number of parcels supported by LIFT for certificates made available for collection at woreda land offices	13,800,000	13,815,890
1.2A. Percentage of SLLCs that are held in joint ownership by a male and female at the point of distribution	50%	73.60%
1.2B. Percentage of SLLCs that are held in the sole name of a woman at the point of distribution	15%	18.99%
1.2.C. Percentage of SLLCs that are held in the sole name of a man at the point of distribution	5%	7.55%
1.3. Cost per certificate issued with LIFT support (£)	£3.75	£3.46

Briefly describe the output’s activities and provide supporting narrative for the score
The output’s activities focus on scaling up land certification in the four highland regional states of Ethiopia. As per the 2019 AR recommendations, LIFT increased its SLLC targets and was on track to overachieve its logframe target of 140 woredas with RLAS. At the start of the year, it had been planned that demarcation would be completed by the end of March 2020 with back-office work, public display (PD), printing and approval being completed by May to allow sufficient time for RLAS to be installed prior to the programme ending. In January 2020, LIFT proposed some amendments to the logframe which saw its demarcation target (Indicator 1.1A) increased by 1.2 million parcels with indicators 1.1B and 1.1C remaining the same. As part of the one-year extension, LIFT’s SLLC targets were further revised (see details in the following section).
To achieve these targets, LIFT adapted its SLLC approach as follows:
- Increasing the size of field teams to increase daily demarcation rates;
- Field teams operating simultaneously in a SLLC active woreda (where field demarcation is active) and semi-active woreda (where demarcation is completed but back-office activities are ongoing) to improve the efficiency of transitioning between woredas;
- Reallocating back-office staff to woredas where data entry rates were lagging;
- Recruiting additional PD teams in woredas where many kebeles had PD pending to complete the process in a shorter period.
Despite the challenges posed by COVID-19 and civil unrest, LIFT accomplished its targets for SLLC as follows:
- 1.1A. Demarcation: LIFT exceeded its revised demarcation target by 252,269;
- 1.1B. Approval: LIFT exceeded its certificate approval target by 2,541;
- 1.1C. Printing: LIFT exceeded its revised printing target by 15,890.
LIFT exceeded its distribution targets of 10.36 million by 1,472,771 (Outcome level). Main achievements included:
- Completion of all back-office work.
- Certificate distribution: While it has not been possible to recommence back office work and PD, through its working arrangements with the regional land bureaus, certificate distribution events were adapted and able to continue. This included holding distribution events at the kebele level, which involves a smaller number of gatherings and providing washing facilities at the events. 1,079,333 certificates have been distributed since COVID-19 was first reported in Ethiopia.
- Certificate backlog: LIFT has continued to make good progress on reducing its distribution backlog (measured by the percentage of certificates that have been distributed to farmers set against the total certificates that have been printed, i.e. are available for distribution). The backlog was 18.3% in September 2019 and this has now reduced to 10.4%.
- Partnership with GoE and Regions: LIFT has continued to maintain good working relationships with RLAUD, as well as the Regional and Woreda Bureaus, and this has resulted in the GoE taking on greater responsibilities and supporting LIFT where required (e.g. certificate distribution in Amhara, Oromia and SNNPR).
LIFT’s Gender Equality and Social Inclusion (GESI) activities included:
- Restored Parcels: The restitution of parcels to women and other vulnerable groups (VGs) is due to non-legitimate claimants forcefully taking over parcels of the rightful holder. Over the year LIFT’s Social Development Officers (SDOs) continued to support field teams until March when field demarcation activities ended. A cumulative total of 3,409 parcels have been restored to 1,873 VG landholders (of which 2,270 parcels have been restored to 1,205 female landholders). In addition, two major areas of focus of the GESI team have included: 1) piloting an approach in three non-SDO LIFT woredas to identify latent disputes that may have been missed during the demarcation process and, 2) ensuring the sustainability of the SDO function within the Woreda Land Administration to ensure women and VGs’ land rights are maintained post-SLLC.
- Non-SDO woreda pilot: The aim of the pilot was to identify latent disputes not identified during SLLC due to SDOs not being in post. Three woredas were selected to pilot the approach in Oromia: Hitosa, Sire and Kersa Malima. Hitosa was the first woreda to undergo the pilot and a launch workshop was held on the 7th November 2019 with the Regional Land Bureau. Fieldwork commenced in December 2019 and was completed in February 2020, during which 11 disputed parcels were restored to 19 vulnerable landholders (nine of the parcels were restored to 17 women).

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Specific VfM indicators that relate to the SLLC component (as per the 2017 revision of LIFT’s VfM framework) includes the following:
Indicator		Target	2016	2017	2018	2019	2020
Efficiency	Cost per certificate	£3.71	£14.32	£5.46	£4.00	£3.39	£3.46
Effectiveness	Cost per household with tenure that is legally recognised and documented	N/A	N/A	£32.54	£21.65	£18.36	£16.53

Cost per certificate: Over the course of LIFT the cost per certificate approved has shown a downward trend and the programme has surpassed its logframe target. This year the programme has achieved a result of £3.45. While this is slightly higher than last year’s result, the cost is below the end of programme logframe target as well as this year’s target of £3.75 per parcel. The slight increase in unit cost compared to last year is due to state of emergency imposed in April 2020 to mitigate COVID-19. As public gatherings were banned, all PD events (which are a precursor to approval and printing) were suspended, thus leaving a large number of demarcated parcels awaiting to complete or start PD. The cost per certificate will reduce when PD events can recommence.
Cost per household with tenure that is legally recognised and documented: LIFT has continued to show a downward trend in cost per household with tenure that is legally recognised (this is based on an average of four parcels per household based on the baseline survey).
Describe any changes to this output during the past year, and any planned changes as a result of this review
Impact of COVID-19: At the start of March 2020, LIFT was on track to exceed its targets when the first confirmed case of COVID-19 was reported in Ethiopia on the 13th March 2020. In response to this, GoE introduced similar measures to European counterparts to contain COVID-19 under a five-month state of emergency that was declared on the 10th April 2020. This included banning public gatherings and closing Government offices whereby staff worked remotely (including woreda, regional and Addis Ababa government offices). Subsequently, Tigray and Amhara Regions implemented a state of emergency and closed their regional borders, banned non-essential travel, travel between the district capitals and rural areas, as well as gatherings of more than 10 people.
LIFT in turn permanently ceased demarcation activities (earlier than planned for in some woredas) and temporarily closed back-office activities and PD to ensure that the programme did not act as a vector for COVID-19. The temporary closure of data entry/digitisation and PD resulted in 1,066,958 parcels being stuck after demarcation as of the 26th March (498,319 awaiting digitisation and 568,639 ready for PD).
One-year extension: Due to COVID-19 and its impact on LIFT’s activities, the programme was given a one-year extension to the 31st July 2021 and LIFT’s SLLC targets were further revised based on the impact of COVID-19 (see table below).
Indicator	Aug 2020 Target	Revised Aug 2020 Target	Revised Oct 2020 Target (one-year extension)	AR Results
1.1A. Cumulative number of parcels supported by LIFT for demarcation	14,000,000	15,200,000	15,500,000	15,752,269
1.1B. Cumulative number of parcels supported by LIFT for certificates approved	14,000,000	14,000,000	14,000,000	14,002,541
1.1C. Cumulative number of parcels supported by LIFT for certificates made available for collection at woreda land offices	14,000,000	14,000,000	13,800,000	13,815,890
1.3. Cost per certificate issued with LIFT support (£)	3.54	3.69	3.75	3.46
[note] End of programme target was increased to 14,150,000 approved certificates
[note] End of programme target remains at 14,000,000

Furthermore, the extension included field staff resourcing to recommence PD events for LIFT to achieve its end of programme printing target. Originally, LIFT and RLAUD anticipated that COVID-19 infections would peak in June/July and that PD could recommence in August/September. However, unlike other countries, the upward infection rate trend has been prolonged over a longer period and as a result, PD events have been unable to recommence as planned. LIFT has therefore adapted its PD approach to mitigate COVID-19 as follows:
- Large halls at Kebele Administration Offices or Farmer Training Centres or open spaces are used as venues to ensure social distancing can be maintained;
- Only two landholders at a time are allowed to review and confirm their parcel information;
- Venues for PD require a water supply that is sufficient for hand washing;
- The duration of PD is increased to 45, 21 and 10 days in Amhara, Oromia and SNNPR respectively to accommodate a reduced daily number of landholders attending PD.
Although PD could not recommence, back-office processes in some woredas and regions were able to continue. LIFT ensured that back-office staff maintained social distancing and adhered to hygiene procedures. By the end of June 2020, a further 376,694 additional parcels had been committed to the registration system database (iMASSREG).
On LIFT’s aerial photography activities, the programme selected woredas where aerial photography had already been provided by GoE, which meant that LIFT could still achieve the targets for parcels demarcated.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
All four recommendations from the 2019 AR have been followed up on:
2019 AR Recommendations	Status
Asset disposal exit strategy to be finalised as the programme starts to unwind.	Exit strategy developed and approved.
Follow-up on the recommendations and implementation of proposed actions to support Internally Displaced People (IDP) and their land rights in SLLC process to ensure their rights are upheld.	A new SLLC Implementation Guidance Note (SIGN-17) was developed and incorporated into the GoE’s SLLC manual.
Investigate why women’s involvement in Land Administration Committees (LACs) are so low and identify what needs to be done to increase their participation.	Postponed – A ToR was developed for the study however field work was not undertaken due to COVID-19. Field work will be undertaken as soon as field travel is possible.
Log frame targets need to be reviewed to ensure stretching and ambitious results are set and definitions are clear (particularly for indicator 1.2).	Targets reviewed.

Key recommendations for SLLC and GESI in the upcoming year are as follows:
- Recommence PD in outstanding woredas as soon as it is permissible;
- Undertake field work on women’s involvement in LACs as soon as travel is possible;
- Ensure that the regions maintain their commitment to distributing LIFT SLLC certificates and specifically ensure that SNNPR recommences COVID-19 compliant certificate distribution events once the regional restrictions are lifted.

Output Title	Rural land Administration System (RLAS) implemented and operational in targeted woredas
Output number per LF		2	Output Score	A+
Impact weighting (%):		25%	Impact weighting % revised since last AR?	No

Indicators	Milestones for this review	Progress (as of 31 October 2020)
2.1 – Number of woreda offices in which RLAS is being implemented and at least 10 transactions have been processed	140	142
2.2 – Number of woreda offices in which RLAS has been operational for 12 months or more that pass the RLAS implementation assessment	90	103

Briefly describe the output’s activities, and provide supporting narrative for the score
The output’s activities support the development of the land administration system where rural land rights are recorded. At the start of the year, 127 woredas had RLAS installed and it was planned that an additional 43 woredas would have RLAS installed from March to June 2020. LIFT was on track to accomplish its SLLC workplan and had sufficient time for RLAS to then be installed. However, GoE’s COVID-19 mitigation measures have had the greatest impact on the RLAS component as it is heavily reliant upon training workshops, providing frequent technical backup support to woreda staff, awareness raising activities and the transportation and installation of RLAS equipment. Therefore, LIFT was unable to undertake RLAS installation activities in the same way as before.
As a result, LIFT adapted its approach to installing RLAS (see details in section on output changes below) and achieved the following:
- Indicator 2.1 – RLAS installed in an additional 15 woredas giving a cumulative total of 142;
- Indicator 2.2 – over the year, a total of 105 woredas underwent an RLAS 12/24/36 month implementation assessment. 74 woredas received a category three score (needs few improvements) and 29 received a category two score (needs many improvements), adding-up to 103 woredas passing the assessment. Areas where woredas were found to require improvements included the awareness level of Kebele Land Administration Committee (KLAC) members and landholders on the importance of formally registering transactions and organisational capacity. Two RLAS woredas in SNNPR showed very poor performance due to weak commitment of the woreda land office management for RLAS operations, which resulted in the woreda not replacing staff that had been transferred to other positions and staff focusing on development campaigns as opposed to RLAS functions.
In order to ensure RLAS sustainability and that landholder’s formally register transactions, LIFT has focused on improving landholders’ awareness on the importance of formal transactions and improving service delivery performance. The following RLAS innovations have been developed:
Initiative	Aim
CALM	Ensure financial sustainability of RLAS operations and efficient service delivery. LIFT developed a “Business Case for the Rural Land Administration Information Service (RLAIS)” to demonstrate to decision-makers how this could support RLAS financial sustainability (resulted in CALM) and will train staff on the new CALM Management Information System.
Model Woreda Office	Improve service provision at the kebele- and woreda-level and thus reduce time and effort (costs) of landholders looking to formally register land transactions. / Improve organisational capacity of WLAO and effect organisational change and practices. / Simplify procedures/workflows in order to improve efficiency of service delivery and reduce time to process transactions.
Satellite Woreda Approach	Improve service provision at the woreda level through formalising an informal approach of better performing woredas providing support in technical areas to weaker performing woredas and thus reduce time and effort (costs) of landholders formally register land transactions as well as improve. / Improve WLAO’s support for RLAS operations and ensuring a high quality of service delivery at the kebele level (i.e. KLAC completing applications correctly). / Improve WLAO’s awareness on the priority of ensuring PAC activities are undertaken.
Mobile Back Office Centre	Increase access to services by creating remote teams that will travel to kebele sectors to register transactions. / Increase awareness on the importance of registering transactions by undertaking awareness raising campaigns (to inform landholders on this service provision and importance of registering transactions).
Revised Woreda RLAS PAC Strategy	Support WLAO in raising landholders’ awareness on the importance of formally registering transactions through a structured approach by establishing kebele-level PAC teams with designated team leaders. / Provides clear guidelines on how to reach different target segments (public platforms, meetings and venues for posters) as well as a structured approach for print materials and information to flow from the WLAO to the sub-kebele level. / Improves monitoring of activities by actors having to report on venues that they have placed posters and events they have attend to increase landholders’ awareness on formally registering transactions.
Land Hotline	Will provide landholders the ability to call in and hear pre-recorded messages on the different types of transactions and what procedures should be taken and thus reduce instances of misinformation or misunderstanding on this.

In addition to the major impact of COVID-19 on RLAS activities, other challenges that LIFT has faced during the year have included insufficient regional budget allocations for RLAS equipment and maintenance, frequent turnover of the trained woreda staff, as well as frequent restructuring of the woreda administration, where 28 ‘old’ RLAS woredas have been split into 62 ‘new’ woredas.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Specific VfM indicators that relate to the RLAS component (as per the 2017 revision of LIFT’s VfM framework) includes the following:
[note] VfM indicators are based on LIFT’s VfM report which is based on results and financial data as of the end of August 2020.
Indicator		Target	2016	2017	2018	2019	2020
Efficiency	Cost of Woreda Office with functioning RLAS	N/A	N/A	N/A	£20,290	£18,220	£17,082
Effectiveness	Cost per formally registered transaction	N/A	N/A	N/A	£90.80	£46.61	£25.13

Cost of Woreda Office with functioning RLAS: A functioning RLAS woreda is defined as a ‘woreda office in which RLAS is being implemented and at least 10 transactions have been processed’ as per LIFT’s logframe. The VfM cost for this reporting period is £17,082 based on 127 woreda offices with a functioning RLAS and an estimated total spend on RLAS of approximately £2,169,461. The lower unit cost (it was £18k last year) indicates improved efficiency.
Cost per formally registered transaction: This metric was introduced in 2019 in order to address MTR comments on covering RLAS more in the VfM framework and was designed as a proxy to RLAS sustainability. Based on 86,331 transactions to date and the cumulative RLAS costs to date (£2,169,461), the average cost per transaction amounts to £25.13. The number of registered transactions has gone up dramatically to reduce this cost by almost half of what it was last year (£46.61).
These figures indicate that LIFT is making good progress in challenging circumstances. The transfer of woredas to the CALM programme will allow LIFT/LIFT UP to focus on significant improvements in a reduced number of woredas. However, the RLAS assessment confirmed that some woredas are not performing well enough and that is where LIFT UP needs to continue to progress initiatives such as the Model Woredas, Satellite Woredas and Light-Touch Communications campaign (see below). In the longer-term, and based on the RLAS financial sustainability study and best practices in land administration, two key strategies are envisioned to ensure that the RLAS becomes sustainable: 1) review the introduction of affordable transaction fees, once RLAS is operating efficiently; and, 2) generate revenues from land information service. Some institutions are already utilising rural land information (Tax Revenue Offices and MFIs) and during LIFT UP these should be consolidated and expanded, in close coordination with the regional governments to develop the necessary procedures.
Describe any changes to this output during the past year, and any planned changes as a result of this review
RLAS activities were expected to recommence in August/September after suspension for COVID-19. However, the infection rate has continued to increase since March and has not yet peaked. In August, LIFT engaged with the regional land bureaus to consider how to install RLAS while also minimising the COVID-19 risk and taking into account the regions’ experience in holding workshops. As a result, LIFT adapted its approach to installing RLAS by:
- Providing training on RLAS/iWoRLAIS to smaller groups of woreda staff;
- Holding awareness workshops on the procedures and benefits of RLAS for woreda-level staff only as this reduces the risk of kebele-level stakeholders becoming a possible vector for COVID-19;
- Holding workshops in larger venues to ensure social distancing and providing PPE to attendees;
During RLAS installation, ensuring individual workstations for each trainee and cleaning mouse pads, keyboards and screens daily throughout the training.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
Taking into account the impact of COVID-19 on RLAS activities, progress on last year’s recommendations is on track:
2019 AR Recommendations	Status
Develop action plan and closely monitor implementation to address the underperforming woredas on RLAS implementation.	Action plan developed and implementation being monitored.
Assess the progress of RLAS action plan including its impact on uptake and sustainability.	RLAS action plan assessed.
Review the impact of regional and woreda restructuring on RLAS implementation.	Reviewed – frequent restructuring of the woreda administration is a major challenge. A draft guideline was completed in February 2020 and submitted to RLAUD. It had been planned that a meeting would be held with the regional land bureaus to discuss the guideline, however, this has been delayed due to COVID-19.
Track the political commitment of the regional government and woreda by assessing allocation of resource (manpower and budget) as well as streamlining RLAS operations into RLAOs and WLAOs mandate.	Tracked – the regions have provided the necessary staffing for RLAS operations, but budget allocations for equipment and maintenance are still a challenge. As some woredas are using RLAS data to more accurately calculate land taxes owed, LIFT is planning to use this as an incentive for regions to prioritise RLAS.
Explore option to use Land Rental Service Providers (LRSPs) for RLAS work by identifying the services that could be included in the LRSPs’ service offer.	Explored – Document developed regarding what LRSPs are well suited to support in the land sector.
Completion of NRLAIS – LIFT to engage with REILA II on the credit module with the module developed and made available.	Credit module finalised.
Follow-up on CALM programme to ensure synergy with LIFT.	Ongoing.

Key recommendations for RLAS in the upcoming year are as follows:
- Install RLAS in the final set of woredas as soon as is permissible under COVID-19;
- Continue to implement the various RLAS action plans at the regional level: “Regional Level Action Plans”, “Satellite Woreda Approach Action Plans” and “Model Woreda Action Plans”;
- Ensure the smooth transfer of RLAS/iWoRLAIS/NRLAIS operational woredas to CALM. As per the RLAS phasing out strategy developed in cooperation with CALM, RLAUD and regional offices, LIFT will transfer the responsibility for ongoing RLAS operational technical support for 113 woredas to CALM by the 31st December 2020 and a further 51 by the 30th June 2021;
- Ensure that LIFT maintains synergies with CALM;
- Encourage political commitment by: increasing the awareness of decision-makers (at regional and woreda level) on the importance of RLAS; incentivising RLAS (some woredas in Amhara and Oromia have started to use RLAS data to collect Annual Rural Land Use Fees and Rural Land Tax, which has resulted in increased tax revenues, and LIFT will support these initiatives to enhance exchange of data between the woreda land offices and woreda revenue offices); disseminating best practices; supporting CALM strategies to guarantee the sustainability of RLAS.
Output Title	Improved supporting functions for the rural land market for poor male and female farmers
Output number per LF		3	Output Score	A+
Impact weighting (%):		25%	Impact weighting % revised since last AR?	No

Indicators	Milestones for this review	Progress (as of 31 October 2020)
3.1. Number of new innovations introduced by LIFT in the Access to Finance, Land Rental and agriculture input sectors, disaggregated by innovations that encourage environmentally sustainable practices	10 / 2	11 / 2
3.2. Cumulative number of market actors that have adopted and continue to promote LIFT innovations, disaggregated by: / MFIs / MFI branches / LRSPs / Woreda offices that enact the Standard Land Rental Contract (SLRC) / Input retailers / Input suppliers	MFIs: 8 / MFI branches: 130 / WLAOs: 45 / LRSPs: 525 / Input Retailers: 125 / Input Suppliers: 12 / Licensed LRSPs: 15 / Total: 860	MFIs: 10 / MFI branches: 138 / WLAOs: 48 / LRSPs: 525 / Input Retailers: 141 / Input Suppliers: 12 / Licensed LRSPs: 26 / Total: 900

Briefly describe the output’s activities, and provide supporting narrative for the score
The output’s activities focus on enabling farmers to fully utilise land investment opportunities and improve market efficiency. The past year has been challenging due to COVID-19 which has affected sectors and industries across the board. The GoE’s COVID-19 restrictions that were imposed to reduce the spread of the virus resulted in it becoming more difficult to progress intervention activities. However, despite these significant challenges, the EEU team has continued to press towards solidifying its existing progress as well as working alongside partners to operate in the face of COVID-19. The key achievements over the past 12 months have included:
- The rollout of the licensing and payment model for LRSPs;
- The implementation of the second phase for the crop insurance pilot scheme;
- Commencing technical capacity support for the judicial sector focused on resolving land disputes.
In addition, the EEU has also continued to support its partners in further expanding established interventions such as the SLLC-linked loan and formalisation of land rental, and bolstered the agricultural input supply system via private sector suppliers.
LIFT has met its end of programme targets for indicator 3.1 having achieved 11 innovations with a target of 10. Additionally, there are a total of 900 market actors putting these innovations into practice across the programme regions (indicator 3.2.). The main results across all EEU sectors have been:
EEU sectors	Results
Access to Finance	138 branches of eight partner MFIs (ACSI, OCSSCO, OMFI, Aggar, Wasasa, PEACE, Harbu and Metemamen MFI) are providing the SLLC-linked loan; / 18,738 loans worth ETB 582.4 million (£16.6 million) have been disbursed to approximately 14,644 beneficiaries (34% to women); / More than ETB 50.7 million savings mobilised (£1.4 million).
Land Rental	Over 1,000 LRSPs have been trained and 525 are operational in 32 woredas as of March 2020; / 1,393 land office staff have been trained (TOT methodology to cascade) on the use of the rental contract and the need for LRSP services in non-LRSP kebeles; / 23,381 land rental transactions have been facilitated by LRSPs benefitting 39,917 farmers; / A total of 26 LRSPs have attained their licenses.
Land Dispute Resolution	Enhancing the ability of the RLAU offices to develop and implement appropriate training to KLACs and kebele experts; / Developing the capacity of woreda judicial officers to adequately understand the new land proclamations and regulations, as well as the rights, obligations and interpretation of the SLLC.
Environment & Conservation Agriculture	141 input retailers are operational and actively promoting and selling agricultural inputs; / Over ETB 14.1 million in sales have been recorded by LIFT’s ten partner input suppliers; / Assessment on the regulatory and capacity building constraints of retailers was conducted.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Specific VfM indicators that relate to the EEU component include the following:
E	Indicator	Target	2017	2018	2019	2020
Efficiency	Cost per innovation by EEU	N/A	£222,481	£163,517	£588,540 / £147,135	£641,819 / £160,454
Efficiency	Leveraging ratio achieved through catalysed access to finance	N/A	4.2	5.9	7.51	7.48
Efficiency	Cost of EEU outreach (beneficiary)	N/A	N/A	N/A	£67	£67.30
Effectiveness	Benefit of increased income per household (or beneficiary)	N/A	N/A	£40.43	£46.09	£69.02
Effectiveness	Cost of sustainable change from EEU interventions	N/A	N/A	£185,814	£980,900	£706,000
Equity	Cost of SLLC holder female beneficiary accessing finance	N/A	£661	£380	£322	£351
[note] The second value, both in 2019 and 2020, is calculated according to the previous definition of innovation.

Cost per innovation by EEU: Innovations refers to new products, services and practices developed and introduced by LIFT. From 2019 (as per 2018 AR’s recommendations), innovations have been defined differently and counted at a higher-level to only include the initial product that was introduced as opposed to variations of it (i.e. the SLLC-linked loan now counts as one innovation as opposed to one innovation per tailored SLLC-linked loan product for each MFI). LIFT has accomplished 11 innovations and the corresponding unit cost is £641,819 (£160,454 based on the previous definition). The increased cost level is due to some of these innovations being in the early start-up stages (such as the licensed LRSP model and insurance product) and it is anticipated that this will be the case over the remainder of LIFT.
Leveraging ratio achieved through catalysed access to finance: £2,255,199 spent by the EEU on access to finance has led to MFIs disbursing ETB 575.2 million in loans by August 2020 (approximately £16.4m), indicating that for every £1 that the EEU has invested, there was £7.48 further invested by its partners. While still a significant positive ratio, it is slightly lower than last year. This is due to the impact of COVID-19 as MFIs have reduced the amount of loans that they have issued from January 2020 to present by 11% compared to the same period last year.
[note] Using the programme exchange rate of ETB 35 to 1 £.
Cost of EEU outreach: Based on 104,825 beneficiaries (people and market actors that have been reached by EEU interventions) and the EEU level of spend to date (£7,060,010), the VfM result is £67.30. This outreach cost has not changed significantly from last year.
Benefit of increased income per household or beneficiary: LIFT’s Cost Benefit Analysis (CBA) was updated in early 2019 to reflect results from various surveys and incorporate actual expenditure over the programme years. This was a VfM best practice by the programme, revisiting assumptions in light of programmatic evidence as well as applying actual costs break-down over the programme years. According to the revised CBA, additional income per household is estimated to be £69.02 for 2020 (across all EEU sectors). This represents a further increase in incomes from the 2019 figure. This is based on an economic analysis, and an external verification may be possible through the upcoming Income Survey.
Cost of sustainable change from EEU interventions: The EEU has tracked which of their innovations have held in terms of achieving market demand and response beyond 12 months (as a proxy for sustainability). In response to the 2018 AR and a sense-check of what goes in the list of innovations, they were reduced to six. This meant a much higher VfM cost result compared to the previous year. This year however, the result is 10 sustainable innovations and the cost for each of those is lower. It indicates a more cost-effective performance.
Cost of SLLC-holder female beneficiary accessing finance: Based on the estimated cumulative spend on access to finance and approximately 6,227 SLLC-linked loans made to women (34% of total loans) by August 2020, the average cost is £351 per female beneficiary accessing finance. This indicates that there has been an increase in the unit outreach cost this year due to the decreased number of loans having been issued due to COVID-19.
Overall, despite not having set targets, some of these average values suggest that the EEU interventions were as efficient and effective as possible, given the challenges posed by COVID-19.
Describe any changes to this output during the past year, and any planned changes as a result of this review
COVID-19 limited and delayed many planned workshops and trainings. The impact on partners has varied based on their sector:
- MFIs have struggled as many of their urban business clients have defaulted or were late on their repayments. There has also been a slow rise in late repayments for the SLLC-linked loan;
- In the land rental sector, formalisation services have been limited as relevant government offices and parties have had limited availability due to offices being closed and gatherings restricted;
- Both agricultural input suppliers and retailers have been negatively impacted by the rise in prices for inputs both for importers and distributors within the country. As a result, local input retailers have also struggled to manage the rising transport and product prices.
LIFT is exploring opportunities on how it can best support partners to recover from this unforeseen shock.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
LIFT has made progress on last year’s recommendations:
2019 AR Recommendations	Status
Conduct an assessment to better understand the existing financial products targeting women and VGs and identify opportunities for additional products and services. Re-examine sharia compliant assessments to ensure the financial products also meet the Muslim community’s needs.	Completed (see Assessment for Financial Products for Women and VGs and LIFT Islamic Finance note).
Evaluate how the default management guide has been mainstreamed in MFI’s operational manuals and/or as a stand-alone manual. Pilot implementation of the default management guide in select branches and evaluate the results.	Default management guide adapted to the needs of each partner MFI.
Monitor the liquidity of MFIs to ensure the supply continues to meet the demand for loans including assessing opportunities that would enable MFIs increase their liquidity.	Ongoing – LIFT continues to monitor the liquidity struggles of partners and link them with appropriate resources (i.e. RUFIP III).
Undertake a comprehensive study on sharecropping rental transactions to better understand the incentives or disincentives arising from knowledge, capacity, legal and social views with recommendation made for policy makers.	Completed (see Sharecropping Assessment).
Assess the feasibility of different payment modalities for rental payment system as well as roll-out to ensure the product meets the beneficiaries’ needs as well as conduct an assessment on licensing and tax appropriate for the LRSPS. Pilot the recommended payment modality, licensing, and relevant taxation in select woredas in Tigray and SNNPR alongside regional land offices.	On track – All aspects of this action are currently being piloted in four woredas across each of the four programme regions.
Establish a clear exit strategy for all EEU interventions with clear ownership of activities by the relevant partners in the sectors EEU is working in.	Ongoing – The initially developed exit strategy continues to be updated based on current realities.
Advocate for ratification of relevant policies and legal framework to support existing interventions and ensure their sustainability, particularly in SNNPR, Oromia and Tigray. Lobby the Government for speedy execution of the legal framework as outlined in the home-grown economic reform.	Ongoing – Despite the challenges of COVID-19 and security concerns, LIFT continues to engage relevant actors to advocate for conducive policies.

Key recommendations for the EEU in the upcoming year are as follows:
- Ensure the establishment of an up-to-date exit strategy for all interventions, with clear ownership of activities by the relevant partners in the sectors in which the EEU is active;
- Advocate for ratification of relevant policies and legal framework to support existing interventions and ensure their sustainability;
- Onboard the relevant actors that will take over the facilitation and coordination functions of the market systems, which LIFT has undertaken so far.
Output Title	Improved policies and institutions for the rural land sector
Output number per LF		4	Output Score	A+
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator	Milestone for this review	Progress (as of 31 October 2020)
4 – Number of research-based land policy reports, regulations, procedures, strategies and plans produced and delivered to the Government of Ethiopia and other key stakeholders that strengthen structures and processes for improved land certification and administration in Ethiopia or knowledge products which make new data or understanding available to a broad range of stakeholders (cumulative target)	82	90

Briefly describe the output’s activities and provide supporting narrative for the score
In cooperation with GoE and other partners supporting land programmes, the output’s activities focus on addressing cross-cutting policy issues with the aim of improving rural land tenure security and the transparency of land allocation. During the review period, LIFT’s major policy objectives have included the following:
1. LIFT’s 2020 priorities: National Rural Land Proclamation being approved; focus on the sustainability of RLAS by: a) developing a strategy for the sustainability of the Satellite Woreda Approach, and b) developing Regional RLAS PAC Guidelines and Training Manual (x4); ensuring the sustainability of the impact of SDOs post-LIFT.
2. Research to be undertaken as per LIFT’s 2019 AR recommendations;
3. Research to inform LIFT UP as part of LIFT’s one-year extension.
Over the last 12 months, LIFT has undertaken the following research papers under Output Indicator 4, bringing the cumulative total to 90 and exceeding its target:
Paper	Description
Land Tenure Issues Associated with IDPs	The report explored tenure security of IDPs and provided recommendations on how to restart SLLC activities post-conflict and ensure that landholders are not unintentionally negatively impacted
The Impact of SLLC-Linked Loan on Women with a Focus on Unintended Consequences	The research focused on ACSI loan beneficiaries due to the MFI having disbursed the loan for the longest period in comparison to other MFIs and examined how the loan product impacted on women’s economic empowerment in married households that applied for the loan due to the product requiring all landholders of a parcel to be involved in the application procedure
RLAS PAC Strategy Guideline and Manual and associated Training Manual	It provided a structured approach to raising awareness on the importance of formally registering land transactions, taking into account different regional contexts. It includes: an outline of the strategy’s approach; an implementation guide for WLAO; an implementation guide for elected kebele team leaders to establish a kebele-level PACT team (KLPT leaders), translated into regional dialects; KLPT leaders training manual
Dispute Resolution	Developed a curriculum and training material for the legal training institute
SLLC-Linked Individual Loan - Lessons Learned and Recommendations for Policy Change	Case Study highlighting the policy change approach undertaken by LIFT to include landholdings as movable collateral for individual loans
Sharecropping Study	A strategy for addressing sharecropping during LIFT UP, based on the sharecropping report delivered by the service provider
Strategy for the Institutionalisation of the SDO Function within the WLAO Structure	It identified the required activities to make the SDO function sustainable and inform LIFT UP
Licensing Requirements for Input Retailers	Assessment report of current licensing requirements including recommendations for policy changes and intervention ideas for LIFT UP

As per previous years, these outputs were selected to meet programmatic needs, produce strategies or procedures for GoE stakeholders, inform future initiatives by GoE or development partners, or advance learning about the land sector in Ethiopia.
Media Engagement: Following up on the 2019 AR recommendations, LIFT examined the option of entering fee-contracts with TV channels to host panel debates and specific programs to raise the profile of LIFT through any possible savings in January 2020. The exercise identified that there were no available savings to undertake this. Despite this, in January the MoA informed LIFT that they had contracted journalists from EBC and Walta News to highlight the work of RLAUD and that they would be covering LIFT as a success story of the directorate. LIFT therefore made field arrangements for success stories to be showcased and media coverage of LIFT has taken place on television and radio channels, newspapers, blogs and social media.
Website and Knowledge Hub: Over the course of the year, LIFT has undertaken work on its website to include informative videos on LIFT, including a short introductory video and longer training videos (in regional languages), as well as an interactive results map showing LIFT’s results in each woreda. In order to ensure that LIFT’s research and relevant documents are accessible to a wider group of stakeholders in the land sector including academics, research institutions etc., a Knowledge Hub has been designed for all documents to be uploaded for public consumption. Currently LIFT has uploaded key Output 4 documents produced from the start of the programme to 2019. It is planned that the Knowledge Hub will be launched in early 2021 and additional documents will be uploaded over the remainder of LIFT.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
N/A (no indicators to report on).
Describe any changes to this output during the past year, and any planned changes as a result of this review
As reported in LIFT’s 2019 AR, the programme produced a cumulative 79 (with an end of programme target of 65) policy reports as of September 2018. As a result, LIFT’s logframe target was increased to a cumulative total of 82 policy reports (October 2020) and 84 (end-of-programme). This increase also accounts for additional research to inform LIFT UP as part of LIFT’s one-year extension.
Additional activities have been postponed due to COVID-19: the Ethiopian Land Conference, which the MoA had planned to jointly hold with other donors and land programmes in April 2020; and the 2020 World Bank Land Conference, where LIFT was selected to present four papers and four posters. Due to the programme’s extension, LIFT’s Project Completion Workshop has also been postponed.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

LIFT has followed up on last year’s recommendations:
2019 AR Recommendations	Status
A greater focus on delivering genuine policy influence.	Ongoing – LIFT has focused on key areas which relates to RLAS sustainability through the Model Woreda and Satellite Woreda approach as well as increasing transactions through developing a Woreda PAC Strategy based on lessons learned throughout LIFT.
Systematically tracking and contributing LIFT’s policy influence.	Ongoing – LIFT regularly reviews its policy influence within the SLLC, RLAS, GESI and EEU components.
Re-assess the possible options of engaging with the media if any efficiencies or savings are identified based on other component’s needs.	No savings identified but LIFT covered as a success story (see Media Engagement above).

Key recommendations for Output 4 in the upcoming year are as follows:
- Promote LIFT’s Knowledge Hub to a wider audience to ensure that LIFT’s research and knowledge is disseminated as broadly as possible;
- Translate key Knowledge Hub documents from English to Amharic;
- Undertake a Project Completion Workshop to disseminate LIFT’s knowledge.
D: RISK

Overview of risk management
LIFT maintains a comprehensive risk matrix covering policy, programmatic, fiduciary and political risks. It is reviewed in detail by the programme’s Senior Responsible Officer, Programme Manager, Deputy Programme Manager and M&E Manager every quarter. In between, it is reviewed as part of the monthly update meetings between LIFT and the FCDO. Throughout the past year, the main risks to the successful implementation of the LIFT programme have been:
COVID-19: As detailed throughout the report, the restrictions imposed to combat the spread of COVID-19 within Ethiopia during the year resulted in many LIFT activities being postponed. This has had the greatest impact on the RLAS component’s workplan as well as the ongoing impact of the EEU’s interventions. While the state of emergency ended in mid-September, COVID-19 still poses a danger to the wider population and therefore LIFT will prioritise the safety of its staff and beneficiaries when planning any programme activities.
National elections: The postponement of the elections due to COVID-19 resulted in domestic tensions. LIFT will closely monitor the elections in 2021 and any potential issues that may arise.
Civil unrest in response to the killing of Haacaaluu Hundeessaa: The killing of Oromo singer Haacaaluu Hundeessaa on the 29th June 2020 triggered violent protests across Oromia and Addis Ababa in the first week of July, leading GoE to implement a nation-wide internet shut down lasting for most of July. Internet connectivity in Addis Ababa was restored in the third week of July but was not fully restored in regional capitals and woredas until the end of the fourth week, severely affecting communication between staff and submission of monitoring reports.

Hostilities between Ethiopia’s Federal Government and Tigray’s Regional Government: GoE declared a State of Emergency for Tigray in November 2020. The risks of a humanitarian crisis and a protracted conflict could have a severe impact on LIFT’s beneficiaries and staff/people involved in the programme. The FCDO and LIFT continue to monitor the situation.

When faced with the challenges listed above, the project has, wherever possible, worked with the FCDO and other partners to find acceptable solutions. As a result, in what have at times been difficult circumstances, the project has been able to maintain momentum and the delivery of results.
Risk Register. The issues above are captured and addressed, including key mitigating actions, in LIFT’s risk register, and each of them has the potential to have a significant impact on LIFT’s performance. The main risks that are deemed to be severe prior to mitigation are the following:
1. Political instability, conflict in any region (including current hostilities in Tigray) or widespread civil unrest undermines Government capacity, markets and the certification process;
2. Conflict in Ethiopia leads to internal displacement of people either into or out of areas in which SLLC/RLAS activities are carried out, leading to SLLC/RLAS being abandoned in a woreda or not being completed in certain kebeles of an affected woreda, or to a sudden deterioration of the security situation in a woreda, thus endangering the safety of LIFT staff and equipment;
3. Macro-economic instability weakens growth and opportunities for farmers to engage in markets;
4. Significant numbers of landholders opt out of registering new transactions such as inheritance, and the register falls out of date;
5. COVID-19 impact on operations and the UK aid budget;
6. The Government fails to maintain the land register, resulting in the register becoming obsolete.
Proposed mitigating actions are designed to reduce these risks’ likelihood and/or impact, however, some residual risks remain severe. In particular, high-impact, context-related risks such as those deriving from the current situation in Tigray should be monitored closely as they evolve.

Update on Partnership Principles
The 2020 Partnership Principles Assessment noted that Ethiopia is facing challenges on its long and complex journey to democratic and economic transition. The prospects for economic development and poverty reduction in Ethiopia remain strong, but the current political unrest and conflict, combined with COVID-19, threaten some of the recent gains made on human rights and domestic accountability.

Annual Statement of Progress
In collaboration with GoE and other development partners, FCDO supported Public Expenditure and Financial Accountability (PEFA) assessment of the Federal Government and six regional governments’ PFM system in 2019/20. Based on PEFA assessment reports, FCDO conducted fiduciary risk assessment of using the PFM system of the Federal Government and two regional governments in July-September 2020. Most financial aid programmes are implemented through the Federal Government PFM system.
FCDO judges the fiduciary risk of making payments through GoE PFM systems to be moderate. The structure of the PFM system broadly reflects good international practice; adequate laws, regulations and guidance are in place to govern practices. Macro-fiscal framework is tight; budget formulation, execution and reporting are based on internationally accepted standards. There are some positive developments over the last year to improve internal and external audits, including follow up of their findings. However, weaknesses in procurement, accounting and internal controls, fiscal transparency, public investment and asset management, implementation of audit recommendations and in-year budget reallocations remain areas of major fiduciary risk. FCDO financial aid programmes have already programme specific safeguards, using different tools (regular and targeted reports, tracking funds flow, joint field trips, beneficiary feedback, etc).
Financial Aid (FA). To date a total FA budget of £13,363,105.80 has been approved by the LIFT Programme Steering Committee (PSC) to undertake SLLC from the first to the eighth set of woredas. The PSC’s Co-Chairs agreed to reallocate some savings (approx. £48,000) made from the FA budget as a result of exchange rate variations to cover external audit costs.
Fiduciary risk. There are robust processes in place to mitigate fiduciary risk and provide fiduciary assurance.
Current level of fiduciary risk and direction of travel since last ASP	Moderate / Stable
Specific assessment of corruption risk and direction of travel since last ASP	Moderate / Stable
Is a full FRA update required?	No

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency

LIFT continues to operate in a changing political environment fraught with uncertainty. Despite these challenges in the operating environment, the programme achieved its targets for the year. In the absence of the EETSP, the ITSP worked to develop an Income Survey utilising savings from other survey activities and the extension year budget, so that all important research areas are covered. DAI is a Strategic Partner of the FCDO and, as such, their full portfolio is monitored under the Strategic Relationship Management Process. The performance scores indicate DAI contracts are generally being delivered at expected standards and a local process of bi-annual review has helped with timely feedback for effective delivery at pace.

Financial performance. Financial management for each component continues to be reported effectively on spend. On FA, Interim Financial Reports (IFRs) confirmed that the funds have been used for the intended purpose in line with FCDO regulations.
The independent audit commissioned by the FCDO on the implementing service provider/DAI for the period 1st November 2017 to 31st March 2019 identified some issues for the first time. These were discussed with the ITSP in October 2020 and resolved to the satisfaction of FCDO.
Furthermore, there were three fraud cases that remain outstanding this year. No FCDO funds were involved. ITSP and FCDO are closely following up on the cases to learn lessons and have further tightened LIFT procedures to protect from such incidences.

Partnership performance. The DAI-led consortium that implements LIFT has maintained strong relationships with the relevant GoE agencies, particularly the Land Administration and Use Directorate (LAUD) in the Ministry of Agriculture. Relationships with the Governments of the four programme regions, particularly their respective land bureau, are important to the successful implementation of LIFT. LIFT has also developed strong partnerships with relevant private sector actors such as MFIs, agricultural input suppliers and other businesses through its EEU, which has been crucial to the significant progress made under Output 3 over the course of the year.
The FCDO has an excellent partnership model with the implementing team, and with the federal and regional governments. The governance structures of the programme are functioning well at all levels. FCDO and DAI have regular meetings whereby progress is reviewed. Such platforms are also used to discuss challenges and risks escalated for timely action by all concerned. For example, the PSC co-chaired by MoA and FCDO representatives has played a key role for the improved performance on SLLC and RLAS. This has been made possible through proper risk analysis and pushing the performance bar higher for the four Regional Governments. The commitment of Regional Governments was further proved through increasing allocation of resources for RLAS implementation. This needs to continue for sustained impact of the programme.

Date of last narrative financial report	January 2020	Date of last audited annual statement	August 2020