## Annual Review – September 2020

Title: Partnerships for Development
Programme Value £ (full life): £35 million		Review date: June 2019-Sept 2020
Programme Code: [AMP ID#] / 205191	AMP start date: / 7 December 2015	AMP end date: / 31 March 2023

Summary of Programme Performance
Year	2016-2017	2017-2018	2018-2019	2019-2020
Overall Output Score	C	B	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5508804.odt / http://iati.dfid.gov.uk/iati_documents/42738310.odt
DevTracker Link to results framework:	http://iati.dfid.gov.uk/iati_documents/46572819.xls

A. SUMMARY AND OVERVIEW

Description of programme

Partnerships for Development (P4D) aims to enhance the UK’s development impact by boosting peer-to-peer partnerships between UK institutions and their counterparts overseas (formerly titled the GREAT for Partnership programme). FCDO’s Governance, Open Societies and Anti-corruption Department (GOSAC) hold overall accountability for the programme as the funding department. The programme’s objectives are to:
1. Increase the number of UK Public Institutions working in peer-to-peer partnerships;
  [note] Peer-to-peer partnerships involve trusting, sustained learning relationships between practitioners in similar fields, and an exchange of knowledge and experience to achieve sustainable changes that impact on public sector reform.
2. Enhance the effectiveness of peer-to-peer partnerships;
3. Improve coordination across different peer-to-peer partnerships and with other DFID and HMG programmes, exploiting synergies so that programmes complement each other
  [note] Due to the merger of DfID and FCO, references to DfID have been changed to FCDO throughout this review.
4. Build the evidence base for peer-to-peer partnerships, identify what works and best practice, to improve the quality of partnerships;
5. Strengthen institutions in partner countries supported by the programme;
6. Promote peer-to-peer partnerships as an aid modality.

The majority of programme activities are coordinated and delivered through a Partnerships Platform, operated by Government Partnerships International (GPI). GPI is a cross-Government unit, based in the Foreign, Commonwealth & Development Office (FCDO). The platform, which has seven functions. These include convening a community of practice linking UK practitioners; brokering new peer-to-peer partnerships between UK and counterpart institutions in developing countries; providing wrap-around support (e.g. advice; training) to partnerships funded and supported by the programme; providing programme assurance for funded partnerships; delivering monitoring, evaluation, research and learning (MERL) activities to funded and supported partnerships; developing communications strategies and products; and delivering public sector reform expertise through peer-to-peer partnerships (direct delivery).
[note] ‘Funded partnerships’ are those that involve a UK institution that receives funding as well as support through P4D – these partners include BGS, OPF, ROLE UK, NCA and GDS.
[note] Note that the programme now refers to this function as Monitoring, Evaluation and Learning (MEL), hence the use of the term MEL rather than MERL as referred to in the Business Case Addendum.
[note] ‘Supported partnerships’ refers to those partnerships that involve a UK institution that receives support but not funding through P4D.
[note] ‘Direct delivery’ refers to GPI advisors delivering public sector reform expertise in developing countries.

Beyond funding Government Partnerships International, P4D is delivered by five partners (two NGOs and three HMG public bodies):
1. The British Geological Survey (BGS) – builds capacity, skills and systems at state institutions that manage data on natural resources in Kenya, Sierra Leone, Tajikistan, Kyrgyz Republic and Ghana, in order to build good governance of the extractives sector.
2. Oxford Policy Fellowship (OPF) – places early career legal and policy advisors as fellows into country governments including Ghana, Liberia and Uganda.
3. Rule of Law Expertise (ROLE) UK – supports pro-bono legal capacity building partnerships abroad through its UK-based management and programme team
4. National Crime Agency (NCA) – deploys three International Liaison Officers in Kenya, Nigeria and Tanzania to work with security and judicial counterparts combatting serious and organised crime
5. Government Digital Service (GDS) – provides expertise through partnerships to improve government digital capability in Colombia, Ukraine, Uzbekistan, Ghana and Rwanda, in order to strengthen developing country institutions.

Approach to the Review

This Annual Review covers the 15-month period between June 2019 and September 2020 as result of the impact of Covid-19 and the ODA prioritisation in the programme and a decision to postpone the original review by three months. P4D responded to the changes in context by revising its Theory of Change and Logframe. Consequently, this Annual Review refers to two Logframes and two Theories of Change (Section B) covering the periods June 2019 to the end of March 2020 and April 2020 to September 2020 respectively. This approach prevented the reviewer, in some cases, from capturing all of the work done on the programme during this time.

Summary supporting narrative for the overall score in this review
In nearly all of its measurable Outputs, the programme exceeded the milestones set, or would have done so if not for Covid-19. Despite the challenges in context which required the programme to scale back, there were positive signs of delivery towards the Outcome and even initial evidence of Impact.
P4D has provided support in over 20 countries through its different avenues of delivery. Funded partners are working in critical areas for UK policy such as anti-corruption, rule of law, transparency and extractives, digital and institutional strengthening. Results have included National Crime Agency (NCA) in Kenya helping to bring forward 27 arrests in a high-profile embezzlement case and a court order for KSH1.1billion in another high-profile case of international interest, and ROLE UK making a significant contribution to sentencing practice in Uganda. GPI has also supported public administration reform in Nepal, Montserrat, Ethiopia, Ghana and Rwanda to build state capacity in those countries.
GPI has provided tailored support to 17 partnerships which has helped to improve delivery of ODA programmes. An Independent Commission for Aid Impact (ICAI) report has recognised GPI’s contribution to offering high quality knowledge-based assistance.
[note] See https://icai.independent.gov.uk/wp-content/uploads/How-UK-aid-learns.pdf, p11.

Contextual and Budget Changes
Significant contextual and budget changes have impacted on this programme. Covid-19 and ODA reprioritisation has required P4D to adapt to remote delivery, and scale back due to reduction of resources. The pausing of activity has caused some reputational damage within certain partnerships, while ongoing processes in Government such as the Integrated Review of security, defence, development and foreign policy, and the Spending Review, have brought more uncertainty to the future direction of the programme. The strategic context for the programme is now dramatically different from when it was established.
The programme’s budget was reduced by over 50% in September 2020 from £8m to £4m. Staff numbers were decreased as a result in GPI (from 15.8 to 4.5), as well as amongst funded partners, the Government Digital Service (GDS) (from 21 to 3.5) and the Oxford Policy Fellowship (OPF) had to scale back delivery and stop contracting newly recruited Fellows who were due to deploy in September. The British Geological Survey (BGS) had to cancel new planned capacity building delivery and technical improvements, switching to remote delivery for the existing activity. The National Crime Agency and Role UK cancelled all planned new training and activity respectively. Role UK has secured additional funding from its parent organisation Advocated for International Development (A4ID) to supplement the shortfall in budget to maintain basic operating costs in order to deliver its commitments up until March 2021.
Given the contextual risks currently facing the programme, and the reduced capacity on all elements of the programme as the result of funding cuts, outputs are likely to decline during this financial year. In addition, it is not possible at present to assess the direction of travel after June 2020. The future of the programme will depend on Spending Review decisions.

Major lessons and recommendations for the year ahead
The lessons and recommendations below synthesise the main strategic messages for this Annual Review. Further programme recommendations can be found in each Section of this review. It is important to note that many of the recommendations in this review are resource dependent and would not be feasible under currently projected forecasts for the ‘mothballed’ programme.

P4D has been an innovative and novel programme for testing new methods in partnerships. P4D has put learning and adaptation at the centre of programme delivery. P4D has brought together UK public expertise from a number of sectors to achieve FCDO international objectives on public sector reform and institutional capacity building.

P4D’s peer-to-peer model has been most effective when it supports FCDO international priorities in country and a broader HMG agenda.  Coordination, cohesiveness, long-term relationship building, and trust appear to be success factors for P4D.

Given the substantial changes in the broader operating context, P4D should be redesigned (building upon what has worked) and its scope reconsidered to align with the new HMG international priorities.  This should explore the option to narrow the focus of the programme, under the new Open Societies Directorate.

The complexity of the different elements of the current programme and its rapid growth has limited GPI’s ability to deepen strategic partnerships. A greater focus on integration of the elements of the programme (e.g. funded partnerships, supported partnerships and direct delivery) and greater selectivity in the sectors and/or countries would reap more substantive benefits from UK expertise, accelerate programme learning and deepen development impact.

The P4D programme is recognised as a leader in adaptive programming and an agile, flexible and responsive tool for UK development action in priority countries. Expanding the communications, MEL and research capacity in the future programme would help to strengthen the evidence base for peer-to-peer partnerships as an effective aid approach.

Recommendations	Owner	Timeline
P4D should be redesigned to respond to FCDO international priorities on state capability. The new programme should build upon the evidence of what works and seek to concentrate and deepen strategic partnerships supporting Open Societies objectives (e.g. digital transformation, transparency, institutional strengthening and resilience).	GOSAC and GPI	Redesigned P4D concept note drafted by March 2021
The redesigned P4D should concentrate on 3 or 4 countries where state capability is central to the delivery of goals by Her Majesty’s Government (HMG).	GOSAC and GPI	Redesigned P4D concept note and ToC drafted by March 2021
A new P4D Theory of Change should be developed to respond to the post-Covid context, and a new integrated offer of the different elements of P4D to strengthen evidence of results as part of the process of redesigning P4D.	GOSAC and GPI	Redesigned P4D ToC drafted by March 2021
GPI’s learning offer should be revised and limited to complement narrower ‘thematic’ priorities and a select number of geographical priorities, aligning with FCDO international objectives on state capability, and supporting HMG partners to learn and improve ODA delivery.	GOSAC and GPI	Detailed GPI core state capability offer developed by March 2021

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The P4D Theory of Change has been adapted from that in the Business Case Addendum. While the underlying logic remains the same, there is now an interim Useful Theory of Change (UToC) in response to Covid-19. The programme undertakes quarterly strategy testing to test the assumptions and assess the evidence emerging that supports that the logic behind the UToC remains solid. Throughout delivery the evidence remained strong that the activities, goods and services produced, and the audience captured was showing progress towards the behaviour change and direct benefits that were aimed for. This has been captured by Stories of Change and Tangible Examples of progress. There has been some evidence surrounding the need to ensure that the rationale for activities is fully understood by partners in order to lead to more sustainable change. However, contextual changes impacting the programme budget and resources in 2020 mean that the assumptions under-pinning the UToC have not held true.

Useful Theory of Change as Revised in 2020

ToC Revision: Impact on Indicators

The Theory of Change (ToC) and Logframe have been adjusted to a more realistic ambition given the Covid 19 context. There have been minimal changes to outcome and impact indicators; changes have primarily been to place indicators within an expanded set of steps in the ToC, and revise indicators to reflect restrictions on delivery and data collection.

The overarching impact indicator remains the same. Outcome indicators were adapted to reflect what remained possible to deliver or measure. As a reduced level of impact was anticipated, what was previously Outcome 1 has been articulated as a second, intermediate impact indicator. The intermediary outcome level has been eliminated for the interim Logframe. Three intermediary outcomes indicators were removed, and the others integrated into the interim Logframe. A full account of these changes and the reasons for them is provided in Annex 1.

For the annual review, the period June 2019 to March 2020 is assessed using the original Logframe with no changes. The original June 2020 milestones are listed, but progress reported only up to the end of March 2020. The revised Logframe is used to assess progress for April to September 2020. Please note some original indicators remained and so will be reported on cumulatively.

Further Planned Changes to the Theory of Change

This UToC will be adapted once more by the end of 2020/21 to reflect emerging contextual evidence. With the reduced scope of the programme the team plans to streamline the UToC to reflect more realistic change pathways, given the constraints on travel, resources and budget.

Value for Money of the Adapted ToC

Temporary constraints have reduced the ambition of the Logframe, and the ability to deliver against the programme objectives. Whilst the programme has performed well against objectives, the programme will need to be redesigned post-Covid to deliver value for money and to align with the new FCDO agenda on state capability (depending on the outcome of the Spending Review). Further reflection on Value for Money can be found in Section E.

Progress towards Outcomes
The Logframe has been revised to reflect the current operating circumstances, which have slowed programming. The budget reduction to the programme under current conditions means that some partnership activity was ended abruptly, and despite efforts to mitigate the impact on partnerships, relationships and trust have been impacted as previous commitments were scaled back.

Outcomes from the original Logframe are listed below, showing how these changed in the interim Logframe.

Outcome 1

Prior to April 2020: Strengthened partner country institutions, through P4D partnerships
The programme exceeded both its milestones in terms of tangible examples of improved institutional functioning and number of quantifiable contributions to observed change by funded partnerships. Funded partnerships were responsible for these behaviour change results; despite good progress with the Public Service Commission in Nepal and the Government of Montserrat (GoM), GPI did not meet its target, being interrupted by Covid-19 and aid reprioritisation respectively.

The examples of how the P4D programme has strengthened institutions have come from a range of the funded partners. Skills exchange and mentoring provided by the NCA international liaison officer (ILO) in Kenya has led to long-lasting changes in processes, policies and approaches to corruption investigation in the country. BGS support has impacted motivation and changed ways of working in the Ministry for Development of Geology (MDG) in Tajikistan and the National GeoData Centre (NGDC) in Kenya. The positive impacts of support are recognised by counterparts: a senior official within Tajikistan’s Ministry for Development of Geology (MDG) stated that new graduates, who usually lack computer skills, can “work completely digitally” following support from BGS. A representative of the Justice, Law and Order Secretariat of Uganda recognised a ROLE-UK supported conference as a crucial milestone in recognising and addressing issues in sentencing, and a local lawyer reported seeing some judges “using the sentencing guidelines more” as a result. A director within Ethiopia’s Environment, Forest and Climate Change Commission (EFCCC) credited OPF support for enabling a law reform programme “that works for Ethiopia” and provides “space for truly homegrown, sustainable solutions.”

April 2020 onward: Counterpart institutions are strengthened and more resilient, including to the effects of Covid-19
No milestone was set for June 2020 in the adapted Logframe, but some tangible examples have been gathered that still require contribution analysis – including four examples of OPF fellows supporting country responses to Covid-19.

Outcome 2

Prior to April 2020: Partnerships seen as an effective aid approach, with a more detailed understanding of effectiveness dynamics
It was not possible to collect perception data directly due to the pandemic, so the indicator on positive perceptions of peer-to-peer working could not be measured. However, qualitative evidence from interviews and feedback questionnaires suggested beneficiaries in partner countries felt more cared for in peer-to-peer partnerships. In terms of lessons and ideas generated and learned, a total of 21 lessons and ideas, far exceeded the June milestone, was gathered by March. These included developing a brokering framework building on lessons learned, and an initiative to gather evidence of mutual learning in partnerships, for both UK and International participants.

April 2020 onward: Developed learning on what works in peer-to-peer working in a crisis
The milestone of 6 meaningful instances of Community of Practice (CoP) members sharing learning within the community was met. The milestone of two meaningful instances of CoP members using learning from fellow members was significantly exceeded with four examples gathered. The target of two substantial lessons and ideas generated during the first three months of the new Logframe was met.

Intermediate Outcome 1

Prior to April 2020: Partnerships develop to be functional and sustainable
Indicators measuring partnerships’ advancement could not be measured in March 2020 as measurements are taken annually at a later point in the year. The programme reached 5 rather than 7 tangible examples of supported partnerships (wrap around support) improving ways of working. These included a strong contribution to changes in MEL processes and approach by the Bank of England, as well as changes in perception and uptake of MEL tools and Thinking and Working Politically (TWP) by the Office for National Statistics.

April 2020 onward: Partnerships are maintaining healthy relationships and delivering workstreams effectively
In the interim Logframe, the outcome focuses on the maintenance of quality of relationships and delivery within partnerships in a challenging context, rather than on improving partnership strength. The platform exceeded its milestone of 50% with 75% of relevant partnerships advancing to, or maintaining, an average of Level 3-4 in their Partnership Capability Assessment (PCA) criteria. PCAs measure the average of partnerships’ scores on up to eight relevant capacities, including culture and utilisation of learning, relationship building skills and trust building, strategic direction and clarity, and sophistication of MEL capabilities. Each capacity is scored on a scale of 1 to 5.

Intermediate Outcome 2

Prior to April 2020: CoP is utilised as a lesson sharing mechanism
Tangible examples of members’ use of the CoP and of member collaborations were not met by March 2020, and the percentage of members utilising the CoP could not be measured due to Covid-19. However, all three indicators would have shown good progress if measured all the way to up to their original June milestone. By June, more than the expected number of CoP members were utilising, generating or sharing lessons (10 examples rather than 8), 67% rather than 30% reported using the CoP to learn or share lessons, and the target of two tangible examples of collaboration had been met, including members from GDS, BGS, OPF, and ROLE UK participating in a collaborative event to share and document learning about remote partnership working.

April 2020 onward: Developed learning on what works in peer-to-peer working in a crisis
The milestone of six meaningful instances of CoP members sharing learning was met and included GDS members sharing resources for online facilitation techniques. Four meaningful instances of CoP members using learning from fellow members were gathered – double the milestone of 2.

Intermediate Outcome 3

Prior to April 2020: Strengthened evidence base for peer-to-peer partnerships as an aid approach
The milestone for tangible examples of users interacting with learning products or events was not met by March 2020. If measured up to June, the milestone would have been exceeded with 21 examples gathered. P4D has also supported the evidence base on peer-to-peer partnerships through innovative tools to promote learning and adaptation, improvements to partners’ MEL approaches, and sharing and collaboration through a refreshed and growing Community of Practice.

April 2020 onward: This indicator was removed
This element was deprioritised in the Covid-19 context, and the indicator removed.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

P4D has been versatile in delivering across HMG international policy objectives and is a good example of joined-up Government work in action. The peer-to-peer model brings UK public servant peer experts to work collaboratively with counterpart governments across a wide range of technical issues (e.g. rule of law, extractives, digital, tax, etc.), including issues of UK national interest such as combatting Serious and Organised Crime, corruption and illicit financial flows. Peer-to-peer partnerships draw on development expertise in ways that can secure diplomatic benefits by building relationships and extending UK influence.

P4D support has helped to reorient HMRC’s programmes in Pakistan, Ghana, Rwanda and Ethiopia for improved delivery and results. Experts from the UK’s Government Digital Service are helping the government in Ghana to build digital platforms for communicating with citizens and providing services to the most vulnerable. The National Crime Agency has embedded an adviser in Kenya’s anti-corruption commission to help the government produce a court order for a high-profile £8.3m corruption case. Legal advisors from Oxford Policy Fellowship have assisted the drafting of legal agreements for procurement of health workers and supplies in Sierra Leone’s response to Covid-19, and supported agreements to access funding to mitigate the impact of the pandemic in Liberia. FCDO Embassies and High Commissions recognise the value added by P4D in supporting the delivery of HMG objectives in country. The agility and flexibility of P4D to provide tailored, adaptive and context-specific support in country is highly valued, including by partner Governments.

There is a strong case for peer-to-peer to continue as a modality; however, the multi-sectoral programme as currently configured needs to be reconsidered in light of change in strategic context, including assessing the impact of the Integrated Review and Spending Review.

## C. DETAILED OUTPUT SCORING

Outputs are presented below to each of the respective Logframes. The revised Logframe has fewer outputs than in the original Logframe, and the weighting has been spread equally across them.

OUTPUT 1

The overall score for this output is A and weighting 33.3%, as the Annual Review is scored on the current Logframe.

Logframe to April 2020

Output Title	Directly funded, stable peer-to-peer partnerships
Output number:		1	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	[If Yes, up or down?] N/A

Indicator(s)	Milestone (June 20)	Progress to end of March 2020
1.1. Number of funded/direct delivery partnerships created (cumulative)	7 (cumulative)	EXCEEDED. / 9 partnerships reached
1.2. New partnerships reporting stable starting points (cumulative)	4 (cumulative)	NOT MET. / 2 (ROLE UK and Government Digital Service)

Logframe from April 2020

Output Title	Funded and Direct Delivery partnerships are set up and supported to deliver workstreams under a covid-19 context
Output number:		1	Output Score:	A
Impact weighting (%):		33.3%	Weighting revised since last AR?	Yes – revised down

Indicator(s)	Milestone (June 20)	Progress to June 2020
1.1 Responsiveness of partnerships (funded and direct delivery) to counterpart needs	Level 2	MET / Level 2
[note] The sentinel indicator on Responsiveness of Partnerships consists of four levels. At Level 1, partnerships are unresponsive to the nuances produced by the Covid-19 crisis including counterpart needs, delivery risks and environmental considerations. Level 2 is partly unresponsive, Level 3 relatively responsive and Level 4 fully responsive. The full scale is provided in Annex 3.

Briefly describe the output’s activities, and provide supporting narrative for the score

The programme exceeded its cumulative target of 7 funded or direct delivery partnerships, reaching 9 partnerships, including BGS, NCA, OPF, ROLE UK, GDS, and direct delivery partnerships in Nepal, Ethiopia, Ghana, and Montserrat. Preparatory work to build International partnership teams in the National Audit Office (NAO) and the Department for Education (DfE) progressed well, but contextual factors prevented the signing of MOUs and the start of the partnership activity.

From April 2020 onward the adapted Logframe measured the quality rather than the quantity of partnerships. Partners met the expected level of responsiveness to partner needs in relation to Covid 19, adapting to offer support in new ways in a challenging context.

Assess the Value for Money (VfM) of this output compared to the proposition in the Business Case, based on performance over the past year

Prior to June 2020, and in terms of effectiveness, the number of partnerships continue to increase based on demand for UK expertise from partners. Two new partnerships were on the verge of being initiated with the National Audit Office and the Department for Education. However, these have to be cancelled when the pandemic hit. Existing partnerships worked extensively with GPI to adapt their offer to counterparts’ needs as result of Covid-19 and moved towards remote delivery to continue their support to partners. Whilst, partnerships responded efficiently to the new reality the challenges of the new context for operational delivery have meant that scale and ambition has to be revised down on the face of limited capacity in partners to engage remotely. Where partnerships have remained deployed in country (e.g. NCA, OPF) they have been the most effective in terms of VfM.

Describe any changes to this output during the past year, and any planned changes as a result of this review

Output 1 changed from measuring the quantity of ‘Directly funded, stable peer-to-peer partnerships’ to measuring the responsiveness of partnerships within the context: ‘Funded and Direct Delivery partnerships set up and supported to deliver workstreams under a covid-19 context.’

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

In line with last year’s recommendations, OPF has continued develop its community of practice, entered into discussions with FCDO to maximise synergies between fellows and country offices, reviewed its MEL strategy and commissioned an independent review of the programme which produced good results. The NCA has implemented GPI’s recommendations to improve reporting quality, though the timeliness of reporting could be further improved. There is evidence of BGS and GDS aligning aspects of their work with FCDO priorities. BGS has not yet actioned the recommendation to review learning in Sierra Leone and Kenya and apply lessons elsewhere.
[note] The OPF Mid-Term Review found that almost all supported governments had been directly influenced by fellows in their policy choices, and signalled high achievement in terms of impact, with each fellow having contributed at least one demonstrable success.

In line with the recommendation to consider governance arrangements which link across FCDO directorates to improve coherence, Terms of Reference for a cross-government board were produced, but this work did not progress. It was difficult to establish an institutional footing and senior champion for the programme, partly because of the wide sectoral coverage. However, a governance board was established for the DfE partnership, and GPI strengthened links by introducing thematic leads whose role included engagement with FCDO policy leads.

A clear lesson for the programme has been that P4D would be more effective if its focus were on the quality of partnerships rather than the quantity. In response, GPI has begun moving toward a more strategic and integrated approach in order to become more demand-driven and focused on country objectives. A different approach to GPI’s own international delivery should be adopted to achieve greater results, for example by collaborating with other UK bodies in the region or country to joint aims.

The programme has recognised the need for an improved needs assessment process, preferably in advance of agreements being made. The quality and consistency of support could be better anchored through a curriculum for GPI advisors and clear articulation of roles and responsibilities when GPI provides support in country. It has also learnt that support yields more results as partnerships mature, suggesting that the ambition for outcome milestones will need to take account of the proportion of new or emerging partnerships at a given time. Finally, the programme could capture the importance of establishing connections as an output, to support its ambition for greater coordination in country, when revising its Theory of Change.

Recommendations
In redesigning the programme, review the model of funded partnerships and GPI’s peer-to-peer delivery to ensure going forward the different components of P4D come together to respond coherently and cohesively to a clear agenda on state capability that aligns with Country Plans.
Deeper and strategic partnerships would have to be appropriately resourced (staff and budget) to deliver quality support and maximise development impact. GOSAC and GPI to review P4D operational model to adapt it and respond to new FCDO priorities effectively.
In redesigning the programme, GOSAC and GPI should also assess what expertise and skills are needed to deliver new state capability objectives.

OUTPUT 2

Up until April 2020, Output 2 measured both the number of supported partnerships (i.e. UK public bodies receiving ODA from other programmes) receiving support from GPI, and examples of support being perceived as useful. No new partnerships could be agreed in the wake of Covid-19, so the count of additional partnerships supported (Indicator 2.1 below) was dropped, and the interim Logframe looked only at usefulness (Indicator 2.2). The output was measured up to June 2020 as in the original LogFrame, and the weighting increased to 33%. The overall score for this output is A and weighting 33.3%, in line with the current Logframe.

Logframe to April 2020

Output Title	Unfunded peer-to-peer partnerships supported and functioning with meaningful wrap-around support
Output number:		2	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	[If Yes, up or down?] N/A

Indicator(s)	Milestone (June 20)	Progress to end of March 2020
2.1. Number of unfunded partnerships supported with wrap-around support (cumulative)	10 (cumulative)	EXCEEDED / 17 unfunded partnerships supported by end of March 2020
2.2. Number of tangible examples of wrap-around support being perceived as useful by unfunded partnerships (cumulative)	10 (cumulative)	EXCEEDED / 18 examples. This indicator was carried over into the new Logframe, with no change to the achievement level by June 2020.

Briefly describe the output’s activities, and provide supporting narrative for the score

Progress was accelerating faster than expected prior to the pandemic, exceeding milestones on all indicators. The programme recorded 23 interventions given by GPI to support the work of 17 UK public bodies and organisations working Internationally (not funded by P4D). These included: the Office for National Statistics (ONS) International Development Team, the Prosperity Fund, the Prime Minister’s Implementation Unit, the Office of Gas and Electricity Markets (OFGEM), the Department for Business, Energy and Industrial Strategy (BEIS) International Climate Finance team, British Geological Survey (BGS) International, Bank of England (BoE), and Her Majesty’s Revenue & Customs (HMRC’s) Capacity Building Unit. Support included MEL and Political Economy Analysis (PEA) capacity building and advice, support on scoping trips, facilitation of lessons learning, and support with review processes for instance. Tangible examples were close to double the milestone, with positive feedback echoed in surveys and interviews.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Before June 2020, demand from GPI wrap-around support from Other Government Departments (OGDs) delivering ODA programmes internationally continue to increase this year from last year which responded to the recognition by others of value added, effectiveness, economy and efficiency of GPI’s work. VfM was further achieved by GPI’s wrap around helping partners to better aligned international objectives across Government and to complement FCDO’s work. Examples include partnerships joined up work in Ghana and Rwanda as well as redesigning of OGDs programmes in Pakistan and Ethiopia to respond to context changes Post June 2020, the P4D Board took the decision to stop all wrap-around support as result of reduced resources.

Describe any changes to this output during the past year, and any planned changes as a result of this review

Output indicator 2.1 was dropped and indicator 2.2 moved into the revised Logframe with the same milestone and progress figures. Correspondingly, Output 2 was reworded as ‘Supported partners receive quality wrap-around support to assist their partnership delivery work.’

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

Following the spirit of last year’s recommendation to refine the partnerships strategy, GPI has moved toward a more strategic approach to selecting countries and sectors, though further tightening of selection would achieve greater economies of scale. GPI also recognised that the offer was too supply-led and had begun moving towards a more demand-led approach through closer working with HMG staff in country.

Relationships with these UK institutions have been positive, and support tailored to suit their varied contexts, partnerships and maturity levels. The programme’s adaptiveness has been facilitated by attitudes and trust in the team and the right working environment to allow for learning and change. There is room to better understand partner needs and to develop a clearer and wider offer in terms of themes and forms of support, which could include the practicalities of how to run a programme.

Recipients of this support also included the facilitation of relationships in country and with other practitioners via the CoP as forms of support, though these are not measured for this output. Critical friendship and challenge is also viewed as a form of support by partners, whether funded or supported. Interviews suggested advisors would add more value if they were quicker to develop a genuine understanding of the work of the partner being supported. Record-keeping practice in relation to wraparound support needs to be strengthened, as not all support is currently captured.

Strategically, the programme successfully grew its stable of funded and supported partnerships, but to some degree grew beyond its capacity to support partnerships, due to understaffing and a higher than expected need for programme management support among new partners. A review paper produced in response to last year’s recommendation to review staffing capacity highlighted the need for additional staff to meet the demand for support.
Recommendations
GOSAC and GPI should revise the P4D Theory of Change to respond to the new context post-Covid in the process of redesigning P4D.
In redesigning the programme, GOSAC and GPI should consider widening the definition of wraparound support to include the Community of Practice and facilitation of relationships.
GPI P4D SRO should ensure roles and responsibilities in relation to MEL (issuing surveys) and record-keeping (logging support provided, whether formal or informal) are clear across GPI and that staff are held accountable to it.

OUTPUT 3

The overall score for this output is A+ and weighting 33.3%, in line with the current Logframe.

Logframe to April 2020

Output Title	Functioning Community of Practice on peer-to-peer partnerships
Output number:		3	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	[If Yes, up or down?] N/A

Indicator(s)	Milestone / June 2020	Progress to end of March 2020
3.1. % increase in attendance at events	15%	57% - average of event attendance between July 2019 and end of March 2020 was skewed upward by single large event.
3.2. % increase in use of learning products from CoP	15%	Not measurable – The survey that measures this indicator is conducted once annually. It was not possible or appropriate to administer the survey to measure this indicator in March 2020, due to the impact of Covid 19.

Logframe from April 2020
Output Title	The Community of Practice develops an enabling environment
Output number:		3	Output Score:	A+
Impact weighting (%):		33.3%	Weighting revised since last AR?	Yes – revised up

Indicator(s)	Milestone (June 2020)	Progress to June 2020
3.1. Steps taken to develop an online platform	12 steps	MET / 12 steps toward Teams platform launch / 7 steps towards Basecamp platform launch
3.2. Degree to which all CoP activity is designed and delivered in a quality, communicative and collaborative manner	Level 2	EXCEEDED / Level 3 (out of 4)
[note] Activity includes emails to the community, roundtables, events delivered, etc.
[note] The sentinel indicator for the quality of CoP activity consists of four levels. At Level 1, design of CoP activities would score the lowest in terms of quality, communication and collaboration, and at Level 4 the highest. The full sentinel scale can be found in Annex 4.

Briefly describe the output’s activities, and provide supporting narrative for the score

Owing to a change in strategy to focus on the relationship building function of the Community of Practice, measures of attendance and product use were exchanged for measures of progress toward an online infrastructure for member exchange and collaboration, and the quality of CoP activity. The survey measuring use of CoP products could not be taken in March, but when taken mid-year usage exceeded the June milestone at 18%.

The CoP met its milestone of 12 steps towards a Teams platform and took further steps towards an alternative platform in response to feedback from beta-testing. The quality of CoP activity reached Level 3, meaning activity was generally good quality, communicate and collaborative. Members of the CoP have begun producing their first collaborative products, including a Practice Note on Remote Partnership Working. The community has grown from 44 at the last annual review to a wider audience of over 200 members, and P4D funded and supported partners have been active participants.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Value for money has been good, with indicators predominantly met or exceeded across both Logframes. The one indicator that was not met for June 2020 was due to a strategic change to focus on member-led and horizontal and informal exchange rather than top-down training events and GPI products, which made this indicator an unsuitable measure. Under the revised strategy, members of the CoP have begun producing their first collaborative products, including a list of member partnerships to aid coordination and a Practice Note on Remote Partnership Working which was issued in September and has been well received, and has been shared with several members’ networks including the civil service Policy Profession. Interviews with funded and supported partners reflected that the CoP is perceived as an important form of support and that informal relationships between members, established through the learning community, have added value to their work in ways that are not measured in the Logframe.

Describe any changes to this output during the past year, and any planned changes as a result of this review

A Community of Practice is fundamentally relational and member led, and it was recognised that the previous indicators were too transactional and focused on GPI-led activity. It was also observed that large events positively skewed the aggregated attendance data. The CoP strategy was adjusted to focus on engagement and indicators were revised to focus on appropriate qualitative measures.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

The CoP is seen as a major component of support by supported and funded partners, and current measures do not necessarily capture the full impact of the learning community as relationships among members deepen. It has also become evident that members would like a clearer forward look and understanding of plans in order to engage more proactively.

To complement the qualitative indicators, a quantitative indicator should be introduced to demonstrate the extent to which the CoP environment is helping to advance the reach of events and resources and give rise to collaborations and improvements to members’ work. GPI staff members should engage fully in the CoP, to ensure GPI expertise and knowledge of best practice is mobilised effectively.

Recommendation
GPI MEL Adviser to develop one or more indicators to 1) demonstrate the extent to which an enabling environment in the CoP is advancing the reach of learning, fostering collaboration and positively impacting members’ work, and 2) reflect on the quality of resources, events and collaborations.
GPI MEL Adviser to amend the Logframe to measure partnerships’ progress toward good practice in response to learning.

OUTPUT 4

This indicator was removed in the Logframe revision, as development of products or events to spearhead peer-to-peer in the international development space was deprioritised due to the impact of Covid 19. The programme will still report against this for accountability. This output does not contribute to the overall scoring of this Annual Review, as scoring is based on the current Logframe.

Logframe to April 2020

Output Title	Useful learning products on peer-to-peer partnerships generated and disseminated
Output number:		4	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR?	[If Yes, up or down?] N/A

Indicator(s)	Milestone / (June 2020)	Progress to end of March 2020
4.1. Combined number of events and learning products (cumulative)	30	NOT MET / 22 events and products by end of March 2020
4.2. % of users of events/learning products expressing they are useful	60%	NOT MEASURABLE – The survey that measures this indicator is conducted once annually, synchronised with the milestone. It was not possible to do the survey in March 2020 due to Covid 19.

Briefly describe the output’s activities, and provide supporting narrative for the score

Due to the change of Logframe in April, the number of events and products counted reflect only up until the end of March and, for that reason, the milestone is not met. The survey that informs views of usefulness could not be taken at March 2020 due to the impact of Covid 19. However, both milestones would have been exceeded if measured up to their original June target, with 34 events and learning products, and 88% of CoP members rating them useful when the annual survey was taken mid-year.

P4D has supported the evidence base on peer-to-peer partnerships through innovative tools to promote learning and adaptation, improvements to partners’ MEL approaches, and sharing and collaboration through a refreshed and growing Community of Practice. Significant events and products included a paper on ‘Adaptive Development Partnerships: Reflections on technical assistance, capacity building and institutional reform,’ presented at a December 2019 workshop GPI co-hosted, which brought together US and UK organisations to share on the theme of Capacity Strengthening in Developing Countries: Adaptive Approaches. There were a number of CoP workshops on peer-to-peer in different sectors, Lesson Learning Forums on themes such as scoping, stories of change and remote delivery, and associated guidance and session notes.

Promotion of the aid modality has advanced through high-profile donor lesson sharing events co-convened by GPI, publications such as ROLE UK’s ‘Judicial Peer-To-Peer Learning To Strengthen The Rule Of Law’, and GPI’s contributions to a forthcoming report by the Organisation for Economic Co-operation and Development’s (OECD’s) Effective Institutions Platform.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Far more has been achieved than anticipated, suggesting excellent value for money in terms of both economy and effectiveness. It is likely that even greater value could have been delivered if there were clear roles and responsibilities of platform staff in relation to the production and dissemination of learning products, which could have expanded this function beyond the CoP and proactive initiatives of the MEL team.

Describe any changes to this output during the past year, and any planned changes as a result of this review

Output 4 was removed from the Interim Logframe. Due to the change in priorities in the wake of COVID-19, programme resources were moved away from the external promotion of peer-to-peer partnerships and sharing of learning. This could create a gap in the ability of the programme to trace the quality and influence of events and resources during the interim period, particularly within the CoP.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

A more strategic approach to the generation and dissemination of learning products, linked to a strategy for building the evidence base on peer-to-peer, would have been helpful to ensure the quality and value add of products generated. There are levers to be explored beyond the CoP and the MEL team to produce and disseminate learning products – such as wider sharing of a planned core curriculum for funded and supported partners.

Recommendations
GPI P4D Senior Responsible Owner (SRO) to define roles and responsibilities of staff in sharing good practice and participating in the production and dissemination of learning products by the CoP. This work can begin in advance of programme redesign.
GPI to take a more strategic approach to the generation and dissemination of learning products, linked to a strategy for building the evidence base.

D: RISK

Overview of risk management
The risk profile of the programme has evolved since early 2020 as result of unexpected context events outside GPI’s control, which have had an impact in the operational delivery of the programme.

The overall risk profile for the programme between September 2019 and March 2020 was Medium. Risks were managed in accordance with FCDO principles, monitored by GPI and reviewed quarterly by the programme Board. Risks were identified for the categories of External Context, Delivery, Operational, Fiduciary, Reputational and Safeguarding and mitigating actions agreed including recording of risk trends. The three top risks were:

Institutional contexts not conducive for peer-to-peer engagement or reform: As the number of partnerships increased, GPI proactively put in place mechanisms, in the form of PEA and Thinking and Working Politically training for HMG partners, to embed political thinking into HMG programme’s design. Furthermore, GPI accompanied partners in missions to support in scoping and design of peer-to-peer programmes, including producing sectoral PEA to inform peer-to-peer programme delivery.

P4D partnership providers unable to source skilled experts to deploy as peers: Interest in HMG to provide peer-to-peer support to partners overseas grew as evidence started to emerge that this aid modality was effective in advancing HMG’s international priorities. GPI commenced discussions with new HMG bodies to agree new partnerships on education, anti-corruption, better regulation and the environment amongst others.

GPI adequately resourced to deliver the functions of a Partnership Platform: Staff recruitment to fill all vacancies remained a challenge but there have been successes to bring in new staff. Resourcing was in an upward trend with positive expectations to match the scaling up of the programme with adequate human resources to manage the demand for the programme support. The programme utilised Deployable Civilian Experts (DCEs) well to respond to gaps in support to partners but was less responsive to the capacity challenges of internal programme management and MEL.
[note] DCEs are technical experts recruited short-term from the private sector, to deliver specific tasks rapidly

P4D was affected by the outbreak of the pandemic near the end of the first quarter of 2020, when in-country support ceased due to FCDO travel advice. New remote methods were explored where partner countries’ post-Covid priorities and digital resources allow. GPI worked closely with partners to mitigate risk through appropriate prioritising of activity and messaging to counterparts. Lack of a portfolio-level risk register at the time meant that there is no formal record of the management of this risk. When the programme risk register was updated, the risk profile remained medium.

The risks to the programme as result of Covid 19 and the ODA prioritisation process have changed post March 2020. The main risks are:

- The programme is unable to be sustained long-term due to decrease in resources.
- Progress in delivery slows down as result of remote support and difficulties of partners to access technology.
The risk management framework of P4D is in the process of being revised to once again respond to the Context changes effectively and to mitigate any other risks. GPI is engaging in FCDO processes to ensure the future P4D programme responds to new international priorities on state capability and is resourced adequality to support that mandate. While the current risk rating is moderate, the expected outcome of this process might mean that the overall risk profile for P4D could increase to Major.

Recommendation
GPI to develop a P4D risk framework, ensuring it aligns with the new FCDO risk framework.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency

FCDO GOSAC has oversight for P4D delivery. GPI is the management agent responsible for the programme leadership, partnerships management, monitoring evaluation and learning, responding to demand, raising awareness and communicating about P4D. The key cost drives for the Partnerships Platform operated by GPI are management costs and assignment costs.

Management costs include staff salaries and administrative costs (management of funding to GPI); and monitoring and evaluation costs. Assignment costs are activity costs of running P4D such as the supply and demand of institutional expertise, quality assurance of partnerships established, monitoring and evaluation, training, pre-deployment support, in-country support and links to international learning on partnerships programming.

Staff costs constitute most of the spending in P4D as provision of UK expertise is at the heart of peer-to-peer as an aid modality.

GPI Performance

GPI’s programme management performance has been assessed regularly through quarterly reporting to the P4D Board chaired by GOSAC. At the Board, GPI has reported on progress against results, key achievements, risks and challenges. During this AR period, and due to Covid-19, GPI’s engagement with GOSAC has been frequent in order to adapt the programme effectively to the change in context.

A Ministerial champion within the home Department, to build awareness internally of the programme, its rationale and its offer, could have helped shape strategy and supported links into sectoral and regional levers and wider FCDO policy.

Programme management for P4D is complex as GPI and FCDO hold different levers, and partners can be uncertain of their respective roles. There has also been inconsistency in the definition of roles and responsibilities for the GPI programme manager role across different partnerships, and different perceptions among partners of what the respective roles of the programme manager and advisors should be.

Demands on project management outstripped GPI’s ability to recruit in time, which was then subsequently paused due to ODA prioritisation. This meant programme management was stretched limiting GPI’s capacity to focus on risk and information management. The unfilled vacancies in the platform’s MEL, programme management and communications functions created risks for GPI’s delivery, which has operated at 75% of its planned capacity. Direct delivery and supported partnerships could have been managed in a more integrated way.

Total expenditure for GPI during the last financial year was £1,613,715. The costs included staff, activity and ‘Deployable Civilian Expert’ (independent consultants, typically ex-public sector) expenditure.

		19-20 actual	20-21 - Q1 actual	Total
Partnerships Platform	DCE costs	£216,496	£12,638	£229,134
	Staff costs	£913,507	£259,537	£1,173,044
	Activity costs	£129,559	£2,661	£132,220
	Other	£79,317	-	£79,317
	Total	£1,338,879	£274,836	£1,613,715

DCE overspend in 2019/20 reflected the need to meet demands that could not be met due to civil service staffing gaps or recruitment delays. The activities underspend was partly due over-forecasting due to a technical system error, compounded by many Q4 19/20 activities being postponed to Q1 20/21 and then cancelled due to the impact of Covid-19.

Partnership Performance: Funded Partners

Most funded programmes represent value for money. Total expenditure for the funded partnerships during the last financial year was £4,973,579. The total cost per funded partnership (staff and activity costs) is included in the table below. Funded partners made concerted and often successful efforts to adapt to remote delivery during Covid-19. For example, BGS made excellent progress against output indicators, given the impact of COVID-19 on delivery, substantially exceeding its milestones for two out of three indicators for its output on establishing information management systems, and exceeding one for the output on capacity building’. GDS substantially exceeded two out of three indicators for the Output ‘Well-targeted, quality peer-to-peer training and coaching provided to civil servants’. OPF received an excellent independent review. ROLE UK has produced a number of learning resources circulated within the Community of Practice.

Aspects of the NCA partnership have, however, been problematic. While there has been some excellent work in NCA’s Kenya partnership, and improvements in terms of programme management through direct work with the International Liaison Office in-country, the partnership in Nigeria did not show much progress due to saturation of the field with many international agencies competing for the work. As such, the Nigeria partnership did not represent value for money in terms of P4D’s objectives and the post was not renewed. The Tanzania post was in its infancy and just gaining momentum prior to Covid and having to return to the UK.

		19-20 actual	20-21 - Q1 actual	Total costs per partnership
Funded Partners	GDS	£610,734	£319,797	£930,531
	BGS	£841,784	£117,884	£959,668
	NCA	£757,972	£137,000	£894,972
	ROLE UK	£1,008,268	£163,628	£1,171,896
	OPF	£795,490	£221,022	£1,016,512
	Total	£4,014,248	£959,331	£ 4,973,579

Spend across funded partnerships was largely in line with forecasts until Q4 of 2019/20. Overseas activity that was forecast in February and March was cancelled as a result of evolving travel restrictions or additional requirements from Covid-19. These changes were often at late notice and too late to adjust forecasts. The NCA overspend is a reflection of delays in receiving the relevant information as highlighted in the programme management section.

Financial Year 20/21 Q1 overspend across several partners resulted both from cautious forecasting on potential activities which were highly dependent on access to international counterparts, and from bringing other activity forward to compensate for that reduced international work, that increased costs that were not originally planned. The NCA underspend resulted from lower than expected end-of-posting costs for the departing Nigeria ILO. For ROLE UK, activities involved pro-bono work by serving Judges or Solicitors, who had to prioritise UK commitments by avoiding the risk of additional travel requirements and or quarantine because of the pandemic. This contributed to their underspend.

Value for Money

The use of a relatively low-cost modality to achieve institutional reform objectives represents good value for money. Overall, P4D achieves economies of scale as it reduces costs for the UK in partnerships programming and enables cross-sector learning for the UK and internationally. The main benefit of the P4D programme is the delivery of the Partnerships Platform, which is a ‘one-stop shop’ for the coordination, lesson learning and development of peer-to-peer partnership programmes. The use of civil servants to deliver the programme has also improved Value for Money (VfM) compared to the original business case.
Many FCDO offices overseas, including in Rwanda and Ghana, and other FCDO teams in the UK are recognising peer-to-peer partnerships as a valuable aid modality.
Economy
GPI, and its funded partners, represent very good value for money when compared with private consultants providing traditional technical assistance. The use of GPI as the implementer of P4D, means that the Partnership Platform salary costs are harmonised with civil service salaries, and public bodies such as NCA and BGS have comparable rates. DCEs have been utilised to cover staff and skills gaps, but at competitive rates signed off through the appropriate procurement channels and following a clear set of criteria to ensure that deployment contributes positively to efficiency and effectiveness. / ROLE UK leverages an excellent return on investment from the value of the legal and judicial advice and assistance provided for free. Since April 2015, legal and judicial experts have delivered nearly 3,000 pro bono days, conservatively valued at £5.7m with over 600 days (equivalent to £1.3m) being delivered since the last P4D Review. The NCA officers deployed under P4D are hosted by the OneHMG platform, which takes advantage of economies of scale. / OPF is the exception, where daily rates are charged at competitive commercial rates for its headquarters staff, although fellows’ salaries are benchmarked against FCDO salaries. Fellows salary is covered by their Ministry and they are considered local civil servants, although the programme provides a supplement with overseas allowances e.g. cost of living etc. / Oxford Policy Fellows are the equivalent to a trainee lawyer at a competitive city firm, which is on average £35,000 per annum compared to the Fellows’ salary provided by their governments, plus supplementation, equals £26,000 per annum. A consultant with the same five years’ experience working on a full-time, long-term basis would cost £77,000 per annum in basic salary, not including allowances, medical or other associated costs. A Fellow represents exceptional value for money for host governments, with one embedded Fellow in government a year costing the equivalent to the cost of two months of short-term senior-level legal support. A full year of this support would cost the equivalent of approximately £350k of commercial legal services. / Partners have worked to minimise travel and accommodations costs – for instance, OPF has strong assurance processes to prevent overspending by fellows and combines events so as to streamline travel costs for attending parties.
Efficiency
The Partnerships Platform has allowed for streamlined MEL and programme assurance frameworks, and upskilling provided to funded and supported partnerships to be able to better deliver their work. It has also allowed UK Public Institutions that wish to set up an international peer-to-peer team to access relevant expertise and assistance, making the process more efficient. The Community of Practice has begun to create an extended infrastructure for mutually supportive relationships and coordination among peer-to-peer practitioners. GPI has also contributed to efficiencies in FCDO country offices through its relationship and knowledge brokering roles, and by handholding new partnerships toward reduced reliance on resource at post. Moves to further align partnerships with country objectives should build further efficiencies. / GPI uses the Stabilisation Unit’s ‘gold-standard’ deployments and security mechanism at no cost to the programme, enabling GPI access expertise as needed. The funded partnerships manage their own deployments and security processes directly. / ROLE UK has minimised event costs by securing pro bono venue and catering support. To progress work, GDS has where necessary filled resource gaps using expertise from among existing GDS staff. The NCA has supported an asset recovery case in Kenya worth far more than the investment in the programme.
Effectiveness
Over the last year, GPI has improved the strategic coherence of the partnerships it manages by ensuring work in a particular country aligns well with the priorities for development of that country, there is understanding of the local context, as well as the UK expertise is integrated across sectors. GPI has been supporting partners with PEA analysis and other tools to ensure delivery of peer-to-peer support is effective in responding to the capacity building needs of the beneficiary. This has been evidenced in the Stories of Change collected. / Despite positive FCDO and partner feedback on the Partnership Platform, the number of partnerships being brokered has sometimes exceeded capacity to provide timely support. / BGS performed well given the impact of COVID-19 on delivery, though effectiveness could be improved by closer attention to risk in individual partnerships. GDS offered good value during a challenging first year, and the NCA ILOs are seen by post as delivering excellent value. However, the partnership in Nigeria has not shown progress and did not represent value for money in terms of P4D’s objectives. OPF received an excellent independent review during the year and a number of country counterparts spoke publicly about the contributions fellows made to their Covid-19 response.
Equity
In line with last year’s recommendation to systematically consider gender implications, a gender working group was initiated and a gender framework was produced. / Both BGS and GDS focus on ensuring the right audience attends their courses / training and that gender is taken into account for participants to provide equal representation as possible. / With GDS, there work is designed to reach wider audiences such as women, children or those with disabilities that may not be able to access information due to family commitments / cultural expectations etc. While the partnership with Columbia demonstrated the importance of structurally competent IT systems etc, we have only just finished the first year and C-19 has impacted the scope of the programme, so there are not any demonstratable results at this time.

The lowering of ambition within the Logframe, while justified by temporary constraints, showed a reduction in value delivered against the programme objectives.

P4D’s effectiveness would be improved by timely matching of support to identified needs, a focus on quality over quantity of partnerships, work to understand partners’ work at an earlier stage, and processes to ensure advisors have the behaviours and skills to use a peer-to-peer approach effectively and in a context-sensitive way. FCDO country staff suggested GPI focus on partnerships that are clearly aligned with FCDO country objectives and of a sufficient scale to deliver results that further those objectives. GOSAC and GPI should take on board these lessons of what works into the future P4D programme, and to develop its understanding of the costs, benefits and risks of different instruments and levers for partnerships.

Recommendation
Building upon the evolution of P4D from a supply to a demand led programme, the next phase of P4D should be for GOSAC and GPI about deepening strategic partnerships around country priorities on state capability.
GOSAC and GPI should consider the importance of appropriate scale and alignment with country objectives in the redesign of the P4D programme.
In designing the future P4D programme, a cost analysis should be done by GOSAC and GPI to consider the benefits and opportunities as well as the risks of using different instruments and levers to deliver improved results as part of building upon a flexible and agile facility able to mobilise quickly to create entry points for the UK on international priorities around state capacity. These could include the use of embedded advisors, short-term interventions and targeted direct delivery.

Date of last narrative financial report	30 September 2020	Date of last audited annual statement	31 March 2020

ANNEX 1: Original Logframe and Interim Logframe Impact and Outcome Indicator Overview

Pre-Covid19	Post-Covid19
IMPACT
Wider partnerships sustainably strengthen institutions, with the UK seen as a centre of P2P excellence: / Indicator 1: % of people accessing P4D learning products subsequently utilising learning to support partnerships to deliver strengthened institutions / Indicator 2: Number of tangible examples of non-P4D supported partnerships strengthening institutions with evidence of contribution from UK-supported interventions (cumulative) / Indicator 3: Number of examples of the UK being perceived as a leader in this space through substantial invitation to advise. (cumulative)	No change.
Rationale: Due to the limitations of Covid19, the programme was unable to continue external engagement with the international development community on peer-to-peer partnership practice. However, the programme will still report against this indicator as it was agreed that for accountability impact level would not be changed.
Strengthened partner country institutions, through P4D partnerships / Indicator 1: Number of tangible examples of P4D (funded/direct delivery) peer-to-peer partnerships resulting in improved institutional functioning (IF), and number of these that are significant (S) (cumulative). / Indicator 2: Number of contribution stories demonstrating P4D (funded/direct delivery) partnerships' contribution to observed change (cumulative)	Counterpart institutions are strengthened and more resilient, including to the effects of Covid-19: / Indicator 1: Number of tangible examples (with contribution analysis) of P4D (funded/direct delivery) peer-to-peer partnerships resulting in improved institutional resilience and strength (IRS) given the covid-19 context. / The indicator is split in terms of change anticipated as a result of Funded Partners (FPs) and Direct Delivery (DD).
Rationale: Due to restrictions in travel we are limited in being able to produce stories of change (this requires face-to-face interviews), therefore the programme created an overarching indicator which will produce a number of tangible examples (with contribution analysis) that shows how P4D has supported institutional resilience, whilst being sensitive to the C-19 context.
OUTCOMES
Partnerships seen as an effective aid approach, with a more detailed understanding of effectiveness dynamics / Indicator 1: Types of positive perception of peer-to-peer working influenced by P4D work / Indicator 2: Number of lessons (L) and/or ideas (I) generated and learned on 'what works' in peer-to-peer partnerships (cumulative)	Developed learning on what works in peer-to-peer working in a crisis / Indicator 1: Meaningful instances of CoP members sharing learning within the community (learning here is considered both delivery of a learning piece or experiences and more interactive situations such as collaborative problem-solving) / Indicator 2: Meaningful instances of CoP members using learning from fellow members / Indicator 3: Number of lessons (L) and/or ideas (I) generated and learned by the P4D programme on 'what works' in peer-to-peer partnerships, including while operating in covid-19
Rationale: The perception analysis indicator was removed due to limitations in being able to do this from travel restrictions and also resource lack.
Partnerships develop to be functional and sustainable / Indicator 1: Proportion of P4D partnerships (funded and direct delivery only) advancing to level 5 in a capacity / Indicator 2: Proportion of P4D partnerships (funded and direct delivery only) advancing through levels / Indicator 3: Number of tangible examples of supported partnerships (wrap around support) improving ways of working (cumulative)	Partnerships are maintaining healthy relationships and delivering workstreams effectively / Indicator 1: Proportion of P4D partnerships (funded and direct delivery only) advancing to, or maintaining, an average of Level 3-4 in their PCA criteria / Indicator 2: Number of tangible examples of supported partnerships (wrap around support) improving ways of working (cumulative)
Rationale: It was considered unreasonable given the restrictions on travel and resources to expect partnership health to have improved in the current environment. Therefore, we have reassessed what would be a good result in this circumstance and are targeting the maintenance or growth of our partners ability to maintain an average 3-4 in their Partnership Capability Assessments.
CoP is utilised as a lesson sharing mechanism / Indicator 1: Number of tangible examples of CoP members utilising, generating, or sharing lessons as a result of CoP participation (cumulative) / Indicator 2: % of CoP members utilising CoP to learn or share lessons / Indicator 3: Number of tangible examples of CoP members collaborating as a result of CoP participation (cumulative)	Developed learning on what works in peer-to-peer working in a crisis / Indicator 1: Meaningful instances of CoP members sharing learning within the community (learning here is considered both delivery of a learning piece or experiences and more interactive situations such as collaborative problem-solving) / Indicator 2: Meaningful instances of CoP members using learning from fellow members
Rationale: We removed the indicator on % of active CoP members due to the changes in staff through surge and other Covid19 related absences. / The shift from tangible examples to meaningful instances is that meaningful instances allows greater flexibility and reduces the resource demand for writing up examples.
Strengthened evidence base for peer-to-peer partnerships as an aid approach / Indicator 1: Number of tangible examples of users interacting with learning products/events developed through or as a result of P4D (cumulative)	Indicator removed.
Rationale: This indicator was removed as due to the restrictions on travel and resource P4D are no longer prioritising developing products or events to spearhead peer-to-peer in the international development space. However, the programme will still report against this for accountability.

ANNEX 2: List of Acronyms

A4ID	Advocates for International Development
BoE	Bank of England
BGS	British Geological Survey
CoP	Community of Practice
DCE	Deployable Civilian Experts
DfE	Department for Education
EFCCC	Ethiopia’s Environment, Forest and Climate Change Commission
FCDO	Foreign, Commonwealth & Development Office
GDS	Government Digital Service
GoM	Government of Montserrat
GOSAC	FCDO Governance, Open Societies and Anti-corruption Department
GPI	Government Partnerships International
HMG	Her Majesty’s Government
HMRC	Her Majesty’s Revenue & Customs
ICAI	An Independent Commission for Aid Impact
ILO	International Liaison Officer
KSH	Kenyan Shilling
MDG	Tajikistan Ministry for Development of Geology
MEL	monitoring, evaluation and learning
MERL	monitoring, evaluation, research and learning
NCA	National Crime Agency
NDGC	Kenya’s National GeoData Centre
ODA	Overseas Development Assistance
OECD	Organisation for Economic Co-operation and Development
OFGEM	Office of Gas and Electricity Markets
OGD	Other Government Departments
OPF	Oxford Policy Fellowship
PCA	Partnership Capability Assessment
P4D	Partnerships for Development
PEA	Political Economy Analysis
ROLE UK	Rule of Law Expertise UK
SRO	Senior Responsible Owner
ToC	Theory of Change
TWP	Thinking and Working Politically
UToC	Useful Theory of Change
VfM	Value for Money

Annex 3: Responsiveness of Partnerships Sentinel Scale
Level 1	Partnership is unresponsive to the nuances produced by the C-19 crisis including: counterpart needs, delivery risks and environmental considerations. This may look like a provider prescribing covid-19 work when a counterpart instead needs a continuation of previous work, or vice versa, or not engaging with counterparts at all. The provider will have no documentation/evidence to show consideration of: risks, suitable mitigating actions, country and global political economy.
Level 2	Partnership is relatively unresponsive to the nuances produced by the C-19 crisis including: counterpart needs, delivery risks and environmental considerations. This may look like a provider pushing covid-19 work when a counterpart instead needs a continuation of previous work, continuing work when a counterpart may find covid-19 response work more useful, or perhaps suggesting a workstream that doesn't quite fit counterpart needs. The provider might have documentation to show a little consideration of; risks, suitable mitigating actions, country and global political economy.
Level 3	Partnership is relatively responsive to the nuances produced by the C-19 crisis including: counterpart needs, delivery risks and environmental considerations. This could look like a provider working with counterparts on work that aligns with request (whether that be continuation of previous work or covid-19 work), but that doesn't quite fit all aspects of the request. The provider will have considered some of: risks, suitable mitigating actions, country and global political economy and has appropriate documentation of where they have done so.
Level 4	Partnership is fully responsive to the nuances produced by the C-19 crisis including: counterpart needs, delivery risks and environmental considerations. This would be a partnership that works with a counterpart on their requested work in full alignment (either continuation of previous workstream or covid-19 work) and adapted where necessary. The provider will have considered all of: risks, suitable mitigating actions, country and global political economy and has appropriate documentation to show how they have informed this decision.

Annex 4: Sentinel Scale for Quality of CoP Activity
Level 1	• Communications about the CoP are unclear about the nature and purpose of the community and its activities. • Notifications of events are last minute, or non-existant, and any messaging lacks clarity and purpose. • Events are designed and delivered without participation from community members and without alignment to an identified need or interest • Resources are shared without clarity as to their nature and purpose • Resources are not shared and not hosted anywhere accessible. • CoP communication does not support the development of networks and coordination between practitioners. • CoP Activity fails to offer any fully accessible spaces/opportunities where members can interact and communicate.
Level 2	• Communications about the CoP are sometimes unclear about the nature and purpose of the community and its activities. • Notifications of events are sometimes sent out with good notice and description, but may also be last minute, or non-existant, lacking sometimes in clarity and purpose. • Some events are aligned to an identified need or interest. • Events are for the most part led by P4D practitioners, but some are designed and delivered with participation from community members. • Some resources are shared with clear reference to their nature and purpose. • Resources are sometimes shared and sometimes hosted somewhere accessible. • CoP communication seldom supports the development of networks and coordination between practitioners. • CoP Activity offers some spaces/opportunities where members can interact and communicate, but these are not fully accessible or limit interaction and communication.
Level 3	• Communications about the CoP are fairly clear about the nature and purpose of the community and its activities. • Notifications of events are generally sent out with good notice and description, and are usually purposeful and clear. • Events are generally held in response to identified community needs or interests. • Events may often be led by P4D practitioners, but are generally designed and delivered with some participation from other members. • Resources are mostly shared with clear reference to their nature and purpose. • Resources are generally shared and where possible hosted accessibly. • CoP communication occasionally supports the development of networks and coordination between practitioners. • CoP Activity offers some spaces/opportunities where members can interact and communicate, which are relatively accessible and allow interaction and communication.
Level 4	• Communications about the CoP are fairly clear about the nature and purpose of the community and its activities. • Notifications of events are sent out with good notice and description, and are purposeful and clear. • Events are held in response to identified community needs, anticipated needs, or interests. • Events are designed and delivered in a participatory manner, and led by a blend of P4D and other member practitioners, with external expertise tapped when relevant. • Resources are shared with clear reference to their nature and purpose. • Resources are always shared and where possible are hosted on accessible platforms. • CoP communication regularly supports the development of networks and coordination between practitioners. • CoP Activity offers spaces/opportunities where members can interact and communicate, which are accessible and allow interaction and communication.