Programme Memorandum / Support to / South Africa’s Shared Growth Strategy / January 2009 / Final Version

TABLE OF CONTENTS

SUMMARY

1. PROGRAMME DETAILS
  1. Programme Description
  2. Programme Appraisal
Background
Approach
Economic Appraisal
Social Appraisal
Institutional Appraisal
Political Appraisal
Environmental Appraisal
Fiduciary Risk Assessment
  1. Lessons and Evaluation

1. IMPLEMENTATION
  1. Management Arrangements
  2. Timing
  3. Funding
  4. Contracting and Procurement
  5. Accounting and Audit
  6. Monitoring and Reporting

RISKS

CONDITIONALITY

ANNEXES
Annex A:	Logical Framework
Annex B:	Risk Matrix
Annex C:	Environmental Screening Note
Annex D:	Consultation Record
Annex E:	Project Header Sheet
APPENDICES
Appendix A:	Matrix of Existing Donor Support to Growth and Employment to South Africa
Appendix B:	Key Performance Indicators for EC Employment Creation, Sector Policy Support to the Economic Cluster Programme of Action
Appendix C:	Fiduciary Risk Assessment: DFID Support to South Africa’s Accelerated and Shared Growth Initiative (Growth Strategy), November 2008
Appendix D:	Full Economic Appraisal

PROGRAMME MEMORANDUM
1. SUMMARY
  1. The ‘Support to South Africa’s Shared Growth Strategy’ programme aims to support the Government of South Africa’s (GoSA) in the implementation of its strategy for bringing about faster ‘inclusive’ growth. Specifically, the programme will strengthen the ability of the Economic Cluster (EcCl), the principal institutional mechanism within GoSA for ensuring Line Department co-ordination on economic matters, to deliver on its ‘enhanced Programme of Action’ (ePoA). The ePoA is an instrument within government designed to increase inter-departmental coordination and enable better monitoring by officials, Minister and Cabinet, including on the Growth Strategy.
    [note] Inclusive growth is growth associated with significant reductions in poverty.
  2. Funds will be used flexibly to support individual projects agreed by the EcCl as well as staff and capacity building in the EcCl itself. Such support to the EcCl will enable it to work closely with GoSA Line Departments to prepare innovative policies, programmes and pilots that help to unblock constraints to growth and create more jobs. Consequently, the programme should be able to enhance the incomes and improve the livelihoods of the significant number of people currently living in poverty in South Africa.
    [note] Data on poverty in South Africa is patchy. Figures collated in the IMF Article IV report for 2008 provide an estimate for poverty, measured at less than $2 per day on a PPP basis, of 34% of total population in 2000. This equates to approximately 15 million people.
  3. The goal of this programme is, therefore, to increase the capacity of the South African economy to deliver high and sustained economic growth. The goal will be in support of GoSA’s delivery of its own growth strategy targets, of achieving annual growth rates in excess of 6 percent annual growth, lowering unemployment to less than 10 percent, and reducing headcount poverty to less than 15 percent by 2014. The purpose of the programme is to strengthen the ability of GoSA’s Economic Cluster to implement effectively its ePoA in order to deliver on the growth, employment and poverty reduction targets.
  4. By supporting the implementation of GoSA’s growth strategy, and by strengthening the institutional mechanisms designed within GoSA, the programme aligns naturally with national strategies and plans linked to poverty reduction. It is also fully consistent with DFID’s own current policy and practise, based on a series of recent pronouncements and initiatives centred on the importance of growth as a means to deliver poverty reduction, and will help to deliver on the growth objective within the DFID Southern Africa plan. In the opening months of the programme, contact between the EcCl Secretariat and the new International Growth Centre which DFID has just established, will be facilitated, with a view to identifying any technical support the latter could offer to the implementation of South Africa’s growth strategy.
  5. In terms of the specific outputs and deliverables of the programme, DFID funds will:
  1. Strengthen institutional capacity in the EcCl’s Secretariat;
  2. Improve cross-cutting working relations between Line Departments that form part of the EcCl;
  3. Finance projects sponsored by GoSA aimed at promoting growth and employment;
  4. Improve the monitoring of the Growth Strategy and ePoA’s implementation;
  5. Encourage lesson-learning within government and communicate best practice.
  1. DFID will provide GoSA with £18 million of (non-budget support) financial aid in annual tranches over a maximum of five years, starting in January 2009. These funds will complement a package of Euro 100 million of budget support that the EC will be providing to GoSA, in support of the Growth Strategy. By providing funds in this way it is intended that donor assistance will move in the direction of greater harmonisation and support for GoSA’s own systems, and away from the somewhat piecemeal approaches that have so far been characteristic.
  2. Whilst tranches of funding will normally be provided at the start of each financial year (April-March), an initial tranche of £2.5m will be provided by end March 2009 to fund a set of pipeline projects that have been identified with partners in GoSA and agreed with the EcCl. These projects are viewed as being consistent with current policy on growth and employment generation and with what key stakeholders believe will continue to be priorities of the next government; with their focus on competitive industrial development, greater competition, government capacity building, employment generation, and skills development.
  3. A Fiduciary Risk Assessment suggested that the risks of financial mismanagement and corruption are not high. Furthermore, whilst there are political changes about to take place in South Africa, the policy priorities around growth and employment are set to continue, and so the programme’s objectives of building government capacity in this area faces manageable risks.

2. PROGRAMME DETAILS
  1. Programme Description
    1. DFID aims to support the Government of South Africa (GoSA) with £18 million over five years to support the implementation of its strategy for faster ‘inclusive growth’. This is based on the recognition by GoSA that, whilst important strides have been taken in putting in place sound macroeconomic policies in South Africa since 1994, growth has not been high enough nor has it reached all sections of society to have achieved significant reductions in poverty. GoSA is now aiming through its strategy to increase growth rates to at least 6% per annum (from 2010), and by 2014, to halve unemployment (from 30% in 2003 to 15%) and halve poverty (from about 34% to 17%).
    2. Within GoSA the growth strategy is supported by the Economic Cluster (EcCl), the principal institutional mechanism within government for ensuring Line-Department co-ordination on economic matters. It has a mandate from Cabinet to plan, design, co-ordinate and monitor actions that have a high impact on growth and employment for its member departments. While the cluster system is working well, its effectiveness is limited by capacity. This includes inadequate:
- access to flexible resources to finance small projects (research and pilots) quickly; and
- capacity to assess the technical quality of proposals;
    1. DFID’s ‘Support to South Africa’s Shared Growth Strategy’ programme will support the work of the EcCl, enhancing its coordinating capacity and specifically financing its enhanced Programme of Action (ePoA). This is designed to help alleviate critical bottlenecks to growth and employment generation in the economy. DFID funds will work flexibly alongside those of the EC, which will be provided as budget support, strengthening overall assistance to the effective implementation of GoSA’s Growth Strategy, through the ePoA.
    2. While GoSA (and EC) budgetary funding for the Growth Strategy’s ePoA will enable the mainstream-implementation of projects, DFID’s support will be for financing short-term policy processes (research, preparation of new policies and reforms, pilot-testing and the like). With such complementarity, the effectiveness of DFID’s finance should increase considerably, having an impact that exceeds significantly the value of the actual input.
    3. The goal of the programme is to increase the capacity of the South African economy to deliver high and sustained economic growth. The goal is consistent with the South African government’s growth strategy targets. The purpose is to strengthen the ability of GoSA’s Economic Cluster to implement effectively its ePoA and reach growth, employment, and poverty reduction targets.
    4. The programme will enable GoSA’s economic cluster to procure high-quality Technical Assistance and other services, leading to innovation, more coordinated joint-working and the scope for lesson learning in the areas of growth and employment creation. The specific outputs of the programme, which will also align with the indicators being used for the EC’s budget support, will include:
1. Strengthened institutional capacity in the Secretariat of the EcCl, including improvement in technical and procurement capacity and assistance with development and approval of funding proposals;
2. Improved cross-cutting working relations between Line Departments of the Economic Cluster;
3. Improved framework for monitoring of the Growth Strategy and the ePoA;
4. Lessons from projects supported having influenced the development of GoSA’s future growth strategy and poverty policies;
5. Lessons from programme implementation communicated and implemented.
    1. More broadly, funds provided by DFID will contribute to GoSA’s implementation of the Growth Strategy and the ePoA by:
- developing plans and detailed actions for generating growth and employment that can be implemented through the EcCl;
- enabling GoSA’s core economic departments to purchase high-quality Technical Assistance flexibly;
- leveraging budget support provided by the EC for promoting faster economic growth and employment-expansion;
- supporting and intensifying the pace of institutional reforms and innovation across government’s economic and social departments, and promoting more joined-up working across line departments;
- financing the implementation of experimental pilots, especially for job-creation, and the creation of productive livelihoods for poor people currently dependent on survival in the informal economy;
- supporting the work of select civil-society and private-sector organisations to take forward aspects of GoSA’s Growth Strategy;
- financing schemes for alleviating infrastructure constraints (e.g. in energy and transport);
- enabling better results-monitoring and strengthening accountability in government around the growth strategy.
    1. By strengthening the EcCl’s effectiveness and ability to coordinate line departments around the ePoA, the programme should lead to improved implementation of GoSA’s strategy for faster and more inclusive growth. This should help to improve the incomes of the roughly 15 million people currently living in poverty.

  1. Programme Appraisal
Background
    1. The GoSA has a strong commitment to pursuing a high and sustainable rate of growth in order to deliver greater poverty reduction. In line with international best practice, a growth diagnostic analysis has already been completed by a high-powered team of economists to get a better understanding of the binding constraints to growth in the country. Six bottlenecks are identified by government as being a constraint on achieving a higher rate of growth:
      [note] http://www.treasury.gov.za/publications/other/growth/default.aspx
- relative volatility of the currency;
- cost, efficiency and capacity of the national logistics system;
- shortages of suitable skilled labour, and the spatial distortions of apartheid affecting low-skilled labour costs;
- barriers to entry, limits to competition and limited new investment opportunities;
- regulatory environment and the burden on small and medium sized enterprises (SMEs);
- deficiencies in state organisation, capacity and leadership.
    1. GoSA has produced a Growth Strategy to tackle these binding constraints and to promote growth and employment. An annual growth rate of 6% per year by 2010 is regarded by GoSA as needed for achieving the Growth Strategy’s employment and poverty targets. However, while the general policy-direction for hastening growth and making it more inclusive is clearer, the mechanisms and actions that various agents need to take in translating policy directions to specific programmes for implementation is in need of being strengthened. Detailed measures, that are properly sequenced, are required to ensure that growth creates more employment and opportunities for poor people.
      [note] http://www.treasury.gov.za/publications/other/growth/default.aspx
    2. Discussions with GoSA officials have pointed to the need for a more systematic approach within government for meeting short-term TA needs flexibly, and one that relies less on donors’ ad hoc support within budget cycles. Such a mechanism within government would have the virtue of not delaying critical reforms, and would promote greater accountability. It would also enable departments to finance innovations while avoiding high transactions costs associated with securing flexible resources from donors. The programme has been designed to meet these kinds of needs.
    3. For DFID, the promotion of faster and more inclusive economic growth is one of four Ministerial priorities. DFID’s recent policy paper ‘Growth: a step change in DFID engagement’ commits DFID into helping countries to achieve rapid economic growth. Four specific objectives are identified
- placing growth at the centre of international efforts for reducing poverty;
- securing commitments from partner countries for pursuing credible growth strategies;
- supporting the formulation and implementation of such strategies; and;
- working with donors to improve the quality of support.
    1. Given the South African government’s already strong commitment for pursuing a high and sustainable growth rate for reducing income poverty, this programme focuses on the last two of DFID’s four growth-related objectives; namely: supporting implementation, and working with donors to deliver quality support. Besides the direct funding this programme will provide to GoSA, DFID SA will, in the opening months of the programme, also facilitate contact between the EcCl and the new International Growth Centre that has recently been launched.
    2. GoSA’s primary source for financing expenditure to stimulate growth, and reduce unemployment and poverty, is through its own budget. While external donors also provide support, in proportional terms this is a relatively small contribution. The EC is planning to provide €100M budget support (from March 2009) for a three-year period. The EC’s funds will supplement GoSA’s budget allocations to Line Ministries and provide additional resources for the implementation of the Growth Strategy. DFID’s funds under this programme are intended to complement and support the effective use of the EC’s funds.
    3. Under its Country Partnership Strategy for 2008-2012 the World Bank also supports the aims of South Africa’s growth strategy, including on private sector development, rural and urban development, and regional integration. Through its provision of flexible funds which GoSA, and in particular the EcCl, can use according to its growth strategy priorities, the programme will complement the activities of the World Bank on these agendas.

Approach
    1. The rationale for this programme is to support GoSA in implementing its growth strategy for more inclusive growth, and poverty reduction in South Africa by:
- strengthening capacity within GoSA to develop and implement innovative policies, programmes and projects aimed at raising economic growth and making it more socially inclusive;
- improving policy co-ordination among core Line Departments around such growth-related policies;
- leveraging the EC’s budget support so that it is aligned more effectively with GoSA’s efforts in promoting growth and creating more jobs.
    1. To achieve this, DFID funds under the programme would be channelled directly to the National Treasury, which will disburse to the relevant line departments. This is because the EcCl is the principal institutional mechanism within GoSA for ensuring Line-Department co-ordination on economic matters and for implementing the Growth Strategy priorities. The EcCl concentrates on 10 focal areas:
- creating supportive macro-economic management;
- implementing industrial policy, focusing on the main sectors and leveraging public spending;
- strengthening capacity of the economic regulator in key industries;
- amending competition policy in enforcing regulation more effectively;
- increasing access, uptake and usage of ICT infrastructure;
- extending the public transport network in phases;
- monitoring implementation and assessing the impact of the planned infrastructure spend;
- co-ordinating better the National Human Resource Development (NHRD) Strategy, with a focus on the Growth Strategy’s priorities;
- integrating small enterprise service delivery (incl. comprehensive procurement strategy, marketing cooperatives, business development support and access to finance);
- reducing regulatory burdens on SMMEs (incl. by-laws).

    1. The first two of these focus areas are aimed at promoting the growth of manufacturing output while creating more jobs; the next six concentrate on improving competitiveness and economic efficiency, and increasing investment; and the last two, on developing stronger links between enterprises in the formal and informal economies while supporting small and medium enterprises.
    2. In order to take forward its work in these areas, and for addressing the priorities of the Growth strategy, the EcCl has a three-year enhanced Programme of Action (ePoA), which is reviewed annually. Actual implementation of the ePoA’s initiatives is done by individual Line Departments, often involving joint working across several departments (e.g. on skills and training issues). The EcCl’s role is primarily to monitor and guide implementation, and promote efficiency by joining-up government. It is co-chaired by the Director Generals of the Departments of Trade and Industry and Public Enterprises, and reports to a Cabinet Committee.
    3. Under the proposed programme, instead of requests (whether for expert TA or for pilot-implementation of Growth Strategy projects) being made to DFID-SA, GoSA Line Departments would channel these requests to the EcCl. The latter, in turn, would assess the technical merits of proposals and, if necessary, would work with the applying Line Department to improve the quality of the proposal. If proposals are approved, the Secretariat would make recommendations to GoSA’s National Treasury (NT) to release funds to successful applicants.
    4. By providing the EcCl with core resources and capacity, it should be possible to meet short-term needs more systematically compared to current arrangements whereby they are often financed in an ad hoc way by external donors. A better capacitated EcCl would enable GoSA departments (responsible for economic growth) to shift gear from general policy awareness to taking specific actions. The line departments would enable such a transformation by:
- commissioning further research on the binding constraints and how precisely these might be addresses within government and the private sector;
- experimenting with various options and implementing successful pilots on a bigger scale through GoSA’s budget;
- financing local and international experts to provide advice and detailed know-how on translating policies into actions;
- ensuring critical links are maintained among the ‘political and policy drivers’ within the state and the private sector;
- ensuring (by regular reporting to EcCl meetings) departments work together in tackling cross-cutting issues, especially with regard to employment creation and creating productive opportunities for unemployed youth and women.
    1. An EcCl empowered by having access to sufficient flexible funds should help line Departments significantly in tackling the binding constraints to economic growth, and should also help to ensure that EC budget support funds are used as effectively as possible to support growth, employment and poverty reduction in South Africa. To this latter end, the programme’s logframe will align closely with Key Performance Indicators (KPIs) that have been prepared jointly between EC and GoSA officials and that are designed to capture the high level impacts intended (see appendix B).
    2. The main stakeholders in the design process have included a number of Line Departments of the EcCl; in particular: the Department of Public Enterprise (DPE), Department of Trade and Industry (DTI), Department of Labour (DoL), Department of Education (DoE), National Treasury (NT), and the Presidency. Consultations with representatives of GoSA departments have been done individually and in workshops. These suggested, almost unanimously, a preference for a financial disbursement arrangement through government systems. Equally unanimously, however, was a clear preference for an arrangement that is quick, provides flexibility, is responsive, supports innovation, is not bureaucratic, and encourages relations being both cross-departmentally and with civil society.
    3. DFID has also consulted other project partners from existing growth and employment related programmes, including representatives from business and organised labour. Their general views echo the need for a quick, flexible and responsive facility that will engage inclusively with business and organised labour.
    4. In the donor community detailed consultations have been held with staff from the EC and with members of the Employment Creation Donor Working Group. Both this programme and the EC’s programme have been designed to complement each other.

Economic Appraisal
    1. There are many studies showing the powerful role that can be played by economic growth in reducing global poverty. This role can manifest itself through direct effects, generating increased employment opportunities and raising levels of income for the poor, as well through indirect effects, by, for instance, increasing the revenues available to governments for targeted social spending. Assuming the EcCl is able to galvanise the set of policy-actions needed for easing binding constraints to growth, which in turn would work to raise the real growth rate (and reduce poverty), the international evidence on the benefits of growth suggests this programme should potentially be a good use of donor funds.
      [note] World Bank and DFID research shows in the last 15 years 80% of poverty reduction was due to economic growth, with 500 million people being lifted above the poverty line.
      [note] The binding constraints have been identified as being i) relative volatility of the currency; ii) cost, efficiency and capacity of the national logistics system; iii) shortages of suitable skilled labour, and the spatial distortions of apartheid affecting low-skilled labour costs; iv) barriers to entry, limits to competition and limited new investment opportunities; v) regulatory environment and the burden on small and medium sized enterprises (SMEs).
    2. The EcCl has a fundamental role to play in creating the appropriate conditions and providing guidance on how best growth’s binding constraints can be eased (through analysis, policy, pilots, programmes, communication and monitoring). Given that the EcCl is at present relatively under-resourced, and is therefore constrained in its ability to foster innovative policy approaches, DFID support, combined with that of the EC, should be crucial in enabling the cluster to pioneer the work required to steer South Africa towards a higher growth path (towards the Growth Strategy 6% per annum target) and to create more jobs and opportunities for the unemployed.
    3. Given the indirect ways in which this programme will provide support to GoSA it is difficult, however, to place a quantitative estimate on the expected returns – i.e. to estimate an economic rate of return for the £18 million investment. This is because of the varied nature of the outputs, the experimental nature of some elements of the programme, and the range of uncertainties that necessarily will be associated with translating inputs to outputs. And it is even more difficult to attribute specific significance to this project, given the multiplicity of factors involved in accelerating growth.
    4. Recent unpublished analyses make it possible to provide approximate estimates of the probable magnitude of impact arising from DFID’s support. In particular, econometric work has been carried out to consider whether, and by how much, DFID-supported projects might lead to generating additional growth, employment, and poverty reduction. A Computable General Equilibrium (CGE) approach has been used to model the effects of implementing policy changes in lifting the binding constraints to growth. See the full Economic Appraisal at Appendix D for more details.
      [note] This is based on two sets of analyses prepared for DFID by (a) Quantec ‘Estimating the Potential Impact of the DFID programme on Growth and Employment: A CGE Analysis’; (b) Haroon Bhorat and Carlene van der Westuizen, University of Cape Town’s Development Policy Research Unit (DPRU).
    5. The estimation of impact is modelled under three scenarios, each of which assumes a different magnitude of improvement over baseline forecasts from the South African National Treasury:
      [note] Note that the modelling of these shifts precedes the current financial crisis and the cumulative effects of the changes may be over-stated if the financial crisis has a significant impact on South Africa’s growth. This does not, however, change the thrust of the overall argument.
- GDP growth increases by an additional 0.3% per annum (under scenario 1) to 0.60% per annum (under scenario 3);
- Employment (for unskilled, semi-skilled and skilled labour) over the five year period rises by 340,000 (under scenario 1) to 695,000 (under scenario 3);
- Average annual wages experience modest rises in the range of 0.01% (under scenario 1) to 0.63% (under scenario 3).
    1. Increases in GDP growth should translate to reductions in poverty, but this depends on the poverty elasticity of growth (that is the percentage change in reducing poverty from a one percent increase in growth). Because of high inequality in South Africa, the transference of gains from growth to social benefits is weaker than that suggested for other developing countries. None the less, the figures suggest that the programme could help to bring about significant reductions in poverty by raising the growth rate and would be a good use of donor funds. Moreover it is more likely to achieve these kinds of effects through the leverage it can be expected to have on the larger amounts of resources the EC will providing for Growth Strategy implementation in the form of budget support.
      [note] The estimates suggest that, using a poverty line of R322 per month, poverty headcount could be reduced by between 2.99 and 3.17 percentage points against a baseline of a 2.81 percentage point reduction whilst, using a poverty line of R174 per month, poverty headcount could be reduced by between 4.13 and 4.36 percentage points, compared to a baseline of a 3.9 percentage point reduction.
    2. In addition, a key part of this programme will be its support for the creation of new policy approaches aimed at transforming the patterns of growth towards those that are more likely to generate employment and economic opportunity for the poor. This would include a range of efforts to promote greater integration of the ‘second economy’, policies to tackle skills shortages of the unemployed, measures to promote better environments for smaller businesses and so forth. As part of the preparation for this programme, DFID has been supporting GoSA’s development of its plans to tackle the challenges of the 2nd economy. The gains that could be made from achieving these kinds of structural shifts in the South African economy, in terms of poverty reduction, could be immense.

Social Appraisal
    1. Poverty and inequality are two of South Africa’s most critical social challenges. Deep-seated inequalities are a direct result of racial and economic distortions generated under Apartheid. For the majority of the population, Apartheid not only blocked off opportunities for non-whites to accumulate land and capital, but it also restricted opportunities for business and professional development. However, poverty is not simply a legacy of the past. It has also been perpetuated by features of the post- transition order (du Toit and Neeves, 2007).
    2. The incidence of income poverty seems to have increased from 1993 to 2000 (Seekings 2007), but decreased from 2001 to 2006. Poverty, however, remains widespread and is concentrated in the Eastern Cape, KwaZulu-Natal and Limpopo and among African and Coloured populations (IPC 2007). Looking more broadly at well being, the human development index has declined since 1994, when South Africa ranked 90th globally, to 121st in 2004 – explained by plummeting life expectancy due to AIDS. And whilst poverty may have reduced, income inequality has not, mainly because of rising inequality within race groups. At the top end, 20 percent of the population earns 72.5% of total income and the richest 10 percent gets 56% of total income. In contrast, the poorest 10 percent gets 0.6% of total income, and the poorest 20 percent, 1.7% of total income (ref).
      [note] It is difficult to analyse poverty trends in South Africa because of differences between and weaknesses in core data sets. In addition the apartheid state never collected data on poverty among African people.
    3. Structural inequalities – such as educational backlogs amongst the poor – are reinforced through the workings of the labour market. The poor have less education and cannot therefore find jobs, and where they do wages are low. In 2003, almost one third of employed South Africans reported earnings lower than the statutory minimum wage for a domestic worker (Seekings, 2007). On the basis of the current path of South African economic growth, it is likely that the economy will continue to favour more employment for skilled and educated workers, while the demand for unskilled workers will decline. There is considerable consensus that future growth in South Africa should primarily be about creating jobs for the 57.4% of the working population that are currently not meaningfully employed. Until now, the expansion in social assistance grants has been the main factor in poverty reduction (van der Berg, Louw, du Toit 2007).
    4. The programme therefore has a potentially very important role to play in stimulating both stronger growth and a pattern of growth that is more beneficial to the poor, promoting employment and other opportunities for them. DFID funds have the potential to be used by the EcCl to find innovative policy approaches that can promote a better integration of the economically marginalised, including those living in the former homelands.
    5. DFID’s support, under the programme, to an improved framework for monitoring the Growth Strategy (output 3) and communicating and implementing lessons from the programme’s implementation (output 4) will be key to understanding how and the extent to which GoSA’s Growth Strategy is achieving its poverty reduction objectives and who among the poor are benefiting.

Institutional Appraisal
    1. South Africa’s transition to a constitutional democracy has had fourteen years within which to develop policies and institutions for reducing poverty. Experience to date shows many positive features of this transition: state structures have a strong capacity to formulate sound social and economic policies (though service delivery systems exhibit structural and systemic weaknesses); there is a well-functioning legal and democratic framework in place; and there is considerable space for civil society to hold government to account.
    2. South Africa’s institutions for ensuring good economic management are robust. These include the National Treasury, various departments of the ‘economic cluster’ (including the Department of Public Enterprises, the Department of Trade and Industry, the Department of Minerals and Energy), the South African Revenue Service (SARS), the Competition Commission (an agency of DTI) and various economic analysis and research organisations outside of government. As a result, the ANC-government has managed to establish a policy framework, especially a solid macroeconomic policy, conducive for growth and poverty reduction.
    3. Co-ordination among GoSA departments responsible for economic policy-making and implementation in some respects is rather good. For example, the EcCl brings together each month the DGs or their representatives of 18 Ministries responsible for economic management and is jointly chaired by the DPE and the DTI. Despite this, there are occasional reports of government departments failing to coordinate adequately. Progress in last year’s mid-term assessment for implementing the Growth Strategy was regarded as being slower by the Deputy President because of weak links between certain departments. This is a potential weakness that the programme will need to address if it is to succeed in its aims and it is suggested that specific measures be identified.
    4. There is a reasonable degree of confidence in government’s ability to translate policy into deliverable actions, and while management and implementation problems exist, the institutional environment is one which allows concerns to be articulated and solutions found. A recent example of this is the official response to the emerging energy crisis, in which the government showed a willingness to listen and work with partners in finding a way forward.
    5. While there are many areas of strength in South Africa’s institutions, there is also evident strain across all three spheres of government. These are largely the result of administrative inefficiencies that lead to poor execution and capacity inadequacies due to a lack of trained staff. The strengthening of capacity (among other things) being targeted by the programme through the EcCl should help address some of the current bottlenecks and difficulties encountered in translating policies into actions. Key areas where this programme might help are: procurement, technical expertise, project and programme design, cross-departmental working to address skills and employment issues, and project management.
    6. The Directors-General of projects receiving support will sign an agreement outlining the project’s key deliverables, milestones and agreed measures of success. Capacity to monitor and evaluate projects that are awarded funding is to be improved as part of the strengthening of the EcCl Secretariat.
    7. A further issue concerns the lack of absorptive capacity of many of the departments within the economic cluster for the funds that they receive. This could cause problems for the effective disbursement and spend of funds that would be made available under this programme. Again, this should be considered with the EcCl Secretariat during the programme.

Political Appraisal
    1. Of potential concern to this programme is the relative shift in policy emphasis that may arise out of the decisions of the ANC Conference in December 2007. While partially successful in creating a favourable climate for investment, government’s prudent macro management has attracted criticism from labour unions and civil society groups frustrated by the state’s perceived inability to reduce poverty through its current economic strategies. While a complete overhaul of the current policies under a new government is unlikely, what is possible is a shift towards more direct measures for reducing poverty (largely through higher government spending on social grants) as well as a more developmental state that will pursue an active industrial policy. The proposed programme’s flexibility, however, should allow for any adaptation required in the selection of projects in response to key changes in policy.
    2. Social frustration with levels of service delivery and job creation has been evident in recent violent xenophobic attacks. It is important that this programme focus quite specifically on the cross-sectoral nature of the growth agenda so that it is seen to be delivering on social poverty reduction and job creation. If the EcCl can ensure that a fair proportion of the work done has a poverty reduction focus, it will be much easier to demonstrate success and sustain the programme irrespective of changes in the political environment.

Environmental Appraisal
    1. It is difficult to assess precisely what the environmental impacts of the programme may be. There are potential environmental implications resulting from the implementation of interventions to (i) meet growing public demand for more and better infra-structure services (including power, rail, transport, ports and oil-pipelines) and (ii) improve the economic efficiency and expansion of activities in key sectors such as tourism; chemicals; mining; bio-fuels; wood, pulp and paper; clothing and textiles. In line with the government’s emerging priorities for promoting sustainable development, it is expected that the EcCl will consider the environmental issues connected with individual projects and choose to fund those that are likely to have a more positive impact on sustainability. Energy-related projects are likely to be focused around creating reliable but also renewable (e.g. solar) sources of energy for South Africa’s growth needs.

Fiduciary Risk Assessment
    1. DFID-SA finalised a Limited Fiduciary Risk Assessment (FRA) in August 2008. (See Appendix C). The overall fiduciary risk rating for this programme is moderate. The FRA concluded that South Africa’s financial legislation reflects best international practice, and without question, has been implemented by a government committed to making the system work – indeed, the reform process has been government-led, with very little external stimulation. It is acknowledged by government, that full implementation and maturity of these systems has not yet been achieved, but credible measures are in place to address areas of weakness.
    2. A PEFA assessment was started by the EC in June 2008, as a precursor to the disbursement of the EC funds designed to support Growth and Employment. The initial PEFA findings show that GoSA’s national systems are robust in terms of financial accountability and transparency. However, it also found that donor practices in terms of alignment with government priorities and systems are weak. This programme will, by providing funds to the EcCl, ensure close alignment with such priorities and systems.

  1. Lessons and Evaluation
    1. DFID SA, and DFID more generally, has built up a set of diverse programme experiences, related to growth and to working through government in cross-departmental ways, relevant for the design of this programme.
    2. In previous experiences, DFID has tended to fund growth-related projects with Departments in piecemeal ways. This has increased the transaction costs for both parties and has diluted efforts to coordinate activities on growth across government. For this programme, the intention is therefore to support the EcCl as the principal coordinating mechanism for growth work across GoSA, providing a flexible set of funds that can be used in accordance with the evolving priorities of the Growth Strategy.
    3. Past experiences have also pointed to the merits of trying to catalyse change, using programme funds to enable innovation and piloting of approaches in ways that can be subsequently scaled up by the government with wider funds available. The funding mechanisms incorporated in this programme aim to do exactly this, including by seeking to leverage the significant budget support resources being made available to GoSA by the EC.
    4. A further lesson built into the programme is its recognition of the need to promote growth that is inclusive, particularly in the South African context. Raising levels of growth and mean incomes may not in itself have an effect in reducing poverty. The programme will support the EcCl to find ways of shifting the patterns of growth in ways that promote better integration of the economically marginalised. This is in line with prospective shifts in emphasis in government policy priorities.
    5. Whilst DFID’s funds will complement those of the EC, supporting GoSA to deliver on the agreed Key Performance Indicators (KPIs), a separate programme logframe will enable the impacts of this programme to be assessed. The indicators capture the effects of the programme in strengthening capacity and coordination of the EcCl, including through examples of successful project implementation, and in improving delivery of the Growth Strategy through stronger monitoring of delivery against the ePoA. The indicators also capture the leveraging effects of programme support through measurement of the extent to which lessons are learned and implemented from pilot projects.

1. IMPLEMENTATION
  1. Management Arrangements
    1. The programme, its mechanisms for funding and monitoring arrangements will be agreed with the EcCl. The Secretariat of the EcCl is responsible for calling meetings of the cluster, setting the agenda and schedule of issues to be discussed in collaboration with the co-chairs and facilitating the reporting of focus groups into the cluster DG meetings. The Secretariat is also responsible for the development of programme content and research, reporting to cabinet and for media briefings around the EcCl’s work and monitoring and evaluating the Cluster’s PoA.
    2. The EcCl also comprises:
- Economic Cluster Line Departments (ECLD). Currently 24 Departments of GoSA are members of the EcCl, of which 13 are active participants. These departments implement GoSA’s growth polices as detailed in the Growth Strategy and the ePoA;
- Focus Groups (FG) meeting monthly in five areas – Macro-Economy, Industrial Strategy, Equity and Development, Public Investment, and Skills development. In the context of the funding arrangement , the function of the FGs is to receive ideas and proposals from Line Departments for funding by the EcCl;
- Funding Committee (FC), meeting bi-annually, made up of the two co-chairs of the EcCl (DTI and DPE) and the chairs of the five focus groups made up of DGs (or their nominees) from key EcCl departments;
    1. The process for accessing DFID funds by EcCl Line Departments will be as follows, and as illustrated in the diagram below. All stages will be managed and tracked carefully by the Cluster Secretariat.
Step 1. ECLDs submit ideas and proposals to FGs (e.g. for financing research, experts, innovations, pilots, workshops). Project proposals will need to align with the EcCl’s ePoA, specifically around the areas of increasing economic efficiencies, promoting dynamic growth sectors, and integrating small and micro-enterprises. In addition, funding decisions will take into account whether and how proposed projects will:
- make a positive impact on employment and development of the Second Economy;
- encourage interdepartmental implementation and co-funding;
- provide measurable milestones and defined impacts;
- achieve innovation;
- enhance visibility and enhance profile;
- be managed and with what capacity;
- be monitored and evaluated.

Step 2. FGs, with active support from the Secretariat, work with ECLDs to prepare project proposals. Projects less than R4 million will be considered for funding by the cluster Co-chairs. Projects above R4 million will be submitted to the Funding Committee and considered at its bi-annual meetings.
Step 3. Cluster Co-chairs and/or the Fund Committee decide on project applications and signal approval or rejection.
Step 4. If approved, the Secretariat will submit a request for funds to National Treasury and may engage with ECLDs to make necessary procurement arrangements.
Step 5. Either the Secretariat or ECLD will enter into a contract with suppliers. NT will endeavour to release funds to Line Department within a week.
Step 6. Suppliers will deliver agreed services directly to the Secretariat or ECLDs.

    1. In the course of scoping and designing this programme, many Line Departments have submitted prospective proposals which should meet the criteria for approval. These will be fast-tracked through the above processes for funding once disbursement begins. These are listed in the box below. They illustrate well how the cluster process will work to address a number of ePoA’s core concerns for ensuring growth’s binding concerns are addressed and employment growth is promoted vigorously. Arrangements have been made with National Treasury to finance front-loaded projects within a week of the first tranche of DFID funds being made available.

Examples of Prospective Projects for funding at programme inception

Increasing public investment to improve the state of infrastructure: / Develop an industrial strategy to promote and support the sustainable use of solar energy for domestic and commercial purposes

Addressing barriers to entry, expanding economic opportunities, and improving the competitive efficiency of firms: / Benchmark firms in southern Africa so that enterprises can supply South African industries with products required for the planned scale-up in infrastructure / Support pilots under the Community Work Programme that provide (socially useful) employment opportunities to poor unemployed youth

Upgrading workers’ skills and capacity: / Develop a National Skills Plan Strategy / Develop curriculum, and consultation programme, for Further Education Training to expand number of skilled artisans / Develop programme to improve the skills of lecturers in FET institutions / Develop an Enterprise Skills Development Agency to help young people to acquire technical skills and enable State Owned Enterprises to provide more effective infrastructural services

Increase government’s institutional capacity and efficiency: / Strengthen, through training, the procurement capacity of State Owned Enterprises and achieve gains in efficiency

Create a more competitive business environment: / Build the capacity of the Competition Commission to investigate proactively anti-competitive market behaviour

    1. The Programme will be managed within DFID by the DFID-SA Deputy Programme Manager for Growth, Trade and Investment and the DFID-SA Senior Economics Adviser.

  1. Timing
    1. DFID will sign a Non Budget Support Financial Aid Memorandum of Understanding with the National Treasury by February 2009, at which point the programme will begin. The final tranche of funding would be disbursed in April 2012 and the overall programme will conclude by December 2013.

  1. Funding
    1. DFID’s contribution under the programme will be £18M over five years.
    2. Scoping undertaken by DFID to identify the most appropriate modality to support GoSA’s Growth Strategy, and in ways consistent with Paris Declaration aid-effectiveness criteria, suggested a non budget financial aid arrangement with the Department of Trade and Industry and the Department of Public Enterprise, the departments in which the EcCl Secretariat is housed. Funds will be transferred to the relevant line departments via the South African National Treasury Reconstruction and Development Fund (RDP). The RDP Fund was set up by the SA NT as a conduit for donor funds and is the preferred mechanism for channelling these programme funds to the EcCl. This mechanism provides GoSA the greatest flexibility in aligning priorities and planning to donor funds.
    3. The tranche schedule is planned as follows:
- Tranche 1: £2.5 million by 31 March 2009 (2008/09)
- Tranche 2: £3.5 million by 30 April 2009 (2009/10)
- Tranche 3: £4 million by 30 April 2010 (2010/11)
- Tranche 4: £4 million by 30 April 2011 (2011/12)
- Tranche 5: £4 million by 30 April 2012 (2012/13)

Disbursement of tranches 3, 4 & 5 will be determined by the outcome of the March 2010 Annual Review as the Annual Review will assess the effectiveness of the Non Budget Support Financial Aid funding mechanism and added value of DFID funding in light of larger EC disbursement in 2010 and 2011. The programme will close in December 2013.
    1. The funding will be used to support innovative projects among line departments to promoting growth and employment as well as increased staffing capacity. Such uses will increase the institutional capacity of the EcCl, strengthen coordination across departments, develop monitoring arrangements for the growth strategy, and lead to lesson sharing within government and with other stakeholders. Specific budget allocations will be determined by the EcCl co-chairs and Funding Committee, but an indicative breakdown of the funding by programme output and type of cost for the full five years is as follows:

 Indicative budget by programme output
Output	Budget (£),
	Total Indicative Budget
1. Strengthened institutional capacity in Secretariat of Economic Cluster	£2,500,000
2. Improved cross-cutting working relations between the Line Departments of the Economic Cluster	£13,000,000
3. Improved framework for monitoring growth strategy and ePoA.	£1,100,000
4. Lessons from projects influence development of GoSA’s future growth and poverty reduction policy.	£,400,000
5. Lessons from programme implementation communicated and implemented	£1,000,000
Overall	£18,000,000

    1. We only expect a very small amount of the overall DFID financing to be used in the purchase of assets. The ownership of any DFID funded assets will be passed to the Government of South Africa on completion of the project.
    2. The framework agreement for the EC programme (100 Million Euro over three years) is expected to be signed by January 2009. The first tranche of the EC funds (20 Million Euro) will be disbursed by April 2009. The EC tranches will amount to 40 Million Euro in 2010 and 40 Million Euro in 2011.
    3. To manage additional requirements created by the need to process finance from DFID and the EC, a portion of DFID funds will be reserved for strengthening the Secretariat’s capacity. The EcCl has already appointed a Director. Additional staff will increase capacity by providing additional technical, procurement and management support.

  1. Contracting and Procurement
    1. The relevant line departments will be responsible for managing all procurement of services, using the GoSA procurement systems as outlined in the Public Financial Management Act (PFMA). It will not therefore be necessary to appoint a Procurement Agent. The Secretariat will provide procurement support to departments and may solicit the services of procurement expertise financed from the DFID programme. The Fiduciary Risk Assessment found that these proposed safeguards will reduce fiduciary risk and enhance value for money.

  1. Accounting/Audit
    1. DFID will agree a Non Budget Support Financial Aid MOU with GoSA. As soon as the MOU has been signed, GoSA will appoint Crown Agents Bank to manage the financial arrangements set out in the MOU. Crown Agents Bank will open an account for the Grant. The Account will be operated solely for the purposes of, and in accordance with, the MOU. GoSA will request funding in tranches from DFID which will then be paid on authorisation through Crown Agents Bank into the RDP Fund.
    2. The GoSA will, within 9 months of the end of each financial year, provide DFID with Annual Audited Statements from its Auditor General confirming that DFID’s Grant has been used for the intended purposes. In addition to the departmental reports, the National Treasury will also provide copies of the RDP Audited Financial Statements with a narrative report.

  1. Monitoring and Reporting
    1. A monitoring framework, which will be based on the KPI’s jointly agreed by GoSA, EC and DFID) and the closely related DFID logframe will be used as the basis for reporting on progress to DFID and the EC. A monthly meeting between the EcCl Secretariat, DFID and the EC will be held to monitor initial implementation. Thereafter it is expected that the EcCl Secretariat will provide a narrative report to the EC and DFID on a quarterly basis.
    2. Joint formal annual reviews of performance and progress will be carried out with the GoSA, EC, and other stakeholders. These reviews will as far as possible be aligned to existing review processes in GoSA. The first annual review in March 2010 will assess progress against the monitoring framework and logframe, but will also consider the effectiveness of the Non Budget Support Financial Aid funding mechanism. If the GoSA are content for the DFID funding to continue being provided through this mechanism, further tranches will be disbursed as planned. However if the GoSA agree that DFID funds should be directed in a different way this will be discussed and agreed with all partners concerned.

1. RISKS
  1. The overall level of risk associated with the programme is low-medium.
  2. Corruption risk around the proposed DFID support is considered to be moderate. For instance, the Auditor General’s reports for 2006/07 reveal no major non-compliance for financial management within the 13 national departments that potentially will be beneficiaries of the DFID support through the EcCl. As noted above, the fiduciary risk assessment carried out was broadly positive.
  3. Other risks of the programme, and their associated probabilities and degrees of impacts, are as follows and as depicted in the matrix below.
1. Political and policy risks (low probability; high impact). South Africa will have a change in government after the next general election which is widely expected to take place before the middle of 2009. This will probably amount to a change in leadership rather than a change in the governing party. Probably the political changes will lead only to a change in policy emphasis, with a shift towards social policy agendas and a more of a developmental state policy model. However, some analysts have argued that, depending on the influence of certain stakeholders within the new government, there is a risk of a more populist agenda emerging that could undermine fiscal prudence and could undermine investment and growth. This risk has a low probability and it is generally expected that the new government will maintain a focus on growth and employment, within a broad framework of macroeconomic stability.
2. Financial and economic risks, including global downturn (high probability; low impact). South Africa’s short term growth prospects are already being hindered by power shortages and relatively high interest rates. With expectations of global conditions worsening, and depressed commodity prices, prospects for higher growth in South Africa are being dented, at least for the short term. South Africa’s current account deficit is around 8% of GDP, and with the retrenchment of investor capital already occurring, South Africa could face balance of payments difficulties. Furthermore, household debt in South Africa has built up to high levels and may increasingly bite as a result of job losses and high interests rates, restraining consumer demand, and hence growth, within the South African economy. Such risks are hard for the programme to mitigate, but by focusing on achieving the capacity changes in government that create the conditions for it to generate stronger growth than would otherwise occur, the risks to actual programme delivery are kept low. By supporting a broader base of growth in South Africa as well as closer integration with African markets, the programme could also make the country less vulnerable to the external conditions;
3. Institutional and administration risks (probability low; impact medium). Delivering South Africa’s growth strategy successfully – regardless of the prevailing economic environment – requires not only good policies and planning, but a capacity within government to co-ordinate departments’ efforts and ensure efficient implementation. While the fundamentals for this are in place, some concerns have been expressed over ‘thin’ capacity within GoSA. This could lead to programme funds not being used effectively to tackle the binding constraints to inclusive growth in South Africa or to effectively scale up successful experiences piloted by the programme. The risk there but, if implemented well, the programme is designed to address some of these capacity constraints, particularly at the level of the EcCl Secretariat.

		Impact
		Low	Medium	High
Probability	Low		C	A
	Medium
	High	B

1. CONDITIONALITY
  1. There are no conditions attached to this commitment. The GoSA have signed up to the Partnership Commitment as outlined in the MOU. Disbursement of Tranches 3 & 4 will be determined by the outcome of the March 2010 Annual Review as the Annual Review will assess the effectiveness of the Non Budget Support Financial Aid funding mechanism and added value of DFID funding in light of larger EC disbursement in 2010 and 2011. Any changes in funding mechanism will not affect the total commitment to GoSA under the programme.
  2. The MOU has been cleared through all of GoSA’s legal systems.