Business Case

Summary Sheet

Title: / Empowerment and Accountability (E&A) Research Programme: Understanding Social and Political Action
Project Purpose: / To produce operationally relevant and robust new research on social and political action that leads to the development of – and investment in - more effective policies and programmes by external actors, including DFID and partners, resulting in measurably improved empowerment and accountability as demonstrated by enhanced voice, choice and control for poor and marginalised groups, including women and girls.
Programme Value: £6.5m		Country/ Region: 6/8 DFID Tier One Countries
Project Code: 204427-101	Start Date: Jan/Feb 2015	End Date: 2020
Overall programme risk rating:	Medium/High
Quest Number:

Intervention Summary (2 Pages)

What support will the UK provide?
The UK will provide up to £6.5 million over 5 years to generate new evidence to understand the impact and effectiveness of social and political action. Results will directly inform DFID and other international and national actors to invest in, develop or improve policies and programmes to effectively strengthen empowerment and accountability (E&A) in at least 4 DFID priority countries. It will enable poor people to have enhanced agency and voice, more inclusive participation and choice in decision-making; increased state-citizen collaboration; more control over their lives through transparent, responsive and accountable governments and environments.

This programme will focus on three themes:
- understanding the context and political processes that enable social and political action and subsequent change to happen and – importantly – not to happen (i.e cases where social and political action would be in the interests of people and yet does not occur).
- understanding when and how social and political action empowers people, builds accountabilities and builds open and inclusive institutions. This includes examining who is involved, what makes it happen, and what strategies were adopted (including the use of technologies). The programme will determine the impacts and relative success and failure of specific action.
- the role of external actors, including donors, in implementing effective programmes that support social and political action with the clear objective of strengthening E&A. Programme results will directly inform DFID programming, as well as other bilateral, multi-lateral and international agencies, and national governments.
What are the main programme activities?

The programme will have two strands:
Defining research framework, evidence synthesis and historical case studies:
This will concentrate on developing a clear guiding research framework for the programme, compile and assess existing evidence, and undertake historical case studies on social and political action and its impact.
Operationally relevant field research to directly inform policies and programmes: Operational and implementation research effectively communicated to understand when and how social and political action empowers people, builds accountabilities and builds open and inclusive institutions and policies and programmes can effectively support this.

This research programme, which will be explicitly comparative, will cover 6-8 DFID Tier One developing countries.[1] It will generate robust evidence with a strong operational focus, as reflected in the proposed research questions. The programme is expected to use a mix of qualitative and quantitative methods, with a substantial field work component across a range of country cases.
[1] All of the cases will be DFID focus countries, and will include FCAS. Non-FCAS cases are needed to allow valid comparisons to be made.

Why is UK support required?
Despite progress towards the MDGs, significant poverty persists. Persistent poverty depends on local contexts but common underlying factors are that poor people lack power to make choices and access the opportunities, resources and services that would help them and their families out of poverty. Poor people – particularly women and girls – are denied rights due to discriminatory, harmful, unfair and/or ineffective social norms and many struggle to make their views heard and to make changes in the institutions that affect their lives.
DFID is committed to supporting developing countries to drive forward and self-fund their own exit from poverty. As well as reducing dependence on aid, this includes supporting processes through which all citizens are empowered to have greater ‘voice, choice, and control’.

DFID’s commitment to E&A is demonstrated in policy and programmes - every single DFID country programme is implementing at least one activity that addresses an aspect of ‘E&A’. Despite this, the evidence base underpinning such activity is weak. This includes whether and how different E&A activities bring change in short, medium and long term and what role (if any) external actors can play.

What are the expected results?

The outputs of this research programme will be:
1. High quality peer reviewed and policy relevant evidence on when and how social and political action occurs in different contexts and the effectiveness of social and political action in terms of measured impacts on building more open and inclusive institutions, empowering people and building horizontal and vertical accountability.
2. Evidence on the role (if any) external actors can play in creating, supporting and influencing social and political action.
3. Stakeholder engagement through research process and uptake facilitates the operational application of new evidence, including by DFID. This will include synthesis of evidence; engagement with different targeted audiencesusing multiple formats to communicate research; and engagement to improve capacity of researchers and policymakers to access and use evidence.
The expected outcome is:
Robust new, high quality evidence on social and political action is accessed by policymakers and practitioners, leading to the development of – and investment in – more effective empowerment and accountability policies and programmes by external actors, including DFID and partners.
The intended impact is:
Measurably strengthened E&A in at least 4 DFID priority countries as demonstrated by enhanced agency and voice, more inclusive participation and choice in decision-making for poor and marginalised groups, including women and girls; increased state-citizen collaboration; more control over their lives through transparent, responsive and accountable governments and environments.

How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?

RED’s Operational Plan has a specific target for new anti-corruption research: “Research programmes on testing what works for anti-corruption and empowerment and accountability underway to produce rigorous evidence. Preliminary results published (2015)”

The need for more investment in operational research on E&A is compelling because every DFID country office is implementing a programme that covers some aspects of E&A. The proposed research will complement existing DFID research programmes including the Effective States and Inclusive Development (ESID); Political Settlements; and forthcoming Conflict Research.

What are the key risks to the success of the programme?
The risk rating is medium/high. The key risks identified for this programme are as follows:
Delivery of a sizeable and complex programme;
- Research partners fail to deliver on time; misuse of funds.
- Research procured fails to have policy relevance.
- Research findings are disparate and do not add up to a coherent body of evidence.
- Poor quality research funded.
- Research does not impact on potential users.

The mitigating measures for the risks listed above are set out in full on p.29 below and include procurement, management, and regular review and reporting procedures. The programme will use milestones and will link payments to deliverables agreed by the implementing partners and DFID.
Strategic Case

CONTEXT AND NEED FOR A DFID INTERVENTION

A1. Supporting ‘empowerment and accountability’ is a priority for DFID

DFID is committed to supporting developing countries to drive forward and self-fund their own exit from poverty. As well as reducing dependence on aid, this includes supporting processes through which all citizens are empowered to have greater ‘voice, choice, and control’:
- voice in decision making,
- choice through access to services, economic opportunities and information;
- control over their own lives.
The expected social and political change also requires stronger institutions that are accountable and responsive to all, but particularly to poor people (see Annex A for DFID’s E&A Theory of Change).

A wide range of international thinkers (most prominent are Acemoglu and Robinson), donors (including DFID) and politicians have emphasised the importance of empowered citizens and open and inclusive institutions for addressing issues of conflict, poverty and sustained economic growth.[1] Prime Minister Cameron’s vision of a ‘golden thread’ of international development emphasises open and inclusive institutions as key to enabling open economies and open societies to thrive.[2]
[1] For example, Acemoglu, D. and Robinson, J., (2012) Why Nations Fail, London: Profile Books; Brown, S. and Grävingholt, J. (2011), From power struggles to sustainable peace: understanding political settlements OECD;; Khan, M. (July 2010), Political Settlements and the Governance of Growth-Enhancing Institutions, unpublished paper
[2] David Cameron, Wall Street Journal http://online.wsj.com/news/articles/SB10001424052970204712904578090571423009066

In summary terms, the assumed ‘theory of change’ is that empowered citizens who participate in social and political change will widen political settlements, strengthen the “social contract” between state and society, improve government responsiveness, and provide space for previously excluded groups to participate in politics and hold government to account. This should, in turn, reduce risks of conflict, give poor people more control over their own development, and is a key condition for sustainable economic growth.[3] Without empowered citizens and stronger and more inclusive institutions, the poor are less likely to lift themselves out of poverty and states are less likely to respond to the needs of all. ‘Empowerment and accountability’[2] (E&A) is used to describe this area of work, though it encompasses a range of political and social action.
[3] Acemoglu and Robinson (2012) op cit. explains that “horizontal” inclusion of elites can kick-start economic growth but that “vertical inclusion” of citizens is essential to sustainable economic growth; Joshi, A. (2010) ‘Assessing the impact of transparency and accountability on service delivery’ (http://r4d.dfid.gov.uk/PDF/Outputs/Mis_SPC/60827_DPRJoshi_Preprint.pdf,) shows that, in many contexts, improving social accountability leads to better governance outcomes for marginalised groups; and the International Centre for Tax and Development (http://www.ictd.ac/) shows that tax arrangements affect the relationship between state and society,
[2] DFID defines empowerment as enabling people to exercise more control over their own development and supporting them to have the power to make and act on their own choices. Accountability is about officials and politicians answering for their actions and being held to account for delivering on their responsibilities.

DFID’s commitment to E&A is demonstrated in policy and programmes - every single DFID country programme is implementing at least one activity that addresses an aspect of ‘E&A’. Despite this, the evidence base underpinning such activity is weak. This includes whether and how different E&A activities bring change in short, medium and long term; how different E&A activities interact; and what role (if any) external actors can play.

A2. What is the problem and why does it persist?
Despite progress towards the MDGs, significant poverty persists. In many countries gaps are widening between rich and poor, and there is significant inequality of opportunity.[4] Many MDG-oriented development interventions successfully tackle the symptoms of poverty, but not underlying causes or barriers to change. Persistent poverty depends on local contexts[5] but common underlying factor are:
[4] See, for example, UNDP’s Human Development index adjusted for inequality: http://hdr.undp.org/en/statistics/ihdi/
[5] Booth, D. (2012) Africa, Power and Politics Research Programme – Synthesis paper: Summary, ODI
- Poor people lack the power to make choices and access the opportunities, resources and services that would help them and their families out of poverty.
- Poor people – particularly women and girls – are denied rights due to discriminatory, harmful, unfair and/or ineffective social norms.
- Poor people struggle to make their views heard and to make changes in the institutions that affect their lives.
- Political elites ignore the concerns of poor people and public officials do not act on commitments to deliver the choices and opportunities they need.

These factors are particularly acute in fragile and conflict-affected states (FCAS). 1.5 bn people live in areas affected by fragility, conflict or large-scale violence, and no low-income FCAS has achieved a single MDG.[6]
[6] WDR 2011. Conflict, Security and Development

Tackling the underlying causes of poverty is difficult. From existing research and programme experience we know that the processes of empowerment are not straightforward, happening in different ways and at different times in different contexts[7] and local politics and existing institutions create both opportunities and constraints.[8] Despite this variation, barriers to change can be broadly categorised as:
[7] Improving Institutions for Pro‐Poor Growth Research Programme (IPPG) (2010) Beyond Institutions: Institutions and organizations in the politics and economics of growth and poverty reduction – a thematic synthesis of research evidence; Leftwich, A., Sen, K. (2011) “‘Don’t mourn, organize.’ Institutions and Organizations in the politics and economics of growth and poverty reduction.” Journal of International Development, 23 (3), 319‐337 conceptualises institutions as “empty boxes” and explain that the way people and / or organisations maintain and engage with them affects their nature; Gaventa, J. and McGee, R. (2013), The Impact of Transparency and Accountability Initiatives. Development Policy Review, 31: s3–s28. doi: 10.1111/dpr.12017.
[8] Booth, D. (2012) op cit.

- Structural factors – the way power is distributed through a political settlement; social structures, such as caste or relationships between ethnic groups; concentration of economic power in the hands of a particular group; or the physical location of groups in difficult terrain.
- Institutional factors – this may include weak formal institutions such as unenforceable or inappropriate property rights; the state not providing public information on government performance; weak opposition and/or civil society to monitor the state; or formal political processes that are inaccessible or unrepresentative. It may also include informal institutions, such as tribal or community practices that systematically exclude particular groups.
Social and political norms – a particular group may control access to resources and politics, or have entrenched ideas about how resources should be distributed, and have little incentive to widen access and include other groups in decision making. Discriminatory social norms lead to groups being marginalised on the basis of sex, ethnicity, or religion and unable to access economic opportunities and services.[9]
[9] Categorisations developed from: Hudson, D., Leftwich, A (2014) “From Political Economy to Political Analysis” Developmental Leadership Programme Research Paper 25

Responding to these barriers – what does the evidence say?

Over the last two decades, most donors have approached ‘accountability’ in terms of governments’ ability to “supply” it and respond to citizens’ needs through stronger institutions, and society’s capacity and ability to “demand” a more responsive state.[10] As a result, donor-funded interventions have either targeted formal institutional reform (the supply side) or supported civil society to be ‘empowered’ to demand greater social accountability or improved access to economic resources (the demand side). Efforts to address both simultaneously are relatively rare.
[10] Taken from analysis of: “Empowerment and accountability – what does the evidence tell us?”; Joshi, A. (2013) Enabling Empowerment and Accountability: The Role of Deliberative Spaces and Collective Action; E&A Policy Team Empowerment and Accountability – Evidence Mapping, unpublished paper, (DFID, 2012

In terms of impact, there is a moderate body of evidence – often focused on a specific area or intervention - indicating that supporting institutional change will empower poor people to negotiate in markets, state, and society, but less sources of evidence that this delivers substantive change or developmental outcomes. Examples include:
- Experience in Pakistan suggests that voter education positively impacts women’s participation in elections and encourages independent voter choice.[11]
  [11] Gine, X. and Mansuri, G. (2011), ‘Together We Will: Experimental Evidence on Female Voting Behaviour in Pakistan’ World Bank Policy Research Paper http://elibrary.worldbank.org/doi/book/10.1596/1813-9450-5692)
- An evaluation of Afghanistan’s largest sub-national governance programme suggests that a community-driven development approach improved legitimacy of government officials.[12]
  [12] Beath et al (2011) Randomized Impact Evaluation of Phase-II of Afghanistan’s National Solidarity Programme (NSP), World Bank
- A body of evidence from India suggests that gender quotas improve levels of representation of women in formal politics (but this does not translate into substantive involvement and influence in political processes).[13]
  [13] Deininger et al 2011; Beaman et al 2009; Chattopadhayay et al 2004; UN Women 2011

Again, there is moderate body of evidence that empowering citizens to demand social accountability delivers governance outcomes, but less evidence that it delivers developmental outcomes.[14] For example,
[14] Joshi, A. (2010) op cit.; McGee, R., and Gaventa, J. (2010) “Review of Impact & Effectiveness of Transparency and Accountability Initiatives: Synthesis Report”. Paper prepared for the Transparency & Accountability Initiative Workshop, October 14-15, 2010. Institute of Development Studies.
- An independent evaluation of Citizen Report Card work in Bangalore showed improved quality of services and increased civic activism. Commitment from civil society, media and government were all important to success.[15]
  [15] Ravindra, A. (2004) An assessment of the impact of Bangalore citizen report cards on the performance of public agencies, World Bank
- Research in India and Uganda found that publishing budget information increased levels of funds reaching schools, and school performance. [16] Work by Archon Fung and Stephen Kosack reviewed 16 RCTs on transparency and accountability initiatives. Their review draws out patterns of what types of information are most successful (e.g focus on inputs rather than outputs, comparative information, combination of subjective and objective information etc).[17]
  [16] Reinikka, R. and Svensson, J. (2005) 'Fighting Corruption to Improve Schooling: Evidence from a Newspaper Campaign in Uganda' Journal of the European Economic Association 3 (2-3): 259-267; Banerjee, A., Duflo, E., Glennerster, R., Banerji, R. and Khemani, S. (2010) ‘Pitfalls of Participatory Programs: Evidence from a Randomized Evaluation of Education in India’, American Economic Journal: Economic Policy 2 (1): 1-30.
  [17] Fung, A. and Kosack, S (2013), “The Five Worlds for Transparency and Accountability’ Blog #6, //Civil Society 4 Development (T4D)

There is less evidence that improving access to economic resources will directly empower poor people to negotiate better in market, state and society. Examples include:
- Evidence suggests that cash transfers have some positive effects on households’ ability to access credit on fairer terms,[18] and increase women’s bargaining power in the home.[19]
  [18] Barrientos, A., and Scott, J. (2008) ‘Social Transfers and Growth: A Review’. Working Paper 52. Manchester: Brooks World Poverty Institute
  [19] Bolsa Familia Suarez et al (2006); Devereux, S. and Jere evaluation in Swaziland (2008)
- There is limited evidence that micro-finance leads to gender empowerment[20] and little evidence that individual empowerment has broader empowering effect.[21]
  [20] Stewart et al (2010) What is the impact of microfinance on poor people? Systematic review of the evidence from sub-Saharan Africa http://r4d.dfid.gov.uk/Output/185865/
  [21] Joshi, A. 2010, op cit.

A3. The evidence gap – what questions remain?
Diverse recent research on the politics of development; on political settlements; and on citizen action and social accountability; is examining the barriers to citizen empowerment, and barriers to making institutions more open and inclusive.
We have grouped areas warranting further research investment as follows:
Understanding social and political action
There is consensus that ‘empowerment’ and ‘making institutions more open and inclusive’ are not things that can be ‘created’ or ‘delivered’ through well-crafted interventions. These processes require those involved to take the principal roles in making change happen. External actors may be able to encourage, but they cannot create change. This is backed up by work by Mansuri and Rao (2013) who argue that ‘organic participation’ (for example locally initiated and led organisations) is less likely to be captured by local elites than ‘induced participation’ (for example, donor introduced local level committees).[22]
[22] Mansuri, G. and Rao, V. (2013), Localizing development: does participation work?, A World Bank Policy Research Report
Recent literature examines the role that ‘collective social and political action’ plays in change processes. The emerging view is that it can be a ‘good thing’, with potential to empower people, strengthen accountability, and transform institutions, but can also have unforeseen consequences – both positive and negative.
The significant evidence gap is understanding how change actually happens, and measuring what impact it has and for whom. Despite a range of examples where people from across society come together to bring about change (see below), we do not understand how and under what circumstances social and political action contributes to change, who is involved and who benefits, or what is the best way for external actors – such as DFID - to encourage it.
Multi-pronged strategies bridge the gap
Recent meta-analyses of donor interventions conclude that results are more promising when interventions have multi-pronged strategies that address both supply and demand - encouraging enabling environments for collective social and political action, and bolstering state capacity to actually respond to citizen voice.[23] Jonathan Fox argues that such interventions that combine social, economic and political activities have better effects because they are “strategic” rather than “tactical”.[24] For example, research shows that, with an element of political participation, community score cards (a social intervention) go from having no impact to having significant impact.[25] Similarly, in South Africa, combining micro-finance and social education has led to decreases in inter-personal violence.[26]
[23] Fox, J. (2014) Social Accountability: What does the evidence really say? World Bank Global Partnership for Social Accountability, World Bank
[24] See, for example: Fox (ibid), Barr, Mugisha et al (2012) Information and collective action in community-based monitoring of schools http://cega.berkeley.edu/assets/cega_events/3/doc7Zeitlin-et-al_Information-and-Collective-Action-in-Community-based-mMonitoring-of-Schools.pdf; Citizen DRC Research (see “Blurring the Boundaries: Citizens across state and society” for a good overview of key findings); and Africa, Power and Politics Research Programme – Synthesis paper: Summary (ibid)
[25] Barr, Mugisha et al (2012) Information and collective action in community-based monitoring of schools http://cega.berkeley.edu/assets/cega_events/3/doc7Zeitlin-et-al_Information-and-Collective-Action-in-Community-based-mMonitoring-of-Schools.pdf
[26] Kim, J. (2007) Understanding the Impact of a Microfinance-based Intervention on Women’s Empowerment and the Reduction of Intimate Partner Violence in South Africa.
Despite recognition of the value of multi-pronged approaches, there is limited evidence on their impact on E&A outcomes. In particular, evidence gaps exist on which designs are effective; how different components should be sequenced; which stakeholders should be involved; ways of identifying policy opportunities and other entry points to achieve greater impact at scale.
Women’s role in change processes – can local action lead to wider change?
Literature on the underlying causes of poverty tends to use broad terms – lumping together multiple groups that are either excluded or included. Gaventa and McGee highlight that the inclusion of women and girls and other marginalised groups is not a given in social and political change processes and may even result in reinforcing existing power relations.[27] More research is needed to understand the role of women in social and political action and if/how this can translate into broader shifts in how communities view and value women and girls in the community, as well as delivery of development outcomes. More research is also needed to understand the perceptions of women involved and their aims in achieving substantive women’s political (both formal and informal) participation.
[27] Gaventa, J. and McGee, R. (2013) The impact of transparency and accountability initiatives, Development Policy Review, 31 (S1): S3-S28

Greater acknowledgement and understanding of social and political norms
Individual beliefs and behaviours are influenced by social norms - what people in a group believe to be a typical action, an appropriate action, or both.[28] Such norms are held in place by reciprocal expectations – i.e. people feel that everyone in their group conforms to an action and so feel that they ought to act in the same way. Because of this interdependence of expectation, social norms can stiffly resist change. Social norms are an important focus of DFID’s work on gender inequality, and is relevant to a far wider range of challenges, including conflict, violence, corruption, and social and political action.
[28] Paluck, Elizabeth Levy, and Laurie Ball (2010). “Social norms marketing aimed at gender based violence: A literature review and critical assessment.” New York: International Rescue Committee.
While there is a growing body of research looking at what works to shift traditional (and often harmful) social norms, more research is needed to understand social and political norms that influence empowerment (e.g. on participation and representation, on roles of different groups- particularly women, patriarchy etc) and political, social and economic inclusion and accountability (e.g. on transparency, voting behaviours, patronage networks etc).

B. WHY SHOULD DFID SUPPORT RESEARCH TO ADDRESS THESE GAPS?
DFID has a clear operational need for better evidence in this area as it is an area of significant expenditure as well as importance in our global strategy.
We have invested in E&A programming for over two decades, and every current country programme has at least one activity in E&A. We estimate that current commitments (2015-18) are around £91m, with 29 country programmes aiming to strengthen civil society; and 18 funding the free flow of information and transparency. The Secretary of State has called for “a fundamental change that empowers people”[29] and the proposed programme will provide the evidence to inform this change. Without it, E&A programmes may have good intentions but could fail to deliver fundamental change.
[29] Secretary of State Oxfam Speech, June 2010
We do not know enough about how developing countries have successfully made institutions stronger and empowered citizens. We know relatively little about how change happens, and the role social and political action has in creating change. There is much to learn about the role of external actors (including DFID) in supporting and influencing social and political action.
As well as meeting DFID’s own needs for more operational evidence, the proposed programme will also help reshape discourses and agreed conclusions in E&A research. Much previous research (including that supported by DFID) has been conceptual and/or focuses on micro case-studies or trends across regions[30]. Empirical researchers are beginning to focus on E&A (e.g. the DFID-cofunded ‘Transparency for Development RCTs’ in health) and we have an opportunity to re-shape the research market by incentivising more empirical and operationally-focussed work, and limiting UK support for further conceptual research that will have limited operational relevance.
[30] Brechenmacher, S. (2014) “Evidence Review: 4 Magic Words” (Carnegie Endowment for International Peace)
Fit with existing DFID priorities and strategy
The programme contributes to a range of current priorities:
- GCSD Team’s Research commitment to deliver practical, operationally-useful information on the best ways to tackle conflict and promote pro-poor growth.[31]
  [31] The GCSD RED priorities paper (November 2011) sets out the proposed strategy for the period 2012/13-2014/15.
- DFID’s Strategic Vision for Girls and Women, particularly an environment that empowers girls and women and enables them to have ‘voice, choice and control’ and an “enabling environment of strong, open and inclusive economies, societies and political institutions which harness the leadership, participation, skills and innovation of girls and women as leaders and active citizens”.[32]
  [32] Stepping-up a gear for Girls and Women: DFID’s Strategic Vision for Girls and Women, to 2020 and beyond (2013)
- DFID’s commitment in response to the Independent Commission for Aid Impact’s (ICAI) report on Empowerment and Accountability to: “…develop a major five-year, multi-country research programme…[that] will include how best to promote constructive community engagement in service delivery and development processes, and what works in terms of supporting social accountability initiatives in different contexts. The research programme will provide recommendations on scaling up and improving the effectiveness of empowerment and accountability interventions.”
Our ICAI commitment has a target of approval of a new E&A research programme by December 2014.

C. Framing the proposed research

What do we mean by social and political action?
Forms, and objectives and the membership of social and political action can vary widely.
- Action can originate from ‘organic’ (domestically created) identity-based movements, from political opposition, or from groups seeking greater autonomy; or can emerge from traditional or customary institutions.
- It can be issue-based and arise out of a specific socio-economic or political concern, ranging from service delivery issues (e.g. challenging teacher absenteeism) to broader discontent with a political regime’s use of public funds.
- It can also have roots in processes created by external actors (Governments, donors, INGOs etc). Such ‘induced’ or ‘invited’ processes include those created under governance, social accountability and citizen programmes – e.g. Community Driven Development initiatives, user groups, media strengthening and participatory planning or governance councils.
- Social and political action can be led by poor and excluded people or sympathetic elites or a coalition of both. Action can be exclusive (limiting participation to a specific group) or involve a diverse actors from civil society, private sector, traditional leaders, and reformers from within the government.
- It can involve constructive engagement and a high degree of cooperation between the parties involved, or be violent and adversarial in seeking redistribution of resources or renegotiation of the status quo.
Figure 1 aims to summarise and give some structure to the wide range of social and political action that the proposed programme will cover.
The programme will be interested in understanding social and political action in all its manifestations and including a wide range of aims and objectives – some developmental, others divisive and conflictual that can also be effective in achieving outcomes. However, the programme is focused on providing operationally relevant research that will strengthen DFID and other development actors’ policies and programmes in relation to E&A. Therefore, the main focus (and majority of funding and effort) will focus on how social and political action affects the lives and wellbeing of poor and marginalised women and men.
Figure 1: Spectrums of Social and Political Action[33]
[33] The axis draws from work by Gaventa et al on the ‘Power Cube’ (http://www.powercube.net/) and Fox’s work on ‘transitions to accountability’ in Mexico cited in Duncan Green’s FP2P blog (http://oxfamblogs.org/fp2p/if-change-requires-both-cooperation-and-conflict-can-we-really-do-both/)

COOPERATION

CONFLICT

ORGANIC
/ CREATED

INDUCED
/
INVITED

Informal local forums and traditional justice institutions
e.g. Area Development Committees in Zambia, the Mesn-zajednicas in Bosnia and Macedonia and the ‘Kgotla’ – or customary courts - in Botswana
Social movements oriented towards socio-economic rights
e.g. Movements for the right to food, work, information etc in India as well as other examples across the globe on the right to natural resources/land, education, health
Sector-specific boards, associations and committees with a focus on improving services/accountability
e.g. Parents and Teachers’ Associations, Water Committees, Health Boards
International movements on rights issues
e.g. One Billion Rising movement against VAWG
Movements aiming to overthrow (often authoritarian) regimes
e.g. Uprisings during the Arab Spring
State or donor-led groups created through targeted E&A or governance programmes
e.g. Community Driven Development (CDD/CDR) e.g Community Development Councils (CDCs) under the National Solidarity Programme (NSP) in Afghanistan or Participatory Budgeting Groups e.g. in Porto Alegre in Brazil
Impacts – intended and unintended; short and long term; positive and negative.
The expectations of E&A are broad and far-reaching. With the GOSAC E&A policy team we have developed an ‘E&A Impact Landscape’ (Annex B) to describe categories of change expected; set out areas of potential impact related to open societies, open politics and open economies, and breaks these down in terms of scale (local, national and international change), and timescale (short and long-term).
The objectives of E&A – such as enhanced agency and voice, more inclusive participation and choice in decision-making; increased state-citizen collaboration; more control through transparent, responsive governments and accountable environments – are embedded within this table. The ‘ Impact Landscape’ also considers to where social and political action is not having any (or the intended impact), or having unintended impacts on areas other than their intended focus.
As mentioned above, this programme will look at social and political action in all its manifestations, including the various aims and objectives the action may have. While the ‘Impact Landscape’ focuses on progressive change in relation to E&A – and the main focus (and majority of funding and effort) will focus on how social and political action affects the lives and wellbeing of poor and marginalised women and men – we anticipate the research will also include action and change that is non-developmental, divisive and conflictual.
Research focus, themes and research questions
The research programme aims to build the evidence base around the following research themes:

Figure 2: Research Themes

1. CONTEXT: understanding the political, social and economic environment
and where change is/is not happening
2. When and how social and political action empowers people, builds accountabilities, and builds open and inclusive institutions?
2a. Membership: who is involved? Who is excluded?

2b. Triggers: How does social and political action come about? What are the issues? What are the incentives?

2c. Processes and strategies: what was adopted? What worked, when and why? What was the role of technology?

2d. Impacts and unintended impacts/failure:
What makes social and political action effective or not in terms of strengthening E&A? What were the intended/ unintended and short/long (or immediate and ripple) impacts?
3. What role (if any) can external actors play in creating, supporting and influencing social and political action?

Theme 1: The programme will start by examining the context to understand political processes that are enabling social and political action and subsequent change to happen and – importantly – not to happen, particularly in cases where objective external assessment would suggest that social and political action would be in the interests of people and yet does not occur.
Theme 2 will then examine when and how social and political action happens and its impact. This will include looking at who is involved, what makes it happen, and what action is taken. This theme will also look at the role of technology as a means of creating and supporting social and political action and how effective it is in change processes. By looking at impacts (Theme 2d), the programme will determine the relative success and failure of specific action in terms of improving the lives and wellbeing of poor and marginalised women and men.
Theme 3 will examine the role of external actors, including donors, in implementing effective programmes that support social and political action with the clear objective of strengthening E&A. Programme results will directly inform DFID programming, as well as other bilateral, multi-lateral and international agencies, and national governments.
 Indicative research questions
		The questions below set out broad channels of investigation. We are interested in examining relationships between different aspects such as how initial or intended outcomes (i.e. triggers that bring people together in the first place) can have an impact on membership and longer term strategies. We are particularly interested in looking at longer running ‘change stories’ (i.e. did a particular example of social and political action have its intended impact) together with the ‘ripple effect’ of social and political action and capture the unintended, longer-term impacts too. / This is an indicative list of research questions to guide potential bidders in shaping the research programme. The researchers will prioritise within, adapt, and add to these.
Research Themes and indicative questions
1. Context / Where is social and political action happening/not happening? / Where is change happening/not happening? What are the enablers and barriers? Is this connected to social and political action or other ‘pushes’ for change? / How open is the social, economic and political enabling environment? And how does this impact on the opportunities for citizen-state engagement? / How do specific political economy conditions (e.g. open/closed deal nature of economy), shape design and impact of interventions?
2a. Membership / Who are the key actors in citizen-state engagement and collaboration – i.e. civil society, state and private sector? Why do they engage, and how can conflicting interests be overcome? What are the roles of ‘interlocuteurs’/’ infomediaries’ etc? / Who is included/excluded? What is the basis for membership and how does this affect how they work with others, approaches, long/short ‘route’ etc? / What are the challenges to membership – e.g. sociocultural factors, gender, inequality?
2b. Triggers / What are the issues people coalesce around, including what are the triggers – i.e. specific policies or broader issues (e.g. inequality/exclusion)? / How can state, private sector and community actors be incentivised to be more responsive to accountability measures?
2c. Processes and strategies / What entry points were used? What political processes did moments of social and political action use/avoid? What are the targets i.e. govts, private sector, local/traditional leaders? / Do different issues/sectors have greater traction? Are some sectors accessible and others blocked to change – e.g. health vs. extractives? / What tools and approaches are used – i.e. tactical and/or strategic, combinations? / What different types of technology were used in social and political action? / Where ICTs and new media used as a mechanism for creating coalitions and collaborations? Did it contribute to achieving the desired change?
2d. Impacts (immediate and the ripple effect) and unintended and failures / How does social and political action lead to social, economic and political change – e.g. inclusive, open and accountable institutions and responsive governments etc. / What is the impact on empowerment and opportunities – e.g. voice, choice and control? / How do different tactical/strategic initiatives interact? Do they increase effects and impacts? / Does social and political action shift social, political and economic norms? How and why? / What are the unintended impacts of one change in the ‘landscape’ on other areas? Can short-term change undermine long-term change? / When and why does social and political action not work, and not effect change?
3. The role of external actors / Who is supporting/driving processes of change? How can external actors (donors, govts etc) encourage, or challenge social and political action? When can external actors’ interventions do harm/disrupt processes? / What is the evidence on effectiveness between tactical (short-term, single focus) vs. strategic (multiple objectives, long term) interventions. / What is the role of emerging powers (BRICs, Arab states)? / What mechanisms can external actors use to understand and support social and political action?

Research delivery
We envisage a programme that delivers two main strands of work:

Strand 1: Defining research framework, evidence synthesis and historical case studies:
This will concentrate on developing a clear guiding research framework for the programme (including refining research questions and theory of change), compile and assess existing evidence, and undertake historical case studies on social and political action and its impact. The historical case studies will cover a range of local, national and international examples from a range of different contexts in recent history.
Examples of case studies could include: the right to information/food movements in India, campaign for nuclear disarmament in the UK and Europe, 1 Billion Rising global movement to end violence against women, peace processes (e.g. Somaliland, South Africa), trade union negotiations etc.
Strand 2: Operationally relevant field research to directly inform policies and programmes:
The bulk of the programme will deliver operationally relevant research on:

Understanding when and how social and political action empowers people, builds accountabilities, and builds open and inclusive institutions

It is impossible to de-link social and political action from the context within which it happens. This component will include political analysis to understand where social and political action is happening and where the space for action is not allowed, including examining political regimes to understand entry points and barriers, windows of opportunities including favourable issues/sectors as well as understanding ‘critical junctures’.
From there, research will focus on unpacking social and political action to understand (a) how social and political action groups and processes are formed; (b) who is included and who is excluded; (c) the triggers and incentives for action; (d) how they form to achieve different outcomes and the relationship between different layers of outcomes; and (e) wider un-intended influence on outcomes.

Role of external actors in creating, supporting and influencing social and political action

This will include understanding when external actors have a positive andnegative effect on change processes. Given the importance of understanding action in specific contexts, this component will aim to develop a series of mechanisms that practitioners can use to (i) help understand/identify social and political action (ii) ways to measure and understand what impact this social and political action is having; and (iii) what support can be given without diverting it from its original intentions.
One potential approach is ‘trialling’ in which researchers explicitly deliver operational research within or alongside DFID programmes. The proposed programme could offer an explicit vehicle for DFID trialling.
c) Stakeholder engagement and sharing of evidence and lessons
This component will ensure that results are effectively communicated and accessed by decision-makers and other actors. The programme will identify key policy opportunities or entry points in order to achieve impact at scale, and target opportunities for influencing policy and practice at national level in the primary research countries, and at international level.

Activities will include:
- Stakeholder engagement through research process to identify priority questions;
- Production of synthesis materials highlighting key findings, and implications for policy and practice in usable, accessible and diverse formats including peer reviewed articles, briefing papers, video, social media.
- Identification and targeting key policy windows and opportunities by liaising with policy advocacy coalitions.
- Engagement of results with different target audiences through policy dialogue, conferences, and diverse social media.
Methods and country selection
This is envisaged as an interdisciplinary programme, cutting across political science, anthropology, sociology, and economics. The indicative research questions above will require a combination of research disciplines, methods, and substantial fieldwork.
The programme implementers will be responsible for managing the research and subsequent analysis, and will report regularly to DFID, to whom they will be accountable. However, given the cross-HMG relevance of anti-corruption research, and the intended interdisciplinary character, the implementer will be expected to engage with other parts of HMG and offer regular briefings to country offices and embassies, and to relevant policy staff in the UK. Where appropriate, the research teams will also be expected to brief DFID’s partners, including partner governments.
The programme is envisaged to cover 6-8 countries, all of which will be DFID Tier One countries, and some of which will be FCAS (non-fragile environments will be included to allow comparisons to be made). To generate evidence that allows for at least bounded generalisations, components of the programme should be comparative at the state- and/or sub-state level.
Impact and objectives we expect to achieve
The programme will deliver new, operationally-relevant evidence to understand social and political action and when (and if) external actors can support social and political action for progressive change. Uptake will mean more evidence based – and therefore effective – E&A initiatives by DFID and its partners in a range of DFID priority countries, including FCAS.
The outputs of this research programme will be:

High quality peer reviewed and policy relevant evidence on when and how social and political action occurs in different contexts and the effectiveness of social and political action in terms of empowering people, building horizontal and vertical accountability, and building more open and inclusive institutions.

Evidence on the role (if any) external actors can play in creating, supporting and influencing social and political action.

1. Stakeholder engagement through research process and uptake facilitates the operational application of new evidence, including by DFID. This may include:
  1. Synthesis of key evidence from the programme’s research as well as evidence emerging from other DFID and non-DFID research and evaluation in this field;
  2. Engagement with different targeted audiences and using multiple formats to communicate research including peer reviewed articles, briefing papers, social media.
  3. Targeting key policy windows and opportunities particularly related to social accountability, governance, citizen action etc.
  4. Stakeholder engagement through research process to improve capacity of researchers and policymakers to access and use evidence.

The expected outcome is:
Robust new, high quality evidence on social and political action is accessed by policymakers and practitioners, leading to the development of – and investment in – more effective empowerment and accountability policies and programmes by external actors, including DFID and partners.
The intended impact is:
Measurably strengthened E&A in at least 4 DFID priority countries as demonstrated by enhanced agency and voice, more inclusive participation and choice in decision-making for poor and marginalised groups, including women and girls; increased state-citizen collaboration; more control over their lives through transparent, responsive and accountable governments and environments.

The programme will complement other DFID-funded research programmes such as the Effective States and Inclusive Development (ESID) and Political Settlements, as well as draw from programmes supported by DFID’s Governance and Transparency Fund with a focus on citizen-state engagement, social and political change processes leading to strengthened citizen empowerment.

Compliance with the Gender Equality Act 2014

The programme will explicitly address the underlying barriers that prevent women from being empowered to voice their interests and priorities, participate and make choices in decision-making processes that affect their lives, engage in formal and informal political processes and have more control over their lives. Gender will be a priority in the design and implementation, and will include consideration and mitigation of the potential backlash against girls and women resulting from interventions. Gender will be a criteria for assessment of bids. The programme is therefore compliant with the Gender Equality Act 2014.

Annex A: DFID’s E&A Theory of Change

Annex B: E&A Impact Landscape
		Local	National	International
Inclusive Societies (and social accountability)	Short-Term	Mutual support / Shifts in social norms on specific harmful/ discriminatory behaviours	Bridging social networks / Specific national policies focused on marginalised groups (e.g. through gender budgeting etc)
	Long-Term	Higher social capital / Change in gender/social relations and a change in status / Social cohesion and bonding across groups through collective mobilisation	Increased voice and agency (empowerment) in public and private life / New perspectives formed through public deliberation and engagement / Public good outcomes that benefit more. / Greater freedom and opportunities, and increased dignity.	Nationally ratified and domesticated International Cultural and Social Human Rights
Open and Inclusive Politics (and political accountability)	Short-Term	Improved services (teacher attendance, functioning health clinics etc) / Citizen action/civic mobilisation	Responsive policies (single issue) related to marginalised groups. / Reduction in occurrence of corruption
	Long-Term	Greater representation of marginalised groups in political life / Politically engaged and empowered citizens	Increased number of institutionalised, State-led accountability mechanisms / Trust in government and government officials / Functioning service delivery systems / Issue-based politics / New broad-based political parties	New and inclusive regional and international political coalitions and networks / Nationally ratified and domesticated International Civil and Political Human Rights
Open and Inclusive Economies (and economic accountability/ empowerment)	Short-Term	Access to fair credit and financial services / Greater competition at all affordability levels / Lower barriers to market access. / Ability to access, own and/or control natural resources	Clarity in regulatory environment / Strengthened consumer and producer rights / Fair tax regimes. / Equitable distribution of natural resource wealth	Corporate Social / Responsibility / Fair international tax regimes (e.g. in extractive sector).
	Long-Term	Property rights protected for all / Wider access to markets at local and national levels / Economically empowered and active citizens	Rule of law that works for all / Sustainable investment climate (security and predictability) / Economic/ structural transformation that enables development for all. / New economic coalitions.	Regional economic integration / Nationally ratified and domesticated International Economic Human Rights

## Appraisal Case

What are the feasible options that address the need set out in the Strategic case?
This appraisal aims to answer two questions:
- Which delivery option is likely to work best in practice?
- Which option maximises the impact of every pound spent to improve poor people’s lives?
It considers four options for delivering the objectives set out in the strategic case:
Option 1: ‘Do nothing – business as usual’
DFID does not invest in a new E&A research programme and funds are used elsewhere.
Option 2: Delivery through an open competition with several components
The research programme would be divided into specific ‘projects’ that would cover the research strands set out above and would be tendered separately. This would include a call for evidence synthesis, historical case studies, country/event-specific operational research and evidence synthesis. A separate contract would be awarded to synthesis evidence from the projects and engage in research uptake activities. An open competition would enable DFID to identify a range of organisations capable of delivering the programme’s objectives. Potential bidders could include University Departments in the UK or elsewhere, private contractors, and NGOs.
Option 3: Design and let a new Research Programme Consortium (RPC)
An organisation/consortium identified through competitive tender would implement this work. The winning proposal would be expected to demonstrate a holistic approach to primary field-based research, be able to undertake thorough analysis, and to present an effective strategy for evidence dissemination. Research would be implemented by provider, consortia partners, or researchers identified through a transparent process
Option 4: Hybrid Option: i) a competition for theoretical and historical case studies and ii) an RPC for operational/implementation research
The research programme would be divided into two separate but closely linked sections. The first would be a competition for theoretical and historical case studies and research through an established research commissioning organisation e.g. a UK Research Council. Operational/implementation research would be carried out by a RPC (as in Option 3). The RPC would also be responsible for developing a core secretariat to ensure coherence between the two strands, develop a research framework, synthesise findings and implement uptake strategies alongside all research partners.
Strength of evidence
This table summarises quality of evidence and underlying delivery assumptions for each option
Option	Evidence rating
Do Nothing	Strong on evidence gaps – the evidence gaps in understanding social and political action are clear and well accepted.
Delivery through open competition with several components	Medium-Strong on previous experience of this model - GCSD has a range of existing, successful competitive granting programmes including poverty alleviation (with ESRC) and urban violence (IDRC). We negotiate partnerships via a Memorandum of Understanding, rather than competition.
Research Programme Consortia	Medium-Strong on previous experience of this model – RED has significant experience in managing RPCs, including clear guidance on structures, reporting, financial management and value for money.
Hybrid Option	Weak-Medium on previous experience of this model – this would be a new approach to GCSD research programme. We have good evidence of the strengths and limitations of competitive research funding programmes and RPCs but this hybrid model tests a new combined approach.

What are likely impacts (+ve and -ve) on climate change and environment for each option?
Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation.
Option	Risks and impacts: category A, B, C, D	Opportunities: category A, B, C, D
1	C	C
2	C	C
3	C	C
4	C	C

Risks and impacts: The programme is assessed as having very low or no environmental impacts and a mild impact on climate, due to operational aspects such as office consumables and travel, primarily international air travel. These are assessed to be the same regardless of implementation option. Standard mitigation actions should include minimising and offsetting air travel; using economy flights as standard; and using recycled paper or paper from sustainably managed forests.
Opportunities: Implementation could offer opportunities to social and political action aimed at improving natural resource management and environmental stewardship. Evidence demonstrates that natural resource management and resilience against climate change are important for pro-poor growth, and empowerment is a contributing factor for interventions in this area.[34] For example, in Gujarat, India, Social Justice Committees within local elected bodies have been successful in providing dalits (lower castes) with benefits related to natural resources.[35] Although it would be over-generalising to assume that E&A alone brings better environmental management and ensures long- term sustainability; it is fair to say that social and political action can improve access to and management of natural resources, can ensure people are involved in resilience activities to protect against climate change and are engaged in processes to make sustainable environmental policies.
[34] Prato, B. & Longo, R (2012) ‘Empowerment of poor rural people through initiatives in agriculture and natural resource management’, OECD, 2012.
[35] Mohanty, R. (2010) “The Infinite agenda of social Justice: Dalit Mobilizatio in Indian institutions of local governance.” Spaces for Change: The Politics of Citizen Participation in New Democratic Arenas, Edited by Andrea Cornwall and Vera Schattan-Coelho.
If any, what are the likely major impacts on social development?
As the strategic case sets out, this research programme is explicitly focused on improving social development outcomes for poor people. Positives impacts are expected to be high, regardless of option (2,3,4) taken. The operational research produced should make DFID interventions more effective.
For FCAS, what are the likely major impacts on conflict and fragility, if any?
DFID expects to spend 30% of its budget in FCAS by 2014 and this is likely to continue in future years. DFID has developed a framework for engagement in statebuilding and peacebuilding in FCAS. Empowerment and accountability approaches can contribute to statebuilding, peacebuilding and improved development outcomes in a number of ways:
- Where it is not possible to work with an incumbent regime, E&A may be the only entry point for development agencies and can help improve human development outcomes (e.g. DFID’s experience in Zimbabwe and Burma).
- FCAS often provide opportunities to challenge previously entrenched power structures and bring about transformations that can significantly contribute to long-term peace and development.[36]
  [36] OECD, (2010) Do No Harm: International Support for Statebuilding Guidance Note, http://www.oecd.org/dac/incaf/donoharminternationalsupportforstatebuilding.htm
- E&A is an important component of support for inclusive political settlements. Interventions can help politically empower excluded groups and support access to resources and capacities to influence policy-making processes, make demands and hold state institutions accountable. At community level, E&A interventions have been shown to help foster local ownership of interventions, secure commitment from communities to maintain assets, improve the quality of implementation and contribute to sustainability.[37]
  [37] World Bank (2007), Aid that works: successful development in fragile states
- Evidence reviews[38] on gender, state-building and peace-building, highlight the importance of inclusive processes and opportunities that include and reach girls and women and enable them to access services, take part in decision making, access decent jobs, and be safe and secure.
  [38] Domingo, P, R. Holmes; AR Menocal, N Jones with D. Bhuvanendra and J. Wood. (November 2013) Assessment of the State of Evidence of Gender Equality, Peacebuilding and Statebuilding. Report for DFID
At least one focus country will be a FCAS, with a strong preference for more. The research will aim to inform in-country activities on how policies and programmes may more effectively support progressive change in that context, plus wider operational lessons for strategies in other FCAS. While empirical evidence on whether or not or how this may contribute to stability or reduce conflict is likely to be beyond the scope of the programme, it is anticipated that activities will not have any negative impact.
What are the costs and benefits of each feasible option? Identify the preferred option.
The mechanism for evaluating the rate of return to research is a results chain that links research undertaken to a policy intervention/change/reform (or lack of) and which then relates the policy intervention/change/reform to a discernible outcome.
This results chain has three components – the link between the research undertaken and the policy change (attribution), the link between the policy change and the outcome (identification) and the quantification of the outcome itself (measurement). Such calculation needs three questions to be addressed: i) did the research influence policy thinking/decisions/processes (the attribution problem); ii) did the policy intervention/change/reform lead to the observed outcome (the identification problem) and iii) can the benefits of outcome(s) be quantified? (the measurement problem).
Figure 1 sets out the components of the results chain, including the ‘transmission belt’ linking research producers to those who use it; and to those who are the ultimate beneficiaries of the research. It also sets out factors that may affect the working of the chain, which in turn may lead to difficulties in attribution and identification.
A DFID-funded literature review on Rates of Return for Research[39] used this framework and concluded that while the returns to social and economic research are likely to be high, and that it may be possible in theory to determine quantitative estimates for the economic return, the informational requirements for the counterfactual analysis are extremely large. Moreover, the calculations of the returns to research are likely to be very sensitive to minor changes in the assumptions regarding links from research to policy with possible problems across all the three areas of Attribution, Identification and Measurement.
[39] Sen Literature Review on Rates of Return to Research 2010. See also Kunal Sen and Geoff Hoare, (2005) Rates of Return to Research: A Literature Review and Critique (Enterplan in association with ODG-DEV and CEG.
As a result, no quantified cost benefit analysis is undertaken in this appraisal. However, the appraisal does consider key design and cost effectiveness issues to ensure that there is a greater chance of the inputs effectively translating into outputs and outcomes. In other words, to improve the probability that the research will deliver returns at the higher end of the probability distribution.
Figure 1: The Results Chain for Different Types of Research
Research Programmes/ Centres
The Attribution Problem
Policy Change/ Intervention /Reform
The Identification Problem
Outcomes-Tangible-Intangible
The Measurement Problem
Impact
Communication
Of Research Findings
Contextual Factors

Option 1: ‘Do nothing - Business as Usual’.
Doing nothing- would continue the status quo. We would continue to have a weak understanding of the effectiveness of existing interventions and may continue to commit public funds to ineffective projects.
Option 2: Delivery through an open competition with several components
The research programme would be divided into specific ‘projects’ that would cover the research strands set out above and would be tendered separately. This would include a call for evidence synthesis, historical case studies, country/event-specific operational research and evidence synthesis. A separate contract would be awarded to synthesis evidence from the projects and engage in research uptake activities.
DFID will have freedom to define the research agenda and direct research activity in line with its interests, and to choose the most suitable supplier for each component competitively. Competition will occur throughout the programme. An open competition would enable DFID to identify a range of organisations capable of delivering the programme’s objectives. Potential bidders could include University Departments in the UK or elsewhere, private contractors, and NGOs.
The disadvantage of this approach is that a considerable intellectual and management requirement would be placed on DFID in terms of defining the agenda and procuring and managing a range of separate contracts. Coherence across the research areas could be undermined by separating the contracts (and without an overall facilitator/coordinator), as in turn may uptake and impact.
For these reasons this approach is rejected.
Option 3: New Strategic Partnership – Research Programme Consortium (RPC).
A single organisation or a Research Programme Consortium (RPC) identified through competitive tender would implement the programme. The winning proposal would be expected to demonstrate a holistic approach to primary field-based research, be able to undertake thorough analysis, and to present an effective strategy for evidence dissemination. Research would be implemented by provider, consortia partners, or researchers identified through a transparent and competitive process
The advantage of this approach is that it would also be most straightforward to procure and manage, with one competitive process significantly reducing DFIDs transaction costs. Designing and letting the competition would require substantial preparation and promotion by DFID staff in order to encourage the development of sufficient potential RPCs to ensure active competition, high ambition and quality in proposals, and driving down costs.
In terms of uptake, it is should be easier to synthesise and communicate findings emerging from a single RPC. However, care will be needed in the design and procurement phase to ensure that bidding consortia are incentivised to develop policy links and uptake channels.
A disadvantage of this approach is that competition would be focussed at the point of choosing a winning consortium: there is little role for competition between individual researchers in the RPC so there is risk that research becomes supply-led and value for money suffers.
It may be appropriate to reserve a specific percentage of research funds for further competition throughout the lifetime of the programme in order to guard against capture of the research agenda. The RPC could use these to let further open competitions and limited competition between the RPC members. DFID could play an active role in this process, exercising either approval or a casting vote.
Option 4: Hybrid Option
The hybrid would divide the programme into two separate but linked sections.
The first would be a competition for theoretical and historical case studies and research managed through an established research commissioning organisation (such as a UK Research Council).
The second would be for operational/implementation research designed and implemented by a RPC (as in Option 3 above). The RPC would also be responsible for providing a core secretariat responsible for bringing together the two strands, developing a research framework, synthesising findings and implementing uptake strategies alongside all research partners.
This approach would aim to bring the benefits of continued competition through a research council. Coherence and uptake would be managed through a separate dedicated RPC. Efforts will need to be made however to ensure response to the coherence and uptake component. Recent experience with the ESRC Poverty Programme in trying to procure uptake services suggests that the market is not always willing to respond. Moreover the timeframe needed to procure research through the research councils will mean that there is likely to be a significant lag between call and delivery of research. Efforts will need to be made to ensure the different aspects of this approach are well timed.
Option 3 versus Option 2: while there is a risk of ‘capture’ with option 3, steps can be taken to minimise this through a requirement for part of the research funds to be open to competition from outside the RPC. Option 3 will require less DFID oversight and management and is likely to lead to a more coherent research programme.
Our assessment is that option 3 is preferable to option 2.
Option 3 versus Option 4: While option 4 is likely to be more competitive on the individual research projects it will require additional inputs to develop coherence and maximise uptake. Past experience with the poverty alleviation programme identifies this as a potential risk.
Option 4 is also likely to have longer lead times for the research activities. Provided the competition element of option 3 can be addressed then this is the preferred option as it is likely to deliver a more timely research programme with greater coherence; a clear strategic role for DFID; and a reasonable management burden.
The overall costs associated with options 2, 3 and 4 are likely to be broadly similar with an element required for administration of each.

Our overall assessment is that Option 3 – a single new RPC - is the preferred option.

Theory of change for E&A Research Programme
Our Theory of Change is based on a standard research delivery and uptake chain. In the proposed E&A research programme, the most important assumptions (and associated risks) are:
- DFID operational teams commit time and effort throughout the research process to ensure that the new research focusses on operational priorities, and that emerging evidence is used to inform more effective investment and implementation choices.
- Policy makers can be influenced by new evidence, including in environments where vested interests directly oppose change.
See E&A Research Programme Theory of change diagram below.

What measures can be used to assess Value for Money for the intervention?

DFID defines value for money as the best use of resources to deliver the desired impact, and effectiveness as achieving a sustainable impact for intended beneficiaries. Three elements are important: economy, efficiency and effectiveness.
In terms of economy: DFID will monitor all costs at component level and use open competition in the procurement to drive value for money. In evaluating bids received against the published criteria, careful attention will be paid to (i) ability of teams to meet the objectives (ii) proposed costs across the components (iii) mix and cost of staff time to conduct research and manage the programme (iv) strength of proposed links to programmes and policy makers.
In terms of efficiency: DFID will monitor the volume and quality of the research being produced, by tracking publications in peer-reviewed journals and potentially using citation indices. DFID will ensure measures for quality assuring research and outputs are robust, including peer review. DFID will also estimate the unit costs of publication and where possible the unit cost relative to measures of quality developed (e.g. citation indices).
In terms of effectiveness: DFID will produce case studies and other examples of where research findings have been adopted into policy or practice to improve the well-being of adolescent girls. DFID will also monitor whether the tools and methods developed as part of this programme are being used by other researchers to contribute to a coherent body of research.
This type of intervention does not easily lend itself to monetising the outputs for the reasons presented above. It is also in the early stages of design. A number of key value for money indicators will form part of the assessment criteria by which bids to undertake this work will be assessed .

Summary VfM statement for preferred option
Funding estimate: £6.5m - based on the assumption of a five year programme involving thorough primary research in 6-8 countries, mostly DFID Tier countries including both Fragile and Conflict Affected States and non-fragile environments, followed up by analysis, reporting and outreach work. This budget is comparable to other research programmes in GCSD’s current portfolio with similar expected outputs and outcomes (e.g. ESID, SLRC, JSRP etc)

 The key value for money indicators for the whole programme include:
- Monitoring of all costs: at all level and spot checks within the management of components;
- Monitoring of costs to ensure that research uptake is properly resourced and planned;
- Unit costs of research outputs;
- The volume and quality of evidence produced;
- The adoption of research findings into policy and practice;
- Evidence for the link between new evidence and implementation

Commercial Case

A competitive procurement process will be used to select the lead institution for a Research Programme Consortium (RPC - a group of individuals or representatives from organisations) to manage and run the programme.
In parallel to submission of this Business Case, RED will work with Procurement and Commercial Department (PCD) to publish a Prior Information Notice (PIN). The PIN will alert the market to the potential upcoming call. We will work with PCD to ensure that the PIN is available to academic and other bodies with a track record in the field of empowerment and accountability and associated research.
DFID will advertise the contract requirement on the DFID website and will then follow OJEU principles.[3] All interested suppliers will be invited to notify DFID of their interest in tendering for the services through a brief Expression of Interest. DFID will then select a number of interested parties who will be invited to tender for the research programme.
[3] With more than 50% of funding going to actual research, the programme is exempt from official OJEU processes. However, we will follow this as it is best practice.
This process will provide:
- Clear transparency around choice of partner, chosen by fair and open competition.
- Competition, to drive down costs, improve value for money, drive innovation, encourage new entrants and help build capacity in the market.
- Specificity: DFID can design the programme to meet accurately our priorities, rather than negotiating with a programme established for another purpose.
- Expertise: A DFID panel with relevant expertise will appraise concept notes and proposals.
- Peer review: The inception report will be peer reviewed (external to RED) to ensure the research proposed will add up to a coherent body of evidence.

As an additional safeguard, the contract will include an inception period during which the contractor will be expected to develop a detailed programme, finalise the logframe/indicators, the yearly budget and workplans. The SRO will lead an appraisal process for the final inception report to decide whether the full programme should proceed, based on outputs delivered during the inception phase and the proposed implementation plan.

## Financial Case

All funding for this programme will be from RED Governance, Conflict and Social Development (GCSD) programme budget. The proposed programme runs from financial year 2015/2020, complying with FCPD guidance. The investment goes beyond the current financial settlement. The Divisional Accountant will be informed and will arrange to process it through FCPD and HMT once approval has been granted.
The expected cost of the programme is £6.5m. over five years (2015/2020). This budget reflects the planned five year programme involving primary research in 6-8 countries (including FCAS) and is comparable to other research programmes in GCSD’s current portfolio with similar expected outputs and outcomes (e.g. ESID, SLRC, JSRP etc). The table below gives an approximate breakdown of these costs by programme year.
Yr 1	Yr 2	Yr 3	Yr 4	Yr5		TOTAL
£0.5m	£1.5m	£1.5m	£1.5m	£1.5m		£6.5m

With the expected programme start in the last quarter of FY 14/15, the programme will cover six financial years. A detailed breakdown of expenditure per FY will be approved when the contract is signed.
Forecasting costs will be the responsibility of the implementing agency (the contractor). The accuracy of the financial profile and forecasting will be closely assessed as part of the inception phase appraisal and during the annual programme reviews.
Payment for directly procured services /deliverables will be made periodically to the contractor upon satisfactory completion of agreed work programmes, achievement of objectives/targets and on receipt of invoices. This will be governed by the specific terms and conditions of the contracts agreed between DFID and the implementing agency.
DFID has a zero tolerance policy on fraud, and will apply standard measures to ensure this policy is adhered to.[4]
[4] These standard measures include, among other provisions, close engagement with partner organisations’ audit processes and scrutiny of their financial statements; DFID will ensure all spend is properly accounted for. We will work with the implementing agency to strengthen financial oversight, where required and where fraud is detected we will demand repayment in full. Continued disbursement of funds will be contingent upon adequate financial oversight mechanisms.
The tendering process will ensure that the selected implementing agency has financial management and accountability systems in place. All programme funds will be fully under the control of the lead institution of the RPC who will be held accountable. All programme expenditure will be subject to full auditing on an annual basis.
Monitoring and accounting of expenditure will take place using the ARIES system; DFID project management procedures for checking expenditure against agreed work plan/activities to ensure Value for Money; and compliance with agreed fees and reimbursable costs. The implementing agency will submit quarterly detailed expenditure summaries and quarterly forecasts of programme expenditure to DFID, all in an agreed format. GCSD will allocate a Senior Responsible Officer to be accountable for this programme.

Management Case

DFID management and governance
DFID will retain executive authority for the programme, including final approval of budgets, workplans and strategy. At inception, DFID’s Senior Responsible Owner (SRO) will be the Social Development Advisor, GCSD Research Team. The programme will be managed by the GCSD research team.
DFID Heads of Office and Social Development/Governance Advisers will be the first option for engagement between researchers and DFID country programmes, and we will work with DFID’s Social Develoment and Governance Heads of Profession (HoPs) to make this as strategic and efficient as possible. We will aim to use Advisers’ provision for ‘cadre 10%’ time to incentivise their engagement, with their designated ‘Technical Quality Assurer’ (TQA) helping to ensure that Advisers’ commitments are met – both in terms of time deployed and quality of delivery.
Management and governance of delivery partners
The programme will be delivered through a Research Programme Consortium. We will be looking for an organisation or group of organisations to provide overall management and strategic direction. We will structure competition so that bids contain:

- A group of individuals or representatives from a group of organisations to provide overall organisation, management and leadership for the programme.
- A nominated Executive Director, with a track record in research management and in directing large, complex, multi-stakeholder research programmes.
- A clear partner/resource to undertake and lead work on Monitoring and Evaluation and Research into Use activities.
- A well-developed TOR for commissioning research on the themes outlined in this business case, plus a well-defined work programme and schedule for this process, ensuring that gender analysis and the use of disaggregated data is part of the proposed research practice.
- A proposal on how they would commission future research areas, and how they will minimise management costs associated with this.
- A realistic budget to cover the entire five year programme including provision for M & E work component.
- A draft TORS and proposed composition for/of the Consortium Advisory Group.(CAG).
- A Duty of Care plan.

Governance

A Consortium Advisory Group (CAG) will be established to advise the RPC on strategy, taking an overview of the programme and its progress. DFID will be a member of this CAG, but will not be bound to take advice from the CAG. Executive authority, including all final decisions regarding budgets, workplans and strategy, will be retained by DFID. The CAG will meet at least twice per year to discuss/review work plans/activities/past progress. The CEO will record the procedures and advice.
In addition to the CAG, DFID expects the RPC to establish mechanisms to enable the programme to work with a wider stakeholder group, either as a forum or a more informal network, to exchange views on technical issues relating to the implementation process and content and to collaborate effectively with the consortium partners.
The final TORS for the high level posts and the CAG , the consortium governance structure will form part of the Inception Report which DFID will appraise at the end of the Inception Phase.

Roles and Responsibilities

Consortium Advisory Group

- Provide advice regarding strategic direction and the programme as a whole.
- Advise on the programme research strategy
- Advise on research budgets
- Advise on all hiring, and dismissal of senior staff in the Research Programme Consortium
- Advise on research contracts above a set limit
- Receive and advise on programme reports generated by the Research Programme
- Take an overview of all theme-based research consortia work

Consortium Executive Director

- Provides managerial and intellectual leadership to the programme
- Develops strategic research plans and generates reports for the programme
- Accountable for the programme delivery of outputs
- Coordinates all themes within the portfolio
- Develops and maintains relations with relevant stakeholders
- First point of contact with DFID

Timeline, delivery plan and milestones
We expect an inception phase to be complete in the first 6 months; research field work and analysis to be conducted in years 1-4; and the final year to be dedicated to research outputs, facilitating uptake, and operational application. In year 5 we expect to begin to measure results at outcome level, and measure convincing progress towards impact.
Monitoring, measuring and evaluating progress and results
The two components will each define a Monitoring and Evaluation strategy and these will inform programme level M&E. All M&E will focus on:
- Progress in completing inputs, activities and expenditure in line with agreed work plans.
- Progress towards, and achievement of, objectives and targets in programme logical framework
- VfM in use of the programme funds
- Changes to programme risks (summarised in risk matrix and in partners’ risk registers)
Theory of change (ToC) and log frame
The Inception phase will be used to refine draft ToC that maps out the process by which research will lead to better outcomes and contributes to programme impact. DFID’s evaluation department will provide guidance and quality assure this.
Based on refined ToC and stakeholder map, the logframe will be finalised with the following parameters:
- SMART indicators-- specific, measurable, achievable, relevant, and time-bound— defined for impact, outcome and outputs, including process indicators if most appropriate for early years.
- Clear data sources specified for each indicator.
- Baselines determined for outcomes and impacts, in coordination with Research Uptake Team.
- Detailed timeline for monitoring activities, incorporating DFID’s reporting requirements (e.g. inception phase report; annual technical reports and internal learning events; six monthly financial reports; a mid-term review) and management and advisory group meetings.
Measuring impact
Evaluation of impact will be based on the refined theory of change. The value added of establishing counterfactual scenarios to attribute the impact of the programme will be worked through in the inception phase. DFID will undertake an independent evaluation in Year 5 of the programme and will retain a budget line for this purpose.
DFID’s budget management and contingency
At design stage, DFID will reserve 10% of the budget to cover independent evaluation, programme level monitoring, additional research uptake, and contingency planning (e.g. responding to changes in risk, new opportunities), and performance-related budget awards for the best or most operationally important research.

Key risks to the success of the programme
The overall risk rating is medium/high. The key risks are:
Delivery of a sizeable and complex programme; involving multiple partners and countries. Medium risk /High impact.
Mitigating measures: The selection criteria will include : consortium’s demonstration of appropriate range and expertise, evidenced by track record; This includes both academic/technical skills, and managerial/administrative capacity, including means and the proven capability to address HR, financial and contracting issues within the consortium with a talented CAG. DFID will monitor this closely, drawing on experience from mitigating this risk in other RPCs. As an additional safeguard, the work will begin with a six-month inception phase, offering DFID the opportunity to break off this work, paying only sunk costs, if it appears that this risk may be realised. Hence, after the inception phase, the probability of this risk will be able to reduce from ‘medium’ to ‘low’.
Research partners fail to deliver on time; misuse of funds. Medium risk/high impact.
Mitigating measures: The assessment of the bids and inception report appraisal will consider the likelihood of delivery of the work to an agreed schedule. The lead institution will be expected to link payments to deliverables and include penalty clauses in sub contracts to the necessary incentives for timely delivery and to quality. The selected consortium will have stringent accounting rules.
Research procured fails to have policy relevance. Low risk/High impact.
Mitigating measures: The consultation process prior to developing th is business has identified the research gap clearly. DFID expect the technical bid to set out the key policy stakeholders and the inception report to establish formal mechanisms to ensure consultation with these stakeholders and keep up with current and emerging needs.
Reseach findings are disparate and do not add up to a coherent body of evidence. Low risk/ low impact.
Mitigating measures: The structure of the RPC with the appropriate networks and skills to propagate research findings and manage outreach work effectively will address this risk.
Poor quality research funded. Risk Low/ High Impact.
Mitigating measure: DFID will select a consortium with a strong focus on research excellence. The programme wille stablish peer review mechanisms to provide researchers the incentive to produce quality outputs.
Reseach does not impact on potential users. Medium risk/ High Impact.
Mitigation measure: Detailed research uptake path ways will be part of the inception phase work. Uptake pans will also be peer reviewed.
Risks, review points, and exit
At the end of the inception phase, and a mid-point in the five year research programme we will build in a review point at which DFID will consider whether these and any new risks identified are fundamentally threatening the success of the programme.
If necessary we would recommend DFID’s exit – from support for research in any particular country; any particular partner or programme component; or the entire programme.