## Annual Review

Title: Africa Regional Department Cross-Portfolio Third Party Monitoring
Programme Value £ (full life): £3,626,726		Review date: June 2021
Programme Code: / 300765	AMP start date: 01 August 2019	AMP end date: 30 September 2022

Summary of Programme Performance
Year	2019/20	2020/21
Overall Output Score	B	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	51207398
DevTracker Link to results framework:	52378730

A. SUMMARY AND OVERVIEW

The Third-Party Monitoring (TPM) programme has been designed to support independent monitoring of the programmes funded by FCDO’s Pan Africa Department (PD). TetraTech International Development (TT) is the leader of a consortium that delivers TPM activities for programmes across the PD portfolio. Their main consortium partner is ORB International, a research agency with extensive experience of working with local partners across Africa. TT is responsible for undertaking six TPM activities that will provide independent feedback on the activities and results delivered by our programme partners, as follows:

1. Data Systems Reviews (DSRs); to review the systems our partners have in place for collecting, aggregating, and reporting data on programme results.
2. Activity Verification Visits (AVV); which includes field visits to verify a sample of reported partner delivered activities and inputs.
3. Beneficiary Feedback (BF); which involves interviewing direct recipients of programme outputs to collect some independent feedback on the quality and usefulness of the outputs.,
4. Rigorous Results Verification (RRV); a sample-based data collection to verify the accuracy of selected reported results,
5. Expenditure Monitoring (EM); to review a sample of records of payments down the delivery chain.
6. Additional ad hoc visits: to follow up on areas of specific interest identified during the above TPM activities.

These activities will help to strengthen PD confidence in what is being delivered and achieved by programmes, particularly in areas where staff are unable to monitor programme delivery or results directly through field visits.

Summary supporting narrative for the overall score in this review
The programme has scored an A, which we deem appropriate for the reasons outlined in this review. This review covers a 15-month period combining FY20-21 with January-March 2020, as agreed with TT in November 2020. This is to enable a transition in programme reporting periods from calendar to financial year. Within this reporting period TT delivered all milestones to at least the agreed quality standards and on occasions exceeded milestone expectations. TT was able to achieve this through a very challenging year which included adapting and flexing in response to Covid-19 and its related restrictions, and a reduced annual budget reflecting reduction in UK GNI and ODA.

Lessons
- Programme Teams find it beneficial to have the PD TPM Programme Team present when discussing the initial scope of TPM activities with TT.
- Programme Teams questioned whether it was maximising Value for Money (VfM) for DSRs to look at reporting/Logframes which PD M&E advisors could do and whether it would be more beneficial for DSRs to have a greater emphasis on partners’ data systems and M&E capacity which are much harder for FCDO to verify themselves.
- Strict deadlines and unforeseen delays in delivery can result in tight deadlines which can place pressure on Programme Teams and implementing partners and in turn affect the quality of deliverables.
- TPM recommendations should be realistic and actionable and take programme context into account. Strong TT understanding of programmes, built through effective engagement with programme teams and sound knowledge management, facilitates this.
- Programme Teams felt that the PD portfolio could benefit from more targeted learning products and events, more frequently than once per year.
- Implementing partners were keen to understand more about the purpose and benefits of TPM for FCDO: including partners in learning events as planned before Covid-19, virtually if necessary, could help strengthen buy-in to TPM.
- Early feedback from Programme Team and implementing partner interviews shows that some PD Programme Teams are not yet using TPM findings and recommendations to pursue improvements to PD programmes with partners.
- At the onset of Covid-19 it appeared no fieldwork and data collection on the ground would be possible. However, rates of infection and restrictions varied within and across countries in Africa, and with the right local intelligence and compliance with safety norms, by early 2021 it was possible to undertake TPM fieldwork on the ground for three programmes.
- As a result of various challenging internal and external factors over the past 15 months (particularly Covid-19 and reduction in UK ODA) bunching of TPM deliverables has placed considerable strain on TT TPM resources and driven up TT’s internal costs through ‘crashing’ (increasing resource utilisation to deliver milestones in a shorter timeframe). Earlier confirmation of budgets and PD programme status in 2021/22 would enable better spacing of deliverables and potentially better value for money.
- There has been a substantial amount of unanticipated recurring management effort required by TT at portfolio level as they have worked with FCDO to adjust financial envelopes during the period and adapt to changing TPM needs in the context of Covid-19 and the removal of JSD form the contract.
Recommendations
- When starting a TPM activity, TT to set-up a three way kick off meeting with the PD TPM Programme Team, the Programme Team and TT to agree priorities in line with TPM scope.
- When TPM activities are delayed or postponed, TT to circulate an updated timeframe to allow all parties to plan their time to feed in as needed.
- TT to ensure that FCDO feedback on reports is disseminated across all TPM authors and used to continually improve TT’s drafting and quality assurance of TPM reports.
- FCDO and TT to agree revised coverage and frequency of TPM provision across PD programmes in light of reduced budget for 21/22, by June 2021. The main TPM activity priorities for the year ahead, assuming affordability permits, are to ensure 1) that any PD programme that would benefit from a DSR, that has not yet had one, get the opportunity; 2) that all PD programmes without a separate TPM arrangement are offered a minimum of one AVV/BF visit; and finally 3) selective use of EMs, follow-up DSRs and potentially RRV where programme teams identify a strong evidence need. in FY21/22.
- FCDO and TT to review the DSR and AVV/BF methodology; to ensure firstly the DSR prioritises the assessment of data systems dimensions that cannot easily be verified by FCDO, and provides a basis for clear recommendations on strengthening disaggregation in all future DSRs; and to consider adding standardised questions on safeguarding in any interviews or questionaries undertaken with beneficiaries, by July 2021
- PD TPM team to consult PD Programme Teams and senior leadership team on how learning synthesis products and events could better meet their needs in 21/22 and confirm any refinements needed to the format, focus or frequency of learning synthesis products and events to TT by July 2021.
- As Covid-19 is likely to remain a challenge throughout the next 12 months, TT and FCDO to continue to assess if in country TPM fieldwork is possible for every TPM activity, include it wherever feasible, and continue to adapt remote data collection tools to ensure high quality data is collected independently even when fieldwork isn’t possible.
- TT and FCDO to look for efficiencies to reduce programme management costs to maximise the funding available for direct TPM activities as part of the contract amendment by July 2021.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The PD TPM team held a workshop with TT in Q2 of 2020 to review and refine the initial theory of change informed by TTs experience so far of delivering TPM for PD programmes an updated version of the TOC can been seen in Annex A.
Overall, the pathways in the theory of change remain valid based on the evidence to date. While there have been substantial changes to the scale and scope of TPM services over the reporting period, anticipated pathways to change remain relevant.
Given the delays in TPM implementation during the reporting period, there is relatively limited evidence so far on outcome and impact levels of the theory of change. As many TPM activities were concluded in the last quarter of FY20-21, it is not yet possible to ascertain the extent to which recommendations from these activities have been acted on, and whether they have led to desired outcome and impact level changes. But there are some assumptions for which we have evidence from the recent learning synthesis and the feedback obtained from programme teams and partners for this review, where we can see they are standing true. The TPM reports delivered so far have been providing a greater assurance on what is being delivered within individual programmes, and various DSRs conducted have identified specific ways in which the reliability and disaggregation of results can be improved. The extent to which learning can be synthesised by commonalities in activity/geography etc to inform broader learning across the ARD portfolio will depend on the TPM coverage of the ARD portfolio and the specific agreed focus of the TPM activities for FY21/22.

Feedback received so far from interviews with implementing partners and programme teams suggests TPM findings have been valuable. The key challenge seems to be ensuring that the recommendations are as equally useful which can be challenging given the scope of individual TPM activities. The most robust evidence we have that the outcome level assumptions stand true comes form the annual TPM survey which highlighted that 93% of PD Programme Teams perceive TPM findings and recommendations to be at least useful. We also checked this logic with IPs and of those that responded all IPs agreed that findings are recommendations were at least useful. The Survey also confirmed that 70% of programme teams reported that their understanding of the strengths and weaknesses of their programme results reporting has increased because of TPM.

It has become clear through discussions with programme teams and implementing partners the importance of ensuring that all parties are clear on the purpose and scope of TPM. It is important that there are clear parameters set out from the start on what TPM can and cannot do. To help facilitate this and ensure that FCDO expectations are clear, a three way kick off meeting with the PD Programme Team, IP and TT team ensures a common understanding and manages expectations in line with the TPM contract scope.

It was clear from interviews with implementing partners and programme teams that TT conduct themselves in a professional manner which is important in building a relationship of trust. Implementing partners did however noted the importance of keeping partners updated on changing workplans so they can plan their time for fact checking draft reports, and that the roles and responsibilities are made clear to partners. It is also important that recommendations are realistic and actionable even if they are smaller impactful recommendations.

Based on TT and FCDO experience to date, the theory of change has been revised to include two further outcome level assumptions and an underlying programme hypothesis as follows:
- Portfolio learning will be most effective where relevant learning from individual programme TPM is synthesized to identify commonalities across programmes/partners/geographies and guided by PD priority evidence needs, and where there is a sufficient volume of PTM activities to yield commonalities.
- Scale and scope of TPM support to PD programmes is sufficient to provide greater assurance on what is being delivered across PD’s portfolio.
- Enhanced VfM opportunities are provided through a regional TPM contract.
Lessons
- As part of the programme team case studies FCDO found that Programme Teams find it beneficial to have the PD TPM Programme Team present when discussing the initial scope of TPM activities with TT to ensure that identified TPM deliverables align to the programme’s reporting needs and the overall agreed scope of the PD TPM contract.
- Strict deadlines and unforeseen delays in delivery can result in tight deadlines which can place pressure on Programme Teams and IPs and in turn can affect the quality of deliverables as staff and partners have less time to review reports in detail and to consider the implications of TPM findings. Tight deadlines were required to meet FCDO reporting commitments following the delay in commencing delivery of TPM work as a result of the level of contractual and financial change required to the programme in FY 20/21. These shortened timeframes can cause harm to relationships or buy-in to TPM from IPs when they do not allow sufficient time for meaningful review and input from relevant stakeholders on the IP side.
- From discussions with Programme Teams and IPs it is clear on the importance of recommendations being realistic and actionable and taking programme context into account. This is important in terms of maximising the value from individual TPM activities but also to help ensure implementing partners’ buy-in.
Recommendations
- When starting a TPM activity, TT will set-up a three way kick off meeting with the PD TPM Programme Team, the Programme Team and TT to ensure a common understanding of the scale and scope and manage overall expectations.
- Using the overarching workplan as a basis to spread out TPM activities throughout the year, when TPM activities are delayed or postponed TT to share an update to the more detailed activity timeframe with the TPM team, Programme Team and IP on expected timings for TPM fieldwork, draft and final reports, to allow all parties to plan their time to feed in as needed.
- TT to ensure that FCDO feedback on reports is disseminated across all TPM authors and used to continually improve TT’s drafting and quality assurance of TPM reports.
- TT to ensure that recommendations are realistic and actionable and take programme context into account to help strengthen relationships with programme teams and implementing partners.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The programme should continue. The benefits of TPM to individual programmes and to PD SLT are well evidenced. TPM has achieved most output milestones despite the extremely challenging context of the intense disruption caused by Covid-19 and the financial constraints placed on the programme. Feedback from Programme Teams has made clear the direct benefit that TPM has provided to their programmes which has been especially important in a year in which travel to the field has not been possible for most FCDO Programme Teams.

## C. DETAILED OUTPUT SCORING

Output Title	Timely, relevant, independent feedback provided on partner delivery of activities
Output number:		1	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review March 2021	Progress	Score
1.1 Number of TPM assessments covering AVV and BF* for which report 'meets most expectations' (cumulative)	6	9 (CONGOs, TWM, FoodTrade, TMEA X2, WISER X4); AUSP Delayed	A+
1.2 % of PD programmes with expected number of AVV/BF assessments completed per year.	85%	83% - 5/6 (WISER, TMEA, CONGOs, TWM, and FoodTrade); AUSP Delayed	A
1.3 Number of Expenditure Monitoring exercises undertaken which meets most expectations reports provided - Activity 5 (cumulative)	1	1 (TDDAP)	A

Briefly describe the output’s activities and provide supporting narrative for the score.
Nine AVV-BFs have taken place during the reporting period. FCDO agreed that a given AVV/BF TPM activity will be classified as delivering more than one count towards the milestone when the AVV/BF exercise samples more than one activity and/or location as it is effectively verifying more than one activity. FCDO were able to bring forward budget from FY21/22 which enabled TT to deliver more than the expected number of milestones with TPM activity for TMEA and WISER comprising multiple milestones counts in a single report; two and four respectively. All final AVV/BF reports were assessed as ‘meeting most expectations’ based on FCDO’s agreed standards.

For 5 PD programmes, TT delivered at least the number of AVV/BF activities that were expected over the review period. For one other PD programme with an AVV/BF expected to take place (AUSP) it was delayed to next FY 21/22, but this was done in agreement with FCDO in February 2021 as the AUSP activity to be covered was itself delayed. As such the delay was out with the control of TT. All other PD programmes were not due to have an AVV/BF this year based on the workplan agreed following 2020/21 budget reductions. As TT undertook to the best of their ability the expected number of AVV/BF assessments FCDO assess indicator 1.2 as meeting expectations given that 83% of PD programmes with planned AVV/BF coverage achieved is broadly at the level expected.

TT was able to deliver the one expected EM exercise for TDDAP which included a fieldwork element and was completed to the agreed quality standards.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
For this output TT met the standards in terms of Value for Money and exceeded expectations in terms of milestones delivered, as these were delivered with a proportional increase in budget brought forward from FY21/22. TT were able to make effective use of additional budget allocation this year after approval of the workplan in order to fund the additional AVV/BF activity, which enabled TT to meet more of FCDO’s needs for TPM than expected.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
At the start of 2020 FCDO expected to deliver 24 AVV/BFs and 3 EM exercises covering 85% of the PD portfolio by December 2020. Following the withdrawal of the Joint Sahel Department from the contract, and in-year budget reductions, the logframe milestones for AVV/BF and EM were revised down to 6 and 1 respectively in July 2020. AVV/BF were prioritised by FCDO as they were seen to be the most significant drivers of the programme level outcomes and impacts.

The logframe milestones were reviewed again and finalised in November as part of a logframe review to take on board the impact of Covid-19 on programme operations and the associated challenges to in country fieldwork. During this review the decision was approved at Director level to align the logframe milestones to the financial year instead of the calendar year, to allow more meaningful reporting cycles for the remainder of the programme.

Following a review of logframe output 1 as part of this Annual Review FCDO proposes to seek agreement with TT to adapt Indicator 1.2 to monitor programme coverage of Expenditure Monitoring activities as well as AVV/BF activities as a measure to ensure the TPM programme provides the desired level of coverage to the portfolio.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
As the activities noted in output 1 had not yet begun when the previous annual review was undertaken there were no recommendations made.

Lessons
TT have observed greater ownership of TPM amongst FCDO Programme Teams when it contributes to the FCDO annual review cycle or feeds into other key programme reports, and anticipate planning TPM activities dispersed all through the financial year is unlikely to gain as much traction as select TPM activities timed to contribute to Programme Teams’ reporting requirements.
Recommendations
- FCDO and TT to agree revised coverage and frequency of TPM provision across PD programmes in light of reduced budget for 21/22, identified Programme Team needs, and learning so far of when TPM is most useful during the annual cycle, as part of the Programme Board in June 2021.
- Revise the whole logframe considering revised expectations following the confirmation of FY21/22 budgets, including a review of the impact ratings, by July 2021.
Output Title	Independent, actionable feedback provided on quality of results data systems and accuracy of priority output results
Output number:		2	Output Score:	A
Impact weighting (%):		35	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review March 2021	Progress	Score
2.1 Number of programmes for which Data Systems Reviews (DSRs) have been undertaken which meets most expectations report provided - Activity 1 / (i) first DSR / (ii) follow-up DSR (cumulative)	i) 8 (4+4) / ii) 1	i) 8 (4 New – AHRF / TDDAP / WISER and ACE) / ii) 1 (SHOCARR)	A
2.2 Number of programmes from which Rigorous Results Verifications (RRVs) has been undertaken with a meets most expectations report provided - Activity 4 (cumulative)	0	0	A

Briefly describe the output’s activities and provide supporting narrative for the score.
An additional 4 DSRs were undertaken since January 2020 for PD programmes that had not already had a DSR under this contract. DSRs were prioritised for PD programmes that were postponed from the inception phase and required a DSR to inform decisions on the programme’s appropriateness for an RRV, namely AHRF and ACE. A DSR was allocated to the TDDAP programme to provide them with a level of assurance on what was being delivered in their programme following the termination of its standalone TPM contract. The final DSR was allocated to the WISER programme at the Programme Team’s request to help inform the design of M&E under PD’s future climate programming. One follow-up DSR which comprised of two separate reports was undertaken for the SHOCARR programme based on recommendations from the original DSR undertaken in FY 19/20.

All DSR reports achieved at least the minimum standard ‘meeting most expectations’ with two reports “meeting all expectations” based on FCDO’s agreed standards, however in some cases substantial FCDO feedback was required on draft reports to enable reports to meet the minimum standard, and some recurring weaknesses have been identified including the lack of clear recommendations for strengthening disaggregation.

No RRV activities were planned in the current reporting period. During the reporting period TT have developed a methodology note on how RRV will be carried out in subsequent years which has been approved by FCDO following review from EQUALs.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
For this output TT have exceeded expectations in terms of VfM. TT agreed to undertake a DSR covering all four components of a particularly complex programme as within scope to ensure that Programme Teams received assurance on the data systems in place for all partners under its programme, which was particularly beneficial and timely for PD’s Africa Clean Energy programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
At the start of 2020 FCDO expected to deliver 7 DSRs and 2 Follow-up DSRs which would have covered the remaining active PD portfolio of programmes that had not yet had a DSR from this TPM contract. As above, due to in-year budget revisions and the withdrawal of the Joint Sahel Department from the Contract the logframe milestone for DSRs was revised down from 7 to 4, and for Follow-up DSRs from 2 to 1, in July 2020.

As the number of PD programmes that are expected to require a DSR or follow-up DSR has reduced significantly since the first year of implementation, and decisions are being taken on whether to retain RRVs as a priority going forwards, we will look at reducing the impact weighting of this indicator at our next logframe review meeting with TT by July 2021.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead.
- FY19/20 AR recommendation - A concept note should be developed by TT and agreed with FCDO before TT begins each specific TPM activity.
  - Completed - TT provide both an initial concept note and a more detailed design document for sign off by Programme Team and TPM team before commencing each TPM activity, which has proven a very effective mechanism for ensuring shared expectations or resolving questions on design and sampling before TPM commences.
- FY19/20 AR recommendation - For programmes where PD contributes funding alongside other development partners; SROs should generally share and discuss TPM feedback with the other development partners.
  - In Progress – As the majority of TPM reports under this reporting period were submitted near the end of the period and final clarifications were being completed at the time of review, we have not yet confirmed with programme SROs if they shared TPM feedback with other development partners. The TPM team will follow up with SROs on their intended use of TPM feedback including sharing with other development partners when reviewing learning needs in July and capture this at the next review.
- FY19/20 AR recommendation - DSRs for the three priority programmes deferred from the inception phase at FCDO’s request should be undertaken as an early priority in implementation, as far as programme conditions allow.
  - Completed - DSRs for AHRF (Desert Locusts) and ACE have been completed in March 2021. In was agreed with FCDO that a DSR was not required for AgDevCo because work undertaken recently through an independent M&E Review of AgDevCo covered the main points that would have been useful from a DSR exercise.
Lessons
Feedback from some Programme Teams questioned whether it was maximising VfM for DSRs to look at reporting/Logframes which PD M&E advisors could do. FCDO and TT to consider adjusting the DSR methodology to have a greater emphasis on the data systems and M&E capacity which are much harder for FCDO to verify themselves.
Recommendations
- The main TPM activity priorities for the year ahead, assuming affordability permits, are to ensure 1) that any PD programme that would benefit from a DSR, that has not yet had one, gets the opportunity; 2) that all PD programmes without a separate TPM arrangement are offered a minimum of one AVV/BF visit; and finally 3) ensuring that EMs and follow-up DSRs are made available to selected programmes as required in FY21/22. This should be included in TTs proposed FY21/22 workplan.
- FCDO and TT to review the DSR methodology to ensure it gives appropriate priority to the assessment of data systems dimensions that cannot easily be verified by FCDO and provides a basis for clear recommendations on strengthening disaggregation before further DSRs are undertaken, by end July 2021.
- TT to ensure all future DSRs provide appropriate scrutiny of disaggregation for priority indicators and make specific recommendations for how additional disaggregation by FCDO’s priority groups can be incorporated into ARD programme M&E systems
Output Title	Portfolio-level TPM mechanism and evidence products respond flexibly to meet PD Programme Team needs
Output number:		3	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review March 2021	Progress	Score
3.1 Completion of major deliverables (excluding TPM reports) in line with agreed scope, quality and timing. (cumulative)	i) 1 Synthesis or thematic learning report / ii) 1 Learning event / iii) 1 Annual report	i) 1 Learning synthesis report delivered (Apr 2021) / ii) 2 virtual learning events delivered to FCDO (Apr 2021) / iii) 1 Draft Annual report (March 2021)	i) A / ii) A / iii) A
3.2 TPM supplier performance against agreed standards for ways of working (cumulative)	''Meets most expectations' standard demonstrated	''Meets most expectations' standard demonstrated	A
3.3 Number of Ad Hoc visits or agreed alternative TPM activity undertaken with “meet most expectation” reports provided. (cumulative)	agree broad scope and process for delivering ad hoc visits July 2020; 0	Broad scope agreed; 0	A

Briefly describe the output’s activities and provide supporting narrative for the score.
In February 2021, FCDO approved an extension of the Learning Synthesis Report from March 2021 to April 2021: although TT could have delivered the learning synthesis report and presentations by March, it was jointly agreed these deliverables would provide better VfM if the learning synthesis report included evidence from all TPM reports produced to date, including those delivered in March 2021. At the time of writing in April 2021 the annual report and the full draft learning synthesis report had been delivered.

FCDO agreed to change the scope of the learning events from what was envisaged in the ToR as a result of the impact of Covid-19 on large gatherings and international travel, making it difficult for a learning event with external suppliers to be arranged. FCDO also agreed with TT to move the deadline from March 2021 to April 2021 for the reasons above. TT delivered two virtual events in line with revised expectations, one with PD’s senior leadership team and the other with PD programme managers and SROs,

The final version of this year’s annual report was delayed until April 2021 in agreement with FCDO to ensure that the report accounted for all completed reports in the review period given the number of reports submitted towards in late March. Given the uncertainty around FY 21/22 budget it was judged prudent to wait until budget allocations were confirmed to ensure that the report was able to highlight future TPM activity.

On ways of working, concerns raised throughout the year to the Programme Director were actioned quickly and robustly to ensure minimal impact on the programme. There were never more than three concerns raised in a single reporting quarter, which was the agreed performance standards set for TT to ‘meet most expectations’ under this milestone. Subsequent discussions with TT however have suggested that going forward they would like to take an alternative approach to logging concerns more formally to ensure they are fully understood and addressed by the TT team, which FCDO are happy to adopt.

An overview document outlining the broad scope and process for delivering ad hoc visits was developed and agreed in July 2020 in line with the agreed milestone for indicator 3.3.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
For this output TT have met expectations in terms of VfM. TT was able to deliver all expected milestones albeit with slight alterations in scope and timeframe to take into account the changing contexts, and did so within the expected budget, with lower outlay in expenses to reflect the remote delivery of the learning events. TT’s management of the contract has been good throughout a very challenging year, flexing as necessary to meet FCDO’s changing requirements.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This output has remained unchanged during the reporting period. As part of this review it has become clear that we should look at changing the overall impact weighting. We will also in consultation with PD Programme Teams review if Ad Hoc visits are still required as a standalone TPM activity: it may be that the flexibility now introduced to vary the scope of AVV/BF activities negates the requirement for Ad Hoc Visits. We will also look for efficiencies in the programme management element of the contract.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
- FY19/20 AR recommendation – FCDO and TT to convene quarterly to review each other’s performance against the Ways of Working during the implementation phase.
  - Completed (ongoing): FCDO and TT have continued to meet on a quarterly basis to review each other’s performance throughout the reporting period.
- Ways of Working to be revised and updated for the implementation phase by April 2020, including a measure of the level of PD input which should reduce by September 2020.
  - Partially completed: The Ways of Working framework has been updated twice taking on board feedback from both sides in June 2020 and January 2021, following the quarterly review meetings. The updates included the addition of a quality assurance expectation that FCDO had of TT, which had initially helped reduce the level of feedback required from FCDO, however, the recent submission of TPM reports has identified scope for further strengthening of TT’s quality assurance process.
- TT to escalate technical and financial issues to FCDO asap and clarify if needed.
  - Completed (ongoing): TT has on various occasions escalated issues to FCDO e.g. on schedule extensions, on a security related disruption to fieldwork, on handling potential adverse findings with delivery partners, on identifying appropriate TPM priorities with a Programme Team, and on adjusting TPM plans to reflect delays in delivery of a programme activity identified as a priority for AVV-BF in 20/21.
- Any requests that constitute a change to the terms and conditions of the contract should be discussed with FCDO before being formally proposed.
  - Completed (ongoing): TT have been very accommodating over the reporting period, working with FCDO to adapt the programme as a result of budget reductions, fieldwork restrictions and other uncertainties affecting PD programmes, while ensuring the programme continues to deliver its overall objectives and outcomes.
Lessons
- Programme Teams highlighted their interest in the learning aspect of the TPM programme. They felt that the portfolio could benefit from more targeted learning products and events, and there could be greater scope to refine the implementation of TPM, as well as PD programme design and delivery, if key learning from TPM can be shared above the level of individual programmes more than once per year.
- The Covid-19 pandemic made it challenging to hold a learning event with external suppliers this year because of travel restrictions etc. Implementing partner interviews for this review showed they were keen to understand more about the purpose and benefits of TPM to FCDO, so having a learning event with implementing partners in 21/22 would help answer this question and could strengthen buy-in to the TPM process. If Covid-19 restrictions continue it will be worth considering a remote learning event involving partners.
- Early feedback from Programme Team and implementing partner interviews shows that some PD Programme Teams are not yet using TPM findings and recommendations to pursue improvements to PD programmes with partners. In some cases this was due to the short time between finalising the reports and conducting the interview. The PD TPM team has so far created more effective incentives for Programme Teams to contribute to the design, review and approval of TPM than using TPM reports. In line with the theory of change, the PD TPM could play a more proactive role in facilitating consideration of TPM findings and their implications for programme improvements.
Recommendations
- PD TPM team to consult PD Programme Teams and senior leadership team on how learning synthesis products and events could better meet their needs in 21/22, any refinements needed to the format, frequency or timing of learning synthesis products and events as part of the contract amendment by July 2021.
- PD TPM team should consider in consultation with Programme Teams how it can play a greater role in promoting/facilitating Programme Team learning from TPM in 21/22.
- FCDO should ensure that concerns raised under the Ways of Working framework are clearly logged through a formal email in addition to verbal discussions.
D: RISK
Overview of risk management - The overall risk for this programme is moderate. The TPM programme team has clear and documented appetites in place for all risk categories such as Context, Operational, Financial and manages risks within the appetites set. These appetites will be amended by PD in line with the new FCDO guidance regarding terminology.
TT has worked closely with FCDO to continually review, monitor, and adjust risks as they arise and proactively identified new risks and proposed robust mitigation. There have been four joint sessions to review and update the risk register as part of the programme quarterly review process this year. The most recent review took place in February 2021 with each risk being re-assessed and mitigation measures added. Through activity reports, TT identify and document limitations that pose a risk to delivering specific TPM activities as intended; given Covid-19 these issues have particularly focused around access to the field by researchers due to limitations on travel. TT’s risk mitigation approach has generally been appropriate over the reporting period but could have given more consideration to identifying and mitigating risks to the quality and independence of TPM undertaken when physical field access is not possible, particularly when conducting data system reviews.
The six major rated net risks and current summary mitigation are as follows (all within appetite):

- Changes to the programme’s financial year ceiling – TT are working with the PD TPM Programme Team to agree PD SLT TPM priorities. Once confirmed TT will continue to work collaboratively with PD programme teams to ensure the scope of work agreed is appropriate to meet their needs and within the financial limits.
- Covid-19 impacts on the TPM team’s ability to deliver fieldwork - TT has engaged with all PD Programme Teams to discuss the implications of Covid-19 and determine how best to adjust TPM activities and timing in response to changing needs and whether there’s value in proceeding with remote TPM when in person fieldwork cannot be conducted safely.
- Deteriorating security situations other than Covid-19 - TT monitors the security situation closely in countries where fieldwork is being undertaken and flags any issues to FCDO in a timely manner. If a security situation threatens delivery, TT alert FCDO and present a range of options for the way forward.
- Generating demand from PD Programme Teams for TPM - TT focus on building strong relationships with PD Programme Teams and support Teams to work through what TPM can be of most benefit to their programme either through individual meetings or larger group meetings.
- Front loading TPM activities increases burden for all involved – TT focus on maintaining excellent communication to ensure timelines for TPM activity are spread across the year. TT keep all stakeholders updated on changes to delivery timeframes.
- Poor Stakeholder Engagement with TPM - TT maintain regular communication with IPs building a relationship of trust. This includes ensuring that all stakeholders are consulted on the design of TPM activities and always consider that requests are not overly burdensome.
Lessons
At the onset of Covid-19 initially it appeared that no TPM fieldwork and data collection on the ground would be possible. However, rates of infections and Covid-19 restrictions within and across countries in Africa varied and with the right local intelligence and compliance with safety norms, by early 2021 it was possible to undertake TPM fieldwork on the ground for three PD programmes, in Kenya, Uganda and Chad.
Recommendations
Covid-19 is likely to remain a challenge throughout the next 12 months. TT and FCDO to continue to assess if in country TPM fieldwork is possible for every TPM activity, and include it wherever feasible, and continue to adapt their remote data collection tools to ensure high quality data is collected independently even when fieldwork is not possible.
E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Delivery - All deliverables including milestones were completed on time or by agreed extensions to the original deadlines where necessary. TT kept FCDO up to date on occasions when deliverables or milestones were running off schedule.
The quality of completed deliverables has been appropriate so far with all final TPM reports at least ‘meeting most expectations’ (FCDO’s minimum quality standard agreed with TT), and some reports ‘meeting all expectations. However there has been quite a variation in the quality of draft reports initially submitted, and several have required substantial FCDO Programme Team time to review and provide feedback to ensure the final reports meet the agreed minimum standard.

On value and innovation, there are some good examples of delivering VfM: with several changes to key staff over the past year, TT has consistently shown commitment to charging replacement staff members at the same daily rate as previous members although some new members brought greater experience; and with changing priorities and budgets over the year, TT has looked for opportunities to absorb re-design costs into the overall activity costs. TT continues to work closely with FCDO to identify innovative ways to absorb budget allocation changes into the programme while still delivering high quality TPM. However, the Programme Team felt TT could have been more proactive in adapting its approach to demonstrating and reporting on VfM when the original agreed VfM indicators could not be meaningfully tracked as intended due to restricted field access. TT could also have shown more innovation when it came to remote data collection approaches to work around Covid-19 field access restrictions.

Commercial - TT and FCDO signed the original 38-month contract in August 2019, with a contract value of £4.5 million. Since then, the TPM contract has had to adapt to changes in the operating context. There will be a second contract amendment at the start of FY21-22. The key changes to the contract within this reporting period include: In March 2020, it was decided that the TPM scope would not include the Joint Sahel Department (JSD) beyond the inception phase. The JSD had assessed that TPM was not the optimal way of meeting its monitoring requirements given the nature of its programmes. In October 2020, FCDO completed a contract amendment to formalise the JSD changes agreed in March 2020, and to reduce the level of budget available in FY20-21. Remaining budget and contract milestones were rolled forward to FY21-22 and FY22-23, retaining the original end date of September 2022. The overall contract value remained at £3.6 million.
At the time of writing this report, the scope and financial implications of this amendment are under discussion and not finalised.
Financial - The TPM contract is hybrid as fees are invoiced as fixed price milestones whereas expenses are charged on actuals. 26 milestones have been submitted to FCDO in relation to the reporting period. Of these, 20 are TPM products and six are management deliverables. The total value of all the milestones delivered during the reporting period is £574,019. The management milestones were delivered at a total value of £220,684. Expenses incurred equate to £48,151 which is significantly lower than originally forecast at the beginning of the year largely due to the lower level of in-country fieldwork possible during Covid-19.
Forecasting for the programming has been variable. Monthly forecasting has been particularly variable largely due to the high level of uncertainty PD programmes have faced in the reporting period in relation to Covid-19 and budget adjustments. Annual forecasting has been consistent with only one scheduled activity being delayed to FY21/22 as a result of external factors out with TTs control. To date TT have not purchased any assets under this contract.

Lessons
- As a result of various challenging internal and external factors over the past 15 months (particularly Covid-19 and reduced UK GNI and ODA) there was a bunching of TPM deliverables towards the later part of the reporting period. Bunching deliverables has placed considerable strain on TT TPM resources and has driven up TT’s internal costs through ‘crashing’ (increasing resource utilisation to deliver milestones in a shorter timeframe). Earlier confirmation of budgets and PD programme status in 2021/22 would enable better spacing of deliverables and potentially better value for money.
- To foster strong stakeholder relationships, it is important to minimise duplication of effort that can occur as part of the handover process between outgoing and incoming members of staff. It is important that historical discussions and knowledge of the programmes are not lost, and individuals can take over activities with minimal impact to the programme or TPM activity.
- There has been a substantial amount of unanticipated recurring management effort required by TT at portfolio level beyond that required for TPM delivery, mainly as a result FCDOs evolving TPM requirements in the context of Covid-19 and adjustments to programme budgets and the removal of JSD form the contract. Another factor driving some of these management costs is the need for repeated engagement with programmes to understand their TPM needs and how to align this with the budget. This was necessary following both rounds of budget adjustments (which affected programme activity as well as the TPM). This results in high recurring management costs at portfolio level and takes away resources originally provisioned to conduct TPM activities.
Recommendations
- TT and FCDO to work closely to ensure that a fully approved workplan and milestone payment plan is in place by the end of July 2021 to ensure that TPM activities can be spread more proportionately throughout the next reporting period.
- TT to ensure that historical knowledge of individual PD programmes and TPM needs is retained within the team by utilising the same lead staff for TPM on a given programme wherever possible, or ensuring a robust handover process in place when staff turnover is necessary.
- FCDO will establish at the Programme Board in June 2021 expectations on TPM coverage for the portfolio and confirm the rationale for any programmes not in scope and ensure this is communicated clearly to PD Programme Teams. TT and FCDO to look for efficiencies to reduce programme management costs and increase the funding available for TPM activities as part of the second contract amendment.
- TT to work with FCDO to ensure that monthly forecasts are updated to reflect changes to the annual rolling workplan.
ANNEX A – Revised TOC – Updated June 2021