## Deliverables Check List
Exhibit E Design Phase Deliverables Check List
Version 7
Phase: | [6 empty] | A: Architect Check/Sign-Off
Project and No: | [6 empty] | Y: Yale Confirmation Sign-Off
Architect: | [7 empty] | Initial Required by Arch &, upon confirmation, by Yale.
Project Planner & PM: | [7 empty] | Item Not Required
Date: | [6 empty] | PD | Pre-Design
[7 empty] | SD | Schematic Design (Preliminary Design per Agreement)
Refer to "Guidelines for Development of Design Phase Deliverables" Version 7
to determine the minimum level of detail and information required at each phase.
| Master Deliverables List | 100% |  | 100% |  | 100% |  | 80% |  | 100% |  | Remarks
|  | PD |  | SD |  | DD |  | CD |  | CD
|  | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
|  | A | Y | A | Y | A | Y | A | Y | A | Y
1 | Strategic Project Planning
2 | Work Plan | [10 empty] | Updates in SD
3 | Written summary of goals and objectives | [10 empty] | Updates in SD
4 | Programming and Space Analysis
5 | Establish overall project program | [10 empty] | Updates in SD
6 | Project NSF and GSF | [10 empty] | Updates in SD
7 | Written summary of Owner's program | [10 empty] | Updates in SD
8 | Site Analysis and Development
9 | Updated previous concept plan | [10 empty] | Updates in SD
10 | Written summary of analysis | [10 empty] | Updates in SD
11 | Building Analyis
12 | See Agreement for specific deliverables
13 | Existing Facilities Assessment
14 | Written summary of all building inspections
15 | Written summary of building systems
16 | Conceptual Alternatives and Analysis | [10 empty] | Refer to Agreement for specific requirements
17 | Alternative No. 1 | [10 empty] | Discuss with Planner scope of services
18 | Alternative No. 2
19 | Development of Design Concepts
20 | Blocking and stacking diagrams | [10 empty] | Updates in SD
21 | Circulation and flow patterns | [10 empty] | Updates in SD
22 | Conceptual design approach of systems | [10 empty] | Updates in SD
Responsibility Assignment Matrix
See Agreement for specific deliverables
23 | Program Review and Evaluation
24 | Written evaluation of Owner’s program
25 | Updated Project program, including:
26 | • Scope of work narrative
27 | Code review & analysis, including:
28 | • Applicable building codes on title sheet
29 | • Occupant loads
30 | • Life safety plan with egress routes
31 | • ADA accessibility requirements
32 | • Fire apparatus access
33 | • Means of compliance on major code issues
34 | • Proposed/Pending code modification log
35 | Deviations from Yale Design Standards Report
36 | Regulatory agency report, including progress reviews as to:
37 | • Building Department
38 | • Fire Marshal
39 | • Zoning
40 | • Planning Commission
41 | • Design review boards
42 | Area efficiency calculations
43 | Investigation & testing report, including:
44 | • Soils
45 | • Borings
46 | Confirm Basis of Design Report for MEP Systems | [10 empty] | Also to be included in O&M Manuals at Project Closeout
47 | Utilities services report, including:
48 | • Utility company requirements
49 | Energy use & conservation analysis report
50 | Design schedule update
51 | Building volume & area calculations
52 | Meeting minutes, including meetings with:
53 | • Project Team
54 | • Administration
55 | • Users
56 | Analysis of Alternatives (See PD)
57 | Civil Design
58 | Site survey (by Owner, submitted by Architect), including:
59 | • Survey with all major site features, spot elevations, contours and utilities
60 | Site utility enabling plans on survey
61 | Site demolition plans & utility relocation plans on survey
62 | Site layout plans on survey, including:
63 | • Building outline and coordinates
64 | Site drainage plans
65 | Site utility plans, including main locations and requirements for:
66 | • Steam
67 | • Sanitary sewer
68 | • Storm water
69 | • Site electrical
70 | • High voltage
71 | • Domestic water
72 | • Fire water
73 | • Irrigation
74 | • Telecom
75 | • Natural gas
76 | • Chilled water
77 | • Fire protection
78 | Site utility details, including:
79 | • Typical manholes
80 | • Typical catch basins
81 | • Standard trench for utility pipes
82 | • Typical cleanouts
83 | • Underground tanks
84 | Utility connection details
85 | Soil erosion and sediment control plan (per City’s requirements), including:
86 | • Construction entrance | [10 empty] | By CM
87 | • Silt fencing | [10 empty] | By CM
88 | • Catch basin protection | [10 empty] | By CM
89 | Site & Landscape Design
90 | Site Plans, including:
91 | • Diagrams showing horizontal relationships
92 | • Setback requirements and impact on fire resistive requirements
93 | • Parking layout
94 | • Roads & driveways
95 | • Loading docks
96 | • Lawns
97 | • Trees & plantings
98 | • Sidewalks
99 | • Waste collection locations
100 | • Emergency phones
101 | • Stairway locations
102 | • Entrance locations
103 | Tree protection plans, including:
104 | • Existing tree survey
105 | • Tree removals
106 | • Tree protection details
107 | Site sections, including:
108 | • Finish grades
109 | • Walkways
110 | • Parking areas
111 | • Longitudinal section
112 | • Cross section
113 | Enlarged/partial site sections
114 | Grading plans
115 | • Existing & proposed contours
116 | • Spot elevations on key site structures
117 | Materials plans, including:
118 | • Materials shown graphically
119 | • Asphalt
120 | • Concrete
121 | • Pavers
122 | Enlarged/partial materials plans
123 | Soils plans, including:
124 | • Planting soils & depths
125 | • Types (e.g., lightweight fill, structural, wetlands)
126 | Site furnishings plans, including:
127 | • Bike rack locations
128 | • Bench locations
129 | • Trash receptacles
130 | Site furnishings details
131 | Site lighting plans
132 | Paving plans
133 | Paving details, including:
134 | • Asphalt
135 | • Concrete
136 | • Stone
137 | Site details, including:
138 | • Retaining walls
139 | • Stairs & ramps
140 | • Terrace
141 | • Handrails
142 | Planting plans, including:
143 | • Soil preparation & planting specifications
144 | • Sod, ground cover, trees and shrubs
145 | Planting details, including:
146 | • Tree pits with guying diagrams
147 | • Sod, ground cover, trees and shrubs
148 | Irrigation plans
149 | Irrigation details, including:
150 | • Head types
151 | • Control valves
152 | • Trench drains
153 | Yale parking inventory impact plan | [10 empty] | Spaces gained or lost on site
154 | Architectural Design
155 | CAD perspective drawings, including:
156 | • Key exterior views from streets
157 | • Key interior views
158 | Demolition plans
159 | Floor plans, including:
160 | • Occupancy plan
161 | • Rooms and corridors
162 | • Stairs
163 | • Elevators
164 | • Doors
165 | • Windows
166 | • Equipment
167 | • Casework
168 | • Smoke control zones
169 | • Rated wall locations
170 | • Keynotes on major components (e.g., wall, door & window types)
171 | Enlarged floor plans
172 | • Occupancy plan
173 | • Rooms and corridors
174 | • Stairs
175 | • Elevators
176 | • Doors
177 | • Windows
178 | • Equipment
179 | • Casework
180 | • Smoke control zones
181 | • Rated wall locations
182 | Enlarged stair plans
183 | Enlarged stair sections from roof to lowest floor, including:
184 | • Longitudinal sections
185 | • Cross sections
186 | Stair details, including:
187 | • Risers, treads & landings
188 | • Handrails
189 | • Hangers
190 | Enlarged elevator plans
191 | Enlarged elevator & shaft sections from roof to pit
192 | Elevator details, including:
193 | • Door, frame & equipment support
194 | • Description of controls & fixtures
195 | Enlarged toilet room plans
196 | Enlarged toilet room elevations
197 | Roof plans, including:
198 | • Equipment & screens
199 | • Roof pads
200 | • Slopes & drains
201 | Roof details
202 | Building sections, including:
203 | • Longitudinal sections
204 | • Cross sections
205 | Enlarged building sections, including:
206 | • Longitudinal sections
207 | • Cross sections
208 | • Wall Elevations at cut lines
209 | Floor sections
210 | Enlarged floor details
211 | Exterior wall sections from roof to foundation
212 | Exterior wall details
213 | Exterior plan details, including:
214 | • At columns
215 | • At critical building junctions
216 | Building exterior elevations, including:
217 | • Window fenestration
218 | • Glazing types
219 | • Roof profile with roof top equipment
220 | • Finish materials
221 | • Cladding systems
222 | Enlarged building exterior elevations, including:
223 | • Window fenestration
224 | • Glazing types
225 | • Roof Profile with roof top equipment
226 | • Finish materials
227 | • Cladding systems
228 | Partition types & assemblies details, including:
229 | • UL/FM classifications
230 | • Base, plan and head sections
231 | • Fire ratings
232 | • STC ratings
233 | • Stud materials
234 | • GWB and other material designations
235 | Interior plan details, including:
236 | • At columns
237 | • At critical building junctions
238 | Window schedule, including:
239 | • Window types
240 | • Window details
241 | Door schedule, including:
242 | • Door and frame types: elevations
243 | • Door and frame details
244 | • Door handing
245 | • Reference to door hardware types
246 | Reflected ceiling plans
247 | Enlarged reflected ceiling plans
248 | • Ceiling types
249 | • Light fixtures
250 | • Smoke & alarm detectors
251 | • Diffusers
252 | • Height above finished floor
253 | Ceiling details | [10 empty] | Major spaces in PD
254 | Study models or renderings
255 | Interior Design/ Furniture, Fixtures & Equipment (FF&E)
256 | Interior finish floor plans, including:
257 | • Room numbers, per Yale standards
258 | • Area (sq. ft.) and area use identification
259 | • Equipment room location(s)
260 | Inventory and layout of required FF&E, including:
261 | • Whiteboards and screens locations
262 | • Audio/visual equipment locations
263 | Inventory of existing FF&E
264 | Schedule of new and existing FF&E, with costs
265 | Furniture plans, including:
266 | • Fixed seating layout
267 | • Loose furnishings layout
268 | Fixed equipment plans
269 | Lab equipment plans
270 | Kitchen and specialty equipment plans
271 | Interior elevations, including:
272 | • Major public spaces
273 | • Lobbies
274 | • Labs
275 | • Offices
276 | • Conference rooms
277 | • Corridors
278 | • Specialty rooms
279 | Interior details, including:
280 | • Special flooring
281 | • Special wall treatment
282 | • Corridor handrails
283 | • Acoustical panels
284 | • Wood veneers
285 | • Wood base
286 | • Stone panels
287 | Finish schedule
288 | Way-finding system
289 | Artwork program & plans
290 | Room signage
291 | Casework/lab benches, including:
292 | • Elevations
293 | • Details
294 | Structural Design
295 | Foundation plans, including:
296 | • Design criteria
297 | • Column/bay spacing
298 | • Floor elevations
299 | Enlarged foundation plans, including:
300 | • Design criteria
301 | • Column/bay spacing
302 | • Floor elevations
303 | • Location of control and expansion joints.
304 | Foundation details, including:
305 | • Wall
306 | • Slab
307 | • Footing
308 | • Wall schedule
309 | • Slab schedule
310 | • Footing schedule
311 | Floor framing plans, including:
312 | • Sizing of structural members and components
313 | • Slab schedule
314 | Enlarged framing plans, including:
315 | • Sizing of structural members and components
316 | Slab schedule
317 | Roof framing plan, including:
318 | • Sizing of structural members and components
319 | • Slab schedule
320 | Enlarged roof framing plan, including:
321 | • Sizing of structural members and components
322 | • Slab schedule
323 | Steel bracing elevations
324 | Steel/concrete sections
325 | Steel/concrete details
326 | Beam schedule
327 | Column & column base schedules
328 | Column details
329 | Mechanical Design | [10 empty] | Refer to Yale Design Standards, Section 15 for a general description of Deliverables
330 | Energy conservation analysis | [10 empty] | Update in SD
331 | Report listing the types of proposed HVAC systems | [10 empty] | Update in SD
332 | Heating and cooling load analysis | [10 empty] | Update in SD
333 | List of required Central Utilities | [10 empty] | Update in SD
334 | List of special building or occupancy requirements | [10 empty] | Update in SD
335 | Detailed heating and cooling loads by room | [10 empty] | Update in SD
336 | Special mechanical systems analysis | [10 empty] | Update in SD
337 | Special occupancy zones analysis | [10 empty] | Update in SD
338 | Overall HVAC site utility plan | [10 empty] | Update in SD
339 | HVAC demolition plans, including: | [10 empty] | Update in SD
340 | • Existing equipment ductwork and piping | [10 empty] | Update in SD
341 | • Equipment, piping, and ductwork identified as “to remain” or “to be removed” | [10 empty] | Update in SD
342 | HVAC floor plans, including:
343 | • Single line diagrams of ducts with sizes and layouts for all spaces | [10 empty] | Single line diagrams only in PD Phase. No duct sizes in PD.
344 | • Single line diagrams of AHU’s and FCU’s
345 | • Connections to existing HVAC systems, fire alarm & campus control systems
346 | • Air intake & discharge locations
347 | • Fire and smoke damper locations
348 | HVAC enlarged/partial floor plans, including:
349 | • Components and required service access areas
350 | • Duct sizes, duct chases, duct runs and airflow quantities relative to each room, including CFM in and out of all doors
351 | • Location of control panels
352 | • Duct runs near electrical rooms
353 | HVAC roof plan
354 | HVAC enlarged/partial roof plan
355 | HVAC building sections
356 | HVAC enlarged building sections, including:
357 | • Cross-sections through areas where there are installation / coordination issues (e.g., tight space, zoning of utilities)
358 | Required service access areas
359 | Enlarged mechanical room floor plans, including:
360 | • Components and required space for equipment and service access areas
361 | • Coil and tube pull areas and clearances
362 | Enlarged sections through major mechanical equipment, including:
363 | • Air handling units
364 | • Cooling towers
365 | HVAC shaft plan, including:
366 | • Required shafts, chases and recesses, with clearances for each
367 | Mechanical riser diagrams
368 | Supply air flow riser diagrams
369 | General exhaust and return air flow diagrams
370 | Fume hood exhaust flow diagrams
371 | Toilet exhaust flow diagrams
372 | Radioactive exhaust flow diagrams
373 | Hot water flow diagrams
374 | HP, MP. LP steam & condensate flow diagrams, including:
375 | • PRV stations
376 | • Condensate pumps and receivers
377 | Chilled water flow diagrams
378 | Air balance plans & diagrams, including:
379 | • Kitchens
380 | • Laboratory equipment rooms
381 | Mechanical schedules, including:
382 | • Total air and ventilation air for each AHU
383 | Mechanical details
384 | Building controls plans, including:
385 | • Single line control diagrams for all mechanical and plumbing systems
386 | • Interlock equipment (e.g., fans, VAV boxes, motorized dampers)
387 | • Interlocks for fume hood exhaust VVE boxes, supply VAV boxes
388 | • Clear differentiation of trade responsibility for control, fire and control power wiring
389 | • Control points
390 | • Control location plans
391 | • Controls sequences of operation
392 | Mechanical equipment, including:
393 | • Schedules showing sizes and capacities
394 | • Equipment details, including structural support requirements
395 | • Exterior/roof top equipment locations indicating visual impact
396 | • Major mechanical equipment redundancy (e.g. “two pumps 100% capacity each”)
397 | Acoustical systems plan, including:
398 | • Acoustical systems details
399 | Seismic control system plan, including:
400 | • Seismic control system details
401 | Duct construction schedule, including:
402 | • Duct system materials and pressure classes
403 | M/E smoke control plan
404 | Yale’s “Request for Extension of Utilities” form
405 | Plumbing & Piping Design | [10 empty] | Refer to Yale Design Standards, Section 15 for a general description of Deliverables
406 | Plumbing site plan
407 | Plumbing floor plans, including:
408 | • Piping layout and piping runs, including near electrical rooms
409 | • Fixture counts per floor
410 | Enlarged/partial plumbing floor plans
411 | Plumbing sections through key areas
412 | Plumbing enlarged/partial sections through key areas
413 | Plumbing schedules
414 | Domestic water flow riser diagram
415 | Water distribution flow diagram
416 | Lab water flow riser diagram
417 | Sanitary drainage flow diagram with pumps
418 | Storm drainage flow diagram
419 | Lab drainage flow diagram
420 | RO/DI riser flow diagrams
421 | RO/DI water equipment/piping diagram
422 | Waste and vent riser diagrams
423 | Acid waste riser diagram
424 | Radiation riser diagram
425 | Central cooling water diagram
426 | Natural gas flow diagram
427 | Compressed air flow diagram
428 | Vacuum riser diagram
429 | Nitrogen riser diagram
430 | Co2 riser diagram
431 | Water header diagram
432 | Steam header diagram
433 | Plumbing details, including:
434 | • Structural support requirements
435 | • Water heating piping
436 | • Coil piping
437 | • Convector piping
438 | • Duct & piping penetration details
439 | Piping plans (domestic & process), including:
440 | • Required service access areas
441 | • Pipe sizes
442 | Final design calculations
443 | Fire Protection Design
444 | Overall fire protection site plan, including:
445 | • Fire hydrant locations and connections
446 | Fire protection plans, including:
447 | • Hazard groups, type of system (wet or dry), density, area of application and total hose allowance
448 | • Header sizes and layouts
449 | • Fire protection service entrance details
450 | Enlarged fire protection plans showing sprinkler head layout, including:
451 | • Pipe sizes
452 | • Standpipe locations and hose connections
453 | • Sprinkler test locations
454 | Fire pump plans, including:
455 | • Schematic diagram
456 | • Calculations
457 | • Details
458 | Fire protection riser diagrams
459 | Design coverage schedule
460 | Fire protection details, including:
461 | • Control valves, check valves, flow switches and gauges
462 | • Hydraulic calculations
463 | • Penetration details
464 | • Structural support requirements
465 | Electrical Power Design
466 | Power site plan, including:
467 | • Exterior equipment locations
468 | Power floor plans, including:
469 | • Power service and distribution
470 | • Locations and sizes of main feeder and branch circuit conduits
471 | • Connections to building systems (e.g., fire alarm & HVAC)
472 | • Receptacles and outlets
473 | • Switching
474 | • Panelboards and terminal cabinets
475 | • Fire alarm devices
476 | • Telephone and data outlets
477 | • Motors, equipment and controls
478 | • Raceways
479 | • Electric closet(s) location(s).
480 | • Electrical room layout
481 | • Telecom room layout
482 | • Equipment layouts
483 | Power roof plan, including:
484 | • Mechanical equipment
485 | Enlarged/partial power floor plans, including:
486 | • Power service and distribution
487 | • Locations and sizes of main feeder and branch circuit conduits
488 | • Connections to building systems (e.g., fire alarm & HVAC)
489 | • Receptacles and outlets
490 | • Switching
491 | • Panelboards and terminal cabinets
492 | • Fire alarm devices
493 | • Telephone and data outlets
494 | • Motors, equipment and controls
495 | • Raceways
496 | • Electric closet(s) location(s).
497 | • Electrical room layout
498 | • Telecom room layout
499 | • Equipment layouts
500 | Power riser diagram, including:
501 | • Circuit breaker and fuse sizes
502 | Electrical schedules, including:
503 | • Conductor and conduit sizes
504 | • Mechanical equipment
505 | • Panelboards
506 | • Circuits
507 | Electrical details, including:
508 | • Conduit penetration details
509 | • Mounting heights
510 | • Raceway back box
511 | • Grounding
512 | • Power service to building
513 | • Special terminal devices
514 | • Chases and clearances
515 | Emergency power generation plan and controls, including:
516 | • Emergency power equipment
517 | Emergency generator layout, including:
518 | Emergency power riser diagram, including:
519 | • Circuit breaker & fuse sizes
520 | Fire detection and alarms plan, including:
521 | • Riser diagram
522 | • Details
523 | Total connected load assessments and summary
524 | Detailed design criteria
525 | Energy conservation measures
526 | Design calculations
527 | Electrical Lighting Design
528 | Lighting plans
529 | Exterior building lighting plans
530 | Enlarged/partial lighting plans
531 | Lighting control riser diagram
532 | General lighting fixture descriptions
533 | Lighting fixture schedule
534 | Lighting control schedule
535 | Fixture/switching layout
536 | Installation details, including:
537 | • Structural support requirements
538 | Light level calculations & design calculations
539 | Fire Alarm Design
540 | General description of fire alarm system
541 | Fire alarm plans, including:
542 | • Fire alarm zones
543 | • Smoke area zones
544 | • Connection to power system, HVAC & central campus monitoring systems
545 | • Devices
546 | • Control and annunciation panels
547 | Enlarged/partial fire alarm plans
548 | Fire alarm riser diagram
549 | Fire alarm details, including:
550 | • Connections
551 | • Conductor type and sizes
552 | Security Design
553 | General description of all security systems
| Access control zones & perimeters | [10 empty] | identify related physical barrier elements
| Intrusion detection zones & system requirements | [10 empty] | identify related physical barrier elements
554 | Security plans, including:
555 | • Card reader
556 | • CCTV cameras
557 | • Electric & magnetic door hardware | [10 empty] | coordinate with door & frame schedules
558 | • Glass break & other intrusion detection | [10 empty] | coord. with door & window schedules
559 | • Keypads
• "Blue Light" call boxes
• power & communication connection points
• Conduit and backboxes
560 | Enlarged/partial security plans
Coordination details for millwork & finishes
561 | Security equipment schedule
562 | Security room layout
563 | Project keying security plan | [10 empty] | Consult with Yale
564 | Security system network diagram
565 | CCTV riser diagrams
566 | Card access riser diagrams
567 | Security door wiring diagrams | [10 empty] | coordinate with door & frame schedules
568 | Security details, including:
569 | • Video monitoring station
570 | • Alarm monitoring station
571 | • Typical rack layout
572 | • Typical back board & ladder layout
573 | • Installation
| Full system commissioning & training | [10 empty] | at construction closeout
574 | Telecommunications
575 | Telecommunications plans | [10 empty] | data & communications; wired & wireless
576 | Cabling riser diagrams
577 | Grounding riser diagrams
578 | CATV riser diagrams
578 | Distributed Antenna System riser diagrams | [10 empty] | cellular / radio based on project program
| Full infrastructure documents including conduit pathways, back boxes, pull boxes and power service points. | [10 empty] | coordinate blocking requirements, cutting & patching
579 | Enlarged plan, including:
580 | • Server room layouts
581 | Enlarged plans, including:
582 | • IDF layouts
Create separate low voltage construction document package
Audio Visual / Technology
Space-specific objectives & basis of design narrative
Coordination with projected university guidelines
Equipment inventory and overall A/V budget
| Wire pathways; conduits, back boxes & pull boxes | [10 empty] | coordinate blocking requirements, cutting & patching
Communication connections
Power connections & heat load calculations
| Full system commissioning & training | [10 empty] | at construction closeout
583 | Materials Research, Specifications & Project Manual
584 | Outline Specifications, including:
585 | • General design criteria and basis of design
• Site landscape maintenance period
586 | • Preliminary HVAC load assessments
587 | • Energy code requirements
588 | • Efficiency of HVAC
589 | Fume hood and lab equipment inventory
590 | Signage and way-finding narrative
591 | Acoustical analysis report
592 | Vibration analysis report
593 | Traffic studies
594 | Audio/visual program narrative
595 | Security program narrative
596 | Commissioning process and reports
597 | Proposed modifications to Owner’s form of Division 1 (General Requirements)
598 | Project Manual, including:
599 | • Bidding requirements
600 | • Project Conditions
601 | • Specifications | [10 empty] | All applicable CSI Divisions
602 | • Technical data
603 | Space Inventory Information
604 | Assignment plans including:
605 | • Room numbers, room square footages, room use descriptions, floor numbers and floor square footages.
606 | Owner’s Comments
607 | Record of Owner’s review comments
608 | Responses to Owner’s review comments
609 | List of changes to be incorporated during subsequent phases
610 | Completion
611 | Signed, sealed, reproducible set of Drawings and Specifications