## Instructions
Project Process Agreement (PPA)
Introduction The PPA is a key artifact in the eXpedited Life Cycle (XLC) that documents the agreement between the key stakeholders regarding which reviews will be conducted for the project, which artifacts are appropriate, and which tests are necessary. The CIRT reviews your IT Intake Request Form which starts the XLC process and can coordinate resources. You should create this PPA once you meet with CIRT to discuss your IT Intake Request Form. Instructions The eXpedited Life Cycle (XLC) is a tailorable process. This Project process Agreement is a template and should be used as a "Menu of Services" which you tailor to meet your business needs and streamline the process. There are several different tabs/spreadsheets which should be reviewed. Definitions Waive: A project team chooses to not do the deliverables/Stage gate reviews/testing functions; however, they must fill in the justification section with a valid reason for choosing to not perform the task. Combine: A project team may merge two types of deliverables/Stage gate reviews/testing functions together if deemed appropriate for their project. If choosing combine, you must fill in the justification section. Delegate: A project team may assign the work to someone else to conduct. If choosing delegate, you must fill in the justification section Once in a Lifecycle: This option is chosen when a function is performed once in a lifecycle of a project against once every sprint or once every release etc.

## XLC PPA for Signatures
Project Process Agreement
Project Name
Project Description
Release
Life Cycle ID
Artifacts:
IT Intake Request Form | Provide (New) | Contingency Plan | Provide (New)
Enterprise Architecture Analysis Artifacts | Provide (New) | System Design Document | Provide (New)
Product Vision Statement | Provide (New) | Database Design Document | Provide (Update)
Business Case | Provide (New) | Physical Database / Model | Provide (New)
User Stories | Provide (New) | Interface Control Document | Provide (New)
Product Roadmap | Provide (New) | Data Use Agreement | Provide (New)
Requirements Document | Provide (New) | Test Case Specification | Provide (New)
Product Backlog | Provide (New) | Data Conversion Plan | Provide (New)
Sprint Backlog | Provide (New) | Computer Match/Interagency Agreements | Provide (New)
Burndown Chart | Provide (New) | Implementation Plan | Provide (New)
Product Increment | Provide (New) | DevOps Plan | Provide (New)
High-Level Technical Design | Provide (New) | User Manual | Provide (New)
Section 508 Product Assessment Package | Provide (New) | Operations & Maintenance Manual | Provide (New)
Acquisition Strategy | Provide (New) | Business Product/Code | Provide (New)
Project Process Agreement | Provide (New) | Version Description Document | Provide (New)
Project Charter | Provide (New) | Training Plan | Provide (New)
Information Security Risk Assessment | Provide (New) | Test Summary Report | Provide (New)
System Security Plan | Provide (New) | Training Artifacts | Provide (New)
Privacy Impact Assessment | Provide (New) | Contingency Test Plan (tabletop) | Provide (New)
Logical Data Model | Provide (New) | Security Assessment | Provide (New)
Release Plan | Provide (New) | Authorization Package | Provide (New)
Project Management Plan | Provide (New) | Plan of Action & Milestones | Provide (New)
System of Records | Provide (New) | CMS CIO Provided Authorization To Operate | Provide (New)
Test Plan | Provide (New) | System Disposition Plan | Provide (New)
Performance Test Plan and Results | Provide (New) | Post Implementation Report | Provide (New)
Project Schedule | Provide (New) | Annual Operational Analysis Report | Provide (New)
Risk Register | Provide (New) | Project Closeout Report | Provide (New)
Issues List | Provide (New) | Monitoring Reports | Provide (New)
Action Items | Provide (New) | Project Defined Artifact 2 | Provide (New)
Decision Log | Provide (New) | Project Defined Artifact 3 | Provide (New)
Lessons Learned Log | Provide (New)
Stage Gates:
Architecture Review (AR) | Perform | Production Readiness Review (PRR) | Perform
Investment Selection Review (ISR) | Perform | Operational Readiness Review (ORR) | Perform
Project Baseline Review (PBR) | Perform | Post Implementation Review (PIR) | Perform
Requirements Review (RR) | Perform | Annual Operational Analysis (AOA) | Perform
Preliminary Design Review (PDR) | Perform | Disposition Review (DR) | Perform
Detailed Design Review (DDR) | Perform | Project Defined Review 1 | Perform
Validation Readiness Review (VRR) | Perform | Project Defined Review 2 | Perform
Implementation Readiness Rev (IRR) | Perform | Project Defined Review 3 | Perform
Tests:
Unit Testing | Conducted | Performance Testing (includes load testing, volume testing, stress testing, and longevity testing). | Conducted
Application Integration Testing | Conducted | Initial Security Control Assessment (SCA) | Conducted
Section 508 Testing | Conducted | Final Integration Testing | Conducted
System Testing | Conducted | Initial Contingency Planning Testing | Conducted
Functional Testing | Conducted | Production Ready Testing | Conducted
End-to-End Integration Testing | Conducted | Monitoring & Reliability Testing | Conducted
User Acceptance Testing | Conducted | Operational Security Control Assessment (SCA) | Conducted
Regression Testing | Conducted | Audits | Conducted
Section 508 Testing | Conducted | Operational Contingency Planning Testing | Conducted
Infrastructure Testing | Conducted | Project Defined Test 1 | Conducted
System Acceptance Testing | Conducted | Project Defined Test 2 | Conducted
APPROVALS:

## XLC PPA - Artifacts
| PROJECT PROCESS AGREEMENT -- | ARTIFACTS | [5 empty] | Provide (New) | Jira | Provide (New) | Jira
[8 empty] | Provide (Update) | Confluence
| Project Name | [6 empty] | Waive | SharePoint
| Project Description | [6 empty] | Combine | XLC Document
| Release | [6 empty] | Agile | Other (*Must fill in justification)
| Life Cycle ID | [7 empty] | Not Applicable
A | A | B | C | D | E | F | G
# | ARTIFACT | CMS IT PROJECT |  |  |  | Domain | ARTIFACT DEFINITION
|  | PROJECT AGREEMENT | WHERE TO FIND | JUSTIFICATION and/or NOTES | AUTHOR (specific for Project)
1 | IT Intake Request Form | Provide (New) | Jira |  |  | Systems Development
2 | Enterprise Architecture Analysis Artifacts | Provide (New) | Jira |  |  | Systems Development
3 | Product Vision Statement | Provide (New) | Jira |  |  | Systems Development
4 | Business Case | Provide (New) | Jira |  |  | Systems Development
5 | User Stories | Provide (New) | Jira |  |  | Systems Development
6 | Product Roadmap | Provide (New) | Jira |  |  | Systems Development
7 | Requirements Document | Provide (New) | Jira |  |  | Systems Development
8 | Product Backlog | Provide (New) | Jira |  |  | Project Management
9 | Sprint Backlog | Provide (New) | Jira |  |  | Project Management
10 | Burndown Chart | Provide (New) | Jira |  |  | Systems Development
11 | Product Increment | Provide (New) | Jira |  |  | Systems Development
12 | High-Level Technical Design | Provide (New) | Jira |  |  | Systems Development
13 | Section 508 Product Assessment Package | Provide (New) | Jira |  |  | Systems Development
14 | Acquisition Strategy | Provide (New) | Jira |  |  | Project Management
15 | Project Process Agreement | Provide (New) | Jira |  |  | Project Management
16 | Project Charter | Provide (New) | Jira |  |  | Project Management
17 | Information Security Risk Assessment | Provide (New) | Jira |  |  | Security
18 | System Security Plan | Provide (New) | Jira |  |  | Security
19 | Privacy Impact Assessment | Provide (New) | Jira |  |  | Security
20 | Logical Data Model | Provide (New) | Jira |  |  | Systems Development
21 | Release Plan | Provide (New) | Jira |  |  | Systems Development
22 | Project Management Plan | Provide (New) | Jira |  |  | Project Management
23 | System of Records | Provide (New) | Jira |  |  | Systems Development
24 | Test Plan | Provide (New) | Jira |  |  | Systems Development
25 | Performance Test Plan and Results | Provide (New) | Jira |  |  | Systems Development
26 | Project Schedule | Provide (New) | Jira |  |  | Project Management
27 | Risk Register | Provide (New) | Jira |  |  | Project Management
28 | Issues List | Provide (New) | Jira |  |  | Project Management
29 | Action Items | Provide (New) | Jira |  |  | Project Management
30 | Decision Log | Provide (New) | Jira |  |  | Project Management
31 | Lessons Learned Log | Provide (New) | Jira |  |  | Project Management
32 | Contingency Plan | Provide (New) | Jira |  |  | Security
33 | System Design Document | Provide (New) | Jira |  |  | Systems Development
34 | Database Design Document | Provide (Update) | Jira |  |  | Systems Development
35 | Physical Database / Model | Provide (New) | Jira |  |  | Systems Development
36 | Interface Control Document | Provide (New) | Jira |  |  | Systems Development
37 | Data Use Agreement | Provide (New) | Jira |  |  | Systems Development
38 | Test Case Specification | Provide (New) | Jira |  |  | Systems Development
39 | Data Conversion Plan | Provide (New) | Jira |  |  | Systems Development
40 | Computer Match/Interagency Agreements | Provide (New) | Jira |  |  | Systems Development
41 | Implementation Plan | Provide (New) | Jira |  |  | Systems Development
42 | DevOps Plan | Provide (New) | Jira |  |  | Systems Development
43 | User Manual | Provide (New) | Jira |  |  | Systems Development
44 | Operations & Maintenance Manual | Provide (New) | Jira |  |  | Systems Development
45 | Business Product/Code | Provide (New) | Jira |  |  | Systems Development
46 | Version Description Document | Provide (New) | Jira |  |  | Systems Development
47 | Training Plan | Provide (New) | Jira |  |  | Systems Development
48 | Test Summary Report | Provide (New) | Jira |  |  | Systems Development
49 | Training Artifacts | Provide (New) | Jira |  |  | Systems Development
50 | Contingency Test Plan (tabletop) | Provide (New) | Jira |  |  | Security
51 | Security Assessment | Provide (New) | Jira |  |  | Security
52 | Authorization Package | Provide (New) | Jira |  |  | Security
53 | Plan of Action & Milestones | Provide (New) | Jira |  |  | Security
54 | CMS CIO Provided Authorization To Operate | Provide (New) | Jira |  |  | Security
55 | System Disposition Plan | Provide (New) | Jira |  |  | Systems Development
56 | Post Implementation Report | Provide (New) | Jira |  |  | Systems Development
57 | Annual Operational Analysis Report | Provide (New) | Jira |  |  | Systems Development
58 | Project Closeout Report | Provide (New) | Jira |  |  | Project Management
59 | Monitoring Reports | Provide (New) | Jira |  |  | Systems Development
60 | Project Defined Artifact 2 | Provide (New) | Jira
61 | Project Defined Artifact 3 | Provide (New) | Jira
|  | ARTIFACTS TO PROVIDE NEW DOCUMENTS: |  |  | 60
|  | ARTIFACTS TO PROVIDE UPDATES TO EXISTING DOCS: |  |  | 1
|  | ARTIFACTS COMBINED: |  |  | 0
|  | ARTIFACTS WAIVED: |  |  | 0

## XLC PPA - Stage Gates
| PROJECT PROCESS AGREEMENT | -- STAGE GATES | [6 empty] | Perform | Once every release
[9 empty] | Delegate | Once every sprint
| Project Name | [7 empty] | Waive | Once in a life cycle
| Project Description | [7 empty] | Combine | Not required
| Release | [7 empty] | Agile | Deligated
Life Cycle ID
A | B | C |  | D | E | F | G | H
# | STAGE GATE REVIEW | CMS IT PROJECT |  |  |  | CMS Governance / Delegated to Projects | STAGE GATE DEFINITION | RISK OF WAIVING REVIEW
|  | PROJECT AGREEMENT | WHEN | JUSTIFICATION and/or NOTES | AUTHOR
1 | Architecture Review (AR) | Perform | Once every release |  |  | Governance | Determine whether the proposed project potentially duplicates, interferes, contradicts or can leverage another investment that already exists, is proposed, under development, or planned for near-term disposition. The business need is assessed to determine if it is sound and conforms to the CMS Enterprise Architecture. | When AR is waived then high level technical design begins with incomplete understanding of desired solution and its relationship to existing systems. This usually leads to unnecessary redundancy and missed opportunity to leverage other IT efforts. It often leads to solutions that conflict with CMS IT strategy. This review is a governance level review.
2 | Investment Selection Review (ISR) | Perform | Once every release |  |  | Governance | Determine if it is a sound, viable, and worthy of funding, support and inclusion in the organization's IT Investment Portfolio. The business need and objectives are reviewed to ensure the effort supports CMS' overall mission and objectives and will not comprise initiatives on the horizon. | When ISR is waived then project is added to CMS portfolio and funds are committed without an assessment of soundness, viability, and worthiness. This review is a governance level review.
3 | Project Baseline Review (PBR) | Perform | Once every release |  |  | May be Delegated | Obtain management approval that the scope, cost and schedule that have been established for the project are adequately documented and that the project management strategy is appropriate for moving the project forward in the life cycle. The PBR includes review of the budget, risk, and user requirements for the investment; emphasis should be on the total cost of ownership and not just development or acquisition costs. | When PBR is waived then work begins without a baselined plan complicating ability to provide direction and track progress against integrated cost, schedule, and technical baselines.
4 | Requirements Review (RR) | Perform | Once every release |  |  | May be Delegated | Verify that the requirements are complete, accurate, consistent and problem-free; evaluate the responsiveness to the business requirements; ensure that the requirements are a suitable basis for subsequent design activities; ensure traceability between the business and system requirements; and affirm final agreement regarding the content of the Requirements Document by the business owner. | When RR is waived then design begins without requirement reconciliation with business need and there is no assurance that the solution can be verified in the test phase. Without a RR, any unexpected requirements issues that drive cost and schedule variances are likely to drive further variances later in the lifecycle.
5 | Preliminary Design Review (PDR) | Perform | Once every release |  |  | Governance | Verify the preliminary design satisfies the functional and nonfunctional requirements and is in conformance with CMS's Technical Reference Architecture (TRA); determine technical solution's completeness and consistency with CMS standards; raise and resolve any technical and/or project-related issues, to identify and mitigate project, technical, security, and/or business risks affecting continued detailed design and subsequent development, testing, implementation, and operations and maintenance activities. | When PDR is waived then detailed design begins without high level application architectural review to validate software and external interfaces or verification that design satisfies functional and non-functional requirements. Without a PDR, any unexpected high level design issues that drive cost and schedule variances are likely to drive further variances later in the lifecycle. This review is a governance level review.
6 | Detailed Design Review (DDR) | Perform | Once every release |  |  | Governance | Verify the final design satisfies the functional and nonfunctional requirements and is in conformance with CMS's Technical Reference Architecture (TRA); determine technical solution's completeness and consistency with CMS standards; raise and resolve any technical and/or project-related issues, to identify and mitigate project, technical, security, and/or business risks affecting continued detailed design and subsequent development, testing, implementation, and operations and maintenance activities. | When DDR is waived then development begins without assurance that design meets stated business needs. Solutions developed from incomplete or unworkable design are likely to have performance gaps that will require unexpected time and money to fix. Without a DDR, any unexpected detailed design issues that drive cost and schedule variances are likely to drive further variances in development, integration, and verification. This review is a governance level review.
7 | Validation Readiness Review (VRR) | Perform | Once every release |  |  | May be Delegated | Ensure the system/application completed thorough Development Testing and is ready for turnover to the formal, controlled test environment for Validation testing. | When VRR is waived then the system/application begins testing without a formal hand off from development to test or rules for communication. This usually includes a controlled baseline, clear statement of what function is and is not working, formal turnover of any required work-around, or initiation of formal configuration management procedures. Waiving VRR often leads to an uncontrolled baseline with errors that cannot be reproduced. Without a VRR, any unexpected development issues that drive cost and schedule variances often drive further variances in integration, and verification.
8 | Implementation Readiness Rev (IRR) | Perform | Once every release |  |  | May be Delegated | Ensure the system/application completed thorough Integration Testing and is ready for turnover to the formal, controlled test environment for Production Readiness | When IRR is waived then the system/application begins testing without a formal hand off from validation to implementation or rules for communication. This usually includes a controlled baseline, clear statement of what function is and is not working, formal turnover of any required work-around, or initiation of formal configuration management procedures. Waiving IRR often leads to an uncontrolled baseline with errors that cannot be reproduced. Without a IRR, any unexpected development issues that drive cost and schedule variances often drive further variances in integration, and verification.
7 | Production Readiness Review (PRR) | Perform | Once every release |  |  | May be Delegated | Ensure the system/application completed its implementation processes according to plan and that it is ready for turnover to the Operations & Maintenance team and operational release into the Production environment. | When PRR is waived then the system/application moves to the production environment without without a formal handoff from implementation or rules for communication. Handoff usually includes verification that it meets performance requirements, clear statement of what function is and is not working, formal turnover of any required work-around, and reconciliation with operations and maintenance procedures. Without a PRR, any unexpected integration and verification issues that drive cost and schedule variances may drive further variances in the next level of testing as well as production.
9 | Operational Readiness Review (ORR) | Perform | Once every release |  |  | Governance | Ensure the system/application completed its implementation processes according to plan and that it is ready for turnover to the Operations & Maintenance team and operational release into the Production environment. | When ORR is waived then the system/application is put into production without verification that it meets performance requirements and that operation and maintenance procedures ensure prompt system recovery without loss of data. Security is a significant component of ORR must be satisfied for the CIO to grant Authority to Operate. This review is a governance level review.
10 | Post Implementation Review (PIR) | Perform | Once every release |  |  | Governance/Delegated (see Stage Gate Definition for more information) | The purpose of the PIR is twofold: (1) To ascertain the degree of success from the project; in particular, the extent to which it met its objectives, delivered planned levels of performance, and addressed the specific requirements as originally defined; (2) To enable the team, and future teams, to learn lessons from the project to improve future CMS work and solutions. In that context, the PIR examines whether the team achieved the results it planned for, what those results actually were, and what caused the results to be different from those planned for (if they are different). Newly-operational systems are required to schedule a Governance-level PIR with the Technical Review Board (TRB) within 6 to 12 months of going into production. Subsequent PIRs (e.g., for each release) should be conducted at the project level (i.e., as a delegated review) unless the system has undergone a total redesign. | When PIR is waived then a project's effectiveness is not evaluated. Did the project meet the expectations of the stakeholders? Did the project provide value? Any increasing operational costs or decreasing capability is not assessed, updates or workarounds are not considered, and inefficient solutions continue to operate. Any decreasing operational costs or improvements are not shared so other efforts can reap similar benefits. This review is a governance level review.
11 | Annual Operational Analysis (AOA) | Perform | Once every release |  |  | May be Delegated | Review project performance to evaluate: Customer Satisfaction, Strategic and Business Results, Financial Performance, and Innovation. | When AOA is waived then a project's continued effectiveness is not evaluated. Any increasing operational costs or decreasing capability is not assessed, updates or work arounds are not considered, and inefficient solutions continue to operate. Any decreasing operational costs or improvements are not shared so other efforts can reap similar benefits.
12 | Disposition Review (DR) | Perform | Once every release |  |  | May be Delegated | Ensure project has been completely and appropriately transitioned/disposed, thereby ending the lifecycle of the IT project. | When DR is waived, then a project is shut down without proper coordination of technical and contractual obligations. This can allow costs to accumulate for a system no longer in production.
13 | Project Defined Review 1 | Perform | Once every release |  |  | May be Delegated | A project defined review that … | When Project Defined Review 1 is waived then ...
14 | Project Defined Review 2 | Perform | Once every release |  |  | May be Delegated | A project defined review that … | When Project Defined Review 2 is waived then ...
15 | Project Defined Review 3 | Perform | Once every release |  |  | May be Delegated | A project defined review that … | When Project Defined Review 2 is waived then ...
Note: Agreed upon artifacts are expected for all stage gate reviews, regardless of who conducts them
|  | GOVERNANCE STAGE GATE REVIEWS: |  |  | 16
|  | DELEGATED STAGE GATE REVIEWS: |  |  | 0
|  | WAIVED STAGE GATE REVIEW: |  |  | 0
|  | COMBINED STAGE GATE REVIEW: |  |  | 0

## XLC PPA - Testing Functions
| PROJECT PROCESS AGREEMENT -- | [6 empty] | Conducted | Once every release
[8 empty] | Not Conducted | once every sprint
| Project Name | 0 | [5 empty] | Combine | Once in a life cycle
| Project Description | 0 | [6 empty] | Not required
| Release | 0 | [6 empty] | Deligated
| Life Cycle ID | 0
A | B | C | D | E | F | G | H
# | TEST | Business App, Infrastructure, or Both | TEST DEFINITION | CMS IT PROJECT
|  |  |  | PROJECT AGREEMENT | WHEN | AUTHOR (specific for Project) | JUSTIFICATION and/or NOTES
Development Testing
1 | Unit Testing |  | Assesses and corrects the functionality and data of a business application’s individual code modules | Conducted | Once every release
2 | Application Integration Testing |  | Assesses the interfaces, data, and interoperability of modules and systems within a single business application. | Conducted | Once every release
3 | Section 508 Testing |  | Ensures that the Electronic Information Technology (EIT) product is compliant with applicable Section 508 Accessibility Standards. | Conducted | Once every release
Validation Testing
4 | System Testing |  | Assesses the functionality and interoperability of a business application and multiple systems, such as databases, hardware, software, or communication devices, and their integration with infrastructure into an overall integrated system. | Conducted | Once every release
5 | Functional Testing |  | Assesses the input/output functions of a business application against pre-defined functional and data requirements. | Conducted | Once every release
6 | End-to-End Integration Testing |  | Evaluates whether the business applications and systems interoperate correctly, pass data and control correctly to one another, and store data correctly. | Conducted | Once every release
7 | User Acceptance Testing |  | Assesses the overall functionality and interoperability of a business application’s solution in an operational mode. | Conducted | Once every release
8 | Regression Testing |  | Validates that modifications have not caused unintended functional or data results and that the application still complies with its specific requirements. Similarly, validates that infrastructure changes have not compromised dependent business applications. | Conducted | Once every release
9 | Section 508 Testing |  | Ensure that the EIT product is compliant with applicable Section 508 Accessibility Standards. | Conducted | Once every release
10 | Infrastructure Testing |  | Assesses the interfaces and interoperability of new or modified infrastructure with other infrastructure and system components, such as databases, hardware, software, or communication devices. | Conducted | Once every release
Implementation Testing
11 | System Acceptance Testing |  | Assesses the solution’s functionality, architecture, and configuration in a production-like environment. | Conducted | Once every release
12 | Performance Testing (includes load testing, volume testing, stress testing, and longevity testing). |  | Performance tests help to determine a system’s and application’s limitations, as well as the maximum of active users utilizing the application throughout servers. | Conducted | Once every release
13 | Initial Security Control Assessment (SCA) |  | Determines the extent to which the security controls in the business application or infrastructure are implemented correctly, operate as intended, and produce the desired outcome with respect to meeting the security requirements for the application or infrastructure. | Conducted | Once every release
14 | Final Integration Testing |  | Confirms that a business application or infrastructure solution works correctly from end to end in an environment configured the same as a production environment and with the same security settings. | Conducted | Once every release
15 | Initial Contingency Planning Testing |  | Ensures the personnel are knowledgeable and capable of performing the notification/activation requirements and procedures as outlined in the CP, in a timely manner. | Conducted | Once every release
Operational Testing
16 | Production Ready Testing |  | Confirms that a production-ready business application or infrastructure has been installed and configured correctly in a production environment and is ready for operational use. | Conducted | Once every release
17 | Monitoring & Reliability Testing |  | Ensures that the implemented application or infrastructure performs as expected in production. | Conducted | Once every release
18 | Operational Security Control Assessment (SCA) |  | Determines the extent to which the security controls in the business application or infrastructure are implemented correctly, operate as intended, and produce the desired outcome with respect to meeting the security requirements for the business application or infrastructure. | Conducted | Once every release
19 | Audits |  | Ensures a business application or infrastructure complies with prescribed auditing requirements and operating standards. Assures accuracy of operating statistics and reporting, risk analysis, information security, disaster recovery and contingency planning, corrective action planning, and quality assurance of all procedures. | Conducted | Once every release
20 | Operational Contingency Planning Testing |  | Ensures the personnel are knowledgeable and capable of performing the notification/activation requirements and procedures as outlined in the CP, in a timely manner. | Conducted | Once every release
Project Defined Testing
21 | Project Defined Test 1 |  | A project defined test that… | Conducted | Once every release
22 | Project Defined Test 2 |  | A project defined test that… | Conducted | Once every release
Note: Agreed upon test plans and reports are expected for all stage gate reviews, regardless of who conducts them
|  | CONDUCTED TESTS: |  | 22
|  | NOT CONDUCTED TESTS: |  | 0
|  | COMBINE TESTS: |  | 0