## Backlog
Epic	Story	Name	Story Statement	Acceptance Criteria	Notes	Details
1		Define the Why	As a member of this organization, I want to know why a change in our work management is required, so I will feel motivated, instead of forced, to make the change.	A concise statement has been vetted by all interested stakeholders and published.	A shared understanding of why a change to Agile is necessary helps to align efforts and reduce negative resistance to change (RTC).	Details
	1.1	Identify Causes	As the change leader, I want to identify a list of potential opportunities or threats driving the organization to consider Agile, to identify causes justifying the change.	SWOT or similar analysis performed, and a list of causes relevant to adopting Agile is published.	"SWOT" stands for "Strengths, Weaknesses, Opportunities, and Threats," a common analysis tool for devising strategy; perform a Web search for detailed steps. Throughout this backlog, "published" means capturing the results in any written form accessible on demand by everyone in the organization, like physical bulletin boards or intranet sites (not just e-mails or memos).	Details
	1.2	Propose Why Statement	As the change leader, I want to propose a concise, motivating "Why Statement" so I can build a persuasive argument for exploring Agile.	A single sentence, short enough to be easily memorized, is presented to the change sponsor and revised based on his/her input.	The statement should be based on the evidence from the "causes" story, but stated in terms appealing to the appropriate emotion to gain attention. Though not required, you may include up to five single-sentence bullet points, to provide detail without information overload.	Details
	1.3	Finalize Why Statement	As the change leader, I want consensus from initial change agents and the change sponsor on the Why Statement to ensure we deliver a consistent and effective message.	The proposed statement is presented to the sponsor and potential change agents in the organization, consensus on wording facilitated, and the statement published.	"Potential change agents" means anyone who has expressed an interest in implementing Agile, regardless of job title, function, or employment type.	Details
	1.4	Refine Why Statement	As the change leader, I want consensus from the Change Team and the sponsor on the Why Statement to maintain a consistent and effective message.	After the Change Team is created, consensus is reached with the members and the sponsor on wording of the Why Statement, and the updated statement is published.		Details
	1.5	Revisit Why Statement	As the change leader, I want to revisit the Why Statement if feedback from stakeholders warrants a change, to ensure it does not become a source of resistance.	Consensus is reached with the Change Team and sponsor on rewording of the why statement, and the updated statement is published.	Pay attention to feedback on the Why Statement from all stakeholders, and if there are repeated questions or concerns, revise the statement to address them. If no patterns are discerned 2-3 months after the Change Team initially agrees on the statement wording, you can delete this story and close the epic.	Details
2		Prepare a Sponsor	As the change leader, I want an enthusiastic supporter as high in the organization as possible, to ensure the necessary resources will be provided and a sense of urgency sustained.	The sponsor has been trained and received formal coaching for at least one quarter, and agrees with the leader that ad hoc coaching is sufficient going forward.		Details
	2.1	Identify Change Sponsor	As the change leader, I want to explain sponsorship tasks to a high-level executive and obtain agreement from them to serve as the change sponsor.	Meeting held with [name], and that person agreed or refused.	The agreement now is only to investigate Agile, not to make the switch. Start with the top executive and work your way down the organizational chart, copying this story as needed. Allow enough time in the sprint after the meeting for the executive to think about the decision.	Details
	2.2	Train Change Sponsor	As the change leader, I want to train the change sponsor on their role so they can begin to motivate an investigation of Agile.	Formal training on the responsibilities and tasks of the sponsor is created and delivered, and any follow-up questions from the session are answered.	For material, refer to Leading Change by John Kotter and the Standard for Change Management from the Association of Change Management Professionals.	Details
	2.3	Coach Change Sponsor	As the change leader, I want to coach the project sponsor on the role so they can effectively motivate change.	The sponsor and leader agree the sponsor successfully completed his/her duties within sprint [number].	Copy this story into future sprints as needed to set aside time for coaching, usually around significant events in the transformation process like an all-hands meeting or critical communication with other executives.	Details
3		Determine Organizational Readiness	As the stakeholders of the potential change, we want to determine if the organization is capable of and ready for Agile, to prevent wasted time and lost goodwill if not.	A "go/delay/no-go" decision is published on whether to pursue implementing some form of Agile, along with any gaps that should be addressed prior to doing so.		Details
	3.1	Review Change History	As the change leader, I want to understand the organization's recent history with organizational change, to determine what kinds of resistance might result.	A summary of major change efforts of the past 10 years (to structure, workforce, processes, tools, etc.) is published, with a short analysis of how this might affect Agile adoption.	This should be no more than two document pages, and bullet lists are fine.	Details
	3.2	Perform Structural Gap Analysis	As the change leader, I want to understand at a high level how our organizational structure might limit Agile success, and what structural changes might be required to gain maximum benefits.	A comparison of the organization's current structure to what it should be under an Agile system is published.	This should be no more than two document pages, and bullet lists are fine.	Details
	3.3	Perform HR Gap Analysis	As the change leader, I want to understand at a high level what changes to human resource practices might be required to implement Agile, to help determine the likelihood of success.	A comparison of the organization's current HR practices to what they should be to fully support an Agile system is published.	This should be no more than two document pages, and bullet lists are fine.	Details
	3.4	Perform Sales/Marketing Gap Analysis	As the change leader, I want to understand at a high level what changes to sales and marketing practices might be required to implement Agile, to help determine the likelihood of success.	A comparison of the organization's current sales and marketing practices to what they should be under an Agile system is published.	This should be no more than two document pages, and bullet lists are fine.	Details
	3.5	Perform Finance Gap Analysis	As the change leader, I want to understand at a high level what changes to finance practices might be required to implement Agile, to help determine the likelihood of success.	A comparison of the organization's current financial management practices to what they should be under an Agile system is published.	This should be no more than two document pages, and bullet lists are fine.	Details
	3.6	Perform Legal Gap Analysis	As the change leader, I want to understand at a high level what changes to legal practices might be required to implement Agile, to help determine the likelihood of success.	A comparison of the organization's current legal practices to what they should be under an Agile system is published.	This should be no more than two document pages, and bullet lists are fine.	Details
	3.7	Review External Constraints	As the change leader, I want to understand what external factors might impact the adoption of Agile, so any risks can be addressed in the change project.	A summary of external constraints on Agile adoption and potential ways to address them is published.	No more than two document pages per constraint type, and bullet lists are fine.	Details
	3.8	Perform Process Gap Analysis	As the change leader, I want to understand at a high level what process changes might be required to implement Agile, to help determine the likelihood of success.	A comparison of the organization's current work management processes to what they would be like generally under an Agile system is published.	Compare the general descriptions of Agile or the method of interest (like Full Stack Scrum) to your current relevant processes. Limit to a page or two per major change, but this will be the largest gap analysis.	Details
	3.9	Assess Organizational Readiness	As the change leader, I want to assess the results of the history and gap analyses to determine whether an Agile adoption should be attempted, to prevent wasting time, money, and stakeholder goodwill if not.	Change leader, agents, and sponsor reach consensus on whether to attempt Agile adoption; drop the idea; or delay it, and in that case, identify what gaps must be addressed before continuing (that is, blocking gaps the transformation itself would not address).		Details
	3.10	Create Organizational Readiness Stories	As the change leader, I want to create stories to address the identified organizational readiness gaps that must be addressed before attempting or as part of Agile adoption, to mitigate the risks they pose to success.	Change leader has created an initial set of stories for addressing the gaps from the gap analysis, given change agents a chance to review them, and addressed any input.		Details
	3.11	Communicate Organizational Readiness	As the change leader, I want to communicate the results of the history and gap analyses to invite help with gaps and reduce negative resistance.	The gap analysis is updated based on prior input, and it and the decision on Agile adoption is published.		Details
4		Specify the Objectives	As a stakeholder, I want to know how Agile success will be measured, to make it easier to sell the effort, celebrate small wins, define “done,” and prevent backsliding.	Three to five SMART goals for the transformation supported by the change leader, sponsor, and team have been published, along with mechanisms for measuring progress.	"SMART" means: Specific, Measurable, Action-based, Realistic, and Time-bound. These goals should be objective metrics around factors like productivity, customer satisfaction, or issues the change means to address.	Details
	4.1	Propose Objectives	As the change leader, I want to propose quantifiable performance measures for the transformation so that everyone knows how it is progressing.	Consensus is reached among the change sponsor and agents on a list of three to five SMART goals, and the list is published.	Objectives should tie to the causes identified earlier.	Details
	4.2	Gain Change Team Approval on Objectives	As the change leader, I want Change Team approval of quantifiable performance measures for the transformation, to verify they are realistic and relevant.	Consensus reached among the sponsor, leader, and Change Team on the list of three to five draft SMART goals, and the list is published.		Details
	4.3	Revisit Objectives and Address Feedback	As the change leader, I want to revisit the quantifiable performance measures if stakeholder feedback warrants a change, so they don't become a source of resistance.	If revision is needed based on significant stakeholder resistance, consensus is reached among the sponsor, leader, and Change Team on a revised list of goals, and it is published.		Details
5		Foster Two-Way Communications	As change agents, we want to proactively seek input, squelch rumors, address concerns, and publicize successes, to prevent and reduce resistance throughout the project.	All stakeholders have been identified, and multiple communication channels are set up to encourage ongoing dialog with them.		Details
	5.1	Create Stakeholder List	As the change sponsor and leader, we want to create an initial list of all individuals and groups who could be impacted by a change to Agile, to begin evangelizing the change as broadly as possible and prevent extra resistance.	The sponsor and leader agree the stakeholder list appears complete, and it includes initial points of contact for the groups.	Determine all possibly impacted people: top, middle, and line managers; internal and external organizations that supply, support or receive output from the organization; auditors; customers, if feasible; and workers.	Details
	5.2	Initiate Stakeholder Contacts	As the change leader, I want to contact all stakeholder groups and attempt to expand the stakeholder list through them, to ensure comprehensive communication as early in the transformation as possible.	The project is introduced to the initial points of contact, other stakeholder names are solicited from them, and the list is published.	If new stakeholders are identified, make a copy of this story for the next sprint and repeat it for the new groups.	Details
	5.3	Create Change Project Site or Board	As the change leader, I want a stakeholder site or bulletin board available, to provide transformation progress on demand and accept comments.	A page/site is tested and available to all stakeholders, and/or if some stakeholders don't have computers, a physical bulletin board is set up.	Possibilities include an intranet site, document management tool, team collaboration tool, Agile tool page, etc. These features are required at minimum: progress charts on change project stories and objectives; a page or blog for summarizing progress in narrative (text) form; and a comments tool or similar feedback mechanism.	Details
	5.4	Create a Push Communication Channel	As the change leader, I want to establish a "push" communication channel to provide regular updates and invite input.	E-mail and/or memo (if some stakeholders don't have computers) distribution list created, schedule set for periodic updates, and first e-mail/memo sent successfully.	Provide brief updates and a link or directions to the project site (for paper communications, include the full URL). Invite input via replies or the site.	Details
	5.5	Schedule and Hold Input Meetings	As the change leader, I want a schedule set for meetings to answer questions and take input.	A schedule has been posted for initial Q&A sessions on the project covering all stakeholders.	These can include slots in all-hands and/or individual team meetings, informal meetings like "lunch and learns," etc.	Details
6		Build Broad Sponsorship	As the change sponsor, I want organizational leaders to understand the full implications and benefits of Agile for their functions, so they assist with instead of resist the change.	Leadership team makes a "go/delay/no-go" decision on whether to implement some system of Agile, and that decision is communicated to all stakeholders.	"Leadership team" refers to the sponsor's peers and boss, or if the sponsor is the top leader, that person and their direct reports.	Details
	6.1	Draft a Presentation	As the change leader, I want to create a draft presentation on Agile for input from the change sponsor and agents, to craft a message that will create leadership support.	Draft presentation delivered to the change sponsor and agents and feedback solicited.	The presentation does not have to be a slide deck: use the format(s) you think will work best with your leadership team.	Details
	6.2	Approve the Presentation	As the change leader, I want consensus on the presentation among the change sponsor and agents, to ensure a persuasive message is delivered to organizational leaders.	Input from a practice run of the presentation is incorporated, and an updated version is approved by consensus.		Details
	6.3	Deliver the Presentation	As the change sponsor and leader, we want to deliver the presentation on Agile to the top organizational leaders so we can address their concerns and solicit support for required changes.	Presentation given to leadership team and its decision published.		Details
	6.4	Communicate Leader Commitments	As the change sponsor, I want a public commitment from the leadership team to support the change, so all employees feel some motivation to change their behaviors.	Leader commitment to required agreements has been communicated in writing to all stakeholders.		Details
7		Create a Change Team	As the change sponsor, I want voting representatives from each stakeholder group to serve on an Agile Change Team, because letting the people who will implement the change influence that change greatly increases the odds of success.	A team has formed and published a team charter.	Form an advisory team to provide feedback from, and another channel of communication to, stakeholder groups. Members are not expected to take any tasks beyond those related to communication, though they can volunteer for tasks. The change leader is responsible for the change activities.	Details
	7.1	Identify Reps for [Stakeholder Group]	As the change leader, I want a voting representative and backup identified from [stakeholder group] to ensure the group's needs are addressed during the transformation.	Agreement indicated in writing from the representatives and their supervisor(s).	Make a copy of this story for each stakeholder group.	Details
	7.2	Perform Change Team Kickoff	As the change leader and stakeholder representatives, we want to decide how we will work together, so we can guide the Agile transformation effectively and efficiently.	A kickoff meeting is held and consensus reached on an initial team charter (see Notes).	The team charter should at least cover: Purpose statement; values; meeting frequency; meeting rules; and team process agreements.	Details
	7.3	Review Representation of Change Team	As the change leader, I want to invite any other individuals or groups who might be impacted by our adoption of Agile to the Change Team, to reduce resistance to the change and spread the benefits.	The Change Team reviewed the existing stakeholder list, and if new individuals and teams were added, they have been invited to send representatives.		Details
8		Choose an Agile System	As stakeholders, we want a scaled Agile system that fits our needs, to gain the maximum benefits from the transformation.	The sponsor, leader, and Change Team reached consensus on an Agile system to implement, and communicated this to all stakeholders.		Details
	8.1	Gather Pros and Cons on Systems	As the change leader, I want to know what systems of scaled Agile are available, and the high-level pros and cons for each, to increase the odds of adopting one that fits our organization.	A Web search has been conducted, and a pro/con list is presented to the Change Team for input.	At minimum, review the following along with any lesser-known systems you come across: Full Stack Scrum (FuSS), Large-Scale Scrum (LeSS), Nexus, and Scaled Agile Framework (SAFe).	Details
	8.2	Choose Systems to Investigate	As the Change Team, we want to choose two or more Agile systems to investigate fully, so we can make a well-informed decision.	The pro/con lists are reviewed and systems are chosen for more detailed comparison.		Details
	8.3	Draft System Comparison Tool	As the change leader, I want to draft criteria for comparing Agile systems, so I can get input to match our choice to our needs.	A draft list of criteria and rating scale is provided to the Change Team and sponsor.		Details
	8.4	Approve System Comparison Tool	As the Change Team, we want to set criteria for comparing Agile systems, so we ensure our choice meets our needs.	The team and sponsor reach consensus on a list of criteria and a rating scale.		Details
	8.5	Rate Agile Systems	As the change leader, I want to rate the systems the Change Team chose to review so we have a quantified basis for a rational decision.	Each system has been rated and the results presented to the team.	If team members are willing to do ratings, the results will be more objective.	Details
	8.6	Approve a System	As the change leader, I want approval from the change sponsor and Change Team to move forward with a chosen system, so we can begin implementation.	Consensus is reached on a system and the choice published.		Details
	8.7	Obtain Authorization to Hire a Coach	As the Change Team, we want authorization to hire an Agile Coach to save time, effort, and trouble.	Authorization to hire a coach has been approved by the sponsor and organization, or not, and the decision published.		Details
	8.8	Create an Agile Coach Job Description	As the Change Team, we want to draft a comprehensive job description so we recruit the right Agile coach.	The job advertisement for a coach has been vetted by HR and the sponsor and posted through the organization's normal means.		Details
	8.9	Select Interview Candidates	As the Change Team, we want to find several Agile coach candidates to interview, to increase our odds of getting the right person.	At least five candidates have been identified for phone interviews.		Details
	8.10	Choose a Coach	As the Change Team, we want to select an Agile coach who can lead us through our Agile transformation as efficiently as possible.	A candidate is approved and the hiring or contractor procurement process has begun.		Details
9		Prepare Stakeholders and Teams	As the Change Team, we want to gain support among, and provide training to, all stakeholder groups and teams, to reduce resistance to the desired behavior changes.	Initial training provided to each group, and any questions or concerns raised have been addressed.	Other than a general introduction to Agile and the chosen system, the training will vary by group.	Details
	9.1	Draft Training Presentations	As the change leader, I want to draft training materials, and scripts appropriate to each stakeholder or team type, to get input and improve training effectiveness.	The proposed training is drafted, and a review meeting scheduled with the Change Team and sponsor.	If using FuSS, download draft presentation slides from: "FullStackScrum.net> Downloads."	Details
	9.2	Test Training Presentation	As the change leader, I want input on the stakeholder training to ensure maximum effectiveness.	The proposed training is presented to the Change Team and sponsor, and revised based on their input.	Use the most-detailed (work team level) version.	Details
	9.3	Deliver Training to [Group/Team]	As the change leader, I want to present the Agile system training to [group/team], to gain input and reduce negative resistance.	Training has been presented, concerns recorded, follow-up questions answered, and the training updated if needed.	Make a copy of this story for each stakeholder group.	Details
10		Go “All-In”	As an organization, we want to implement our Agile system as quickly and completely as possible, to reduce resistance based on inertia and cynicism about change, and allow for shared learnings across teams.	All teams have been performing the required actions of the chosen system for six iterations, and met the system's required performance standards at least two sprints in a row.	An incremental adoption is fine, but should be by all teams at once and of the whole method (possibly after a pilot test to prove feasibility and value).	Details
	10.1	Create Child Stories for "All-in" Epic	As the change leader, I want to review with the Change Team an initial set of child stories for implementing the Agile system, to minimize problems at the start.	An initial set of stories for this epic have been drafted by the change leader, reviewed with the Change Team, and published.	Review of the story titles, three-part statements, and acceptance criteria is sufficient.	Details
	10.2	Celebrate Project Success	As stakeholders, we want to know the Agile system has been implemented so we can celebrate our accomplishment.	The project objectives have been met, the Change Team disbanded, and stakeholders notified in writing.	This story is blocked until all other epics are completed (including Epic 11). An optional celebration is recommended.	Details
11		Customize through Experimentation	As Agile teams, after adoption of the Agile system, we want to experiment with changes one at a time, to balance the need for a systematic approach with the need for team empowerment.	All teams have received training on experimentation, tried one change through one sprint, and been coached on evaluating that change.	A team cannot perform these stories until it has met the system's performance standards for three sprints, or two months if not using sprints.	Details
	11.1	Create Experimentation Training	As the change leader, I want to create team experimentation training materials, so each team can begin experimenting as soon as it learns the system.	The training is reviewed with the Change Team, updated, and published.	For material applicable to any Agile system, see "System> Customize FuSS."	Details
	11.2	Train [Team Name] on Experimentation	As the change leader, I want to train the [name] team on conducting process experiments and evaluating changes so it will be able to isolate change effects.	The team is trained on experimentation and proposes a change for the next sprint/period.	Create a story copy for each team (including any program-level teams).	Details
	11.3	Coach [Team Name] on Evaluating Experiments	As the change leader, I want to coach the [name] team on evaluating changes so it will only retain system customizations supported by evidence.	The team is coached through evaluating a change during a Retrospective or team meeting, and it decides to accept, reject, or revise the tested change.		Details