## ACTIVITY_ATTRIBUTES
ACTIVITY ATTRIBUTES
PROJECT No:	MA-015-02	FULL PROJECT NAME:	Project Orion
LAST UPDATE:	21-Jul	PROJECT MANAGER:	A Smith

ACTIVITY			ACTIVITY RESOURCE REQUIREMENTS					ACTIVITY SCHEDULE ATTRIBUTES
ACTIVITY ID	ACTIVITY TITLE	ACTIVITY DESCRIPTION	NUMBER AND TYPE OF TEAM RESOURCES REQUIRED	SKILL REQUIREMENTS	MATERIALS, SUPPLIES OR EQUIPMENT	TYPE OF EFFORT	RESOURCE LOCATIONS	IMPOSED DATES OR OTHER CONSTRAINTS	PREDECSSOR ACTIVITY IDs	RELATIONSHIP	LEAD OR LAG	SUCCESSOR ACTIVITY IDs	RELATIONSHIP	LEAD OR LAG
WBS1.2.1-A001	Assign project manager	Send resource request to resource manager, who will identify the project manager.	One level 2 project manager	As for level 2 project manager description. Plus knowledge of kubernetes	None additional to standard (laptop etc).	50% billable	US	Must be available from start of October	None	N/A	N/A	A002	FS	0
WBS1.2.1-A002	Create Project record	Create project record in Project Management system	Project Manager	Knowledge of Project Management Method	None	Billable hrs (est. 2)	US	Complete on allocation to project	A001	FS	0	A003	FS	0
WBS1.2.3-A003	Assign project team	Book the project team in resource booking system.	Review SOW and create 1 resource booking for each project team member. Project Admin is booked separately via PMO.	Use Resource Booking system	None	Billable hrs (est. 2)	US	Complete on allocation to project	A002	FS	0	A004	FS	3d lag

## DEFINITIONS
DEFINITIONS
PROJECT No.

The project number is assigned by the PMO (Project Management Office) once the project is approved for funding.
This Link Takes You to Project No. in the Template
PROJECT MANAGER

The person responsible for the successful delivery of the project to time costs and quality constraints.
This Link Takes You to Project Manager in the Template
FULL PROJECT NAME

The name or title of the project.
This Link Takes You to the Full Project Name in the Template
LAST UPDATE

Date of the last update to this form.
This Link Takes You to Last Update
ACTIVITY ID

Give each activity a unique ID, this may include a reference to the work package in the work breakdown structure.
This Takes You to Activity ID in the Template
ACTIVITY TITLE

Give each activity a title that is as understandable as possible, in other words a title that the project team will understand.
This Link Takes You to Activity Title in the Template
ACTIVITY DESCRIPTION

Describe the activity clearly so that the person responsible understands the work.
This Link Takes You to Activity Description in the Template
RESOURCES REQUIRED

Enter the number and type of team resources required. For example, 2 developers.
This Link Takes You to Resources Required
SKILL REQUIREMENTS

Document the skills the team will need. For example, Java, C#, PHP or skill level such as senior or junior.
This Link Takes You to Skill Requirements
MATERIALS, SUPPLIES OR EQUIPMENT

Document any required resources that are not human.
This Link Takes You to Materials, Supplies or Equipment
TYPE OF EFFORT

How you will measure the effort required. For example, 4 days fixed duration or 4 days fixed effort.
This Link Takes You to Type of Effort
RESOURCE LOCATIONS

Note down where the work will take place.
This Link Takes You to Resources Locations
IMPOSED DATES OR OTHER CONSTRAINTS

Note any fixed dates or other constraints on the activity.
This Link Takes You to Imposed Dates or other Constraints
PREDECESSOR ACTIVITIES

Enter the activity IDs that need to be completed before this activity can start
This Link Takes You to Predecessor in the Template
RELATIONSHIPS

The type of dependency with the activity's predecessors. For example, start-to-start, finish-to-start.
Task dependencies in project planning.
This Link Takes You to Relationships
LEAD OR LAG

Any delay (lag) between the predecessor and this activity or any acceleration (lead).
This Link Takes You to Lead or Lag
SUCCESSOR ACTIVITIES

Enter any other activities that rely on the completion of this activity.
This Link Takes You to Successor in the Template
RELATIONSHIPS

The type of dependency with the activity's predecessors. For example, start-to-start, finish-to-start.
Task dependencies in project planning.
This Link Takes You to Relationships
LEAD OR LAG

Any delay (lag) between the predecessor and this activity or any acceleration (lead).
This Link Takes You to Lead or Lag

This template was provided by
https://www.stakeholdermap.com/

## Useful_resources
Project Management resources
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
Issue Log Template [free download]
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel